## Dashboard_2026
PO Year | 2026 |  |  |  | PO Year | (All) | [8 empty] | PO Year | 2026 | [5 empty] | PO Year | 2026
Count of WID | Column Labels |  |  |  | Count of WID | Column Labels |  |  |  | Count of WID | Column Labels |  |  |  | Count of WID | Column Labels | [5 empty] | Count of WID | ZTE ZONE
Assignment | MAKASSAR | MANADO | TERNATE | Grand Total | SM ATP | MAKASSAR | MANADO | TERNATE | Grand Total | FI INEOM | MAKASSAR | MANADO | TERNATE | Grand Total | SM ATP | MAKASSAR | MANADO | TERNATE | Grand Total |  |  | Connected Date | TERNATE | MANADO | MAKASSAR | Grand Total
Jan | 1 |  | 67 | 68 | Jan |  |  | 37 | 37 | Jan |  |  | 37 | 37 | No Need |  |  | 15 | 15 |  |  | Jan | 50 |  | 1 | 51
Feb | 33 |  | 37 | 70 | Feb | 1 |  | 30 | 31 | Feb | 1 |  | 30 | 31 | passed | 42 | 37 | 209 | 288 |  |  | Feb | 37 |  | 1 | 38
Mar |  | 10 | 31 | 41 | Mar | 10 |  | 10 | 20 | Mar | 1 |  | 10 | 11 | Progress | 5 | 2 | 26 | 33 |  |  | Mar | 18 |  | 20 | 38
Apr | 3 | 15 | 45 | 63 | Apr | 12 | 16 | 36 | 64 | Apr | 18 | 12 | 30 | 60 | Work Not Start | 23 | 1 | 38 | 62 |  |  | Apr | 36 | 19 | 3 | 58
May | 15 | 13 | 26 | 54 | May | 5 | 14 | 28 | 47 | May | 6 | 9 | 18 | 33 | Grand Total | 70 | 40 | 288 | 398 |  |  | May | 26 | 12 | 11 | 49
Jun | 1 |  | 41 | 42 | Jun | 7 | 1 | 37 | 45 | Jun | 8 | 9 | 46 | 63 | [7 empty] | Jun | 38 |  | 3 | 41
Jul | 7 | 2 | 41 | 50 | Jul | 6 | 3 | 35 | 44 | Jul | 7 | 3 | 36 | 46 | [7 empty] | Jul | 22 | 2 | 5 | 29
Aug | 10 |  |  | 10 | Aug | 2 | 3 | 15 | 20 | Aug | 2 | 3 | 14 | 19 | [7 empty] | Aug | 19 | 3 | 2 | 24
Grand Total | 70 | 40 | 288 | 398 | Grand Total | 43 | 37 | 228 | 308 | Grand Total | 43 | 36 | 221 | 300 | [7 empty] | Grand Total | 246 | 36 | 46 | 328
[15 empty] | ZTE ZONE | MAKASSAR |  | ZTE ZONE | MANADO | ZTE ZONE | TERNATE
PO Year | 2026 | [13 empty] | PO Year | 2026 |  | PO Year | 2026 | PO Year | 2026
| Column Labels | [13 empty] | SM ATP | Count of WID |  | SM ATP | Count of WID | SM ATP | Count of WID
Values | MAKASSAR | MANADO | TERNATE | Grand Total | [10 empty] | passed | 42 |  | passed | 37 | No Need | 15
Count of MOS | 47 | 39 | 250 | 336 | [10 empty] | Progress | 5 |  | Progress | 2 | passed | 209
Count of HI Done | 46 | 39 | 246 | 331 | [10 empty] | Work Not Start | 23 |  | Work Not Start | 1 | Progress | 26
Count of Connected Date | 46 | 36 | 246 | 328 | [10 empty] | Grand Total | 70 |  | Grand Total | 40 | Work Not Start | 38
PO Year | 2026 | [18 empty] | Grand Total | 288
Count of WID | Column Labels
SM Kitting, PTW & EHS | MAKASSAR | MANADO | TERNATE | Grand Total
01-Passed | 44 | 34 | 201 | 279
03-NY SM | 23 |  |  | 23
Work Not Start |  | 1 | 38 | 39
Progress | 3 | 2 | 13 | 18
passed |  | 3 | 35 | 38
No Need |  |  | 1 | 1
Grand Total | 70 | 40 | 288 | 398
PO Year | 2026
Count of WID | Column Labels
SM ATP | MAKASSAR | MANADO | TERNATE | Grand Total
No Need |  |  | 15 | 15
passed | 42 | 37 | 209 | 288
Progress | 5 | 2 | 26 | 33
Work Not Start | 23 | 1 | 38 | 62
Grand Total | 70 | 40 | 288 | 398
PO Year | 2026
Count of WID | Column Labels
SM Dismantle | MAKASSAR | MANADO | TERNATE | Grand Total
No Need | 42 | 23 | 184 | 249
Passed | 26 | 16 | 93 | 135
Progress | 1 |  | 11 | 12
SM Passed | 1 | 1 |  | 2
Grand Total | 70 | 40 | 288 | 398
PO Year | 2026
Count of WID | Column Labels
Inbound | MAKASSAR | MANADO | TERNATE | Grand Total
Inbound | 22 | 16 | 90 | 128
Ongoing | 3 | 1 | 3 | 7
No Need | 7 | 5 | 89 | 101
Grand Total | 32 | 22 | 182 | 236
PO Year | 2026
Count of WID | Column Labels
FI Ineom | MAKASSAR | MANADO | TERNATE | Grand Total
Done Tagging | 42 | 36 | 203 | 281
No Need |  | 1 | 15 | 16
Progress | 5 | 2 | 32 | 39
Work Not Start | 23 | 1 | 38 | 62
Grand Total | 70 | 40 | 288 | 398
PO Year | 2026
Count of WID | Column Labels
eATP Done | MAKASSAR | MANADO | TERNATE | Grand Total
00-eATP Approved Tsel | 9 | 12 | 103 | 124
09-eATP NY Uploaded |  | 10 | 28 | 38
10-Tagging New Asset & SM ATP Done, Wait BAPA | 2 |  |  | 2
11-Tagging New Asset Done, SM ATP NY & Wait BAPA | 2 |  |  | 2
12-Tagging New Asset Done, Wait BARA |  |  | 1 | 1
14-Tagging New Asset NY, SM ATP Done |  |  | 1 | 1
15-Tagging New Asset NY, SM ATP NY | 5 |  | 2 | 7
17-Work NY Done | 29 | 10 | 40 | 79
(blank) | 14 | 5 | 95 | 114
Ny Upload |  |  | 1 | 1
15-Tagging New Asset Done, SM ATP Done | 1 |  |  | 1
Done Upload eATP Waitting Review | 8 | 3 | 17 | 28
Grand Total | 70 | 40 | 288 | 398
Count of WID | Column Labels
Assignment | MAKASSAR | MANADO | TERNATE | Grand Total
Connected | 149 | 199 | 616 | 964
2023 | 20 | 30 | 49 | 99
2024 | 71 | 127 | 234 | 432
2025 | 12 | 5 | 87 | 104
2026 | 46 | 37 | 246 | 329
Work Not Start | 23 | 11 | 11 | 45
2023 |  | 9 | 5 | 14
2025 |  |  | 2 | 2
2026 | 23 | 2 | 4 | 29
Progress |  |  | 4 | 4
2026 |  |  | 4 | 4
Prorgress | 1 |  |  | 1
2026 | 1 |  |  | 1
(blank) |  | 1 | 34 | 35
2026 |  | 1 | 34 | 35
Grand Total | 173 | 211 | 665 | 1049

## Dashboard Sulawesi
PO Year | Zona | Milestone | Bulan | Plan | Ach | Persen | Remarks
SULAWESI
| Milestone | Assignment Site | 2026 ( Jan - Agustus) Makassar - Manado - Ternate |  |  |  | Remarks
|  |  | Plan | Ach | Delta | %
| MOS Done | 398 | 398 | 336 | 62 | 84% | 50 sites plan mos (ternate), 25 sites waiting confirm (makassar) | MAKASSAR
| SM Kitting, PTW & EHS |  | 336 | 279 | 57 | 83% |  |  | 53 | 39 | 35 | 34 | 9 |  |  |  |  | 72
| HI Done |  | 336 | 331 | 5 | 99% | 2 pending HI due to access issue | Month | Assignment | Connected | SM ATP (70%) | FI INEOM APPROVED (20%) | EATP | No Need SM ATP | GAP SM ATP | Team | Issue | Minimum Site Assignment
| Connected |  | 336 | 328 | 8 | 98% |  | January | 1 | 1 | 0 | 0 | 9 |  | 5 | 1 |  | 8
| SM ATP |  | 336 | 288 | 48 | 86% | Pending ATP mostly on mining area | February | 33 | 1 | 1 | 1 |  |  |  | 1 | Assignment end of February, plan had change from Tsel | 8
| SM Dismantle |  | 147 | 135 | 12 | 92% |  | March | 0 | 20 | 10 | 1 |  |  |  | 3 |  | 24
| Inbound Done |  | 147 | 128 | 19 | 87% |  | April | 3 | 3 | 12 | 18 |  |  |  | 2 |  | 16
| FI Ineom |  | 336 | 281 | 55 | 84% | Pending Ineom mostly on mining area | May | 15 | 11 | 5 | 6 |  |  |  | 2 |  | 16 | <-- Target April
| eATP Done |  | 336 | 124 | 212 | 37% | eATP sites waiting PO release in system | Jun | 1 | 3 | 7 | 8 |  |  |  | 1 | 1. Waiiting assignment Juni 2026 2. waitting material for continue progress connected
| BAUT Done |  | 336 | 0 | 336 | 0% |  | Juli | 7 | 5 | 6 | 7 |  |  |  | 1 | 1. Waiiting assignment Juli 2026 2. waitting material for continue progress connected
[8 empty] | Agustus | 10 | 2 | 2 | 2 |  |  |  | 1 | 1. Waiiting assignment Agustus 2026 2. waitting material for continue progress connected
| MAKASSAR - MANADO | [6 empty] | MANADO
| Milestone | Assignment Site | 2026 ( Jan - Agustus Makassar - Manado - Ternate |  |  |  | Remarks |  | 38 | 31 | 31 | 30 | 12 |  |  |  |  | 0
|  |  | Plan | Ach | Delta | % |  | Month | Assignment | Connected | SM ATP (70%) | FI INEOM APPROVED (20%) | EATP | No Need SM ATP | GAP SM ATP | Team | Issue | Minimum Site Assignment
| MOS Done | 110 | 110 | 86 | 24 | 78% | 26 sites hold by zte/Tsel | January | 0 | 0 | 0 | 0 | 12 |  | 2
| SM Kitting, PTW & EHS |  | 86 | 78 | 8 | 91% |  | February | 0 | 0 | 0 | 0
| HI Done |  | 86 | 85 | 1 | 99% |  | March | 10 | 0 | 0 | 0 |  |  |  | 2
| Connected |  | 86 | 82 | 4 | 95% |  | April | 15 | 19 | 16 | 12 |  |  |  | 2
| SM ATP |  | 82 | 79 | 3 | 96% |  | May | 13 | 12 | 14 | 9 |  |  |  | 2
| SM Dismantle |  | 43 | 42 | 1 | 98% |  | Jun |  | 0 | 1 | 9 |  |  |  | 2 | 1. Waiiting assignment Juni 2026 2. waitting material for continue progress connected
| Inbound Done |  | 43 | 22 | 21 | 51% |  | Juli | 2 | 2 | 3 | 3 |  |  |  | 2 | 1. Waiiting assignment Juli 2026 2. waitting material for continue progress connected
| FI Ineom |  | 82 | 78 | 4 | 95% |  | Agustus | 0 | 3 | 3 | 3 |  |  |  |  | 1. Waiiting assignment Agustus 2026 2. waitting material for continue progress connected
| eATP Done |  | 82 | 9 | 73 | 11% | eATP sites waiting PO release in system
| BAUT Done |  | 82 | 0 | 82 | 0% |  | TERNATE
[9 empty] | 247 | 205 | 178 | 171 | [5 empty] | 0
| TERNATE | [6 empty] | Month | Assignment | Connected | SM ATP (70%) | FI Ineom Approved (20%) | EATP | No Need SM ATP | GAP SM ATP | Team | Issue | Minimum Site Assignment
| Milestone | Assignment Site | 2026 ( Jan - Agustus) Ternate |  |  |  | Remarks | Januari | 67 | 50 | 37 | 37 | 103 | 15 | 26 | 5 | BAUT ISSUE (1 site no need SM ATP. dismantle only) 14 Site Pending ATP due Waitting Access In Iwip 1 site pending HI & OA due Accsess to site landslide
|  |  | Plan | Ach | Delta | % |  | Februari | 37 | 37 | 30 | 30 |  |  |  | 5 | 9 site no need SM ATP. dismantle only 8 Site Pending ATP due Waitting Access In Iwip 2 site pending OA due Waitting Access In Iwip
| MOS Done | 288 | 288 | 250 | 38 | 87% | 50 sites plan mos | Maret | 31 | 18 | 10 | 10 |  |  |  | 6 | 3 site no need SM ATP. dismantle only 1 Site Pending ATP due Waitting Access In Iwip 2 site pending OA due Hard Access
| SM Kitting, PTW & EHS |  | 250 | 201 | 49 | 80% |  | April | 45 | 36 | 36 | 30 |  |  |  | 6 | 1. Done Follow Up to IT Iwip for Closing in Iwip 2. Done Assignment from ZTE site list April (date Assign 20 April 2026)
| HI Done |  | 250 | 246 | 4 | 98% | 1 pending HI due to access issue | May | 26 | 26 | 28 | 18 |  |  |  | 6 | 1. Waiiting assignment May 2026 2. waitting material for continue progress connected
| Connected |  | 250 | 246 | 4 | 98% |  | Jun | 41 | 38 | 37 | 46 |  |  |  | 6 | 1. Waiiting assignment Juni 2026 2. waitting material for continue progress connected
| SM ATP |  | 246 | 209 | 37 | 85% | Pending ATP mostly on mining area | Juli | 41 | 22 | 35 | 36 |  |  |  | 6 | 1. Waiiting assignment Juli 2026 2. waitting material for continue progress connected
| SM Dismantle |  | 104 | 93 | 11 | 89% |  | Agustus | 0 | 19 | 15 | 14 |  |  |  | 6 | 1. Waiiting assignment Agustus 2026 2. waitting material for continue progress connected
| Inbound Done |  | 104 | 90 | 14 | 87%
| FI Ineom |  | 246 | 203 | 43 | 83%
| eATP Done |  | 246 | 103 | 143 | 42%
| BAUT Done |  | 246 | 0 | 246 | 0%

## Site_KAL
No | ASSIGNMENT DATE | WID | DU NAME | DU | Site ID | NE ID | Subc | Site Name | Branch | Cluster | RTPO / Kabupaten | Tower Owner | Program | Long | Lat | Address | Detail SOW | Band | SOW | Dismantle | CAF | Nodin | Site Solution | Datafill | Permite Submite | Permite Realease | Permite Expired | Simple Data Preparation (%) | Delivery Order 1 | Delivery Order 2 | Delivery Order 3 | Delivery Note 1 | Delivery Note 2 | Delivery Note 3 | Material On Site | LDM | Delivery Return | Return Note | Validation | Remaks | Simple Data Preparation (%) | TI Partner | Team On Site | Clock in Date | MOS | HI Start | HI Done | HI Progress | CI | CI Status | Connected Broadcast | Connected Date | Connected Status | GAP Analysis | Blocking Issue | SM Status | SM Kitting, PTW & EHS | SM Dismantle | SM ATP Status | SM ATP | FI Ineom | FI Ineom Status | ATP IEPMS | Dismantle | Alarm Status | DEPEDENCY | DETAIL DEPEDENCY | Clock out Date | Implementation Duration | Task Progress | Task Tamplate | Remarks | Simple Closing (%) | Date Submit ATP | eATP STATUS | eATP BLOCKING | SYSTEM UPLOAD | APPROVAL DATE | Simple Closing (%) | BAPA | BASO | BAUT/BAST | BARA | REMARK | Simple Closing (%) | STATUS | DATE | HISTORY | GAP | gap remark | PO Status | PO Number | PO Release Date
1 |  | 2501-ADSTR-4G#RO-PLK041-30046 | Wireless RAN/Settlement Site/2501-ADSTR-4G#RO-PLK041-30046 | DU00005030736 | STA091 | STA091MT1 | YPTT | Addsect_SUKAUHULU | PONTIANAK | SINTANG | SINTANG | TELKOMSEL | CP#2 AS4 2025 | 111.3104 | 0.10325 | DUSUN SUKAU HULU RT 04 RW 03 DESA SUKA BERSATU KEC SEPAUK SINTANG | Add Antena Rosenberger 12 port, RRU R9264M M7290 (1), VEMc4 (1), VBPe3p (1) | L900 | EQP Add Sector LTE 900 2T2R | 1 pcs RRU R8852E S9000 include Brackte, SFP, 35m RRU PWR Cable 2 core Type-D 6mm², 1 Pcs RRU Fiber LC-LC 50m,1 Pcs BBU Board VEMc1, ( Plan Mapping ) | Release | Release | Release | Release | 2025-06-13 | 2025-06-14 | 2025-06-16 | Expired Need Extend | DOEID25014A9 | NO NEED | NO NEED | DNWID0682025051501 | NO NEED | NO NEED | 22-May-25 | 26-May-25 | 25-May-25 | - | 2025-06-24 | - | DOP Finish | YPTT | La Sanudi | 22-May-25 | 22-May-25 | 22-May-25 | 25-May-25 | 100% | 25-May-25 | Laccima Ok | 2025-06-03 | 25-May-25 | Connected | Connected | [8 empty] | 25-May-25 | 25-May-25 | Main Fail(Exsisting) | Clear | No Issue | 25-May-25 | 3 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Processing on IOMS | no issue | Scarlett | - | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-6576 | 2025-06-05
2 |  | 2505-U32T32R-4G#RO-SHR002-220040-S1 | Wireless RAN/Settlement Site/2505-U32T32R-4G#RO-SHR002-220040-S1 | DU00005599429 | SHR002 | SHR002VV1 | YPTT | RAWAK | PONTIANAK | SINTANG | SINTANG | TELKOMSEL | CP#2 AS4 2025 | 110.8713 | -0.14439 | JL. BATANG RAWAK NANGA TAMAN RT.06 RW.04 KEC. SEKADAU HULU KAB. SEKADAU | Add VBPe2q (1), Add A9652 S23 (1), Upp RRU (3), Upp Ant (3) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Dismentle RRU PWR Cable 2 core Type-D 10mm² 119m, RRU PWR Cable 2 core Type-D 16mm² 250m , Cable Jumper type NM-4.3M 5m 4 Pcs | Release | Release | Release | Release | 24-May-25 | 26-May-25 | 2025-06-09 | Expired Need Extend | DOEID25052792 | DOEID25052793 | NO NEED | DNWID0682025052703 | DNWID0712025052701 | NO NEED | 22-May-25 | 2025-06-03 | - | - | 2025-06-24 | - | DOP Finish | YPTT | Andi Asmini | 30-May-25 | 22-May-25 | 31-May-25 | 31-May-25 | 100% | 2025-06-01 | Laccima Ok | 2025-06-03 | 31-May-25 | Connected | Connected | [8 empty] | 2025-06-03 | 2025-06-02 | Clear | Clear | No Issue | 2025-06-03 | 4 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Processing on IOMS | no issue | Scarlett | - | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-6612 | 2025-06-11
3 |  | 2505-NNE4G-4G#RO-SAG067-220039 | Wireless RAN/Settlement Site/2505-NNE4G-4G#RO-SAG067-220039 | DU00005599419 | SAG067 | SAG067MT1 | YPTT | MALENGGANG | PONTIANAK | SINTANG | SANGGAU | DMT | CP#2 AS4 2025 | 110.7228 | 0.79023 | KALIMANTAN BARAT. SANGGAU, SELKAYAM,MELENGGANG | add RRU R9264 M7290(1), VBPe1p(1) Antena MOBI 12 port (2) fw3rv rgv kl, | L2300 | EQP New NE 4G LTE 2300 20 Mhz | Dismantle Antenna 8 port sec 2,3 | Release | Release | Release | Release | 26-May-25 | 28-May-25 | 2025-06-11 | Expired Need Extend | DOEID25052791 | DOEID250530FB | NO NEED | DNWID0682025052702 | DNWID0682025053102 | NO NEED | 2025-06-03 | 2025-06-04 | - | - | 2025-06-24 | - | DOP Finish | YPTT | Andi Asmini | 29-May-2025 | 2025-06-03 | 2025-06-04 | 2025-06-04 | 100% | 2025-06-04 | Laccima Ok | 2025-06-12 | 2025-06-04 | Connected | Connected | [8 empty] | 2025-06-09 | 2025-06-04 | FCE & GNSS (Exsisting) | Clear | Waiting LOM | 2025-06-08 | 11 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Processing on IOMS | no issue | Scarlett | - | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-6612 | 2025-06-11
4 |  | 2505-MSCTR-4G#RO-SPT021-220042 | Wireless RAN/Settlement Site/2505-MSCTR-4G#RO-SPT021-220042 | DU00005599430 | SPT021 | SPT021ML1 | YPTT | KUALAKUAYAN | PALANGKARAYA | KUALA KUAYAN | KOTAWARINGIN TIMUR | TELKOMSEL | CP#2 AS4 2025 | 112.5103 | -1.9676 | JL. ALTERNATIF KELURAHAN KUALA KUAYAN RT 07 RW 02 MENTAYA HULU KAB. KOTAWARINGIN TIMUR KALTENG | Add Reuse Ant 4Port MS HighBand HBXX-3817TB1-VTM Commscope (1) | L1800 | EQP Upgrade Multisector LTEMacro6 | Antena Prose 10 Port (1 Pcs) | Release | Release | Release | Release | 27-May-25 | 28-May-25 | 2025-06-11 | Expired Need Extend | DOEID25060224 | NO NEED | NO NEED | DNWID0672025060202 | NO NEED | NO NEED | 2025-06-04 | 2025-06-04 | - | - | - | - | DOP Finish | YPTT | Del Piero | 2025-06-03 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 100% | 2025-06-04 | Laccima Ok | 2025-06-12 | 2025-06-04 | Connected | Connected | [8 empty] | 2025-06-05 | 2025-06-04 | Clear | Clear | No Issue | 2025-06-04 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Processing on IOMS | no issue | Scarlett | - | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-6722 | 2025-06-19
5 |  | 2505-REENG-4G#RO-SPT154-220043 | Wireless RAN/Settlement Site/2505-REENG-4G#RO-SPT154-220043 | DU00005611431 | SPT154 | SPT154ME1 | YPTT | PTWINDUNABATINDOLESTARI | PALANGKARAYA | KOTAWARINGIN | KOTAWARINGIN TIMUR | TBG | CP#2 AS4 2025 | 113.0609 | -1.9914 | Pundu, Cempaga Hulu, East Kotawaringin Regency, Central Kalimantan 74354 | Add Antena Rosenberger 12 Port(1), RRU R9614 S23 (1), VBPe1p(1) | L2300 | EQP eNode B Modular Relocation Service New NE LTE 2300 | Antena Comscope 4 port(1 Pcs), Jumper DM-DM (2 pcs) | Release | Release | Release | Release | 2025-06-02 | 2025-06-03 | 2025-06-17 | Expired Need Extend | DOEID25060317 | NO NEED | NO NEED | DNWID0672025060308 | NO NEED | NO NEED | 2025-06-05 | 2025-06-07 | - | - | - | - | DOP Finish | YPTT | Del Piero | 2025-06-06 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 100% | 2025-06-07 | Laccima Ok | 2025-06-15 | 2025-06-07 | Connected | Connected | [8 empty] | 2025-06-09 | 2025-06-07 | Clear | Clear | No Issue | 2025-06-08 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | no issue | Scarlett | 2025-07-08 | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-6722 | 2025-06-19
6 |  | 2505-NNE4G-4G#RO-PTS170-220036 | Wireless RAN/Settlement Site/2505-NNE4G-4G#RO-PTS170-220036 | DU00005599437 | PTS170 | PTS170ME1 | YPTT | RIAUAGROTAMAPLANTATION | PONTIANAK | SINTANG | KAPUAS HULU | TBG | CP#2 AS4 2025 | 111804112 | 350619 | SANG-SANG, SILAT HILIR, KAPUAS HULU, KALIMANTAN BARAT | Add R9614 S23(1), VBPe1p(1) | L2300 | EQP New NE 4G LTE 2300 20 Mhz | - | Release | Release | Release | Release | 30-May-25 | 2025-06-02 | 2025-06-16 | Expired Need Extend | DOEID25052852 | NO NEED | NO NEED | DNWID0682025060201 | NO NEED | NO NEED | 2025-06-09 | - | - | - | - | - | DOP Finish | YPTT | Andi Asmini | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 100% | 2025-06-09 | Laccima Ok | 2025-06-15 | 2025-06-09 | Connected | Connected | [8 empty] | 2025-06-10 | - | Clear | Clear | No Issue | 2025-06-10 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | no issue | Scarlett | 2025-07-30 | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-6722 | 2025-06-19
7 |  | 2505-MSCTR-4G#RO-STA340-220045 | Wireless RAN/Settlement Site/2505-MSCTR-4G#RO-STA340-220045 | DU00005599431 | STA340 | STA340MT1 | YPTT | GANDIS | PONTIANAK | SINTANG | SINTANG | TBG | CP#2 AS4 2025 | 11162912 | -100736 | RT.005 Dusun Gandis Hulu Desa Gandis Hulu, Kecamatan Dedai, Kabupaten Sintang, Kalimantan Barat | RRU R9264 M7290(1), Antena Mobi 4port MB4B-DB-19DE-IN-43(1), | L900 | EQP Upgrade Multisector LTE | RRU R8852E S9000 (1) | Release | Release | Release | Release | 2025-06-03 | 2025-06-04 | 2025-06-18 | Expired Need Extend | DOEID25052854 | DOEID25052853 | NO NEED | DNWID06802024072416 | NO NEED | NO NEED | 2025-06-11 | 2025-06-12 | 2025-06-12 | - | 2025-06-24 | - | DOP Finish | YPTT | Andi Asmini | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 100% | 2025-06-12 | Laccima Ok | 2025-06-17 | 2025-06-12 | Connected | Connected | [8 empty] | 2025-06-16 | 2025-06-12 | Clear | Clear | No Issue | 2025-06-12 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Processing on IOMS | no issue | Scarlett | - | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-6814 | 2025-06-26
8 |  | 2212-4GGSM-4G#2758-NTH160-0452 | Wireless RAN/Settlement Site/2212-4GGSM-4G#2758-NTH160-0452 | - | NTH160 | NTH160MT1 | YPTT | N3TBINAJAYA | PALANGKARAYA | BINA JAYA | KAPUAS | DMT | CP#2 AS4 2026 | 114.4505 | -1.1288 | BINA JAYA, DADAHUP, KAPUAS, KALIMANTAN TENGAH | NEW INFRA | L900 | EQP New NE 4G LTE 900 20 MHz | - | Release | Release | Release | Release | 12 may 25 | 15 may 25 | 16-May-25 | Expired Need Extend | DOEID24071945 | NO NEED | NO NEED | DNWID06702024072416 | NO NEED | NO NEED | 2025-06-12 | - | - | - | - | - | DOP Finish | YPTT | Del Piero | 2025-06-12 | 06-May-25 | 06-May-25 | 06-May-25 | 100% | 2025-06-12 | Laccima Ok | 2025-06-20 | 06-May-25 | Connected | Connected | [8 empty] | 2025-06-14 | - | Clear | Clear | No Issue | 2025-06-14 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Processing on IOMS | no issue | Scarlett | - | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-5680 | 2024-12-21
10 |  | 2506-NNE4G-4G#RO-PTS032-040049 | Wireless RAN/Settlement Site/2506-NNE4G-4G#RO-PTS032-040049 | DU00005663302 | PTS032 | PTS032ML1 | YPTT | NANGASUHAID | PONTIANAK | SINTANG | KAPUAS HULU | EMA | CP#2 AS4 2026 | 111.9975 | 0.6175 | KALIMANTAN BARAT. KAPUAS HULU, SUHAID,NANGA SUHAID | NEW INFRA | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | Release | Release | 2025-06-15 | 2025-06-15 | 2026-07-01 | Expired Need Extend | DOEID250609AE | DOEID250609AF | NO NEED | DNWID0682025061602 | DNWID0712025061601 | NO NEED | 2025-06-17 | - | - | - | - | - | DOP Finish | YPTT | Andi Asmini | 2025-06-18 | 2025-06-17 | 2025-06-18 | 2025-06-18 | 100% | 2025-06-20 | Laccima Ok | 2025-06-22 | 2025-06-18 | Connected | Connected | [8 empty] | 2025-06-20 | - | Clear | Clear | No Issue | 2025-06-21 | 4 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | no issue | Scarlett | 2024-07-03 | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-6814 | 2025-06-26
11 |  | 2504-NNE4G-4G#RO-BJM788-250023 | Wireless RAN/Settlement Site/2504-NNE4G-4G#RO-BJM788-250023 | DU00005472666 | BJM788 | BJM788MV1 | YPTT | UNLAMKAYUTANGI | BANJARMASIN | BANJAR | KOTA BANJARMASIN | Telkomsel | CP2_RO Offload blacksite | 11458433 | -329771 | Jln. Brigjen H. Hasan Basry Kel. Kayu Tangi, Kec. Banjarmasin Utara Kota Banjarmasin. | Add Antena Mobi 12 Port (1), RRU R9614 S23(1), dan VEMc4 (1) | L2300 | EQP New NE 4G LTE 2300 50 Mhz | Antenna RF XXPOL VET Tongyu TDQ-182020DE-65F(1 pcs), Board VEMc1 | Release | Release | - | Release | 2025-06-02 | 2025-06-03 | 2025-06-30 | Expired Need Extend | DOEID25060334 | NO NEED | NO NEED | DNWID0662025060303 | NO NEED | NO NEED | 2025-06-12 | 2025-06-12 | - | - | - | - | DOP Finish | YPTT | Yoga | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 100% | 2025-06-12 | Lacima Ok |  | 2025-06-12 | Connected | Connected | [8 empty] | 2025-06-13 | 2025-06-12 | Clear | Clear | No Issue | 2025-06-12 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | no issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-6820 | 2025-06-26
12 |  | 2504-NNE4G-4G#RO-BJM027-250022 | Wireless RAN/Settlement Site/2504-NNE4G-4G#RO-BJM027-250022 | DU00005472657 | BJM027 | BJM027MV1 | YPTT | PANGERAN | BANJARMASIN | BANJAR | KOTA BANJARMASIN | DMT | CP2_RO Offload blacksite | 11458385 | -33018 | JL PANGERAN NO. 718/78 RT 10 KEL. PANGERAN KEC. BANJARMASIN UTARA KAB. BANJARMASIN KALSEL | Add RRU R9614 S23 (1) | L2300 | EQP New NE 4G LTE 2300 50 Mhz | - | Release | Release | - | Release | 2025-06-02 | 2025-06-03 | 2025-06-30 | Expired Need Extend | DOEID25060333 | NO NEED | NO NEED | DNWID0662025060302 | NO NEED | NO NEED | 2025-06-12 | - | - | - | - | - | DOP Finish | YPTT | Yoga | 2025-06-13 | 2025-06-12 | 2025-06-13 | 2025-06-13 | 100% | 2025-06-13 | Lacima Ok |  | 2025-06-13 | Connected | Connected | [8 empty] | 2025-06-13 | - | Clear | Clear | No Issue | 2025-06-13 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | no issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-6820 | 2025-06-26
13 |  | 2505-ADSTR-4G#RO-BJM742-220002 | Wireless RAN/Settlement Site/2505-ADSTR-4G#RO-BJM742-220002 | DU00005621174 | BJM742 | BJM742IV1 | YPTT | Addsect_DUTAMALLBANJARMASIN | BANJARMASIN | BANJAR | KOTA BANJARMASIN | Inprasia | CP2_2025 LOI List 51 | 11460272 | -332218 | Duta Mall Banjarmasin Kalsel JL. A Yani KM 2.5 | Add Antena Prose 10 Port (1) dan RRU R9264 M1821 (1) | L1800 | EQP Add Sector LTE 1800 2T2R | 1 Pcs Antena Kathrein 2 port dan 2 pcs Jumper DM-DM 5m | Release | Release | - | Release | 2025-06-01 | 2025-06-01 | 2025-06-30 | Expired Need Extend | DOEID25060335 | DOEID25060336 | NO NEED | DNWID0692025060501 | DNWID0662025060502 | NO NEED | 2025-06-24 | 2025-06-24 | - | - | - | - | DOP Finish | YPTT | Yoga | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | 100% | 2025-06-24 | Lacima OK | 2025-07-04 | 2025-06-26 | Connected | Connected | [8 empty] | 2025-06-26 | 2025-06-24 | Clear | Clear | No Issue | 2025-06-24 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Processing on IOMS | no issue | Scarlett | - | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-6939 | 2025-07-03
14 |  | 2505-MSCTR-4G#RO-MRB026-220024 | Wireless RAN/Settlement Site/2505-MSCTR-4G#RO-MRB026-220024 | DU00005599417 | MRB026 | MRB026MT1 | YPTT | TANGGULREJO | BANJARMASIN | HULU SUNGAI | BARITO KUALA | DMT | CP2_2025 LOI List 51 | 11440527 | -342134 | Desa Tanggul rt.7 Kec. Tabunganen Kab. Barito Kuala Kalimantan Selatan | Add Antena Mobi 4 port (1) dan RRU R9264M M7290(1) | L900 | EQP Upgrade Multisector LTE 900 | 1 pcs Antenna Sectoral 80010213 Kathrein, 1 pcs Antenna RF TDQ-182020DE-65F(V2) Tongyu dan 2 pcs RRU ZXSDR R8852E S9000 | Release | Release | - | Release | 28-May-25 | 2025-06-01 | 2025-06-30 | Expired Need Extend | - | - | - | DNWID0662025060305 | NO NEED | NO NEED | 2025-06-10 | 2025-06-10 | - | - | - | - | DOP Finish | YPTT | Yoga | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 100% | 2025-06-10 | Lacima OK | 2025-06-11 | 2025-06-10 | Connected | Connected | [8 empty] | 2025-06-10 | 2025-06-10 | Clear | Clear | No Issue | 2025-06-10 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Processing on IOMS | no issue | Scarlett | - | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-6722 | 2025-06-19
15 |  | 2506-NNE4G-4G#RO-SAG071-040045 | Wireless RAN/Settlement Site/2506-NNE4G-4G#RO-SAG071-040045 | DU00005663290 | SAG071 | SAG071MG1 | YPTT | MAJUKARYA | PONTIANAK | SINTANG | SANGGAU | PTI | New Infra Batch1 - List 47 | 11042535 | 15825 | KALIMANTAN BARAT. SANGGAU, PARINDU,MAJU KARYA | NEW INFRA | L900 | EQP New NE 4G LTE 900 10 MHz | - | Release | Release | Release | Release | 2025-06-22 | 2025-06-23 | 2025-07-07 | Expired Need Extend | DOEID250623B6 | DOEID250623B5 | NO NEED | DNWID0682025062301 | DNWID0712025062301 | NO NEED | 2025-06-24 | - | - | - | - | - | DOP Finish | YPTT | Andi Asmini, Del Piero | 2025-06-25 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 100% | 2025-07-25 | Lacima OK | 2025-07-31 | 2025-07-26 | Connected | Connected | [8 empty] | 01-Aug-25 | - | Clear | Clear | Rect batt | 2025-07-31 | 35 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | no issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-6940 | 2025-07-03
16 |  | 2506-NNE4G-4G#RO-NGP024-040037 | Wireless RAN/Settlement Site/2506-NNE4G-4G#RO-NGP024-040037 | DU00005663286 | NGP024 | NGP024MD1 | YPTT | KELAKIK | PONTIANAK | SINTANG | MELAWI | PTI | New Infra Batch1 - List 47 | 11175951 | -36026 | KALIMANTAN BARAT. MELAWI, NANGA PINOH,KELAKIK | NEW INFRA | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | Release | Release | 2025-06-22 | 2025-06-23 | 2025-07-07 | Expired Need Extend | DOEID250623B7 | DOEID250623B8 | NO NEED | DNWID0682025062303 | DNWID0712025062303 | NO NEED | 2025-06-30 | - | - | - | - | - | DOP Finish | YPTT | Del Piero | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 100% | 2025-06-08 | Laccima Ok | 2025-07-10 | 2025-07-08 | Connected | Connected | [8 empty] | 2025-07-09 | - | Clear | Clear | Rect batt | 2025-07-09 | 10 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | no issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7042 | 2025-07-09
17 |  | 2506-NNE4G-4G#RO-NGP023-040048 | Wireless RAN/Settlement Site/2506-NNE4G-4G#RO-NGP023-040048 | DU00005663301 | NGP023 | NGP023ML1 | YPTT | BATUBEGIGISPLITNGP007S12 | PONTIANAK | SINTANG | MELAWI | DMT | New Infra Batch1 - List 47 | 11155084 | -79621 | KALIMANTAN BARAT. MELAWI, TANAH PINOH,BATU BEGIGI | NEW INFRA | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | Release | Release | 2025-06-18 | 2025-06-19 | 2025-07-03 | Expired Need Extend | DOEID250630HX | DOEID250630HY | NO NEED | DNWID0682025070101 | DNWID0712025070101 | NO NEED | 2025-07-02 | - | - | - | - | - | DOP Finish | YPTT | Del Piero | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-03 | 100% | 2025-06-09 | Laccima Ok | 2025-07-10 | 2025-07-08 | Connected | Connected | [8 empty] | 2025-07-10 | - | Clear | Clear | Rect batt | 2025-07-10 | 8 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | no issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7413 | 2025-07-31
18 |  | 2506-ADSTR-4G#RO-EPQ206-230013 | Wireless RAN/Settlement Site/2506-ADSTR-4G#RO-EPQ206-230013 | DU00005761760 | EPQ206 | EPQ206EL1 | YPTT | PLI115_PELIHARIOleg | BANJARMASIN | BANJARMASIN | TANAH LAUT | TBG | 2025 - Batch#1 (One Leg) | 1147508 | -37926 | KALIMANTAN SELATAN, TANAH LAUT, PELAIHARI, PELAIHARI | Add Antena Mobi 12 Port , R9264 M1821, VBPe1p | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | - | - | 2025-07-15 | 2025-07-16 | 16-Aug-25 | Expired Need Extend | DOEID250714DI | DOEID250714DJ | NO NEED | DNWID0692025071401 | DNWID0662025071403 | NO NEED | 2025-07-16 | - | - | - | - | - | DOP Finish | YPTT | Yoga | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-17 | Laccima Ok | 2025-07-31 | 2025-07-22 | Connected | Connected | [8 empty] | 2025-07-22 | - | Clear | Clear | No Issue | 2025-07-17 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | no issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7412 | 2025-07-31
19 |  | 2506-NNE4G-4G#RO-NGP015-040043 | Wireless RAN/Settlement Site/2506-NNE4G-4G#RO-NGP015-040043 | DU00005663284 | PTS034 | PTS034ML1 | YPTT | CENDANAPANGSUMA | PONTIANAK | SINTANG | KAPUAS HULU | EMA | New Infra Batch1 - List 47 | 11199746 | 6175 | KALIMANTAN BARAT. KAPUAS HULU, SUHAID,NANGA SUHAID | NEW INFRA | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | Release | Release | 2025-07-22 | 2025-07-23 | 06-Aug-25 | Expired Need Extend | DOEID250721B6 | DOEID250721B7 | NO NEED | DNWIDO682025072102 | DNWIDO712025072103 | NO NEED | 2025-07-23 | - | - | - | - | - | DOP Finish | YPTT | Del Piero | 2025-07-23 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 100% | 21-Aug-25 | - | - | 21-Aug-25 | Connected | Connected | [8 empty] | 2025-09-09 | - | - | - | Waiting Rect batt | 2026-09-08 | 16 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check In | in Progress | no issue | Scarlett |  | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7414 | 2025-07-31
20 |  | 2506-NNE4G-4G#RO-BBR401-230030 | Wireless RAN/Settlement Site/2506-NNE4G-4G#RO-BBR401-230030 | DU00005761768 | BBR401 | BBR401IL1 | YPTT | BandaraSyamsuddinNoor | BANJARMASIN | BANJARMASIN | KOTA BANJARMASIN | APS | New Infra CP#3 Batch1 | 1147607 | -3436532 | Jalan Akses Bandara Baru, Landasan Ulin Utara, Kec. Landasan Ulin, Kota Banjar Baru, Kalimantan Selatan 70713 | NEW INFRA | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | - | Release | 2025-07-27 | 2025-07-28 | 28-Aug-25 | Expired Need Extend | DOEID25072984 | DOEID25072985 | NO NEED | DNWID0692025072901 | DNWID0662025072901 | NO NEED | 2025-07-30 | - | - | - | - | - | DOP Finish | YPTT | Yoga | 2025-07-30 | 2025-07-30 | 2025-07-31 | 03-Aug-25 | 100% | 15-Aug-25 | Laccima Ok | 19-Aug-25 | 15-Aug-25 | Connected | Connected | [8 empty] | 24-Aug-25 | - | - | - | waiting port metroE dan Recty | 24 Aug | 24 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7650 | 2025-08-27
21 |  | 2506-NNE4G-4G#RO-MPW127-040036 | Wireless RAN/Settlement Site/2506-NNE4G-4G#RO-MPW127-040036 | DU00005663295 | MTP067 | MTP067MT1 | YPTT | RANTAUBALAI | BANJARMASIN | BANJARMASIN | BANJAR | PTI | 2025 - Batch#1 (74) | 11514376 | -34443 | KALIMANTAN SELATAN, BANJAR, ARANIO, RANTAU BALAI | NEW INFRA | L900 | EQP New NE 4G LTE 900 10 MHz | - | Release | Release | - | Release | 06-Aug-25 | 07-Aug-25 | 2025-09-04 | Expired Need Extend | DOEID25073077 | DOEID25073078 | NO NEED | DNWID0662025073002 | DNWID0692025073001 | NO NEED | 2025-07-31 | - | - | - | - | - | DOP Finish | YPTT | Yoga | 2025-07-31 | 2025-07-31 | 2025-07-31 | 05-Aug-25 | 100% | 05-Aug-25 | Laccima Ok | 07-Aug-25 | 05-Aug-25 | Connected | Connected | [8 empty] | 24-Aug-25 | - | Clear | Clear | Waiting permit | 24 Aug | 24 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7650 | 2025-08-27
22 |  | 2505-ADSTR-4G#RO-BJM742-220001 | Wireless RAN/Settlement Site/2505-ADSTR-4G#RO-BJM742-220001 | DU00005621176 | BLC037 | BLC037MV1 | YPTT | Addsect_SEKAPUK | KOTABARU | KOTABARU | TANAH BUMBU | TSEL | Capacity Upgrade 4G | 11551499 | -37175 | JL.PROPINSI DUSUN RT 03 KEL.SEKAPUK KEC.SATUI KAB TANAH BUMBU | Add RRU R9614 S23 (1) | L2300 | EQP Add Sector LTE 2300 4T4R | - | Release | Release | - | Release | 2025-07-31 | ######### | 30-Aug-25 | Expired Need Extend | DOEID250805EU | NO NEED | NO NEED | DNWID0662025080503 | NO NEED | NO NEED | 08-Aug-25 | [5 empty] | DOP Finish | YPTT | Yoga | 08-Aug-25 | 08-Aug-25 | 08-Aug-25 | 09-Aug-25 | 100% | 14-Aug-25 | Laccima Ok | 19-Aug-25 | 14-Aug-25 | Connected | Connected | [8 empty] | 14-Aug-25 | - | Clear | Clear | Waiting LOM VBP | 14 Aug | 6 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8129 | 2025-10-16
23 |  | 2506-ADSTR-4G#RO-EPQ200-230007 | Wireless RAN/Settlement Site/2506-ADSTR-4G#RO-EPQ200-230007 | DU00005761759 | EPQ200 | EPQ200M41 | YPTT | MPW182_RSUDUBINIPOlegDMT | PONTIANAK | SINGKAWANG | MEMPAWAH | DMT | ONE LEG | 10896433 | 33681 | KALIMANTAN BARAT, MEMPAWAH, MEMPAWAH HILIR, KUALA SECAPAH | Ant Mobi 12 Port (1), RRU R9264 M1821(1), VBPe1p(1) | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | Release | Release | - | - | - | #VALUE! | DOEID250808CR | DOEID250808CS | NO NEED | DNWID0682025080801 | DNWID0712025080801 | NO NEED | 09-Aug-25 | - | - | - | - | - |  | YPTT | Julianto | 09-Aug-25 | 09-Aug-25 | 09-Aug-25 | 09-Aug-25 | 100% | Waiting Kabel optik dari EPQ200 ke MPWxxx | - | - | 12-Oct-25 | Connected | Connected | [8 empty] | 16-Oct-25 | - | - | - | Waiting Optik |  |  | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Waiting Vendor Approval | No Issue | Scarlett | [13 empty] | PO Confirmed | S1ID2023070102WBF1-8129 | 2025-10-16
24 |  | 2507-U32T32R-4G#RO-BRI009-280009-S3 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-BRI009-280009-S3 | DU00005895018 | BRI009 | BRI009VE1 | YPTT | MUALIMIN | BANJARMASIN | HULU SUNGAI | HULU SUNGAI TENGAH | TSEL | CP#3 Batch1 Capacity Upgrade 4G | 11538692 | -259293 | JL. MUALIM NO. 66 RT 13/04 KEL. BARABAI DARAT, KEC. BARABAI, KAB. HULU SUNGAI TENGAH KALSEL | MIMO ZXRAN A9652A S23(1), Pole for new antenna (3m) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | 1 Pcs RRU R8978 S2300 include SFP, Brcaket, Conector Power, 70m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 90m, 4 pcs Jumper 1/2" 4.3M-NM 5m | Release | Release | - | Release | 05-Aug-25 | 06-Aug-25 | 2025-09-03 | Expired Need Extend | DOEID250808D5 | DOEID250808D6 | NO NEED | DNWID0662025080904 | DNWID0692025080902 | NO NEED | 10-Aug-25 | 12-Aug-25 | 13-Aug-25 | - | 13-Aug-25 | handcarry | DOP Finish | YPTT | Yoga | 10-Aug-25 | 10-Aug-25 | 10-Aug-25 | 11-Aug-25 | 100% | 11-Aug-25 | Laccima Ok | 14-Aug-25 | 11-Aug-25 | Connected | Connected | [8 empty] | 12-Aug-25 | 11-Aug-25 | Clear | Clear | No Isuue | 11-Aug-25 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8129 | 2025-10-16
25 |  | 2507-NNE4G-4G#RO-PRG037-280035 | Wireless RAN/Settlement Site/2507-NNE4G-4G#RO-PRG037-280035 | DU00005895023 | PRG037 | PRG037M41 | YPTT | GURUBAHITPTI | BANJARMASIN | HULU SUNGAI | BALANGAN | PTI | CP#3 Batch1 New NE 4G | 115449901 | -2395135 | Jl. Ahmad Yani RT003, Kel. Mantimin, Kec. Batu Mandi, Kab. Balangan | BBU VBPe1p(1), RRU R9614 S2300(1) | L2300 | EQP New NE 4G LTE 2300 50 Mhz | - | Release | Release | Release | Release | 07-Aug-25 | 09-Aug-25 | 2025-09-06 | Expired Need Extend | DOEID250808DA | DOEID250808D9 | NO NEED | DNWID0692025080903 | DNWID0662025080902 | NO NEED | 12-Aug-25 | - | - | - | - | - | DOP Finish | YPTT | Yoga | 12-Aug-25 | 12-Aug-25 | 12-Aug-25 | 12-Aug-25 | 100% | 12-Aug-25 | Laccima Ok | 14-Aug-25 | 12-Aug-25 | Connected | Connected | [8 empty] | 12-Aug-25 | - | Clear | Clear | No Isuue | 12-Aug-25 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8129 | 2025-10-16
26 |  | 2507-U32T32R-4G#RO-MTW015-280028-S3 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-MTW015-280028-S3 | DU00005895045 | MTW015 | MTW015M41 | YPTT | LAHEI | PALANGKARAYA | BARITO | BARITO UTARA | TSEL | CP#3 Batch1 Capacity Upgrade 4G | 114928844 | -872784 | LAHEI 2 SEBRANG, RT.08 KEL.LAHEI KEC.LAHEI KAB.BARITO UTARA - KALTENG | BBU VBPe2q(1), MIMO A9732 M1821(1), Pole for new antenna (3m) | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | 1 pcs VBPc7 | Release | Release | Release | Release | 05-Aug-25 | 06-Aug-25 | 2025-09-03 | Expired Need Extend | DOEID250808DH | DOEID250808DI | NO NEED | DNWID0672025080905 | DNWID0702025080901 | NO NEED | 12-Aug-25 | 13-Aug-25 | - | - | - | handcarry | DOP Finish | YPTT | Benny | 12-Aug-25 | 12-Aug-25 | 13-Aug-25 | 13-Aug-25 | 100% | 13-Aug-25 | Laccima Ok | 14-Aug-25 | 13-Aug-25 | Connected | Connected | [8 empty] | 14-Aug-25 | 13-Aug-25 | Clear | Clear | No Isuue | 13-Aug-25 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8129 | 2025-10-16
27 |  | 2507-ADSTR-4G#RO-MPW134-280034 | Wireless RAN/Settlement Site/2507-ADSTR-4G#RO-MPW134-280034 | DU00005895049 | MPW134 | MPW134M41 | YPTT | PENTEKTBG | PONTIANAK | SINGKAWANG | MEMPAWAH | TBG | CP#3 Batch1 Capacity Upgrade 4G | 109153896 | 51651 | Jl. Sungai Pinggan, Kab. PontianakDesa PentekKec. Sadaniang | Add Antena mobi 12 port(1) | L2300 | EQP Add Sector LTE 2300 4T4R | 1 Pcs antena Commscope LDX-9014DS-VTM, 1 Pcs antena Commscope HBXX-6517DS-VTM | Release | Release | Release | Release | 11-Aug-25 | 12-Aug-25 | 26-Aug-25 | Expired Need Extend | DOEID250811AP | NO NEED | NO NEED | DNWID0682025081104 | NO NEED | NO NEED | 13-Aug-25 | 14-Aug-25 | - | - | - | - | NY VALIDATION | YPTT | Arya | 13-Aug-25 | 13-Aug-25 | 13-Aug-25 | 13-Aug-25 | 100% | 13-Aug-25 | Laccima Ok | 14-Aug-25 | 13-Aug-25 | Connected | Connected | [8 empty] | 16-Aug-25 | 13-Aug-25 | Clear | Clear | Prepare tools & mengembalikan kunci ke GH | 16-Aug-25 | 4 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No Issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | No Need |  |  |  | PO not clear |  | PO Confirmed | S1ID2023070102WBF1-8129 | 2025-10-16
28 |  | 2507-U32T32R-4G#RO-MTW176-280017-S1 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-MTW176-280017-S1 | DU00005895012 | MTW176 | MTW176M41 | YPTT | TAWANJAYADMT | PALANGKARAYA | BARITO | BARITO UTARA | DMT | CP#3 Batch1 Capacity Upgrade 4G | 114914124 | -1152399 | Buntok Baru, Central Teweh, North Barito Regency, Central Kalimantan | MIMO ZXRAN A9652A S23(1), Pole for new antenna (3m) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release | 03-Aug-25 | 05-Aug-25 | 2025-09-02 | Expired Need Extend | DOEID250808DD | DOEID250808DE | NO NEED | DNWID6702025080908 | DNWID0702025070904 | NO NEED | 14-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Benny | 14-Aug-25 | 14-Aug-25 | 14-Aug-25 | 15-Aug-25 | 100% | 15-Aug-25 | Laccima Ok | 19-Aug-25 | 15-Aug-25 | Connected | Connected | [8 empty] | 15-Aug-25 | - | Clear | Clear | No Isuue | 15-Aug-25 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | No Need |  |  |  | PO not clear |  | PO Confirmed | S1ID2023070102WBF1-8129 | 2025-10-16
29 |  | 2507-U32T32R-4G#RO-MTW176-280017-S3 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-MTW176-280017-S3 | DU00005895021 | MTW176 | MTW176M41 | YPTT | TAWANJAYADMT | PALANGKARAYA | BARITO | BARITO UTARA | DMT | CP#3 Batch1 Capacity Upgrade 4G | 114914124 | -1152399 | Buntok Baru, Central Teweh, North Barito Regency, Central Kalimantan | BBU VBPe2q(1), MIMO ZXRAN A9652A S23(1), Pole for new antenna (3m) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | 1 Pcs RRU R8998G S2300 include SFP, Brcaket, Conector Power, 70m RRU PWR Cable 2 core Type-D 10mm², 2 Pcs RRU Fiber LC-LC 90m, 4 pcs Jumper 1/2" 4.3M-NM 5m | Release | Release | Release | Release | 03-Aug-25 | 05-Aug-25 | 2025-09-02 | Expired Need Extend | DOEID250808DF | DOEID250808DG | NO NEED | DNWID0672025080906 | DNWID0702025080907 | NO NEED | 14-Aug-25 | 15-Aug-25 | - | - | - | - | NY VALIDATION | YPTT | Benny | 14-Aug-25 | 14-Aug-25 | 14-Aug-25 | 15-Aug-25 | 100% | 15-Aug-25 | Laccima Ok | 19-Aug-25 | 15-Aug-25 | Connected | Connected | [8 empty] | 15-Aug-25 | 15-Aug-25 | Clear | Clear | No Isuue | 15-Aug-25 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | No Need |  |  |  | PO not clear |  | #N/A | #N/A | #N/A
30 |  | 2506-NNE4G-4G#RO-BLC046-040038 | Wireless RAN/Settlement Site/2506-NNE4G-4G#RO-BLC046-040038 | DU00005663293 | KBA051 | KBA051M41 | YPTT | PAMUKANINDAHPTI | BANJARMASIN | KOTA BARU | KOTA BARU | PTI | CAPEX RAN 2 PART 3 2025 | 11625384 | -238738 | KALIMANTAN SELATAN, KOTA BARU, PAMUKAN UTARA, PAMUKAN INDAH | NEW INFRA | L900 | EQP New NE 4G LTE 900 10 MHz | - | Release | Release | Release | Release | 03-Aug-25 | 04-Aug-25 | 31 Aug | Expired Need Extend | DOEID250808D7 | DOEID250808D8 | NO NEED | DNWID0692025080901 | DNWID0662025080901 | NO NEED | 15-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Yoga | 14-Aug-25 | 15-Aug-25 | 14-Aug-25 | 16-Aug-25 | 100% | 16-Aug-25 | Laccima Ok | 19-Aug-25 | 20-Aug-25 | Connected | Connected | [8 empty] | 16-Aug-25 | - | Clear | Clear | waiting tim metroE |  | 4 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8129 | 2025-10-16
31 |  | 2507-U32T32R-4G#RO-KKP007-280025-S3 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-KKP007-280025-S3 | DU00005895015 | KKP007 | KKP007VR1 | YPTT | TIMPAH | PALANGKARAYA | BARITO | KAPUAS | TSEL | CP#3 Batch1 Capacity Upgrade 4G | 114479898 | -1721984 | JL. PEMDA RT 04, DS. TIMPAH, KEC. TIMPAH, KAB. KAPUAS | BBU VBPe1p(1), BBU VBPe2q(1), MIMO A9732 M1821(1), Pole for new antenna (3m) | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | 2 Pcs Board VBPc7 | Release | Release | Release | Release | 03-Aug-25 | 05-Aug-25 | 2025-09-02 | Expired Need Extend | DOEID250805ES | DOEID250805ET | NO NEED | DNWID0672025080502 | NO NEED | NO NEED | 16-Aug-25 | 18 Aug | - | - | - | - | NY VALIDATION | YPTT | Benny | 16-Aug-25 | 16-Aug-25 | 16-Aug-25 | 17-Aug-25 | 100% | 18-Aug-25 | Laccima Ok | 19-Aug-25 | 18-Aug-25 | Connected | Connected | [8 empty] | 18-Aug-25 | 18-Aug-25 | Clear | Clear | waiting user BSS | 18-Aug-25 | 3 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8129 | 2025-10-16
32 |  | 2508-NNE4G-4G#RO-KKP082-070040 | Wireless RAN/Settlement Site/2508-NNE4G-4G#RO-KKP082-070040 | DU00005931474 | KKP082 | KKP082 | YPTT | HURUNGPUKUNG | PALANGKARAYA | BARITO | KAPUAS | TBG | - | 114.3896 | -1.4164 | Hurung Pukung, Kapuas Tengah, Kapuas, KALIMANTAN TENGAH | Add Jumper | L2300 | EQP Add Sector LTE 2300 4T4R | - | Release | Release | Release | Release | 06-Aug-25 | 08-Aug-25 | 22-Aug-25 | Expired Need Extend | - | - | - | DNWID0672025081501 | NO NEED | NO NEED | 16-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Benny | 18-Aug-25 | 16-Aug-25 | 18-Aug-25 | 18-Aug-25 | 100% | 18-Aug-25 | Laccima Ok | 19-Aug-25 | 18-Aug-25 | Connected | Connected | [8 empty] | 18-Aug-25 | - | Clear | Clear | No Issue | 18-Aug-25 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7922 | 2025-09-25
33 |  | 2506-ADSTR-4G#RO-EPQ203-230010 | Wireless RAN/Settlement Site/2506-ADSTR-4G#RO-EPQ203-230010 | DU00005761772 | EPQ203 | EPQ203ED1 | YPTT | TJL018_SUNGAIPIMPINGOleg | BANJARMASIN | NEW HULU SUNGAI | TABALONG | CMI | ONE LEG | 115.3275 | -2.2126 | KALIMANTAN SELATAN, TABALONG, TANJUNG, SUNGAI PIMPING | BBU VBPe1p(1), RRU R9264 M1821(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1) | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | - | Release | 2025-07-18 | 2025-07-19 | 19-Aug-25 | Expired Need Extend | DOEID25081603 | DOEID25081604 | NO NEED | DNWID0662025081601 | DNWID0692025081601 | NO NEED | 16-Aug-25 | - | - | - | - | - | DOP Finish | YPTT | Ponco | 16-Aug-25 | 16-Aug-25 | 17-Aug-25 | 17-Aug-25 | 100% | 17-Aug-25 | Laccima Ok |  | 17-Aug-25 | Connected | Connected | [8 empty] | 28-Aug-25 | - | Clear | Clear | waiting task | 28 Aug | 1 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8129 | 2025-10-16
34 |  | 2507-U32T32R-4G#RO-KKP046-280007-S2 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-KKP046-280007-S2 | DU00005895019 | KKP046 | KKP046M41 | YPTT | MARAPITPTI | PALANGKARAYA | BARITO | KAPUAS | PTI | CP#3 Batch1 Capacity Upgrade 4G | 114.3578 | -1.3234 | Jl.Umum, Ds. Marapit RT II, Kec. Kapuas Tengah, Kab. Kapuas | BBU VBPe1p(1), ZXRAN A9652A S23(1), Pole for new antenna (3m) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | - | Release | Release | - | Release | 14-Aug-25 | 15-Aug-25 | 2025-09-05 | Expired Need Extend | DOEID25081833 | DOEID25081834 | NO NEED | DNWID0672025081801 | DNWID0702025081801 | NO NEED | 19-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Benny | 19-Aug-25 | 19-Aug-25 | 19-Aug-25 | 19-Aug-25 | 100% | 19-Aug-25 | Laccima Ok |  | 19-Aug-25 | Connected | Connected | [8 empty] | 20-Aug-25 | 20-Aug-25 | Clear | Clear | No Isue | 20-Aug-25 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  | LOM jumper ^ connector, solved tgl 4okt; Issue TRM, solved 4okt | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
35 |  | 2507-U32T32R-4G#RO-KKP046-280007-S3 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-KKP046-280007-S3 | DU00005895039 | KKP046 | KKP046M41 | YPTT | MARAPITPTI | PALANGKARAYA | BARITO | KAPUAS | PTI | CP#3 Batch1 Capacity Upgrade 4G | 114.3578 | -1.3234 | Jl.Umum, Ds. Marapit RT II, Kec. Kapuas Tengah, Kab. Kapuas | ZXRAN A9652A S23(1), Pole for new antenna (3m) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | 1 Pcs RRU R8998G S2300 include SFP, Brcaket, Conector Power, 70m RRU PWR Cable 2 core Type-D 10mm², 2 Pcs RRU Fiber LC-LC 90m | Release | Release | - | Release | 14-Aug-25 | 15-Aug-25 | 2025-09-05 | Expired Need Extend | DOEID25081835 | DOEID25081836 | NO NEED | DNWID0672025081802 | DNWID0702025081802 | NO NEED | 19-Aug-25 | 20-Aug-25 | - | - | - | - | NY VALIDATION | YPTT | Benny | 19-Aug-25 | 19-Aug-25 | 19-Aug-25 | 19-Aug-25 | 100% | 19-Aug-25 | Laccima Ok |  | 19-Aug-25 | Connected | Connected | [8 empty] | 20-Aug-25 | 20-Aug-25 | Clear | Clear | No Isue | 20-Aug-25 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | #N/A | #N/A | #N/A
36 |  | 2507-REENG-4G#RO-KBA012-280030 | Wireless RAN/Settlement Site/2507-REENG-4G#RO-KBA012-280030 | DU00005895031 | KBA012 | KBA012M41 | YPTT | SEJAKAHTBG | BANJARMASIN | BATULICIN | KOTA BARU | TBG | CP#3 Batch1 Re-Engineering 4G | 116.2226 | -3.5625 | DERANGGA, PULAU LAUT TIMUR, KOTA BARU, KALIMANTAN SELATAN | BBU VBPe1p(1), Reuse 1 Pcs RRU R8998G S2300 inlcude Conector Power use ex dismantle take from WH Tsel | L2300 | EQP eNode B Modular Relocation Service New NE LTE 2300 | - | Release | Release | - | Release | 08-Aug-25 | 07-Aug-25 | 2025-09-05 | Expired Need Extend | DOEID25081317 | DOEID25081316 | NO NEED | DNWID0662025081301 | DNWID0692025081302 | NO NEED | 18-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Yoga | 19-Aug-25 | 18-Aug-25 | 19-Aug-25 | 19-Aug-25 | 100% | 19-Aug-25 | Laccima Ok |  | 19-Aug-25 | Connected | Connected | [8 empty] | 19-Aug-25 | - | Clear | Clear | No Isue | 19-Aug-25 | 0 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7923 | 2025-09-25
37 |  | 2507-U32T32R-4G#RO-KKP080-280003-S1 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-KKP080-280003-S1 | DU00005895051 | KKP080 | KKP080M41 | YPTT | KAYUBULANTBG | PALANGKARAYA | BARITO | KAPUAS | TBG | CP#3 Batch1 Capacity Upgrade 4G | 11443437 | -1.464 | KALIMANTAN TENGAH. KAPUAS, KAPUAS TENGAH,KAYU BULAN | BBU VBPe2q(1), ZXRAN A9652A S23(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | - | Release | Release | - | Release | 08-Aug-25 | 11-Aug-25 | 2025-09-08 | Expired Need Extend | DOEID25081877 | DOEID25081878 | NO NEED | DNWID0672025081803 | DNWID0702025081804 | NO NEED | 20-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Benny | 20-Aug-25 | 20-Aug-25 | 21-Aug-25 | 21-Aug-25 | 100% | 21-Aug-25 | Laccima Ok |  | 21-Aug-25 | Connected | Connected | [8 empty] | 22-Aug-25 | - | Clear | Clear | No Isue | 22-Aug-25 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
38 |  | 2507-U32T32R-4G#RO-KKP080-280003-S2 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-KKP080-280003-S2 | DU00005895025 | KKP080 | KKP080M41 | YPTT | KAYUBULANTBG | PALANGKARAYA | BARITO | KAPUAS | TBG | CP#3 Batch1 Capacity Upgrade 4G | 11443437 | -1.464 | KALIMANTAN TENGAH. KAPUAS, KAPUAS TENGAH,KAYU BULAN | ZXRAN A9652A S23(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | 1 Pcs RRU R8998G S2300 include SFP, Brcaket, Conector Power, 70m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 90m, 4 pcs Jumper 1/2" 4.3M-NM 5m | Release | Release | - | Release | 08-Aug-25 | 11-Aug-25 | 2025-09-08 | Expired Need Extend | DOEID25081879 | DOEID25081880 | NO NEED | DNWID0672025081804 | DNWID0702025081803 | NO NEED | 20-Aug-25 | 21-Aug-25 | - | - | - | - | NY VALIDATION | YPTT | Benny | 20-Aug-25 | 20-Aug-25 | 21-Aug-25 | 21-Aug-25 | 100% | 21-Aug-25 | Laccima Ok |  | 21-Aug-25 | Connected | Connected | [8 empty] | 22-Aug-25 | 21-Aug-25 | Clear | Clear | No Isue | 22-Aug-25 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | [5 empty] | #N/A | #N/A | #N/A
39 |  | 2507-U32T32R-4G#RO-NGP014-280012-S3 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-NGP014-280012-S3 | DU00005895040 | NGP014 | NGP014VR1 | YPTT | NANGASOKANTSEL | PONTIANAK | SINTANG | MELAWI | TSEL | CP#3 Batch1 Capacity Upgrade 4G | 111501246 | -0.90226 | JL.PROPINSI KOTA BARU - NANGA SOKAN DS.PANDAN KEC.NANGA SOKAN KAB.MELAWI | Add BBU VBPe2q(1), A9732 M1821(1), Pole for new antenna (3m) | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release | 18-Aug-25 | 19-Aug-25 | 2025-09-02 | Expired Need Extend | DOEID250819C6 | DOEID250819C7 | NO NEED | DNWID0682025081908 | DNWID0712025081905 | NO NEED | 21-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Arya | 21-Aug-25 | 21-Aug-25 | 21-Aug-25 | 22-Aug-25 | 100% | 22-Aug-25 | Laccima Ok |  | 22-Aug-25 | Connected | Connected | [8 empty] | 23-Aug-25 | - | Clear | Clear | No Isue | 22-Aug-25 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8068 | 2025-10-09
40 |  | 2507-NNE4G-4G#RO-SHR323-280040 | Wireless RAN/Settlement Site/2507-NNE4G-4G#RO-SHR323-280040 | DU00005895035 | SHR323 | SHR323MR1 | YPTT | BELITANGSATUDMT | PONTIANAK | SINTANG | Sekadau | DMT | CP#3 Batch1 New NE 4G | 11125303 | 13244 | Dusun Belitang I RT.09 RW.05 SEKADAU 76114, Kalbar | Add BBU VBPe1p(1) | L2100 | EQP New NE 4G LTE 2100 20 Mhz | - | Release | Release | Release | Release | 18-Aug-25 | 19-Aug-25 | 2025-09-02 | Expired Need Extend | NO NEED | NO NEED | NO NEED | DNWID0682025081905 | NO NEED | NO NEED | 23-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Arya | 23-Aug-25 | 23-Aug-25 | 23-Aug-25 | 23-Aug-25 | 100% | 23-Aug-25 | Laccima Ok |  | 23-Aug-25 | Connected | Connected | [8 empty] | 23-Aug-25 | - | Clear | Clear | No Isue | 23-Aug-25 | 0 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8130 | 2025-10-16
41 |  | 2507-ADSTR-4G#RO-SAG067-280033 | Wireless RAN/Settlement Site/2507-ADSTR-4G#RO-SAG067-280033 | DU00005895026 | SAG067 | SAG067M41 | YPTT | Melenggang | PONTIANAK | SINTANG | SANGGAU | DMT | CP#3 Batch1 Capacity Upgrade 4G | 110722822 | 790234 | KALIMANTAN BARAT. SANGGAU, SELKAYAM,MELENGGANG | EQP Add Sector LTE 2300 4T4R | L2300 | Reconfiq Jumper (Tidak ada penambahan HW), Add Jumper NM-4.3M 4 pcs | - | Release | Release | Release | Release | 18-Aug-25 | 19-Aug-25 | 2025-09-02 | Expired Need Extend | NO NEED | NO NEED | NO NEED | DNWID0682025081907 | NO NEED | NO NEED | 24-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Arya | 24-Aug-25 | 24-Aug-25 | 24-Aug-25 | 24-Aug-25 | 100% | 24-Aug-25 | Laccima Ok |  | 24-Aug-25 | Connected | Connected | [8 empty] | 24-Aug-25 | - | Clear | Clear | No Isue | 24-Aug-25 | 0 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8130 | 2025-10-16
42 |  | 2506-ADSTR-4G#RO-EPQ201-230008 | Wireless RAN/Settlement Site/2506-ADSTR-4G#RO-EPQ201-230008 | DU00005761751 | EPQ201 | EPQ201M41 | YPTT | SBS016_SEMPARUKOlegBIT | PONTIANAK | SINGKAWANG | SAMBAS | BIT | CAPEX RAN 2 PART 3 2025 | 10908783 | 117592 | KALIMANTAN BARAT, SAMBAS, SEMPARUK, SEMPARUK | R9264 M1821(1), Mobi 12 port (1), VBPe1p(1) | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | Release | Release | 22-Aug-25 | 22-Aug-25 | 2025-09-05 | Expired Need Extend | DOEID25082286 | NO NEED | NO NEED | DNWID0682725082202 | NO NEED | NO NEED | 25-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Del Piero | 25-Aug-25 | 25-Aug-25 | 26-Aug-25 | 26-Aug-25 | 100% | 2025-09-22 | Laccima Ok | 02-Oct-25 | 2025-09-22 | Connected | Connected | [8 empty] | 15-Oct-25 | - |  |  | waiting visit | 26-Aug-25 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7905 | 2025-09-24
43 |  | 2508-NNE4G-4G#RO-SAG511-070006 | Wireless RAN/Settlement Site/2508-NNE4G-4G#RO-SAG511-070006 | DU00005931518 | SAG511 | SAG511M41 | YPTT | HIBUNPARINDUDMT | PONTIANAK | SINTANG | SANGGAU | DMT | CP#3 Part 68 | 11049015 | 23079 | Pusat Damai, Parindu, Sanggau Regency, West Kalimantan | BBU VBPe1p(1), RRU R9614 S2300(1) | L2300 | EQP New NE 4G LTE 2300 50 Mhz | - | Release | Release | Release | Release | 22-Aug-25 | 25-Aug-25 | 2025-09-08 | Expired Need Extend | DOEID250825C6 | NO NEED | NO NEED | DNWID0682025082509 | NO NEED | NO NEED | 28-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Arya | 26-Aug-25 | 26-Aug-25 | 26-Aug-25 | 26-Aug-25 | 100% | 26-Aug-25 | Laccima Ok |  | 26-Aug-25 | Connected | Connected | [8 empty] | 25-Oct-25 | - | - | - | waiting plan | 26-Aug-25 | 0 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED |  |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-7905 | 2025-09-24
44 |  | 2508-NNE4G-4G#RO-SHR032-130002 | Wireless RAN/Settlement Site/2508-NNE4G-4G#RO-SHR032-130002 | DU00005955084 | SHR032 | SHR032M41 | YPTT | SUNGAIAYAKDUAPTI | PONTIANAK | SINTANG | SEKADAU | PTI | LIST 13_New NE 4G | 1110708 | 11044 | KALIMANTAN BARAT, SEKADAU, BELITANG HILIR, SUNGAI AYAK DUA | NEW INFRA | L1800 | EQP New NE 4G LTE 1800 20 Mhz-4T4R | - | Release | Release | Release | Release | 27-Aug-25 | 27-Aug-25 | 2025-09-10 | Expired Need Extend | DOEID25082517 | DOEID25082518 | NO NEED | DNWID0682025082504 | DNWID0712025082501 | NO NEED | 27-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Arya | 27-Aug-25 | 27-Aug-25 | 27-Aug-25 | 28-Aug-25 | 100% | 28-Aug-25 | Laccima Ok |  | 28-Aug-25 | Connected | Connected | [8 empty] | 07-Oct-25 |  |  |  | waiting rru | 6 Oct | 40 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7905 | 2025-09-24
45 |  | 2508-REENG-4G#RO-SHR032-130007 | Wireless RAN/Settlement Site/2508-REENG-4G#RO-SHR032-130007 | DU00005955081 | SHR032 | SHR032MT1 | YPTT | SUNGAIAYAKDUAPTI | PONTIANAK | SINTANG | SEKADAU | PTI | LIST 13_Re-Engineering 4G | 1110708 | 11044 | KALIMANTAN BARAT, SEKADAU, BELITANG HILIR, SUNGAI AYAK DUA | Add RRU R8852E S9000(3), BBU VBPe1p(1) | L900 | EQP eNode B Relocation Service | - | Release | Release | Release | Release | 27-Aug-25 | 27-Aug-25 | 2025-09-10 | Expired Need Extend | DOEID25082519 | NO NEED | NO NEED | DNWID0682025082508 | NO NEED | NO NEED | 27-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Arya | 27-Aug-25 | 27-Aug-25 | 04-Oct-25 | 04-Oct-25 | 100% | 05-Oct-25 | Laccima Ok |  | 04-Oct-25 | Connected | Connected | [8 empty] | 07-Oct-25 |  |  |  | waiting rru | 6 Oct | 40 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7905 | 2025-09-24
46 |  | 2508-REENG-4G#RO-BEK020-070031 | Wireless RAN/Settlement Site/2508-REENG-4G#RO-BEK020-070031 | DU00005931532 | BEK020 | BEK020M41 | YPTT | BUKITSERAYAN2DMT | PONTIANAK | SINGKAWANG | BENHKAYANG | DMT | CP#3 Part 68 | 1092183 | 86105 | PETAK BATUAH, SAMALANTAN, BENGKAYANG, KALIMANTAN BARAT | Reuse 1 Pcs RRU R8998G S2300(1), BBU VBPe1p(1) | L2300 | EQP eNode B Modular Relocation Service New NE LTE 2300 | - | Release | Release | Release | Release | 21-Aug-25 | 20-Aug-25 | 10-Oct-25 | Expired Need Extend | DOEID25082516 | NO NEED | NO NEED | DNWID0682025082505 | NO NEED | NO NEED | 27-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Del piero | 27-Aug-25 | 27-Aug-25 | 27-Aug-25 | 27-Aug-25 | 100% | 2025-09-10 | Laccima Ok |  | 27-Aug-25 | Connected | Connected | [8 empty] | 2025-09-10 | - | - | - | RRU broken | 2025-09-10 | 14 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7905 | 2025-09-24
47 |  | 2508-NNE4G-4G#RO-NBA019-070002 | Wireless RAN/Settlement Site/2508-NNE4G-4G#RO-NBA019-070002 | DU00005931509 | NBA019 | NBA019M41 | YPTT | TIANGTANJUNGDMT | PONTIANAK | SINGKAWANG | LANDAK | DMT | CP#3 Part 68 | 1094076 | 693909 | PANDU RAYA, MEMPAWAH HULU, LANDAK, KALIMANTAN BARAT | Add BBU VBPe1p(1), RRU R9614 S2300(1), | L2300 | EQP New NE 4G LTE 2300 50 Mhz | - | Release | Release | Release | Release | 22-Aug-25 | 25-Aug-25 | 2025-09-08 | Expired Need Extend | DOEID25082515 | NO NEED | NO NEED | DNWID0682025082506 | NO NEED | NO NEED | 28-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Del piero | 28-Aug-25 | 28-Aug-25 | 28-Aug-25 | 28-Aug-25 | 100% | 28-Aug-25 | Laccima Ok |  | 28-Aug-25 | Connected | Connected | [8 empty] | 28-Aug-25 | - | - | - | - | 28-Aug-25 | 0 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED |  |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-7905 | 2025-09-24
48 |  | 2508-NNE4G-4G#RO-STA037-130016 | Wireless RAN/Settlement Site/2508-NNE4G-4G#RO-STA037-130016 | DU00005955094 | STA037 | STA037M41 | YPTT | MENSIAPBARUPTI | PONTIANAK | SINTANG | SINTANG | PTI | LIST 13_New NE 4G | 11134808 | 14932 | KALIMANTAN BARAT, SINTANG, TEMPUNAK, MENSIAP BARU | NEW INFRA | L1800 | EQP New NE 4G LTE 1800 20 Mhz-4T4R |  | Release | Release | Release | Release | 29-Aug-25 | 30-Aug-25 | 2025-09-13 | Permit Ready | DOEID250826FA | DOEID250826FB | NO NEED | DNWID0682025082604 | DNWID0712025082603 | NO NEED | 29-Aug-25 | - | - | - | - | - | DOP Finish | YPTT | Arya | 29-Aug-25 | 29-Aug-25 | 30-Aug-25 | 31-Aug-25 | 100% | 31-Aug-25 | Laccima Ok |  | 2025-09-03 | Connected | Connected | [8 empty] | 2025-09-03 | - | - | - | - | 2025-09-03 | 5 | 01-Task Progress Connected | 00-Selfcheck Quality | Approved | eATP | Check Out | Waiting Vendor Approval | No issue | Scarlett |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  | Waiting Tower RFI (Back To PTK ) | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-7905 | 2025-09-24
49 |  | 2506-NNE4G-4G#RO-SAG068-230044 | Wireless RAN/Settlement Site/2506-NNE4G-4G#RO-SAG068-230044 | DU00005761753 | SAG068 | SAG068MT1 | YPTT | TBG SIMPANG SOSOKTBG | PONTIANAK | SINTANG | SANGGAU | TBG | CAPEX RAN 2 PART 3 2025 | 11023148 | 29409 | KALIMANTAN BARAT, SANGGAU, TAYAN HULU, SOSOK | New Infra | L900 | EQP New NE 4G LTE 900 10 MHz | - | Release | Release | Release | Release | 28 Aug | 28 Aug | 2025-09-11 | Expired Need Extend | DOEID250826F5 | DOEID250826F6 | NO NEED | DNWID0682025082605 | DNWID0712025082602 | NO NEED | 28-Aug-25 | - | - | - | - | - | DOP Finish | YPTT | Arya | 2025-09-04 | 28-Aug-25 | 2025-09-04 | 2025-09-05 | 100% | 2025-09-05 | Laccima Ok |  | 2025-09-04 | Connected | Connected | [8 empty] | 20-Oct-25 | - | - | - | waiting pln | 9 Oct | 35 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  | Waiting Tower RFI (Back To PTK ) | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-7905 | 2025-09-24
50 |  | 2508-U32T32R-4G#RO-PTK300-070011-S2 | Wireless RAN/Settlement Site/2508-U32T32R-4G#RO-PTK300-070011-S2 | DU00005931528 | PTK300 | PTK300M41 | YPTT | TERMINALSINTANGTBG | PONTIANAK | PONTIANAK | PONTIANAK | TBG | CP#3 Part 68 | 10934375 | -1491 | JL. KHATULISTIWA GG. PARIT WAN SALIM, RT. 03/07 SIANTAN PONTIANAK UTARA PONTIANAK | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Dismantle 1 Pcs RRU R8998G S2300 include SFP, Brcaket, Conector Power, 40m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 60m, 4 Pcs Jumper 1/2" 4.3M-NM 5m | Release | Release | Release | Release | 2025-09-25 | 2025-09-26 | 2025-09-09 | Expired Need Extend | DOEID25082210 | NO NEED | NO NEED | DNWID0682025082201 | NO NEED | NO NEED | 22-Aug-25 | - | - | - | - | - | NY VALIDATION | YPTT | Adhe | 31-Aug-25 | 22-Aug-25 | 31-Aug-25 | 31-Aug-25 | 100% | 31-Aug-25 | Laccima Ok |  | 31-Aug-25 | Connected | Connected | [8 empty] | 2025-09-05 | 31-Aug-25 | - | - | - | 2025-09-05 | 5 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
51 |  | 2508-NNE5G-5G#RO-PTK449-190025 | Wireless RAN/Settlement Site/2508-NNE5G-5G#RO-PTK449-190025 | DU00005979087 | PTK449 | PTK449M41 | YPTT | GRAHAPENATSEL | PONTIANAK | PONTIANAK | PONTIANAK | TSEL | 2025 - 5G City & Offload | 109344276 | -40364 | JL. GAJAHMADA, GEDUNG GRAHA PENA PONTIANAK | Reuse 1 Pcs DCPD10B & 2 Pcs MCB100A Use from Buffer, ZXRAN A9652A S23(3), Pole for new antenna (3m)(3) | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Need Dismantel 2pcs RRU R8998G S2300 inlcude SFP, Bracket, Conector Power, 80m RRU PWR Cable 2 core Type-D 10mm², 1 pcs RRU Fiber LC-LC 90m | Release | Release | Release | Release | 28-Aug-25 | 29-Aug-25 | 2025-09-12 | Expired Need Extend | DOEID250829L2 | DOEID250829L3 | NO NEED | DNWID0682025083007 | DNWID0712025083006 | NO NEED | 2025-09-01 | 2026-09-18 | - | - | - | - | NY VALIDATION | YPTT | Adhe | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-03 | 100% | 2025-09-11 | Laccima Ok |  | 2025-09-11 | Connected | Connected | [8 empty] | 2025-09-23 | 2025-09-18 | - | - | waiting CI cluster 5G | 2025-09-18 | 17 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
52 |  | 2508-NNE5G-5G#RO-PTK491-190029 | Wireless RAN/Settlement Site/2508-NNE5G-5G#RO-PTK491-190029 | DU00005979068 | PTK491 | PTK491M41 | YPTT | HOTELBESTWESTERNPTKTSEL | PONTIANAK | PONTIANAK | PONTIANAK | TSEL | 2025 - 5G City & Offload | 109329206 | -37333 | Jl. Sultan Abdurrahman, Akcaya, pontianak Selatan Kota Pontianak - Kalbar | Add ZXRAN A9652A S23(3), Pole for new antenna (3m)(3) | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Need Dismantel 2pcs RRU R8998G S2300 inlcude SFP, Bracket, Conector Powe, 40m RRU PWR Cable 2 core Type-D 10mm², 2 pcs RRU Fiber LC-LC 50m | Release | Release | Release | Release | 28-Aug-25 | 29-Aug-25 | 2025-09-12 | Expired Need Extend | DOEID250829L4 | DOEID250829L5 | NO NEED | DNWID0682025083005 | DNWID0712025083005 | NO NEED | 2025-09-05 | 2026-09-16 | - | - | - | - | NY VALIDATION | YPTT | Adhe | 2025-09-06 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 100% | 2025-09-11 | Laccima Ok |  | 2025-09-08 | Connected | Connected | [8 empty] | 2025-09-16 | - | - | - | waiting CI | 2025-09-11 | 5 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
53 |  | 2508-NNE5G-5G#RO-BJM742-190030 | Wireless RAN/Settlement Site/2508-NNE5G-5G#RO-BJM742-190030 | DU00005979091 | BJM742 | BJM742M41 | YPTT | DUTAMALLBANJARMASIN | BANJARMASIN | BANJARMASIN | BANJARMASIN | TSEL | 2025 - 5G City & Offload | 11460272 | -332218 | Duta Mall Banjarmasin Kalsel JL. A Yani KM 2.5 | ZXRAN A9652A S23(3), Pole for new antenna (3m)(3) | L2300 | EQP New NE 5G NR 2300 30 MHz Massive MIMO 32T32R | - | Release | Release | Release | Release | 28-Aug-25 | 2025-09-01 | 2025-09-30 | Expired Need Extend | DOEID250829C4 | DOEID250829C5 | DOEID250829C5 | DNWID0662025082901 | DNWID0692025082901 | NO NEED | 2025-09-01 | - | - | - | - | - | NY VALIDATION | YPTT | yoga | 2025-09-01 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 100% | 2025-09-10 | Laccima Ok |  | 2025-09-09 | Connected | Connected | [8 empty] | 01-Oct-25 | - | - | - | waiting CI 15:00 8 sep | 01-Oct-25 | 30 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-connected |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
54 |  | 2508-NNE5G-5G#RO-BJM021-190013 | Wireless RAN/Settlement Site/2508-NNE5G-5G#RO-BJM021-190013 | DU00005979075 | BJM021 | BJM021M51 | YPTT | TENDEANTSEL | BANJARMASIN | BANJARMASIN | BANJARMASIN | TSEL | 2025 - 5G City & Offload | 11459358 | -331791 | Jl Kapt Piere Tendean 102 Kec.Banjarmasin Tengah Kodya Banjarmasin | ZXRAN A9652A S23(3), Pole for new antenna (3m)(3), Reuse 1 Pcs DCPD10B & 2 Pcs MCB100A Use from Buffer | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Need Dismantel 1pcs RRU R9614 S2300 inlcude SFP, Bracket, Conector Power, 30m RRU PWR Cable 2 core Type-D 10mm², 1 pcs RRU Fiber LC-LC 40m | Release | Release | Release | Release | 28-Aug-25 | 2025-09-01 | 2025-09-30 | Expired Need Extend | DOEID250829C2 | DOEID250829C3 | NO NEED | DNWID0662025082905 | DNWID0692025082904 | NO NEED | 2025-09-03 | 2026-09-20 | - | - | - | - | NY VALIDATION | YPTT | yoga | 2025-09-04 | 2025-09-03 | 2025-09-05 | 2025-09-05 | 100% | 2025-09-08 | Laccima Ok |  | 2025-09-09 | Connected | Connected | [8 empty] | 2025-09-20 | 2025-09-20 | - | - | waiting CI cluster 5G | 2025-09-20 | 16 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
55 |  | 2508-NNE5G-5G#RO-BJM162-190008 | Wireless RAN/Settlement Site/2508-NNE5G-5G#RO-BJM162-190008 | DU00005979060 | BJM162 | BJM162M41 | YPTT | HOTELNASABANJARMASINTSEL | BANJARMASIN | BANJARMASIN | BANJARMASIN | TSEL | 2025 - 5G City & Offload | 11458767 | -3324053 | Jalan Djok Mentaya No. 8, Banjarmasin Near Center, Banjarmasin | Add BBU VBPe1p(1), A9652A S23(3), DCPD10b Reuse | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | 1pcs RRU R8998G S2300 inlcude SFP, Bracket, Conector Power, 20m RRU PWR Cable 2 core Type-D 10mm², 1 pcs RRU Fiber LC-LC 20m | Release | Release | Release | Release | 28-Aug-25 | 2025-09-01 | 2025-09-30 | Expired Need Extend | DOEID250829FD | DOEID250829FE | NO NEED | DNWID0662025082906 | DNWID0692025082907 | NO NEED | 2025-09-06 | 2026-09-23 | - | - | - | - | NY VALIDATION | YPTT | yoga | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-12 | 100% | 2025-09-12 | Laccima Ok |  | 2025-09-12 | Connected | Connected | [8 empty] | 2025-09-23 | 2025-09-23 | - | - | waiting plan hi | 2026-09-23 | 17 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
56 |  | 2508-NNE4G-4G#RO-BJM327-190065 | Wireless RAN/Settlement Site/2508-NNE4G-4G#RO-BJM327-190065 | DU00006018989 | BJM327 | BJM327M41 | YPTT | SKPERMAIANTASANDMT | BANJARMASIN | BANJARMASIN | BANJARMASIN | DMT | - | 11458519 | -331234 | Jl. Saka Permai, Banjarmasin Bar., Kota Banjarmasin, Provinsi Kalimantan Sel. 70123 | Add RRU R9264M M7290(1), | L900 | EQP New NE 4G LTE 900 10 Mhz | - | Release | Release | Release | Release | 29-Aug-25 | 2025-09-01 | 2025-09-30 | Expired Need Extend | - | - | - | DNWID0662025090306 | NO NEED | NO NEED | 2025-09-06 | 2026-09-19 | - | - | - | - | NY VALIDATION | YPTT | yoga | 2025-09-06 | 2025-09-06 | 2025-09-08 | 2025-09-12 | 100% | 2025-09-12 | Laccima Ok |  | 2025-09-13 | Connected | Connected | [8 empty] | 2025-09-22 | 2025-09-22 | - | - | og HI | 2026-09-22 | 16 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8134 | 2025-10-16
57 |  | 2508-NNE5G-5G#RO-BJM327-190010 | Wireless RAN/Settlement Site/2508-NNE5G-5G#RO-BJM327-190010 | DU00005979074 | BJM327 | BJM327M41 | YPTT | SKPERMAIANTASANDMT | BANJARMASIN | BANJARMASIN | BANJARMASIN | DMT | 2025 - 5G City & Offload | 11458519 | -331234 | Jl. Saka Permai, Banjarmasin Bar., Kota Banjarmasin, Provinsi Kalimantan Sel. 70123 | A9652A S23(3), | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R Impact NR | Need Dismantel 1pcs R9614 S2300 inlcude SFP, Bracket, Conector Power, 40m RRU PWR Cable 2 core Type-D 10mm², 1 pcs RRU Fiber LC-LC 60m | Release | Release | Release | Release | 29-Aug-25 | 2025-09-01 | 2025-09-30 | Expired Need Extend | DOEID250903BL | DOEID250903BQ | NO NEED | DNWID0662025090302 | DNWID0662025090306 | NO NEED | 2025-09-06 | - | - | - | - | - | NY VALIDATION | YPTT | yoga | 2025-09-06 | 2025-09-06 | 2025-09-08 | 2025-09-12 | 100% | 2025-09-12 | Laccima Ok |  | 2025-09-12 | Connected | Connected | [8 empty] | 2025-09-22 | 2025-09-22 |  |  |  | 2026-09-22 | 16 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  | Lom Power Dan Optik (2 hari baru sampai ke Site ) | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
58 |  | 2508-U32T32R-4G#RO-PTS003-070022-S2 | Wireless RAN/Settlement Site/2508-U32T32R-4G#RO-PTS003-070022-S2 | DU00005931519 | PTS003 | PTS003VV1 | YPTT | NGBADAUTSEL | PONTIANAK | SINTANG | KAPUAS HULU | TSEL | CP#3 Part 68 | 111897314 | 1037281 | JL. DEBU KEC. BADAU KAB.KAPUAS HULU / JL. PANCASILA/BADAU II RT. 3, RW. 3 KEL, DESA NANGA BADAU, | BBU VBPe2q(1), ZXRAN A9652A S23(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Dismantle 1 Pcs RRU R8998G S2300 include SFP, Brcaket, Conector Power, 85m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 100m, 4 pcs Jumper 1/2" 4.3M-NM | Release | Release | Release | Release | 22-Aug-25 | 25-Aug-25 | 2025-09-23 | Expired Need Extend | DOEID250826GW | NO NEED | NO NEED | DNWID0682025082608 | NO NEED | NO NEED | 2025-09-08 | 2026-09-13 | 2026-09-13 | - | - | - | NY VALIDATION | YPTT | arya | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-09 | 100% | 2025-09-09 | Laccima Ok | 2025-09-12 | 2025-09-09 | Connected | Connected | [8 empty] | 2025-09-10 | 2025-09-09 | - | - | - | 2025-09-10 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No Issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
59 |  | 2508-REENG-4G#RO-SAG046-070062 | Wireless RAN/Settlement Site/2508-REENG-4G#RO-SAG046-070062 | DU00005931517 | SAG046 | SAG046MF1 | YPTT | BANTAITSEL | PONTIANAK | SINTANG | SANGGAU | TSEL | CP#3 Part 68 | 110587129 | 51058 | JL. DAROK RT. 1 RW. 1 DUSUN NALA, DESA BANTAI ,KEC. BONTI KAB SANGGAU | BBU VBPe1p(1), Donor RRU R8998G S2300(1), Antena Mobi 12 Port(1) | L2300 | EQP eNode B Modular Relocation Service New NE LTE 2300 | Dismantle 1 pcs antena Kathrein 739650, 1 Pcs antena Tongyu TDQ-182020DE-65F, 2 Pcs Jumper 1/2" DM-DM 5m, 4 Pcs Jumper 1/2" DM-4.3M 5m | Release | Release | Release | Release | 22-Aug-25 | 25-Aug-25 | 2025-09-23 | Expired Need Extend | DOEID250901FM | DOEID250901FN | NO NEED | DNWID0682025090202 | DNWID0712025090202 | NO NEED | 2025-09-12 | 2026-09-14 | - | - | - | - | NY VALIDATION | YPTT | arya | 2025-09-12 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 100% | 2025-09-14 | Laccima Ok |  | 2025-09-14 | Connected | Connected | [8 empty] | 2025-09-19 | - | - | - | - | 2026-09-14 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No Issue | Scarlett | 17-oct-25 | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8130 | 2025-10-16
60 |  | 2508-REENG-4G#RO-MPW713-070047 | Wireless RAN/Settlement Site/2508-REENG-4G#RO-MPW713-070047 | DU00005931511 | MPW713 | MPW713MF1 | YPTT | TANJUNGSALEHPST | PONTIANAK | SINTANG | KUBURAYA | PST | CP#3 Part 68 | 1091434354 | -1017237 | Desa Tanjung Saleh, Kec. Sungai Kakap, Kab. Kubu Raya, Kalimantan Barat | Reuse 1 Pcs RRU R8998G S2300, VBPe1p | L2300 | EQP eNode B Modular Relocation Service New NE LTE 2300 | - | Release | Release | Release | Release | 2025-09-02 | 2025-09-01 | 2025-09-10 | Expired Need Extend | DOEID250901FK | DOEID250901FL | NO NEED | DNWID0682025090201 | DNWID0712025090201 | NO NEED | 2025-09-09 | - | - | - | - | - | NY VALIDATION | YPTT | Adhe | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 100% | 2025-09-09 | Laccima Ok | 2025-09-12 | 2025-09-09 | Connected | Connected | [8 empty] | 2025-09-10 | - | - | - | - | 2026-09-10 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | Closed | No Issue | Scarlett | 17-oct-25 | [12 empty] | PO Confirmed | S1ID2023070102WBF1-8130 | 2025-10-16
61 |  | 2508-NNE4G-4G#RO-BJM793-190069 | Wireless RAN/Settlement Site/2508-NNE4G-4G#RO-BJM793-190069 | DU00005979069 | BJM793 | BJM793ME1 | YPTT | PASARKELAYANTSEL | BANJARMASIN | BANJAR | KOTA BANJARMASIN | TSEL | New NE 4G | 114597716 | -3328496 | Jl. Kol Sugiono No. 19 Rt. 005 Kel. Kelayan Luar Kec. Banjarmasin Tengah Kota Banjarmasin Prov. Kalimantan Selatan | Add RRU R9614 S2300(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1), | L2300 | EQP New NE 4G LTE 2300 50 Mhz | 1 pcs antena Tongyu TDQ-182020DE-65F | Release | Release | Release | Release | 29-Aug-25 | 2025-09-01 | 2025-09-30 | Expired Need Extend | DOEID250829FD | DOEID250829FE | NO NEED | DNWID0662025082906 | DNWID0692025082907 | NO NEED | 2025-09-09 | 2025-09-18 |  |  |  |  | NY VALIDATION | YPTT | yoga | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-17 | 100% | 2025-09-17 |  |  | 2025-09-18 | Connected | Connected | [8 empty] | 2025-09-18 | 2025-09-18 |  |  |  | 2025-09-18 | 9 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7922 | 2025-09-25
62 |  | 2508-NNE5G-5G#RO-BJM109-190006 | Wireless RAN/Settlement Site/2508-NNE5G-5G#RO-BJM109-190006 | DU00005979058 | BJM109 | BJM109VE1 | YPTT | ANTASANBESARPTI | BANJARMASIN | BANJAR | KOTA BANJARMASIN | PTI | 2025 - 5G City & Offload | 11458461 | -332074 | Jl. Sutoyo S No. 179, Kel. Antasan Besar, Kec. Banjar Tengah | BBU Board VEMc4 (1), ZXRAN A9652A S23(3), Pole for new antenna (3m)(3) | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | 1 pcs VEMc1, 2pcs RRU R8998G S2300 inlcude SFP, Bracket, Conector Power, 60m RRU PWR Cable 2 core Type-D 10mm², 2 pcs RRU Fiber LC-LC 50m | Release | Release | Release | Release | 29-Aug-25 | 2025-09-01 | 2025-09-30 | Expired Need Extend | DOEID250908AS | NO NEED | NO NEED | DNWID0662025090806 | NO NEED | NO NEED | 2025-09-14 | 2025-09-14 | - | - | - | - | NY VALIDATION | YPTT | yoga | 2025-09-14 | 2025-09-14 | 2025-09-14 | 2025-09-14 | 100% | 2025-09-14 |  |  | 2025-09-14 | Connected | Connected | [8 empty] | 2025-09-22 | 2025-09-14 |  |  |  | 2025-09-14 | 0 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
63 |  | 2508-NNE5G-5G#RO-BJM117-190004 | Wireless RAN/Settlement Site/2508-NNE5G-5G#RO-BJM117-190004 | DU00005979070 | BJM117 | BJM117VE1 | YPTT | TELAWANGPTI | BANJARMASIN | BANJAR | KOTA BANJARMASIN | PTI | 2025 - 5G City & Offload | 114582408 | -3328603 | Jl. Selatan Dahlia Gg. Budaya RT26/RW01, Kel. Telawang, Kec. Banjarmasin Barat, Kab. Banjarmasin | ZXRAN A9652A S23(3), Pole for new antenna (3m)(3) | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | 1 pcs VEMc1, 1pcs RRU R8998G S2300 inlcude SFP, Bracket, Conector Power, 20m RRU PWR Cable 2 core Type-D 10mm², 1 pcs RRU Fiber LC-LC 60m | Release | Release | Release | Release | 29-Aug-25 | 2025-09-01 | 2025-09-30 | Expired Need Extend | DOEID250908AR | NO NEED | NO NEED | DNWID0662025090805 | NO NEED | NO NEED | 2025-09-15 | 2025-09-15 | - | - | - | - | NY VALIDATION | YPTT | yoga | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 100% | 2025-09-15 |  |  | 2025-09-15 | Connected | Connected | [8 empty] | 2025-09-26 | 2025-09-26 |  |  |  | 2026-09-26 | 11 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
64 |  | 2508-NNE4G-4G#RO-PTK117-190075 | Wireless RAN/Settlement Site/2508-NNE4G-4G#RO-PTK117-190075 | DU00005979093 | PTK117 | PTK117MV1 | YPTT | MKLPGADINGPERMAI | PONTIANAK | PONTIANAK | PONTIANAK | TSEL | New NE 4G | 10935841 | -7506 | KEL BANSIR DARAT - KEC. PONTIANAK TENGGARA - PONTIANAK - KALBAR | Add Ant mobi 12 port(1), VBPe1P(1), R9614 S23(1) | L2300 | EQP New NE 4G LTE 2300 50 Mhz | Dismantle 1 pcs antena Tongyu TDQ-182020DE-65F | Release | Release | Release | Release | 2025-09-10 | 2025-09-11 | 2025-09-25 | Expired Need Extend | DOEID250905BY | NO NEED | NO NEED | DNWID0682025090606 | NO NEED | NO NEED | 2025-09-11 | 2025-09-22 | - | - | - | - | NY VALIDATION | YPTT | Yusri | 2025-09-11 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 100% | 2025-09-13 |  |  | 2025-09-13 | Connected | Connected | [8 empty] | 16-Oct-25 | 2025-09-22 |  |  |  | 2025-09-22 | 11 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8130 | 2025-10-16
65 |  | 2508-ADSTR-4G#RO-BJM795-190070 | Wireless RAN/Settlement Site/2508-ADSTR-4G#RO-BJM795-190070 | DU00005979105 | BJM795 | BJM795MW1 | YPTT | CR_TELUKKELAYAN | BANJARMASIN | BANJAR | KOTA BANJARMASIN | TSEL | Capacity Upgrade 4G | 1145947 | -332964 | Jl. KS Tubun No. 20 Rt. 15 Kel. Kelayan Barat Kec. Banjarmasin Selatan Kota Banjarmasin Prov. Kalimantan Selatan | Add RRU R9614 S2300(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1), | L2300 | EQP New NE 4G LTE 2300 50 Mhz | 1 pcs antena Tongyu TDQ-182020DE-65F | Release | Release | Release | Release | 29-Aug-25 | 2025-09-01 | 2025-09-30 | Expired Need Extend | DOEID250829FF | NO NEED | NO NEED | DNWID066202582907 | NO NEED | NO NEED | 2025-09-15 | 2026-09-16 | - | - | - | - | NY VALIDATION | YPTT | yoga | 2025-09-15 | 2025-09-15 | 2025-09-16 | 2025-09-16 | 100% | 2025-09-16 |  |  | 2025-09-16 | Connected | Connected | [8 empty] | 2025-09-16 | 2025-09-16 | - | - | - | 2025-09-16 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-7922 | 2025-09-25
66 |  | 2508-NNE4G-4G#RO-NBA012-070007 | Wireless RAN/Settlement Site/2508-NNE4G-4G#RO-NBA012-070007 | DU00005931523 | NBA012 | NBA012M41 | YPTT | KUALABEHETBG | PONTIANAK | SINGKAWANG | LANDAK | TBG | CP#3 Part 68 | 110006369 | 584065 | KUALA BEHE, KUALA BEHE, LANDAK, KALIMANTAN BARAT | BBU VBPe1p(1), RRU R9614 S2300(1), | L2300 | EQP New NE 4G LTE 2300 50 Mhz | - | Release | Release | Release | Release | 27 Aug | 28 Aug | 2026-09-27 | Expired Need Extend | DOEID250827CE | DOEID250827CF | NO NEED | DNWID0682025082801 | DNWID0712025082801 | NO NEED | 2025-09-16 | - | No Need |  |  |  | NY VALIDATION | YPTT | Arya | 2026-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 100% | 2025-09-16 | Laccima Ok |  | 2025-09-16 | Connected | Connected | [8 empty] | 2025-09-17 | 2025-09-16 | - | - | - | 2025-09-17 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality |  | Task Progress Pending |  | Not Start |  |  |  | IN PROGRESS | [5 empty] | NY APPROVED |  |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8130 | 2025-10-16
67 |  | 2508-NNE5G-5G#RO-PTK334-190017 | Wireless RAN/Settlement Site/2508-NNE5G-5G#RO-PTK334-190017 | DU00005979101 | PTK334 | PTK334M41 | YPTT | DARANANTEBTC | PONTIANAK | PONTIANAK | PONTIANAK | BTC | 2025 - 5G City & Offload | 109327434 | -35376 | JL. PUTRI DARANANTE, GG. SUKA JAYA RT.3 RW 14 NO.44, KEC. PONTIANAK KOTA, KODYA PONTIANAK | DCPD10B(1), BBU VBPe2q(1), ZXRAN A9652A S23(3), Pole for new antenna (3m) | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | 1pcs RRU R8998G S2300 inlcude SFP, Bracket, Conector Power, 40m RRU PWR Cable 2 core Type-D 10mm², 1 pcs RRU Fiber LC-LC 60m | Release | Release | Release | Release | 2025-09-16 | 2025-09-17 | 1 Oct | Expired Need Extend | DOEID250905BV | DOEID250905BW | NO NEED | DNWID0682025090808 | DNWID0712025090601 | NO NEED | 2025-09-19 | 2026-09-22 |  |  |  |  | NY VALIDATION | YPTT | Adhe | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-20 | 100% | 2025-09-20 |  |  | 2025-09-20 | Connected | Connected | [8 empty] | 2025-09-23 | 2025-09-22 | - | - | - | 2025-09-22 | 3 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 14-Dec-23 | No Need | APPROVED | PROPOSE INVOICE |  |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
68 |  | 2508-NNE4G-4G#RO-PTK319-190077 | Wireless RAN/Settlement Site/2508-NNE4G-4G#RO-PTK319-190077 | DU00005979073 | PTK319 | PTK319M41 | YPTT | IMACRO_EPQ010_TBHDINKESAYANITBG | PONTIANAK | PONTIANAK | PONTIANAK | TBG | Capacity Upgrade 4G | 10934196 | -4675 | Jl. A. Yani, Kota Pontianak, Kalimantan Barat | RRU R9614 S2300(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain ) | L2300 | EQP New NE 4G LTE 2300 50 Mhz | 1 pcs antena Commscope HBXX-6516DS-VTM | Release | Release | Release | Release | 2025-09-17 | 2025-09-18 | 02-Oct-25 | Expired Need Extend | DOEID250905C0 | NO NEED | NO NEED | DNWID0682025090607 | NO NEED | NO NEED | 2025-09-20 | 2026-09-21 |  |  |  |  | NY VALIDATION | YPTT | Del Piero | 2025-09-21 | 2025-09-20 | 2025-09-21 | 2025-09-21 | 100% | 2025-09-26 | Laccima Ok | 16-Oct-25 | 2025-09-26 | Connected | Connected | [8 empty] | waiting review | 2025-09-21 |  |  | waiting review | 18-Oct-25 | 27 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 2023-11-04 | BAST | No Need | No Need | 2023-11-09 | No need | APPROVED | PROPOSE INVOICE | Passed |  |  | 03-Connected |  | PO Confirmed | S1ID2023070102WBF1-8133 | 2025-10-16
69 |  | 2508-NNE4G-4G#RO-PTK417-190078 | Wireless RAN/Settlement Site/2508-NNE4G-4G#RO-PTK417-190078 | DU00005979103 | PTK417 | PTK417M41 | YPTT | PURNAMA2TBG | PONTIANAK | PONTIANAK | PONTIANAK | TBG | Capacity Upgrade 4G | 109338365 | -62389 | JL. PERDANA RAYA, NO. 101 KEL. BANGKA BELITUNG PONTIANAK SELATAN PONTIANAK | BBU VBPe1p(1), RRU R9614 S2300(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1) | L2300 | EQP New NE 4G LTE 2300 50 Mhz | 1 pcs antena Commscope TBXLHA-6565C-VTM | Release | Release | Release | Release | 2025-09-22 | 2025-09-21 | 2025-11-07 | Expired Need Extend | DOEID250905C1 | NO NEED | NO NEED | DNWID0682025090605 | NO NEED | NO NEED | 2025-09-20 | 2026-09-22 |  |  |  |  | NY VALIDATION | YPTT | Adhe | 2025-09-21 | 2025-09-20 | 2025-09-21 | 2025-09-21 | 100% | 2025-09-21 | Laccima Ok | 2025-09-25 | 2025-09-20 | Connected | Connected | [8 empty] | 2025-09-23 | 2025-09-22 |  |  |  | 2025-09-22 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No issue | Scarlett | 2023-11-23 | BAST | No Need | No Need | 2023-11-27 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 03-connected |  | PO Confirmed | S1ID2023070102WBF1-8133 | 2025-10-16
70 |  | 2508-NNE4G-4G#RO-PTK309-190076 | Wireless RAN/Settlement Site/2508-NNE4G-4G#RO-PTK309-190076 | DU00005979098 | PTK309 | PTK309M41 | YPTT | TBHUNTAN2TBG | PONTIANAK | PONTIANAK | PONTIANAK | TBG | Capacity Upgrade 4G | 10934459 | -6121 | Universitas Tanjungpura, Jl.Profesor Dr. Hj. Hadari Nawawi, Kota Pontianak, Kalimantan Barat | BBU VBPe1p(1), RRU R9614 S2300(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1) | L2300 | EQP New NE 4G LTE 2300 50 Mhz | 1 pcs antena Commscope HBXX-6516DS-VTM | Release | Release | Release | Release | 2025-09-19 | 2025-09-19 | 03-Oct-25 | Expired Need Extend | DOEID250905BZ | NO NEED | NO NEED | DNWID0682025090604 | NO NEED | NO NEED | 2025-09-20 | 2026-09-22 |  |  |  |  | NY VALIDATION | YPTT | Arya | 2025-09-22 | 2025-09-20 | 2025-09-22 | 2025-09-22 | 100% | rollback | - | - |  | - | ROLLBACK | [8 empty] | ROLLBACK | 2025-09-27 | - | - | ROLLBACK | 2025-09-27 | 5 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No issue | Scarlett | 2023-11-23 | BAST | No Need | No Need | 2023-11-27 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 03-connected |  | #N/A | #N/A | #N/A
71 | 2025-09-24 | 2508-U32T32R-4G#RO-SHR001-070027-S2 | Wireless RAN/Settlement Site/2508-U32T32R-4G#RO-SHR001-070027-S2 | DU00005931508 | SHR001 | SHR001M41 | YPTT | SUNGAIAYAKTSEL | PONTIANAK | SINTANG | SEKADAU | Telkomsel | CP#3 Part 68 | 11106221 | 10367 | JL. SUNGAI AYAK HILIR KEC. BELINTANG HILIR KAB. SANGGAU | BBU VBPe2q(1), A9732 M1821(1), Pole for new antenna (3m)(1) | l2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release | 22 Aug | 25-Aug-25 | 08-Oct-25 | Expired Need Extend | DOEID250826GX | NO NEED | NO NEED | DNWID0682015082607 | NO NEED | NO NEED | 2025-09-25 | - |  |  |  |  | NY VALIDATION | YPTT | Arya | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-26 | 100% | 2025-09-26 | Laccima Ok | 02-Oct-25 | 2025-09-26 | Connected | Connected | [8 empty] | 2025-09-27 | - | - | - | - | 2025-09-26 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No issue | Scarlett | 2023-11-23 | BAST | No Need | No Need | 2023-11-30 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 03-connected |  | PO Confirmed | S1ID2023070102WBF1-8132 | 2025-10-16
72 | 2025-09-24 | 2509-NNE4G-4G#RO-MTP076-030006 | Wireless RAN/Settlement Site/2509-NNE4G-4G#RO-MTP076-030006 | DU00006019006 | MTP076 | MTP076M41 | YPTT | DSLIMAMARDMT | BANJARMASIN | BANJAR | BANJAR | DMT | Red Coverage List 13 | 11487128 | -33563 | Kel. Tambangan Kecamatan Astambul Kalimantan Selatan | Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(3), | L900 | EQP New NE 4G LTE 900 10 Mhz | 3 pcs antena Rosenberger S-Wave EW/EW/EW/EW-65-18DV2/12I-64K, 3 pcs antena Commscope LDX-9014DS-VTM, 150m RRU PWR Cable 2 core Type-D 16mm², 3 Pcs | Release | Release | Release | Release | 2026-09-12 | 2025-09-15 | 13-Oct-25 | Expired Need Extend | DOEID250923F8 | NO NEED | NO NEED | DNWID0662025092303 | NO NEED | NO NEED | 2025-09-27 | 3 Oct |  |  |  |  | NY VALIDATION | YPTT | yoga | 2025-09-27 | 2025-09-27 | 2025-09-27 | 2025-09-28 | 100% | 2025-09-28 | Laccima Ok | 2025-09-30 | 2025-09-29 | Connected | Connected | [8 empty] | 04-Oct-25 | 04-Oct-25 |  |  |  | 04-Oct-25 | 7 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No issue | Scarlett | 2023-11-23 | BAST | No Need | No Need | 2023-11-27 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 03-connected |  | PO Confirmed | S1ID2023070102WBF1-8131 | 2025-10-16
73 | 2025-09-24 | 2508-NNE4G-4G#RO-STA397-070004 | Wireless RAN/Settlement Site/2508-NNE4G-4G#RO-STA397-070004 | DU00005931521 | STA397 | STA397M41 | YPTT | TEMAWANGMUNTAITBG | PONTIANAK | SINTANG | SINTANG | TBG | CP#3 Part 68 | 111201456 | -79692 | Dusun Sempetang RT 009 RW - , Desa Sirang Setambang Kec. Sepauk Kab. Sintang Prov. Kalimantan Barat | BBU VBPe1p(1), RRU R9614 S2300 (1), | L2300 | EQP New NE 4G LTE 2300 50 Mhz | - | Release | Release | Release | Release | 27-Aug-25 | 28-Aug-25 | 27-Oct-25 | Expired Need Extend | DOEID25091905 | NO NEED | NO NEED | DNWID0682025091901 | NO NEED | NO NEED | 2025-09-26 | - |  |  |  |  | NY VALIDATION | YPTT | Arya | 2025-09-27 | 2025-09-26 | 2025-09-27 | 2025-09-27 | 100% | 2025-09-27 | Laccima Ok | 02-Oct-25 | 2025-09-28 | Connected | Connected | [8 empty] | 2025-09-27 | - |  |  |  | 2025-09-27 |  | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 12-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8135 | 2025-10-16
74 | 2025-09-24 | 2509-NNE4G-4G#RO-STA349-030008 | Wireless RAN/Settlement Site/2509-NNE4G-4G#RO-STA349-030008 | DU00006019011 | STA349 | STA349M41 | YPTT | MANTERPTI | PONTIANAK | SINTANG | SINTANG | PTI | Red Coverage List 13 | 11148373 | -8423 | JI. Dusun Purwosari RT002/RW003, Kel. Manter, Kee. Sungai Tebelian, Kab.Sintang | R9264M M7290(2), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(3), Filter | L900 | EQP New NE 4G LTE 900 10 Mhz | 3 Pcs antena Tongyu TDQ-182020DE-65F | Release | Release | Release | Release | 2025-09-18 | 2025-09-22 | 2025-11-10 | Expired Need Extend | DOEID250922KH | NO NEED | NO NEED | DNWID0682025092301 | NO NEED | NO NEED | 2025-09-27 | 2026-09-30 |  |  |  |  | NY VALIDATION | YPTT | Arya | 2025-09-28 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 100% | 2025-09-29 | Laccima Ok | 02-Oct-25 | 2025-09-29 | Connected | Connected | [8 empty] | 2025-11-07 | 2025-09-30 |  |  |  | 2025-09-30 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 14-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8135 | 2025-10-16
75 | 2025-09-30 | 2509-U32T32R-4G#1023-PLI002-090247-S2 | Wireless RAN/Settlement Site/2509-U32T32R-4G#1023-PLI002-090247-S2 | DU00006038006 | PLI002 | PLI002M41 | YPTT | INDOFOOD | BANJARMASIN | BANJAR | TANAH LAUT | TSEL | Tech CP3 Part 2 Capacity_67 | 114735809 | -355697 | LIANG ANGGANG RT.07 / IV KEC.BATI BATI KAB. TANAH LAUT KALIMANTAN SELATAN | BBU VBPe2q(1), ZXRAN A9652A S23(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release | 2025-09-20 | 2025-09-22 | 20-Oct-25 | Expired Need Extend | DOEID250923F9 | NO NEED | NO NEED | DNWID0662025092305 | NO NEED | NO NEED | 05-Oct-25 | - |  |  |  |  | NY VALIDATION | YPTT | yoga | 05-Oct-25 | 05-Oct-25 | 05-Oct-25 | 06-Oct-25 | 100% | 06-Oct-25 |  |  | 06-Oct-25 | Connected | Connected | [5 empty] | 07-Oct-25 |  |  | 07-Oct-25 | - |  |  |  | 07-Oct-25 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 13-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8301 | 2025-11-01
76 | 2025-09-28 | 2509-NNE4G-4G#RO-MPW079-030009 | Wireless RAN/Settlement Site/2509-NNE4G-4G#RO-MPW079-030009 | DU00006019013 | MPW079 | MPW079M41 | YPTT | KUALADUA3DMT | PONTIANAK | SINTANG | KUBURAYA | DMT | Red Coverage List 13 | 10940525 | -18842 | KUALA DUA, SUNGAI RAYA, KUBU RAYA, KALIMANTAN BARAT | BBU VBPe1p(1), R9264M M7290(2) | L900 | EQP New NE 4G LTE 900 10 Mhz | - | Release | Release | Release | Release | 2025-09-12 | 2025-09-15 | 31-Oct-25 | Expired Need Extend | DOEID250922KI | NO NEED | NO NEED | DNWID0682025092302 | NO NEED | NO NEED | 2025-09-29 | - | - | - | - | - | NY VALIDATION | YPTT | Agus | 2025-09-29 | 2025-09-29 | 2025-09-30 | 2025-09-30 | 100% | 2025-09-30 | Laccima Ok | 02-Oct-25 | 2025-09-30 | Connected | Connected | [5 empty] | 29-Oct-25 |  |  | 29-Oct-25 | - |  |  | waiting approval TO | 29-Oct-25 | 30 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 13-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8135 | 2025-10-16
77 | 2025-09-28 | 2509-ADSTR-4G#RO-MPW060-030005 | Wireless RAN/Settlement Site/2509-ADSTR-4G#RO-MPW060-030005 | DU00006019010 | MPW060 | MPW060M41 | YPTT | _Addsect_DESAJAWATENGAHTSEL | PONTIANAK | SINTANG | KUBURAYA | TSEL | Red Coverage List 13 | 109467824 | -375 | JL. TRANS KALIMANTAN RT.01 RW.2 DESA JATENG KEC. SEI AMBAWANG KAB. KUBU RAYA | R9264M M7290(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1), pole mounting(1) | L900 | EQP New NE 4G LTE 900 10 Mhz | 1 Pcs RRU R8852E S9000 inlude SFP, bracket, Conector power. 70m RRU PWR Cable 2 core Type-D 6mm², 1 Pcs RRU Fiber | Release | Release | Release | Release | 2025-09-12 | 2025-09-15 | 16-Oct-25 | Expired Need Extend | DOEID250922KN | DOEID250922KO | NO NEED | DNWID0682025092306 | DNWID0712025092302 | NO NEED | 01-Oct-25 | 02-Oct-25 | - | - | - | APPROVED | DOP Finish | YPTT | Adhe | 01-Oct-25 | 01-Oct-25 | 01-Oct-25 | 02-Oct-25 | 100% | 02-Oct-25 |  |  | 02-Oct-25 | Connected | Connected | [5 empty] | 10-Oct-25 |  |  | 10-Oct-25 | 02-Oct-25 |  |  |  | 02-Oct-25 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 06-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8303 | 2025-11-01
78 | 2025-09-28 | 2509-NNE4G-4G#RO-PTS170-030007 | Wireless RAN/Settlement Site/2509-NNE4G-4G#RO-PTS170-030007 | DU00006019005 | PTS170 | PTS170M41 | YPTT | RIAUAGROTAMAPLANTATIONTBG | PONTIANAK | SINTANG | KAPUAS HULU | TBG | Red Coverage List 13 | 111804112 | 350619 | SANG-SANG, SILAT HILIR, KAPUAS HULU, KALIMANTAN BARAT | R9264M M7290(2), 7090C filter(2) | L900 | EQP New NE 4G LTE 900 10 Mhz | - | Release | Release | Release | Release | 2025-09-22 | 2025-09-24 | 08-Oct-25 | Expired Need Extend | DOEID250923LA | NO NEED | NO NEED | DNWID0682025092402 | NO NEED | NO NEED | 01-Oct-25 | -(NY Dismantle note: exsisting R8852E S9000 dan antena kathrein 2 port keep dari project) | - | - | - | APPROVED | DOP Finish | YPTT | Arya | 01-Oct-25 | 01-Oct-25 | 01-Oct-25 | 02-Oct-25 | 100% | 02-Oct-25 |  |  | 01-Oct-25 | Connected | Connected | [5 empty] | 06-Oct-25 |  |  | 06-Oct-25 | -(NY Dismantle note: exsisting R8852E S9000 dan antena kathrein 2 port keep dari project) | - |  |  | 03-Oct-25 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 12-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8303 | 2025-11-01
79 | 2025-09-28 | 2508-REENG-4G#RO-BEK071-070032 | Wireless RAN/Settlement Site/2508-REENG-4G#RO-BEK071-070032 | DU00005931534 | BEK071 | BEK071M41 | YPTT | IMACRO_EPQ063_BANGUNSARIQIN | PONTIANAK | SAMBAS | BENGKAYANG | QIN | CP#3 Part 68 | 109484138 | 828549 | JL. JERENDENG ABDUL RAHMAN, BUMI AMAS, KEC. BENGKAYANG, KABUPATEN BENGKAYANG, KALIMANTAN BARAT 79211, INDONESIA | BBU VBPe1p(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1), 1 Pcs RRU R8998G S2300 inlcude Conector Power use ex dismantle take from WH Tsel | L2300 | EQP eNode B Modular Relocation Service New NE LTE 2300 | 1 Pcs antena Commscope TBXLHA-6565C-VTM, 6 Pcs Jumper 1/2" DM-DM | Release | Release | Release | Release | 2025-09-15 | 2025-09-16 | 15-Oct-25 | Expired Need Extend | DOEID250923L8 | DOEID250923L9 | NO NEED | DNWID0682025092401 | DNWID0712025092401 | NO NEED | 05-Oct-25 | 08-Oct-25 | - | - | - | APPROVED | DOP Finish | YPTT | Del Piero | 05-Oct-25 | 05-Oct-25 | 06-Oct-25 | 06-Oct-25 | 100% | 06-Oct-25 |  |  | 06-Oct-25 | Connected | Connected | [5 empty] | 07-Oct-25 |  |  | 07-Oct-25 | 08-Oct-25 |  |  |  | 6 Oct | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 12-Dec-23 | BAST | No Need | No Need | 16-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8303 | 2025-11-01
80 | 2025-10-08 | 2509-U32T32R-4G#1023-PLI020-090248-S3 | Wireless RAN/Settlement Site/2509-U32T32R-4G#1023-PLI020-090248-S3 | DU00006038000 | PLI020 | PLI020VE1 | YPTT | YONIFPLEIHARI | BANJARMASIN | BANJAR | TANAH LAUT | TSEL | Tech CP3 Part 2 Capacity_67 | 114776752 | -3789345 | JL. JEND A YANI, RT 13/III, KEL ANGSAU-PLEIHARI, KAB. TANAH LAUT | BBU VBPe2q(1), ZXRAN A9652A S23(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | 1 Pcs RRU R8998G S2300 include Conector power, Bracket, 35m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 60m, 4 pcs Jumper 1/2" DM-NM 5m | Release | Release | Release | Release | 08-Oct-25 | 10 Oct | 2025-11-07 | Expired Need Extend | DOEID251010F0 | NO NEED | NO NEED | DNWID0662025101102 | NO NEED | NO NEED | 13-Oct-25 | 13-Oct-25 | - | - | - |  | NY VALIDATION | YPTT | yoga | 13-Oct-25 | 13-Oct-25 | 13-Oct-25 | 13-Oct-25 | 100% | 13-Oct-25 |  |  | 13-Oct-25 | Connected | Connected | [5 empty] | 14-Oct-25 |  |  | 14-Oct-25 | 13-Oct-25 |  |  |  | 13-Oct-25 | 0 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 13-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 03-connected |  | PO Confirmed | S1ID2023070102WBF1-8722 | 2025-12-09
81 | 2025-10-08 | 2508-4GGSM-4G#RO-KGN020-290052 | Wireless RAN/Settlement Site/2508-4GGSM-4G#RO-KGN020-290052 | DU00006010310 | KGN020 | KGN020MT1 | YPTT | BAJAYAU_TENGAH | BANJARMASIN | BANJAR | HULU SUNGAI SELATAN | DMT | 2025 - Batch#2 (95) | 1150095116 | -270566953 | KALIMANTAN SELATAN, HULU SUNGAI SELATAN, DAHA BARAT, BAJAYAU TENGAH | R9264M M7290(3), Mobi 12 Port(3), VBPe3p(1), Vemc4(1), Filter(6) | L900 | EQP New NE 4G LTE 900 10 Mhz | - | Release | Release | Release | Release | 2025-10-13 | 15 Oct | 2026-11-12 | Expired Need Extend | DOEID251013G0 | DOEID251013G1 | NO NEED | DNWID066202510141 | DNWID069202510143 | NO NEED | 15-Oct-25 | - | - | - | - | - | NY VALIDATION | YPTT | yoga | 16 Oct | 15-Oct-25 | 16-Oct-25 | 17-Oct-25 | 100% | 2025-11-18 |  |  | 2025-11-19 | Connected | Connected | [5 empty] | 22-Dec-26 |  |  | waiting TRM | - |  |  |  |  | ############### | [5 empty] | Not Start | [13 empty] | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8721 | 2025-12-09
82 | 2025-10-08 | 2509-U32T32R-4G#1023-SAG015-090293-S1 | Wireless RAN/Settlement Site/2509-U32T32R-4G#1023-SAG015-090293-S1 | DU00006037995 | SAG015 | SAG015VE1 | YPTT | TAYAN | PONTIANAK | SINTANG | SANGGAU | TSEL | Tech CP3 Part 2 Capacity_67 | 11011091 | -3075 | Desa Tayan, Kabupaten Sanggau | BBU VBPe2q(1), ZXRAN A9652A S23(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | 1 Pcs RRU R8978G S2300 include Conector power, Bracket, 70m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 90m, 4 pcs Jumper 1/2" 4.3M-NM 5m | Release | Release | Release | Release | 13 Oct | 12 Oct | 2026-11-07 | Expired Need Extend | DOEID250928BB | NO NEED | NO NEED | DNWID0682025092907 | NO NEED | NO NEED | 09-Oct-25 | - | - | - | - | - |  | YPTT | Adhe | 9 Oct | 09-Oct-25 | 10-Oct-25 | 11-Oct-25 | 100% | 11-Oct-25 |  |  | 11-Oct-25 | Connected | Connected | [5 empty] | 13-Oct-25 |  |  | 13-Oct-25 |  |  |  |  | 13 Oct | 4 | [5 empty] | Not Start | [15 empty] | PO Confirmed | S1ID2023070102WBF1-8302 | 2025-11-01
83 | 2025-10-08 | 2509-U32T32R-4G#1023-SAG176-090286-S1 | Wireless RAN/Settlement Site/2509-U32T32R-4G#1023-SAG176-090286-S1 | DU00006037992 | SAG176 | SAG176VR1 | YPTT | BATANGTARANG | PONTIANAK | SINTANG | SANGGAU | TSEL | Tech CP3 Part 2 Capacity_67 | 11009518 | 137696 | JL.ANGKASA PURI, DUSUN MELABAN, DESA HILIR, KECAMATAN BALAI, KABUPATEN LANDAK | BBU VBPe2q(1), A9732 M1821(1), Pole for new antenna (3m)(1) | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release | 1 Oct | 2 Oct | 29 Oct | Expired Need Extend | DOEID251009GK | NO NEED | NO NEED | DNWID0682025100907 | NO NEED | NO NEED | 19-Oct-25 | - | - | - | - | - | NY VALIDATION | YPTT | Arya | 19 Oct | 19-Oct-25 | 19-Oct-25 | 20-Oct-25 | 100% | 20-Oct-25 |  |  | 21-Oct-25 | Connected | Connected | [5 empty] | 2025-11-10 |  |  | 2025-11-10 | - |  |  |  | 20 Oct | 1 | [5 empty] | Not Start | [13 empty] | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8300 | 2025-11-01
84 | 2025-10-08 | 2509-NNE4G-4G#1022-SAG035-090219 | Wireless RAN/Settlement Site/2509-NNE4G-4G#1022-SAG035-090219 | DU00006037969 | SAG035 | SAG035ML1 | YPTT | ENGKAHAN | PONTIANAK | SINTANG | SANGGAU | TSEL | Tech CP3 Part 2 Capacity_18 | 110408383 | 858909 | DUSUN PESING DESA ENGKAHAN RT.01 KEL. ENGKAHAN KEC. SEKAYAM KAB. SANGGAU | RRU R9264 M1821(1) | L1800 | EQP eNode B Relocation Service/EQP New NE 4G LTE 1800 20 Mhz | 1 pcs RRU R8852E S2100 include sfp,bracket. Conector power, 70m RRU PWR Cable 2 core Type-D 6mm², 1 Pcs RRU Fiber LC-LC 80m, 2 pcs Jumper 1/2" DM-DM 5m | Release | Release | Release | Release | 1 Oct | 03-Oct-25 | 2025-11-01 | Expired Need Extend | DOEID251009GH | NO NEED | NO NEED | DNWID0682025100905 | NO NEED | NO NEED | 20-Oct-25 | 21 Oct | - | - | - | - | NY VALIDATION | YPTT | Arya | 20-Oct-25 | 20-Oct-25 | 21-Oct-25 | 21-Oct-25 | 100% | 21-Oct-25 |  |  | 21-Oct-25 | Connected | Connected | [5 empty] | 2025-11-13 |  |  | 2025-11-13 |  |  |  |  | 21-Oct-25 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 2024-01-03 | BAST | No Need | No Need | 2024-01-12 | No Need | APPROVED | PROPOSE INVOICE |  |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8300 | 2025-11-01
85 | 2025-10-08 | 2508-4GGSM-4G#RO-MTP041-290037 | Wireless RAN/Settlement Site/2508-4GGSM-4G#RO-MTP041-290037 | DU00006010345 | MTP041 | MTP041MT1 | YPTT | GARISHANYAR | BANJARMASIN | BANJARMASIN | BANJARMASIN | DMT | 2025 - Batch#2 (95) | 11502683 | -318999 | KALIMANTAN SELATAN, BANJAR, CINTAPURI DARUSSALAM, GARIS HANYAR | R9264M M7290(3), Mobi 12 Port(3), VBPe3p(1), Vemc4(1), Filter(6) | L900 | EQP New NE 4G LTE 900 10 Mhz | - | Release | Release | Release | Release | 21-Oct-25 | 22-Oct-25 | 2025-11-19 | Expired Need Extend | DOEID251020E3 | DOEID251020E4 | NO NEED | DNWID0662025102003 | DNWID0692025102002 | NO NEED | 21-Oct-25 | - | - | - | - | - | NY VALIDATION | YPTT | yoga | 21-Oct-25 | 21-Oct-25 | 21-Oct-25 | 22-Oct-25 | 100% | 23-Oct-25 |  |  | 23-Oct-25 | Connected | Connected | [5 empty] | 15-Dec-25 |  |  | Ongoing | [5 empty] | -45951 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 13-Dec-23 | BAST | No Need | No Need | 14-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8721 | 2025-12-09
86 | 2025-10-22 | 2509-U32T32R-4G#1023-SAG067-090265-S2 | Wireless RAN/Settlement Site/22509-U32T32R-4G#1023-SAG067-090265-S2 | DU00006037999 | SAG067 | SAG067M41 | YPTT | SIMPANG_TIGA_MELENGGANGDMT | PONTIANAK | SINTANG | SANGGAU | DMT | Tech CP3 Part 2 Capacity_67 | 110722822 | 790234 | KALIMANTAN BARAT. SANGGAU, SELKAYAM,MELENGGANG | BBU VBPe2q(1), ZXRAN A9652A S23(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Jumper 4.3M - NM 5m (4pcs) | Release | Release | Release | Release | 2025-09-24 | 2025-09-25 | 31-Oct-25 | Expired Need Extend | DOEID251018AQ | DOEID251018AR | NO NEED | DNWID0682025101801 | DNWID0712025101802 | NO NEED | 22-Oct-25 | 2026-11-09 | - | - | - | - | NY VALIDATION | YPTT | Arya | 22-Oct-25 | 22-Oct-25 | 22-Oct-25 | 22-Oct-25 | 100% | 22-Oct-25 |  |  | 22-Oct-25 | Connected | Connected | [5 empty] | 2025-11-10 |  |  | 2025-11-10 |  |  |  |  | 22-Oct-25 | [6 empty] | Not Start | [15 empty] | PO Confirmed | S1ID2023070102WBF1-8300 | 2025-11-01
87 | 2025-10-22 | 2509-REENG-4G#1024-SAG038-090307 | Wireless RAN/Settlement Site/2509-REENG-4G#1024-SAG038-090307 | DU00006037966 | SAG038 | SAG038ME1 | YPTT | BUNUTKM7 | PONTIANAK | SINTANG | SANGGAU | TSEL | Tech CP3 Part 2 Capacity_27 | 110550224 | 134942 | JL. DARANANTE RT .7 RW.03, KEL. BUNUT, KEC. KAPUAS, KAB. SANGGAU | VBPe1p(1), R8998G S2300(1), Mobi 12 port(1), Pole for new antenna (3m)(1), Upp ant | L2300 | EQP eNode B Modular Relocation Service New NE LTE 2300 | 1 Pcs Tongyu TDQ-182020DE-65F, 1 Pcs antena Kathrein 739650, 210m RRU PWR Cable 2 core Type-D 16mm², 3 Pcs RRU Fiber LC-LC 70m | Release | Release | Release | Release | 2025-09-24 | 2025-09-25 | 31-Oct-25 | Expired Need Extend | DOEID251009GI | DOEID251009GJ | NO NEED | DNWID0682025100910 | DNWID0712025100901 | NO NEED | 23-Oct-25 | 25 Oct | - | - | - | - | NY VALIDATION | YPTT | Arya | 23-Oct-25 | 23-Oct-25 | 23-Oct-25 | 24-Oct-25 | 100% | 24-Oct-25 |  |  | 24-Oct-25 | Connected | Connected | [5 empty] | 2025-11-10 |  |  | 2025-11-10 | 25-Oct-25 |  |  |  | 24-Oct-25 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 12-Dec-23 | BAST | No Need | No Need | 16-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8449 | 2025-11-13
88 | 2025-10-22 | 2508-4GGSM-4G#RO-PRG023-290066 | Wireless RAN/Settlement Site/2508-4GGSM-4G#RO-PRG023-290066 | DU00006010357 | PRG023 | PRG023MT1 | YPTT | HAMARUNG | BANJARMASIN | NEW HULU SUNGAI | NEW HULU SUNGAI | DMT | 2025 - Batch#2 (95) | 115554 | -233001 | KALIMANTAN SELATAN, BALANGAN, JUAI, HAMARUNG | R9264M M7290(3), Mobi 12 Port(3), VBPe3p(1), Vemc4(1), Filter(6) | L900 | EQP New NE 4G LTE 900 10 Mhz | - | Release | Release | Release | Release | 22-Oct-25 | 23-Oct-25 | 2025-11-20 | Expired Need Extend | DOEID251020E5 | DOEID251020E6 | NO NEED | DNWID0662025102004 | DNWID0692025102201 | NO NEED | 24-Oct-25 | - | - | - | - | - | NY VALIDATION | YPTT | Yoga | 21-Oct-25 | 24-Oct-25 | 21-Oct-25 | 22-Oct-25 | 100% | 26-Oct-25 |  |  | 27-Oct-25 | Connected | Connected | [5 empty] | 24-Dec-26 |  |  | Ongoing | [5 empty] | -45951 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 13-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8721 | 2025-12-09
89 | 2025-10-25 | 2507-U32T32R-4G#RO-SAG055-280020-S2 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-SAG055-280020-S2 | DU00005895016 | SAG055 | SAG055VR1 | YPTT | NOYANTSEL | PONTIANAK | SINTANG | SANGGAU | TSEL | CP#3 Batch1 Capacity Upgrade 4G | 11057744 | 76562 | JL GOLKAR RT 02/01 DUSUN NOYAN, KEC NOYAN, KAB SANGGAU | BBU VBPe2q(1), A9732 M1821(1), Pole for new antenna (3m)(1) | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release | 2 Oct | 03-Oct-25 | 2025-11-05 | Expired Need Extend | DOEID251009GC | NO NEED | NO NEED | DNWID0682025100903 | NO NEED | NO NEED | 28-Oct-25 | - | - | - | - | - | NY VALIDATION | YPTT | Julianto | 28-Oct-25 | 28-Oct-25 | 28-Oct-25 | 29-Oct-25 | 100% | 29-Oct-25 |  |  | 29-Oct-25 | Connected | Connected | [5 empty] | 2025-11-13 |  |  | 2025-11-13 |  |  |  |  | 29-Oct-25 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 13-Dec-23 | BAST | No Need | No Need | 14-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8449 | 2025-11-13
90 | 2025-10-25 | 2508-4GDCS-4G#RO-PTS036-290040 | Wireless RAN/Settlement Site/2508-4GDCS-4G#RO-PTS036-290040 | DU00006010350 | PTS036 | PTS036ML1 | YPTT | NANGATUBUK | PONTIANAK | SINTANG | KAPUAS HULU | DMT | 2025 - Batch#2 (95) | 112915 | 617259 | KALIMANTAN BARAT, KAPUAS HULU, KALIS, NANGA TUBUK | R9264 M1821(3), Mobi 12 Port(3), VBPe3p(1), Vemc4(1) | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | Release | Release | 28-Oct-25 | 28-Oct-25 | 2025-11-30 | Expired Need Extend | DOEID251024DZ | DOEID251024E0 | NO NEED | DNWID0682025102402 | DNWID0712025102404 | NO NEED | 26-Oct-25 | - | - | - | - | - | NY VALIDATION | YPTT | Arya | 26-Oct-25 | 26-Oct-25 | 27-Oct-25 | 27-Oct-25 | 100% | 2025-11-20 |  |  | 2025-11-21 | Connected | Connected | [5 empty] | 01-Dec-25 |  |  | 01-Dec-25 |  |  |  |  | 04-Dec-25 | 39 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 13-Dec-23 | BAST | No Need | No Need | 14-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8449 | 2025-11-13
91 | 2025-10-25 | 2509-U32T32R-4G#1023-PTS080-090253-S2 | Wireless RAN/Settlement Site/2509-U32T32R-4G#1023-PTS080-090253-S2 | DU00006038031 | PTS080 | PTS080VF1 | YPTT | KANTORBUPATIKAPUASHULUPTI | PONTIANAK | SINTANG | KAPUAS HULU | PTI | Tech CP3 Part 2 Capacity_67 | 11292873 | 844527 | Jl. Tanjung Pua RT001/RW001, Kel. Kedamin Hulu, Kec. Kedamin, Kab. Kapuas Hulu | BBU VBPe2q(1), ZXRAN A9652A S23(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | 1 Pcs RRU R8998G S2300 include Conector power, Bracket, 35m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 60m, 4 pcs Jumper 1/2" DM-NM 5m | Release | Release | Release | Release | 13-Oct-25 | 15-Oct-25 | 29-Oct-25 | Expired Need Extend | DOEID251017ES | NO NEED | NO NEED | DNWID0682025101705 | NO NEED | NO NEED | 28-Oct-25 | 29 Oct | - | - | - | - | NY VALIDATION | YPTT | Arya | 28-Oct-25 | 28-Oct-25 | 28-Oct-25 | 29-Oct-25 | 100% | 29-Oct-25 |  |  | 29-Oct-25 | Connected | Connected | [5 empty] | 29-Oct-25 |  |  | 29-Oct-25 | 29-Oct-25 | - | - | - | 29-Oct-25 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 14-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8449 | 2025-11-13
92 | 2025-10-26 | 2508-4GDCS-4G#RO-PTS037-290041 | Wireless RAN/Settlement Site/2508-4GDCS-4G#RO-PTS037-290041 | DU00006010364 | PTS037 | PTS037ML1 | YPTT | NANGA_SEMANGAT | PONTIANAK | SINTANG | KAPUAS HULU | TBG | CAPEX RAN 3 PART 2 2025 | 11288841 | 6552 | KALIMANTAN BARAT, KAPUAS HULU, KALIS, KALIS RAYA | VEMc4(1), BBU VBPe3p(1), RRU R9264 M1821(3), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(3) | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | Release | Release | 28-Oct-25 | 28-Oct-25 | 2025-11-30 | Expired Need Extend | DOEID251028Q6 | NO NEED | NO NEED | DNWID0682025102903 | NO NEED | NO NEED | 31-Oct-25 | - | - | - | - | - | NY VALIDATION | YPTT | Arya | 31-Oct-25 | 31-Oct-25 | 2025-11-03 | 2025-11-04 | 100% | 2025-11-08 |  |  | 2025-11-08 | Connected | Connected | [5 empty] | 04-Dec-25 |  |  | 01-Dec-25 |  |  |  |  | 02-Dec-25 | 32 | 01-Task Progress Connected | 00-Selfcheck Quality | Approved | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 15-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8723 | 2025-12-09
93 | 2025-10-26 | 2508-4GGSM-4G#RO-MTP026-290033 | Wireless RAN/Settlement Site/2508-4GGSM-4G#RO-MTP026-290033 | DU00006010361 | MTP026 | MTP026MT1 | YPTT | BUNGLAITBG | BANJARMASIN | BANJARMASIN | BANJAR | TBG | CAPEX RAN 3 PART 4 2025 | 11508518 | -347208 | KALIMANTAN SELATAN, BANJAR, ARANIO, BUNGLAI | VEMc4(1), BBU VBPe3p(1), R9264M M7290(3), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(3), Filter (6) | L900 | EQP New NE 4G LTE 900 10 Mhz | - | Release | Release | Release | Release | 31-Oct-25 | 2025-11-01 | 2025-11-30 | Expired Need Extend | DOEID251030D6 | NO NEED | NO NEED | DNWID0662025103001 | NO NEED | NO NEED | 31-Oct-25 | - | - | - | - | - | NY VALIDATION | YPTT | Yoga | 31-Oct-25 | 31-Oct-25 | 2025-11-01 | 2025-11-02 | 100% | 2025-11-18 |  |  | 2025-11-18 | Connected | Connected | [5 empty] | 20-Dec-26 |  |  | Ongoing | [5 empty] | -45961 | [5 empty] | Not Start | [15 empty] | PO Confirmed | S1ID2023070102WBF1-8839 | 2025-12-19
94 | 2025-10-26 | 2509-U32T32R-4G#1023-PTS002-090252-S1 | Wireless RAN/Settlement Site/2509-U32T32R-4G#1023-PTS002-090252-S1 | DU00006038023 | PTS002 | PTS002VR1 | YPTT | JONGKONG | PONTIANAK | SINTANG | KAPUAS HULU | TSEL | Tech CP3 Part 2 Capacity_67 | 112280293 | 656734 | JALAN LINTAS SENARA DESA JONGKONG, KECAMATAN EMBAU, KABUPATEN KAPUAS HULU | BBU VBPe2q(1), A9732 M1821(1), Pole for new antenna (3m)(1) | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release | 2025-09-24 | 2025-09-25 | 2025-11-15 | Expired Need Extend | DOEID250928B8 | NO NEED | NO NEED | DNWID0682025092904 | NO NEED | NO NEED | 31-Oct-25 | - | - | - | - | - | NY VALIDATION | YPTT | Arya | 2026-11-01 | 31-Oct-25 | 2025-11-02 | 2025-11-02 | 100% | 2025-11-02 |  |  | 2025-11-02 | Connected | Connected | [5 empty] | 04-Dec-25 |  |  | 01-Dec-25 |  |  |  |  | 03-Dec-25 | 32 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 14-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8723 | 2025-12-09
95 | 2025-10-28 | 2508-4GGSM-4G#RO-SAG074-290039 | Wireless RAN/Settlement Site/2508-4GGSM-4G#RO-SAG074-290039 | DU00006010312 | SAG074 | SAG074M41 | YPTT | UPETBG | PONTIANAK | SINTANG | SANGGAU | TBG | CAPEX RAN 3 PART 2 2025 | 1104806 | 36515 | KALIMANTAN BARAT, SANGGAU, BONTI, UPE | VEMc4(1), BBU VBPe3p(1), RRU R9264M M7290(3), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(3), Filter (6) (New infra) | L900 | EQP New NE 4G LTE 900 10 Mhz | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID251028Q7 | NO NEED | NO NEED | DNWID0682025102904 | NO NEED | NO NEED | 30-Oct-25 | - |  |  |  |  | NY VALIDATION | YPTT | Del Piero | 30 Oct | 30-Oct-25 | 30-Oct-25 | 2025-11-14 | 100% | 2025-11-14 |  |  | 2025-11-20 | Connected | Connected | [5 empty] | 2025-11-29 |  |  | 2025-11-29 | - | - | - | - | 2025-11-17 | 18 | 01-Task Progress Connected | 00-Selfcheck Quality | Approved | eATP | Check out | eATP Approved Tsel | No Issue | Scarlett | 2023-11-11 | BAST | No Need | No Need | 12-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  |  |  | PO Confirmed | S1ID2023070102WBF1-8723 | 2025-12-09
96 | 2025-10-28 | 2508-4GDCS-4G#RO-SAG058-290010 | Wireless RAN/Settlement Site/2508-4GDCS-4G#RO-SAG058-290010 | DU00006010313 | SAG058 | SAG058M41 | YPTT | DMT_SUNGAI TEKAM | PONTIANAK | SINTANG | SANGGAU | DMT | CAPEX RAN 3 PART 2 2025 | 110.7067 | 0.84568 | Dusun Sei Empelas RT 002 RW 001 Desa Sungai Tekam Kecamatan Sekayam Kabupaten Sanggau Provinsi Kalimantan Barat | VEMc4(1), BBU VBPe3p(1), RRU R9264 M1821(3), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(3) (New infra) | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID251028IM | DOEID251028IN | NO NEED | DNWID0682025102814 | DNWID0712025102802 | NO NEED | 31-Oct-25 | - |  |  |  |  | NY VALIDATION | YPTT | Arya Laviandra | 31 Oct | 31-Oct-25 | 31-Oct-25 | 2025-11-13 | 100% | 2025-11-13 |  |  | 2025-11-17 | Connected | Connected | [5 empty] | 2025-11-26 |  |  | 2025-11-26 | - |  |  |  | 2025-11-25 | 25 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 13-Dec-23 | BAST | No Need | No Need | 14-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  |  |  | PO Confirmed | S1ID2023070102WBF1-8723 | 2025-12-09
97 | 2025-10-28 | 2508-REENG-4G#RO-SAG058-290029 | Wireless RAN/Settlement Site/2508-REENG-4G#RO-SAG058-290029 | DU00006010316 | SAG058 | SAG058MR1 | YPTT | DMT_SUNGAI TEKAM | PONTIANAK | SINTANG | SANGGAU | DMT | CAPEX RAN 3 PART 2 2025 | 110.7067 | 0.84568 | Dusun Sei Empelas RT 002 RW 001 Desa Sungai Tekam Kecamatan Sekayam Kabupaten Sanggau Provinsi Kalimantan Barat | ADD BBU VBPe3p(1) | L2100 | EQP New NE 4G LTE 2100 20 Mhz | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID251028IO | NO NEED | NO NEED | DNWID0682025102808 | NO NEED | NO NEED | 31-Oct-25 | - |  |  |  |  | NY VALIDATION | YPTT | Arya Laviandra | 31 Oct | 31-Oct-25 | 31-Oct-25 | 2025-11-13 | 100% | 2025-11-13 |  |  | 2025-11-17 | Connected | Connected | [5 empty] | 2025-11-26 |  |  | 2025-11-26 | - |  |  |  | 2025-11-25 | 25 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 14-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  |  |  | PO Confirmed | S1ID2023070102WBF1-8723 | 2025-12-09
98 | 2025-11-02 | 2509-REENG-4G#1024-PTS005-090315 | Wireless RAN/Settlement Site/2509-REENG-4G#1024-PTS005-090315 | DU00006038012 | PTS005 | PTS005MF1 | YPTT | NBPM_16464 | PONTIANAK | SINTANG | KAPUAS HULU | DMT | Tech CP3 Part 2 Capacity_27 | 11196117 | 58531 | BATU AGUNG, SEMITAU, KAPUAS HULU, KALIMANTAN BARAT | Reuse 1 Pcs RRU R8998G S2300 include Conector Power(1), BBU VBPe1p(1) | L2300 | EQP eNode B Modular Relocation Service New NE LTE 2300 | - | Release | Release | Release | Release | 1 Oct | 3 Oct | 2026-11-05 | Expired Need Extend | DOEID251020WM | DOEID251020WL | NO NEED | DNWID0682025102102 | DNWID0712025102104 | NO NEED | 2025-11-04 | - | - | - | - | - | NY VALIDATION | YPTT | Arya | 2026-11-04 | 2025-11-04 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-05 |  |  | 2025-11-06 | Connected | Connected | [5 empty] | 2025-11-06 |  |  | 2025-11-06 |  |  |  |  | 2026-11-05 | 1 | [5 empty] | Not Start | [13 empty] | 16-Propose Mapping |  | PO Confirmed | S1ID2023070102WBF1-8720 | 2025-12-09
99 |  | 2507-U32T32R-4G#RO-NGP007-280015-S2 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-NGP007-280015-S2 | DU00005895043 | NGP007 | NGP007M41 | YPTT | KOTABARUTSEL | PONTIANAK | SINTANG | MELAWI | TSEL | CP#3 Batch1 Capacity Upgrade 4G | 111543286 | -790331 | JL. PANGERAN AGUNG KERTASARI KOTA BARU KEC TANAH PINOH KAB. MELAWI | SW Only, Dismental only | L1800 | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE ¦Remove 1 RF, Remove 1 RRU | Need Dismantle 1 Pcs RRU R9264 M1821 include SFP, conector Power, Bracket, 60m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 80m, 4 Pcs Jumper 1/2" DM-4.3M 5m, 1 Pcs antena Tongyu TDQ-182020DE-65F | Release | Release | Release | Release | 06-Oct-25 | 08-Oct-25 | 2025-11-21 | Expired Need Extend | NO NEED | NO NEED | NO NEED | NO NEED | NO NEED | NO NEED | 2025-11-07 | 2026-11-10 | - |  |  |  | NY VALIDATION | YPTT | Julianto | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-07 |  |  | 2025-11-07 | Connected | Connected | [5 empty] | 2025-11-10 |  |  | 2025-11-10 | 2025-11-10 |  |  |  | 2025-11-08 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 14-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  |  |  | PO Confirmed | S1ID2023070102WBF1-8720 | 2025-12-09
100 | 2025-11-08 | 2509-U32T32R-4G#1023-SHR008-090254-S2 | Wireless RAN/Settlement Site/2509-U32T32R-4G#1023-SHR008-090254-S2 | DU00006038024 | SHR008 | SHR008M41 | YPTT | POLRESSEKADAU | PONTIANAK | SINTANG | SEKADAU | TSEL | Tech CP3 Part 2 Capacity_67 | 110906273 | 14225 | JL. RAYA SOSOK SANGGAU RT. 03/01 DESA BINJAI KEC.TAYAN HULU KAB.SANGGAU | BBU VBPe2q(1), ZXRAN A9652A S23(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release | 2025-09-24 | 2025-09-25 | 2025-11-23 | Expired Need Extend | DOEID250928B9 | NO NEED | NO NEED | DNWID0682025092905 | NO NEED | NO NEED | 2025-11-09 | - |  |  |  |  | NY VALIDATION | YPTT | Julianto | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-10 | 100% | 2025-11-10 |  |  | 2025-11-10 | Connected | Connected | [5 empty] | 2025-11-17 |  |  | 2025-11-17 | - |  |  |  | 2025-11-10 | 1 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 14-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  |  |  | PO Confirmed | S1ID2023070102WBF1-8720 | 2025-12-09
101 | 2025-11-10 | 2509-REENG-4G#1024-SHR339-090322 | Wireless RAN/Settlement Site/2509-REENG-4G#1024-SHR339-090322 | DU00006038049 | SHR339 | SHR339MT1 | YPTT | TBG_SERARAS | PONTIANAK | SINTANG | SEKADAU | TBG | Tech CP3 Part 2 Capacity_27 | 111021667 | 66954 | TUMBANG TUKUN, SEKADAU HULU, SEKADAU, KALIMANTAN BARAT | Reuse 1 Pcs RRU R8852E S9000(1), BBU VBPe1p(1), 7090C filter(1) | L900 | EQP eNode B Modular Relocation Service New NE LTE 900 ¦Add 1 RRU | - | Release | Release | Release | Release | 01-Oct-25 | 06-Oct-25 | 2025-11-24 | Expired Need Extend | DOEID25110335 | NO NEED | NO NEED | DNWID0682025110304 | NO NEED | NO NEED | 2025-11-11 | - |  |  |  |  | NY VALIDATION | YPTT | Julianto | 2025-11-11 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 100% | 2025-11-14 |  |  | 2025-11-13 | Connected | Connected | [5 empty] | 2025-11-17 |  |  | Ongoing |  |  |  |  | 2025-11-14 | 3 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 2023-11-27 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  |  |  | PO Confirmed | S1ID2023070102WBF1-8840 | 2025-12-19
102 | 2025-11-10 | 2510-ADSTR-4G#RO-MPW018-240013 | Wireless RAN/Settlement Site/2510-ADSTR-4G#RO-MPW018-240013 | DU00006272383 | MPW018 | MPW018M41 | YPTT | Addsect_PALIXTSEL | PONTIANAK | SAMBAS | KUBURAYA | TSEL | CP3_P4 | 109253731 | -62206 | JALAN RAYA S. KAKAP RT.13 RW.IX KAMPUNG PARIT GADO DESA PAL IX KEC. PONTIANAK SELATAN, KAB. KUBU RAYA | Add Jumper | L1800 | EQP Add Sector LTE 1800 2T2R | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID25111016 | NO NEED | NO NEED | DNWID0682025111002 | NO NEED | NO NEED | 2025-11-10 | - | 2026-11-25 |  |  |  | NY VALIDATION | YPTT | Del Piero | 2025-11-12 | 2025-11-10 | 2025-11-13 | 2025-11-13 | 100% | 2025-11-16 |  |  | 2025-11-15 | Connected | Connected | [5 empty] | 2025-11-17 |  |  | 2025-11-17 | - | - | - | - | 2025-11-16 | 4 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 2023-11-30 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  |  |  | PO Confirmed | S1ID2023070102WBF1-8843 | 2025-12-19
103 | 2025-11-19 | 2509-U32T32R-4G#1023-SAG196-090294-S2 | Wireless RAN/Settlement Site/2509-U32T32R-4G#1023-SAG196-090294-S2 | DU00006038047 | SAG196 | SAG196M41 | YPTT | SEIRINGINTBG | PONTIANAK | SINTANG | SEKADAU | DMT | Tech CP3 Part 2 Capacity_67 | 11088734 | 1531 | Jl.Merdeka Selatan RT.18 RW.17 Desa Sei Ringin Kec.Sekadau Hilir Kab.Sekadau Prop.Kalimantan Barat | BBU VBPe2q(1), ZXRAN A9652A S23(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release |  |  |  | permit released | DOEID251028IU | NO NEED | NO NEED | DNWID0682025102812 | NO NEED | NO NEED | 2025-11-21 | 2025-11-27 |  |  |  |  | NY VALIDATION | YPTT | Arya Laviandra | 2025-11-20 | 2025-11-21 | 2025-11-20 | 2025-11-22 | 100% | 2025-11-22 |  |  | 2025-11-22 | Connected | Connected | [5 empty] | 2025-11-29 |  |  | 2025-11-29 | - | - | - | - | 2025-11-22 | 2 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Need | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 13-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  |  |  | PO Confirmed | S1ID2023070102WBF1-8841 | 2025-12-19
104 | 2025-11-23 | 2508-4GDCS-4G#RO-PTS033-290071 | Wireless RAN/Settlement Site/2508-4GDCS-4G#RO-PTS033-290071 | DU00006010320 | PTS033 | PTS033M41 | YPTT | TANJUNGJONGKONGDMT | PONTIANAK | SINTANG | KAPUAS HULU | DMT | CAPEX RAN 3 PART 2 2025 | 112291 | 668215 | KALIMANTAN BARAT, KAPUAS HULU, JONGKONG, JONGKONG KIRI HULU | VEMc4(1), BBU VBPe3p(1),RRU R9264 M1821(4), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(4), (New infra) | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | Release | Release |  |  |  | permit released | DOEID251121Q9 | NO NEED | NO NEED | DNWID0682025112203 | NO NEED | NO NEED | 2025-11-24 | - |  |  |  |  | NY VALIDATION | YPTT | Arya Laviandra | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-27 | 100% | 2025-11-27 |  |  | 2025-11-27 | Connected | Connected | [5 empty] | 04-Dec-25 |  |  | 01-Dec-25 | - | - | - | - | 2026-11-27 | 3 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Need | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 13-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 03-Connected | closed | PO Confirmed | S1ID2023070102WBF1-8841 | 2025-12-19
105 | 2025-11-21 | 2507-U32T32R-4G#RO-NGP018-280013-S2 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-NGP018-280013-S2 | DU00005895017 | SHR017 | SHR017M41 | YPTT | NANGAMAHAPTSEL | PONTIANAK | SINTANG | SEKADAU | TSEL | RCI WK-34 | 11075585 | -4238 | JL. POROS LANDAU APIN DESA NANGA MAHAP RT. 02/02, KEC NANGA MAHAP, KAB, SEKADAU | SW Only, dan dismental only | L1800 | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | 1 Pcs RRU R8894E M1821 include SFP, conector Power, Bracket, 85m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 100m, 4 Pcs Jumper 1/2" 4.3M-4.3M 5m ) | Release | Release | Release | Release |  |  |  | permit released | NO NEED | NO NEED | NO NEED | NO NEED | NO NEED | NO NEED | 2025-11-22 | 2026-11-22 |  |  |  |  | NY VALIDATION | YPTT | Del Piero | 2025-11-22 | 2025-11-22 | 2025-11-22 | 2025-11-22 | 100% | 2025-11-22 |  |  | 2025-11-22 | Connected | Connected | [5 empty] | 2025-11-29 |  |  | 2025-11-29 | - | - | - | - | 2026-11-22 | 0 | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Need | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 13-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  |  |  | PO Confirmed | S1ID2023070102WBF1-9356 | 2026-03-06
106 | 2025-11-28 | 2508-4GDCS-4G#RO-STA031-290038 | Wireless RAN/Settlement Site/2508-4GDCS-4G#RO-STA031-290038 | DU00006010335 | STA031 | STA031M41 | YPTT | SEMAJAUMEKARTBG | PONTIANAK | SINTANG | SINTANG | TBG | CAPEX RAN 3 PART 2 2025 | 11131322 | 36196 | KALIMANTAN BARAT, SINTANG, KETUNGAU HILIR, SEMAJAU MEKAR | BBU V9200 Package with VeMc4(1), BBU VBPe3p(1), RRU R9264 M1821(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(3), (New Infra) | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | Release | Release |  |  |  | permit released | DOEID251127I2 | NO NEED | NO NEED | DNWID0682025112704 | NO NEED | NO NEED | 2025-11-28 | - |  |  |  |  | NY VALIDATION | YPTT | Del Piero | 2025-11-29 | 2025-11-28 | 2025-11-29 | 01-Dec-25 | 100% | waiting TRM |  |  | 01-Dec-25 | Connected | Connected | [5 empty] | 17-Dec-26 |  |  | waiting TRM | - | - | - | - |  |  | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Need | Scarlett | 06-Dec-23 | BAST | No Need | No Need | 13-Dec-23 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  | 03-Connected | closed | PO Confirmed | S1ID2023070102WBF1-8842 | 2025-12-19
107 | 2025-11-04 | 2510-NNE4G-4G#RO-BLC336-140006-S2 | Wireless RAN/Settlement Site/2510-NNE4G-4G#RO-BLC336-140006-S2 | DU00006191892 | BLC336 | BLC336VR1 | YPTT | IAAS PPA New Mess (PT. PERKASA PUTRA ABADI) | BANJARMASIN | KOTABARU | TANAH BUMBU | SCO | capacity Acceleration CP1 2026 - A4 ZTE | 11560753 | -351436 | Mangkalapi, Kusan Hulu, Tanah Bumbu Regency, South Kalimantan | A9732 M1821(1), DCPD10B(1), pole for new antenna (3m)(1) | L1800 | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | 1 Pcs RRU R9224E M1821, include SFP, conector Power, Bracket, 25m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 60m, 4 Pcs Jumper 1/2" 4.3M-4.3M 5m ) | Release | Release | Release | Release |  |  |  | permit released | DOEID25110115 | NO NEED | NO NEED | DNWID0662025110105 | NO NEED | NO NEED | 2025-11-05 | 2026-11-22 |  |  |  |  | NY VALIDATION | YPTT | Yoga | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-29 | 100% | 2025-11-26 |  |  | 2025-11-30 | Connected | Connected | [5 empty] | 2025-11-23 |  |  | 2025-11-27 | [11 empty] | Not Start | [15 empty] | PO Confirmed | S1ID2023070102WBF1-8839 | 2025-12-19
108 | 2025-11-04 | 2510-NNE4G-4G#RO-BLC336-140007-S2 | Wireless RAN/Settlement Site/2510-NNE4G-4G#RO-BLC336-140007-S2 | DU00006201226 | BLC336 | BLC336VL1 | YPTT | IAAS PPA New Mess (PT. PERKASA PUTRA ABADI) | BANJARMASIN | KOTABARU | TANAH BUMBU | SCO | capacity Acceleration CP1 2026 - A4 ZTE | 11560753 | -351436 | Mangkalapi, Kusan Hulu, Tanah Bumbu Regency, South Kalimantan | - | L1800 | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release |  |  |  | permit released | NO NEED | NO NEED | NO NEED | NO NEED | NO NEED | NO NEED | 2025-11-05 | - |  |  |  |  | NY VALIDATION | YPTT | Yoga | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-29 | 100% | 2025-11-26 |  |  | 2025-11-30 | Connected | Connected | [5 empty] | 05-Dec-25 |  |  | 2025-11-23 | 2025-11-23 | [10 empty] | Not Start | [15 empty] | #N/A | #N/A | #N/A
109 | 2025-11-04 | 2510-NNE4G-4G#RO-BLC336-140008 | Wireless RAN/Settlement Site/2510-NNE4G-4G#RO-BLC336-140008 | DU00006191895 | BLC336 | BLC336ER1 | YPTT | IAAS PPA New Mess (PT. PERKASA PUTRA ABADI) | BANJARMASIN | KOTABARU | TANAH BUMBU | SCO | capacity Acceleration CP1 2026 - A4 ZTE | 11560753 | -351436 | Mangkalapi, Kusan Hulu, Tanah Bumbu Regency, South Kalimantan | Imacro ZXSDR A8612 M1821(1), pole for new antenna (3m)(1) | L1800 | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release |  |  |  | permit released | DOEID25110116 | NO NEED | NO NEED | DNWID0662025110101 | DNWID0662025111402 | NO NEED | 2025-11-05 | - |  |  |  |  | NY VALIDATION | YPTT | Yoga | 2025-11-05 | 2025-11-05 | 2025-11-05 | 07-Dec-25 | 100% | 2025-11-26 |  |  | 08-Dec-25 | Connected | Connected | [5 empty] | 10-Dec-25 |  |  | 01-Dec-25 | [11 empty] | Not Start | [15 empty] | PO Confirmed | S1ID2023070102WBF1-8839 | 2025-12-19
110 | 2025-11-04 | 2512-U32T32R-4G#RO-BLC336-010029-S3 | Wireless RAN/Settlement Site/2512-U32T32R-4G#RO-BLC336-010029-S3 | DU00006395692 | BLC336 | BLC336VL1 | YPTT | IAASPPANEWMESS | BANJARMASIN | KOTABARU | TANAH BUMBU | SCO | capacity Acceleration CP1 2026 - A4 ZTE | 11560753 | -351436 | Mangkalapi, Kusan Hulu, Tanah Bumbu Regency, South Kalimantan | Kabel power 90m dan optik 90m 1 pcs | L1800 | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | 1 Pcs RRU R9224E M1821, include SFP, conector Power, Bracket, 25m RRU PWR Cable 2 core Type-D 70mm², 1 Pcs RRU Fiber LC-LC 90m, 4 Pcs Jumper 1/2" 4.3M-4.3M 5m ) | Release | Release | Release | Release |  |  |  | permit released | NO NEED | NO NEED | NO NEED | DNWID0662025120501 | NO NEED | NO NEED | 2025-11-05 | 10 Dec |  |  |  |  | NY VALIDATION | YPTT | Yoga | 2025-11-05 | 2025-11-05 | 2025-11-05 | 01-Dec-25 | 100% | 2025-11-26 |  |  | 02-Dec-25 | Connected | Connected | [5 empty] | 2025-11-13 |  |  | 01-Dec-25 | [6 empty] | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 16-Dec-23 | BAST | No Need | No Need | 2024-02-13 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  |  |  | PO Confirmed | S1ID2023070102WBF1-9355 | 2026-03-06
111 | 2025-11-04 | 2507-U32T32R-4G#RO-BLC277-300008 | Wireless RAN/Settlement Site/2507-U32T32R-4G#RO-BLC277-300008 | DU00005900244 | BLC277 | BLC277VR1 | YPTT | B2B_PPA_NEW_OFFICE Ex. RTA097_AGM | BANJARMASIN | KOTABARU | TANAH BUMBU | SCO | capacity Acceleration CP1 2026 - A4 ZTE | 11560606 | -351705 | PT PPA | BBU VBPe2q(1), A9732 M1821(1), Pole for new antenna (3m)(1) | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release |  |  |  | permit released | DOEID25110112 | NO NEED | NO NEED | DNWID0662025110102 | NO NEED | NO NEED | 2025-11-05 | - |  |  |  |  | NY VALIDATION | YPTT | Yoga | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-09 | 100% | 2025-11-26 |  |  | 2025-11-10 | Connected | Connected | [5 empty] | 2025-11-13 |  |  | 2025-11-13 | [6 empty] | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 09-May-24 | BAST | No Need | No Need | 16-May-24 | No Need | APPROVED | PROPOSE INVOICE | [5 empty] | PO Confirmed | S1ID2023070102WBF1-8839 | 2025-12-19
112 | 2025-11-04 | 2510-NNE4G-4G#RO-BLC277-140003-S1 | Wireless RAN/Settlement Site/2510-NNE4G-4G#RO-BLC277-140003-S1 | DU00006191887 | BLC277 | BLC277VR1 | YPTT | PPANEWOFFICE-SCO | BANJARMASIN | KOTABARU | TANAH BUMBU | SCO | capacity Acceleration CP1 2026 - A4 ZTE | 11560606 | -351705 | PT PPA | BBU VBPe2q(1), A9732 M1821(1), Pole for new antenna (3m)(1) | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Need dsmantle 1 Pcs Board VBPc7 | Release | Release | Release | Release |  |  |  | permit released | DOEID25110114 | NO NEED | NO NEED | DNWID0662025110104 | NO NEED | NO NEED | 2025-11-05 | 2026-11-14 |  |  |  |  | NY VALIDATION | YPTT | Yoga | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-09 | 100% | 2025-11-26 |  |  | 2025-11-10 | Connected | Connected | [5 empty] | 2025-11-13 |  |  | 2025-11-13 | [6 empty] | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 2024-01-09 | BAST | No Need | No Need | 2024-03-06 | No Need | APPROVED | PROPOSE INVOICE | [5 empty] | PO Confirmed | S1ID2023070102WBF1-8839 | 2025-12-19
113 | 2025-11-04 | 2510-NNE4G-4G#RO-BLC277-140004-S3 | Wireless RAN/Settlement Site/2510-NNE4G-4G#RO-BLC277-140004-S3 | DU00006191889 | BLC277 | BLC277VL1 | YPTT | PPANEWOFFICE-SCO | BANJARMASIN | KOTABARU | TANAH BUMBU | SCO | capacity Acceleration CP1 2026 - A4 ZTE | 11560606 | -351705 | PT PPA | - | L1800 | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Need Dismantle 1 Pcs R9224E M1821 Include SFP, Bracket, Conector power, 30m RRU PWR Cable 2 core Type-D 10mm²,1 Pcs RRU Fiber LC-LC 60m, 1 Pcs antena Tongyu TYDB-182020DE4-33FT2 Sec 1, Lowering antena TMM L2300 Sec 3, antena MS L1800 & L2100 Sec 3, | Release | Release | Release | Release |  |  |  | permit released | NO NEED | NO NEED | NO NEED | NO NEED | NO NEED | NO NEED | 2025-11-05 | 2026-11-14 |  |  |  |  | NY VALIDATION | YPTT | Yoga | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-12 | 100% | 2025-11-26 |  |  | 2025-11-13 | Connected | Connected | [5 empty] | 05-Dec-25 |  |  | 2025-11-13 | [6 empty] | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 2024-01-10 | BAST | No Need | No Need | 2024-01-25 | No Need | APPROVED | PROPOSE INVOICE | [5 empty] | PO Confirmed | S1ID2023070102WBF1-8839 | 2025-12-19
114 | 2025-11-04 | 2509-REENG-4G#1024-BLC189-090297 | Wireless RAN/Settlement Site/2509-REENG-4G#1024-BLC189-090297 | DU00006037976 | BLC189 | BLC189ME1 | YPTT | STP PT. PUTRA PERKASA ABADI | BANJARMASIN | KOTABARU | TANAH BUMBU | SCO | capacity Acceleration CP1 2026 - A4 ZTE | 115629194 | -3488098 | PTPUTRAPERKASAABADISTP | Reuse 1 Pcs RRU R8998G S2300 include Conector Power(1), BBU VBPe1p(1) | L2300 | EQP eNode B Modular Relocation Service New NE LTE 2300 | - | Release | Release | Release | Release |  |  |  | permit released | DOEID25110113 | NO NEED | NO NEED | DNWID0662024110103 | NO NEED | NO NEED | 2025-11-05 | - |  |  |  |  | NY VALIDATION | YPTT | Yoga | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-30 | 100% | 2025-11-26 |  |  | 01-Dec-25 | Connected | Connected | [5 empty] | 16-Dec-25 |  |  | 01-Dec-25 | [6 empty] | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 2024-03-01 | BAST | No Need | No Need | 2024-03-05 | No Need | APPROVED | PROPOSE INVOICE | [5 empty] | PO Confirmed | S1ID2023070102WBF1-8839 | 2025-12-19
115 | 2025-12-06 | 2512-NNE4G-4G#RO-COH672-010002 | Wireless RAN/Settlement Site/2512-NNE4G-4G#RO-COH672-010002 | DU00006395682 | COH672 | COH672MR1 | YPTT | COMBATSOMPAK | PONTIANAK | PONTIANAK | KUBURAYA | TSEL | capacity Acceleration CP1 2026 - A4 ZTE | 10986546 | -213928 | Pulau Limbung, Kec. Sungai Raya, Kabupaten Kubu Raya, Kalimantan Barat 78392 | BBU Board VEMc4(1), RRU R9264 M1821(1) | L2100 | EQP New NE 4G LTE 2100 20 Mhz | 2 Pcs RRU R8852E S1800 include SFP, Conector Power, Bracket, 40m RRU PWR Cable 2 core Type-D 6mm², 2 Pcs RRU Fiber LC-LC 20m, 4 pcs Jumper 1/2" DM-DM 5m 1 Pcs Board VEMc 1 | Release | Release | Release | Release |  |  |  | permit released | DOEID251206C4 | NO NEED | NO NEED | DNWID0682025120601 | NO NEED | NO NEED | 07-Dec-25 | 11 Dec |  |  |  |  | NY VALIDATION | YPTT | Arya | 2025-12-07 | 07-Dec-25 | 07-Dec-25 | 08-Dec-25 | 100% | 09-Dec-25 |  |  | 09-Dec-25 | Connected | Connected | [5 empty] | 2026-01-06 |  |  | waiting QC | [6 empty] | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 2024-04-09 | BAST | No Need | No Need | 2024-04-16 | No Need | APPROVED | PROPOSE INVOICE | [5 empty] | PO Confirmed | S1ID2023070102WBF1-8843 | 2025-12-19
116 | 2025-12-08 | 2512-U32T32R-4G#RO-PTK036-010027-S3 | Wireless RAN/Settlement Site/2512-U32T32R-4G#RO-PTK036-010027-S3 | DU00006395691 | PTK036 | PTK036VR1 | YPTT | MALLAYANIMEGAMALL | PONTIANAK | PONTIANAK | Kota Pontianak | TSEL | capacity Acceleration CP1 2026 - A4 ZTE | 10934518 | -51127 | Mall A Yani Pontianak | BBU Board VEMc4(1), BBU VBPe1p(1), BBU VBPe2q(1), A9752 M1821(1), Pole for new antenna (3m)(1) | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Need Dismantle 1 Pcs Board VEMc 1 | Release | Release | Release | Release |  |  |  | permit released | DOEID251208GX | NO NEED | NO NEED | DNWID0682025120804 | NO NEED | NO NEED | 08-Dec-25 | 11 Dec |  |  |  |  | NY VALIDATION | YPTT | Del Piero - Arya | 2025-12-08 | 08-Dec-25 | 08-Dec-25 | 09-Dec-25 | 100% | 10-Dec-25 |  |  | 10-Dec-25 | Connected | Connected | [5 empty] | 23-Dec-26 |  |  | waiting QC | [6 empty] | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 2024-01-10 | BAST | No Need | No Need | 2024-01-25 | No Need | APPROVED | PROPOSE INVOICE | [5 empty] | PO Confirmed | S1ID2023070102WBF1-8843 | 2025-12-19
117 | 2025-12-11 | 2511-U4T4R-4G#RO-SAG497-290005 | Wireless RAN/Settlement Site/2511-U4T4R-4G#RO-SAG497-290005 | DU00006395676 | SAG497 | SAG497MT1 | YPTT | PTAACSCO | PONTIANAK | SINTANG | SANGGAU | SCO | capacity Acceleration CP1 2026 - A4 ZTE | 110194625 | -3414 | Enggadai, Kec. Meliau, Kabupaten Sanggau, Kalimantan Barat | R9264M M7290(1) | L900 | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | 1 pcs RRU R8852E S9000 include, SFP, Bracket, Conector power, 2 Pcs Jumper 1/2" DM-4.3M 5m, 70m RRU PWR Cable 2 core Type-D 6mm², 1 pcs RRU Fiber LC-LC 90m | Release | Release | Release | Release |  |  |  | permit released | DOEID251210EG | NO NEED | NO NEED | DNWID0682025121001 | NO NEED | NO NEED | 11-Dec-25 | Waiting Integrasi |  |  |  |  | NY VALIDATION |  | Del Piero | 2025-12-11 | 11-Dec-25 | 18-Dec-25 | 20-Dec-25 | 100% | 20-Dec-25 |  |  | 20-Dec-25 | Connected | Connected | waiting Antena 12 port 2pcs |  |  |  |  | 14-Dec-25 |  |  | waiting LOM | [6 empty] | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 2024-02-29 | BAST | No Need | No Need | 2024-03-05 | No Need | APPROVED | PROPOSE INVOICE | [5 empty] | PO Confirmed | S1ID2023070102WBF1-8992 | 2026-01-10
118 | 2025-12-12 | 2512-ADSTR-4G#RO-MPW564-110110 | Wireless RAN/Settlement Site/2512-ADSTR-4G#RO-MPW564-110110 | DU00006420776 | MPW564 | MPW564ML1 | YPTT | SEIDURIANTBG | PONTIANAK | PONTIANAK | KUBURAYA | TBG | CP1 Part 2 2026 | 10942356 | -5905 | Dusun Bale,Rt.002 Rw.003, Desa Durian,Kecamatan Sungai Ambawang,Kabupaten Kubu Raya,Provinsi Kalimantan Barat | BBU Board VEMc4(1), RRU R9264 M1821(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1) | L1800 | EQP Add Sector LTE 1800 2T2R | Need Dismantle 1 pcs Antena MOBI 4 Port Lowband , 1 Pcs VEMc1 | Release | Release | Release | Release |  |  |  | permit released | DOEID251211LI | NO NEED | NO NEED | DNWID0682025121111 | NO NEED | NO NEED | 12-Dec-25 | Waiting Integrasi |  |  |  |  | NY VALIDATION |  | Arya | 2025-12-12 | 12-Dec-25 | 13-Dec-25 | 14-Dec-25 | 100% | 14-Dec-25 |  |  | 14-Dec-25 | Connected | Connected | [5 empty] | 13-Dec-25 |  |  | 14-Dec-25 | 14-Dec-25 | [5 empty] | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 2024-01-25 | BAST | No Need | No Need | 2024-01-30 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  |  |  | PO Confirmed | S1ID2023070102WBF1-8992 | 2026-01-10
119 | 2025-12-13 | 2512-NNE4G-4G#RO-STA347-110101 | Wireless RAN/Settlement Site/2512-NNE4G-4G#RO-STA347-110101 | DU00006420801 | STA347 | STA347MR1 | YPTT | MERARAIDUAEBT | PONTIANAK | SINTANG | SINTANG | EBT | CP1 Part 2 2026 | 111449816 | -138506 | Merarai Dua, Sungai Tebelian, Kabupaten Sintang, Kalimantan Barat | DCPD10B Suit(1), BBU Board VEMc4 (1), BBU VBPe1p(1), RRU R9264 M1821(2) | L2100 | EQP New NE 4G LTE 2100 20 Mhz | 2 Pcs R8852E S1800 include SFP, Bracket, Conector power, 120m RRU PWR Cable 2 core Type-D 6mm², 2 Pcs RRU Fiber LC-LC 80m, 4 Pcs Jumper 1/2" DM-4.3M 5m, 1 Pcs VEMc1 | Release | Release | Release | Release |  |  |  | permit released | DOEID251211LE | DOEID251211LF | NO NEED | DNWID0682025121110 | DNWID0712025121102 | NO NEED | 13-Dec-25 | 14 Dec |  |  |  |  | NY VALIDATION |  | Del Piero | 2025-12-13 | 13-Dec-25 | 13-Dec-25 | 13-Dec-25 | 100% | 13-Dec-25 |  |  | 13-Dec-25 | Connected | Connected | [8 empty] | 13-Dec-25 | 14-Dec-25 | [5 empty] | 01-Task Progress Connected | 00-Selfcheck Quality | APPROVED | eATP | Check Out | eATP Approved Tsel | No Issue | Scarlett | 2024-01-17 | BAST | No Need | No Need | 2024-02-13 | No Need | APPROVED | PROPOSE INVOICE | Passed |  |  |  |  | PO Confirmed | S1ID2023070102WBF1-8992 | 2026-01-10
120 | 2025-12-02 | 2512-REENG-4G#RO-BLC012-110085 |  |  | BLC012 | BLC012MV1 | YPTT | B2B Market BIB | BANJARMASIN | BATULICIN | KOTABARU |  | CP1 Part 2 2026 | [14 empty] | Permit NY Requested | [12 empty] | NY VALIDATION | YPTT |  |  | 2025-09-01 | 2025-09-05 | 2025-09-05 | 100% | [5 empty] | Work Not Start | [20 empty] | Not Start | [15 empty] | #N/A | #N/A | #N/A
121 | 2025-12-02 | BBR055VR1 |  |  | BBR055 | BBR055VR1 | YPTT |  | BANJARMASIN | BANJARBARU | BANJARMASIN |  | CP1 Part 2 2026 | [14 empty] | Permit NY Requested | [12 empty] | NY VALIDATION | YPTT | [11 empty] | Work Not Start | [20 empty] | Not Start | [15 empty] | #N/A | #N/A | #N/A
122 | 2025-12-02 | BBR242MV1 |  |  | BBR242 | BBR242MV1 | YPTT |  | BANJARMASIN | BANJARBARU | BANJARMASIN |  | CP1 Part 2 2026 | [14 empty] | Permit NY Requested | [12 empty] | NY VALIDATION | YPTT | [11 empty] | Work Not Start | [20 empty] | Not Start | [15 empty] | #N/A | #N/A | #N/A
123 | 2025-12-02 | 2512-NNE4G-4G#RO-COH063-110068 |  |  | COH063 | COH063MV1 | YPTT | MIHILCON | BANJARMASIN | BANJARBARU | BANJARMASIN |  | CP1 Part 2 2026 | [14 empty] | Permit NY Requested | [12 empty] | NY VALIDATION | YPTT | [11 empty] | Work Not Start | [20 empty] | Not Start | [15 empty] | #N/A | #N/A | #N/A
124 | 2025-12-02 | 2512-NNE5G-5G#RO-BJM743-110020 |  |  | BJM743 | BJM743VP1 | YPTT | HOTEL_PALM_BANJARMASIN | BANJARMASIN | BANJARMASIN | BANJARMASIN |  | CP1 Part 2 2026 | [14 empty] | Permit NY Requested | [12 empty] | NY VALIDATION | YPTT | [11 empty] | Work Not Start | [20 empty] | Not Start | [15 empty] | PO Confirmed | S1ID2023070102WBF1-9291 | 2026-02-23
125 | 2025-12-15 | 2512-ADSTR-4G#RO-STA035-110083 |  |  | STA035 | STA035MV1 | YPTT | JERORA | PONTIANAK | SINTANG | SINTANG |  | CP1 Part 2 2026 | [7 empty] | Release | [6 empty] | Permit NY Requested | [6 empty] | 16-Dec-25 | [5 empty] | NY VALIDATION | YPTT | Del Piero |  | 16-Dec-25 | 16-Dec-25 | 16-Dec-25 | 100% | 17-Dec-25 | Laccima Ok |  | 17-Dec-25 | Connected | Connected | [5 empty] | 17-Dec-25 | [14 empty] | Not Start | [15 empty] | PO Confirmed | S1ID2023070102WBF1-8991 | 2026-01-10
126 | 2025-12-16 | 2512-NNE5G-5G#RO-PTK354-110030 |  |  | PTK354 | PTK354VP1 | YPTT | MC_HOSCOKROAMINOTO | PONTIANAK | PONTIANAK | PONTIANAK |  | CP1 Part 2 2026 | [7 empty] | Release | [6 empty] | Permit NY Requested | [6 empty] | 17-Dec-25 | [5 empty] | NY VALIDATION | YPTT | Arya |  | 17-Dec-25 | 17-Dec-25 | 19-Dec-25 | 100% | 19-Dec-25 | Laccima Ok |  | 19-Dec-25 | Connected | Connected | [5 empty] | 20-Dec-26 | [14 empty] | Not Start | [15 empty] | PO Confirmed | S1ID2023070102WBF1-8992 | 2026-01-10
127 | 2025-12-16 | 2512-NNE5G-5G#RO-PTK021-110022 |  |  | PTK021 | PTK021VP1 |  | SUTOYO | PONTIANAK | PONTIANAK | PONTIANAK |  | CP1 Part 2 2026 | [7 empty] | Release | [6 empty] | Permit NY Requested | [6 empty] | 18-Dec-25 | [5 empty] | NY VALIDATION | YPTT | Lasa |  | 18-Dec-25 | 18-Dec-25 | 19-Dec-25 | 100% | 21-Dec-25 | Laccima Ok |  | 21-Dec-25 | Connected | Connected | [5 empty] | 20-Dec-26 | [14 empty] | Not Start | [15 empty] | PO Confirmed | S1ID2023070102WBF1-8991 | 2026-01-10
128 | 2025-12-19 | 512-U32T32R-4G#RO-STA105-110059-S3 |  |  | STA104 |  | YPTT |  | PONTIANAK | SINTANG | SINTANG | [6 empty] | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | [15 empty] | 21-Dec-25 | [5 empty] | NY VALIDATION |  | DEL PIERO | 2025-12-21 | 21-Dec-25 | 21-Dec-25 | 22-Dec-25 | 100% | 23-Dec-25 | Laccima Ok |  | 22-Dec-25 | Connected | Connected | [5 empty] | 23-Dec-25 | [30 empty] | #N/A | #N/A | #N/A
129 | 2025-12-23 | 2512-U32T32R-4G#RO-TJL105-110078-S2 |  |  | TJL105 | TJL105VV1 | YPTT | PT_MABUUNTENGAH | BANJARMASIN | KOTABARU | KOTABARU | [23 empty] | 25-Dec-25 | [7 empty] | YOGA | 2025-12-24 | 24-Dec-25 | 25-Dec-25 | 25-Dec-25 | 100% | 25-Dec-25 | Laccima Ok |  | 26-Dec-25 | Connected | Connected | [5 empty] | 26-Dec-26 | [30 empty] | PO Confirmed | S1ID2023070102WBF1-9165 | 2026-01-30
130 | 2025-12-22 | 2512-NNE5G-5G#RO-PTK128-110027 |  |  | PTK128 | PTK128M51 | YPTT | IMACRO_PTK128_4_GAJAHMADAPONTIANAKPTI | PONTIANAK | PONTIANAK | PONTIANAK | PTI | CP1 part 164 | 10934069 | -3248 | JL GAJAH MADA 150 RT03/RW07 KEL. BENUA MELAYU DARAT, KEC. PONTIANAK SELATAN, KODYA PONTIANAK | DCPD10B Suit(1), BBU VBPe2q(1), A9652D M2326(3), Pole for new antenna (3m)(3) | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | - | Release | Release | Release | Release |  |  |  |  | DOEID25122202 | NO NEED | NO NEED | DNWID0682025122201 | NO NEED | NO NEED | 23-Dec-25 | - | [6 empty] | Julianto | 2025-12-23 | 23-Dec-25 | 24-Dec-25 | 24-Dec-25 | 100% | 24-Dec-25 |  |  | 24-Dec-25 | Connected | Connected | waiting DCPD10B |  |  |  |  | 2026-01-14 | [30 empty] | PO Confirmed | S1ID2023070102WBF1-8991 | 2026-01-10
131 | 2025-12-22 | 2512-NNE5G-5G#RO-PTK482-110033 |  |  | PTK131 | PTK131M51 | YPTT | RUKOPALPTI | PONTIANAK | PONTIANAK | PONTIANAK | PTI | CAPEX RAN 1 2026 Acceleration Support Part 5 For 5G Implementation | 109334863 | -36169 | JL. S. PARMAN RUKO W PALMA C6, RT001/RW033, KEL. BENUA MELAYU DARAT, KEC. PONTIANAK SELATAN, KAB. PONTIANAK | DCPD10B Suit(1), BBU Board VEMc4(1), BBU VBPe2q(1), A9652D M2326(3), Pole for new antenna (3m)(3) | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Need Dismantle 1 Pcs Board VEMc 1, 1 Pcs RRU R8998G S2300 Include SFP,Bracket, Conector Power, 15m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 20m, 4 Pcs Jumper 1/2" 4.3M-NM 5m | Release | Release | Release | Release |  |  |  |  | DOEID251223DQ | NO NEED | NO NEED | DNWID0682025122303 | NO NEED | NO NEED | 24-Dec-25 | waiting report tim | [6 empty] | Hijar | 2025-12-24 | 24-Dec-25 | 24-Dec-25 | 29-Dec-25 | 100% | 24-Dec-26 |  |  | 25-Dec-25 | Connected | Connected | OG |  |  |  |  | 2026-01-04 | [30 empty] | PO Confirmed | S1ID2023070102WBF1-9165 | 2026-01-30
132 | 2025-12-23 | 2512-NNE4G-4G#RO-COH944-110121 |  |  | SHR031 | SHR031M41 | YPTT | KEDOMBATBG | PONTIANAK | SINTANG | SEKADAU | TBG | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | 11103973 | -5872 | KALIMANTAN BARAT, SEKADAU, SEKADAU HILIR, GONIS TEKAM | DCPD10B Suit(1), BBU Board VEMc4(1), RRU R9264 M1821(1), | L1800 | EQP New NE 4G LTE 1800 20 Mhz | Need Dismantle 1 pcs antena Commscope LDX-9014DS-VTM, 1 Pcs Board VEMc1 | Release | Release | Release | Release |  |  |  |  | DOEID25121994 | NO NEED | NO NEED | DNWID0682025121901 | NO NEED | NO NEED | 24-Dec-25 | waiting report tim | [6 empty] | Del Piero | 2025-12-24 | 24-Dec-25 | 25-Dec-25 | 25-Dec-25 | 100% | 25-Dec-25 |  |  | 25-Dec-25 | Connected | Connected | OG |  |  |  |  | 2026-01-04 | [30 empty] | PO Confirmed | S1ID2023070102WBF1-9165 | 2026-01-30
133 | 2025-12-20 | 2512-NNE4G-4G#RO-PRG023-110076 |  |  | PRG023 | PRG023M41 | YPTT | HAMARUNGDMT | BANJARMASIN | NEW HULU SUNGAI | BALANGAN | DMT | CP1_P1_2026 | 115554 | -233001 | KALIMANTAN SELATAN, BALANGAN, JUAI, HAMARUNG | DCPD10B Suit(1), RRU R9264 M1821(2), | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | Release | Release |  |  |  |  | DOEID251215J1 | NO NEED | NO NEED | DNWID0662025121504 | NO NEED | NO NEED | 21-Dec-25 | - | [6 empty] | Yoga | 2025-12-21 | 21-Dec-25 | 24-Dec-25 | 24-Dec-25 | 100% | 24-Dec-25 |  |  | 24-Dec-25 | Connected | Connected | [5 empty] | 25-Dec-25 | [30 empty] | PO Confirmed | S1ID2023070102WBF1-8991 | 2026-01-10
134 | 2025-12-24 | 2512-NNE5G-5G#RO-BJM017-110039 |  |  | BJM017 | BJM017M41 | YPTT | GRAPARIBANJARMASINTSEL | BANJARMASIN | BANJAR | KOTA BANJARMASIN | TSEL | CP1 part 164 | 11462304 | -334663 | GEDUNG TELKOMSEL, JL. A. YANI KM 5,7 KEC. BANJARMASIN SELATAN KODYA BANJARMASIN, KALIMANTAN SELATAN 70248 | DCPD10B Suit(1), BBU Board VEMc4(1), BBU VBPe2q(1), A9652D M2326(3), Pole for new antenna (3m)(3) | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Need Dismantle 1 Pcs Board VEMc1, 1 Pcs Board VBPd2, RRU TDD | Release | Release | Release | Release |  |  |  |  | DOEID251226A8 | NO NEED | NO NEED | DNWID0662025122608 | NO NEED | NO NEED | 27-Dec-25 | waiting report tim | [6 empty] | Yoga | 2025-12-27 | 27-Dec-25 | 27-Dec-25 | 27-Dec-25 | 100% | 27-Dec-25 |  |  | 27-Dec-25 | Connected | Connected | OG |  |  |  |  | 2026-01-15 | [30 empty] | PO Confirmed | S1ID2023070102WBF1-9165 | 2026-01-30
135 | 2025-12-24 | 2512-NNE5G-5G#RO-BJM015-110006 |  |  | BJM015 | BJM015M41 | YPTT | BANJARMASINKM2TSEL | BANJARMASIN | BANJAR | KOTA BANJARMASIN | TSEL | CP1 part 164 | 11459963 | -33231 | JL. A. Yani Km.2 No.11, Kec. Banjarmasin Tengah, Kodya Banjarmasin, kalimantan Selatan | DCPD10B Suit(1), BBU VBPe1p(1), BBU VBPe2q(1), A9652D M2326(3), Pole for new antenna (3m)(3) | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Need Dismantle 1 pcs Board VBPd2 | Release | Release | Release | Release | [10 empty] | 30-Dec-26 | [7 empty] | Yoga | 2026-12-30 | 30-Dec-25 | 30-Dec-25 | 31-Dec-25 | 100% | 31-Dec-25 |  |  | 31-Dec-25 | Connected | Connected | [5 empty] | 2026-01-14 | [30 empty] | PO Confirmed | S1ID2023070102WBF1-9165 | 2026-01-30
136 | 2025-12-24 | 2512-NNE5G-5G#RO-BJM107-110011 | Wireless RAN/Settlement Site/2512-NNE5G-5G#RO-BJM107-110011 | DU00006420686 | BJM107 | BJM107VP1 | YPTT | GANGBERINGINPTI | BANJARMASIN | BANJAR | KOTA BANJARMASIN | PTI | CP1 part 164 | 11456432 | -331835 | Jl. Ir. Pm. Noor Gang Beringin RT049/RW016, Kel. Pelambuan, Kec. Banjarmasin Barat, Kab. Banjarmasin | DCPD10B Suit(1), BBU VBPe2q(1), A9652D M2326(3), Pole for new antenna (3m)(3) | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Need Dismantle 1 Pcs R8998G S2300 include SFP, Bracket, conector Power,30m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 50m, 4 pcs Jumper 1/2" 4.3M-NM 5m, 1 Pcs Board VBPd2 | Release | Release | Release | Release | 22-Dec-25 | 23-Dec-25 | 2026-01-20 | Expired Need Extend | DOEID251230B5 | NO NEED | NO NEED | DNWID0662025123001 | NO NEED | NO NEED | 2026-01-06 | 2026-01-07 | [6 empty] | Yoga | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 100% | 2026-01-06 |  |  | 2026-01-06 | Connected | Connected | [5 empty] | 2026-01-07 | [30 empty] | PO Confirmed | S1ID2023070102WBF1-9291 | 2026-02-23
137 | 2026-01-05 | 2512-U32T32R-4G#RO-NGP005-110104-S3 | Wireless RAN/Settlement Site/2512-U32T32R-4G#RO-NGP005-110104-S3 | DU00006420734 | NGP005 | NGP005VR1 | YPTT | MENUKUNGTSEL | PONTIANAK | SINTANG | MELAWI | TSEL | Program CP1 Part 2 | 1122289 | -42061 | DESA MANUKUNG KEC. MENUKUNG KAB. MELAWI | A9752 M1821(1), Pole for new antenna (3m)(1) | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release | 13-Dec-25 | 16-Dec-25 | 2026-01-14 | Expired Need Extend | DOEID260106AH | NO NEED | NO NEED | DNWID0682026010603 | NO NEED | NO NEED | 2026-01-07 | - | [6 empty] | Del Piero | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-08 | 100% | 2026-01-09 |  |  | 2026-01-07 | Connected | Connected | [5 empty] | 2026-01-09 | [30 empty] | PO Confirmed | S1ID2023070102WBF1-9181 | 2026-02-02
138 | 2026-01-05 | 2512-NNE4G-4G#RO-RTA067-110091-S2 | Wireless RAN/Settlement Site/2512-NNE4G-4G#RO-RTA067-110091-S2 | DU00006420622 | RTA067 | RTA067VE1 | YPTT | SPGKIWADMT | BANJARMASIN | HULU SUNGAI | TAPIN | DMT | Program CP1 Part 2 | 11515633 | -2932733 | Jl. SPG RT05/01, Kec Tapin Utara , Kab Rantau, Banjarmasin KalTim | VEMc4(1), BBU VBPe2q(1), A9652D M2326(1), Pole for new antenna (3m)(1) | L2300 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 32T32R | Need Dismantle 1 pcs VEMc1 | Release | Release | Release | Release | 17-Dec-25 | 19-Dec-25 | 2026-01-16 | Expired Need Extend | DOEID251230B1 | NO NEED | NO NEED | DNWID0662025123002 | NO NEED | NO NEED | 2026-01-07 | 2026-01-08 | [6 empty] | Yoga | 2026-01-07 | 2026-01-07 | 2026-01-08 | 2026-01-10 | 100% | 2026-01-11 |  |  | 2026-01-09 | Connected | Connected | [5 empty] | 2026-01-09 | [30 empty] | PO Confirmed | S1ID2023070102WBF1-9292 | 2026-02-23
139 | 2026-01-08 | 2512-NNE5G-5G#RO-BJM341-110018 |  |  | BJM341 | BJM341VP1 |  | MT_KINIBALU | BANJARMASIN | BANJARMASIN | BANJARMASIN | [5 empty] | DCPD10B Suit(1), BBU Board VEMc4(1), BBU VBPe1p(1), BBU VBPe2q(1), A9652D M2326(3), Pole for new antenna (3m)(3) |  |  | Need Dismantle 1 Pcs R8998G S2300 include SFP, Conector Power, Bracket, 30m RRU PWR Cable 2 core Type-D 10mm², 2 Pcs RRU Fiber LC-LC 50m, 4 pcs Jumper 1/2" N.M-4.3M 5m, 1 Pcs Board VEMc 1, 1 Pcs Board VBPd2 | Release | Release | Release | Release | [10 empty] | 2026-01-11 | [7 empty] | YOGA | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-13 | 100% | 2026-01-13 |  |  | 2026-01-12 | Connected | Connected | [5 empty] | 2026-01-15 | [30 empty] | PO Confirmed | S1ID2023070102WBF1-9292 | 2026-02-23
140 | 2026-02-02 | 2602-NNE4G-4G#RO-PTK300-030061-S1 |  |  | PTK300 | PTK300VE1 | YPTT | TB_TERMINALSI | PONTIANAK | PONTIANAK | Kota Pontianak | TBG | 2026 CP1 PART 3 | 10934375 | -1491 | JL. KHATULISTIWA GG. PARIT WAN SALIM, RT. 03/07 SIANTAN PONTIANAK UTARA PONTIANAK | A9652D M2326(1), Pole for new antenna (3m) | L2300 | EQP New NE 4G LTE 2300 20 Mhz Massive MIMO 32T32R Macro 1 | - | Release | Release | Release | Release | 2026-02-07 | 2026-02-07 | 2026-02-14 | Expired Need Extend | DOEID260205BB | NO NEED | NO NEED | DNWID0682026020501 | NO NEED | NO NEED | 2026-02-07 | - | [6 empty] | Julianto | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | 100% | 2026-02-07 |  |  | 2026-02-07 | Connected | Connected | [8 empty] | 2026-02-09 | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9361 | 2026-03-09
141 | 2026-02-02 | 2602-ADSTR-4G#RO-MPW022-030027 |  |  | MPW022 | MPW022ML1 | YPTT | PADANG TIKAR | PONTIANAK | SINTANG | KUBURAYA | TSEL | 2026 CP1 PART 3 | 10926418 | -695 | JL. MEDAN SARI RT. 05/III DESA PADANG TIKAR, KEC. BATU AMPAR KAB.MEMPAWAH / KUBU RAYA | RRU R9264 M1821(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1) | L1800 | EQP Add Sector LTE 1800 2T2R | Need Dismantle 1 pcs antena Kathrein 739650 | Release | Release | Release | Release | 2026-02-07 | 2026-02-07 | 2026-02-14 | Expired Need Extend | DOEID260205B7 | NO NEED | NO NEED | DNWID0682026020904 | NO NEED | NO NEED | 2026-02-10 | 2026-02-12 | [6 empty] | Julianto | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-11 | 100% | 2026-02-11 |  |  | 2026-02-11 | Connected | Connected | [8 empty] | waiting review | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9361 | 2026-03-09
142 | 2026-02-02 | 2601-4GGSM-4G#RO-NGP028-170002 |  |  | NGP028 | NGP028MT1 | YPTT | ANJUNG_LAYCMI | PONTIANAK | SINTANG | MELAWI | CMI | 2026 New Infra CP1 Part 2 | 11173820 | -38209 | KALIMANTAN BARAT, MELAWI, NANGA PINOH, TANJUNG LAY | BBU VBPe3p(1), R9264M M7290(2), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(3), 7090C filter(3) | L900 | EQP New NE 4G LTE 900 10 Mhz | - | Release | Release | Release | Release | 2026-02-07 | 2026-02-07 | 2026-02-14 | Expired Need Extend | DOEID260209A1 | NO NEED | NO NEED | DNWID0682026020901 | NO NEED | NO NEED | 2026-02-11 | - | [6 empty] | La Sanudi | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 100% | 00-Jan-00 |  |  | 2026-02-15 | Connected | Connected | [36 empty] | PO Confirmed | S1ID2023070102WBF1-9459 | 2026-03-21
143 | 2026-02-02 | 2601-NNE4G-4G#RO-NGP028-170005 |  |  | NGP028 | NGP028ML1 | YPTT | ANJUNG_LAYCMI | PONTIANAK | SINTANG | MELAWI | CMI | 2026 New Infra CP1 Part 2 | 11173820 | -38209 | KALIMANTAN BARAT, MELAWI, NANGA PINOH, TANJUNG LAY | RRU R9264 M1821(2), DCPD10B Suit(1), | L1800 | EQP New NE 4G LTE 1800 20 Mhz | - | Release | Release | Release | Release | 2026-02-07 | 2026-02-07 | 2026-02-14 | Expired Need Extend | DOEID260209A2 | NO NEED | NO NEED | DNWID0682026020905 | NO NEED | NO NEED | 2026-02-11 | - | [6 empty] | La Sanudi | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 100% | 00-Jan-00 |  |  | 2026-02-15 | Connected | Connected | [36 empty] | PO Confirmed | S1ID2023070102WBF1-9459 | 2026-03-21
144 | 2026-02-02 | 2602-ADSTR-4G#RO-NGP186-030053 |  |  | NGP186 | NGP186MV1 | YPTT | MT_DESAKENUAL | PONTIANAK | SINTANG | MELAWI | DMT | 2026 CP1 PART 3 | 111736726 | -335115 | DUSUN TANJUNG INDAH RT 03/02 DS. TANJUNG NIAGA, KEC. NANGA PINOH, KABUPATEN MELAWI, KALIMANTAN BARAT | DCPD10B Suit(1), BBU Board VEMc4(1), BBU VBPe1p, RRU R9614 S2300(1) | L2300 | EQP Add Sector LTE 2300 4T4R | Need Dismantle 1 pcs VEMc1 | Release | Release | Release | Release | 2026-02-07 | 2026-02-07 | 2026-02-14 | Expired Need Extend | DOEID260205BA | NO NEED | NO NEED | DNWID0682026020506 | NO NEED | NO NEED | 2026-02-07 | 2026-02-09 | [6 empty] | La Sanudi | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | 100% | 2026-02-07 |  |  | 2026-02-07 | Connected | Connected | [8 empty] | 2026-02-09 | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9361 | 2026-03-09
145 | 2026-02-02 | 2602-ADSTR-4G#RO-NGP021-030008 |  |  | NGP021 | NGP021MV1 | YPTT | MT_NANGAPINOHROAD3 | PONTIANAK | SINTANG | MELAWI | DMT | 2026 CP1 PART 3 | 11172374 | -3374 | KEL. TANJUNG TENGANG KEC. NANGA PINOH KALBAR | DCPD10B Suit(1), BBU Board VEMc4(1), RRU R9614 S2300(1) | L2300 | EQP Add Sector LTE 2300 4T4R | Need Dismantle 1 Pcs VEMc1 | Release | Release | Release | Release | 2026-02-07 | 2026-02-07 | 2026-02-14 | Expired Need Extend | DOEID260205B5 | NO NEED | NO NEED | DNWID0682026020502 | NO NEED | NO NEED | 2026-02-07 | 2026-02-09 | [6 empty] | La Sanudi | 2026-02-08 | 2026-02-07 | 2026-02-08 | 2026-02-08 | 100% | 2026-02-08 |  |  | 2026-02-08 | Connected | Connected | [8 empty] | 2026-02-09 | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9361 | 2026-03-09
146 | 2026-02-02 | 2602-ADSTR-4G#RO-SBS004-030036 |  |  | SBS004 | SBS004ML1 | YPTT | STOSEKURA | PONTIANAK | SINGKAWANG | SAMBAS | DMT | 2026 CP1 PART 3 | 109220251 | 1468786 | STO TELKOM SEKURA, KAB. SAMBAS KEC. SAMBAS | Add Jumper | L1800 | EQP Add Sector LTE 1800 2T2R Macro7 | - | Release | Release | Release | Release | 2026-02-07 | 2026-02-07 | 2026-02-14 | Expired Need Extend | DOEID260205B8 | NO NEED | NO NEED | DNWID0682026020505 | NO NEED | NO NEED | 2026-02-08 | - | [6 empty] | Djamali | 2026-02-08 | 2026-02-08 | 2026-02-08 | 2026-02-08 | 100% | 2026-02-08 |  |  | 2026-02-08 | Connected | Connected | [8 empty] | waiting review | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9361 | 2026-03-09
147 | 2026-02-02 | 2512-NNE5G-5G#RO-PTK319-110034 |  |  | PTK319 | PTK319VP1 | YPTT | IMACRO_EPQ057_PONTIANAK | [45 empty] | Work Not Start | [36 empty] | #N/A | #N/A | #N/A
148 | 2026-02-04 | 2602-U32T32R-4G#RO-BJM742-030042 |  |  | BJM742 | BJM742VR1 | YPTT | DutamallBanjarmasin | BANJARMASIN | BANJAR | KOTA BANJARMASIN | TSEL | 2026 CP1 PART 3 | 11460272 | -332218 | Duta Mall Banjarmasin Kalsel JL. A Yani KM 2.5 | DCPD10B Suit(1), BBU VBPe2q(2), A9752 M1821(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Need Dismantle 2 Pcs VBPc7, 1 Pcs VBPc0 & return 1 MIMO | Release | Release | Release | Release | 2026-02-07 | 2026-02-07 | 2026-02-14 | Expired Need Extend | DOEID26020753 | NO NEED | NO NEED | DNWID0662026020702 | NO NEED | NO NEED | 2026-02-11 | waiting list tim | [6 empty] | Yoga | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-12 | 100% | 2026-02-12 |  |  | 2026-02-13 | Connected | Connected | [8 empty] | 2026-02-15 | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9492 | 2026-04-04
149 | 2026-02-21 | 2602-ADSTR-4G#RO-STA004-060086 |  |  | STA004 | STA004M41 | YPTT | Addsect_SINTANGROAD | PONTIANAK | SINTANG | SINTANG | TSEL | Capacity Upgrade 4G | 11145488 | 2333 | JL. PONTIANAK - SINTANG, DS.NENAK RT 07/03 KEL.SUNGAI UKOI, KEC.SUNGAI TEBAKAN. | Reuse 1 Pcs Pole Mounting Use Ex Dismantle / Buffer, BBU Board VEMc4, R9264M M7290(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1) | L900 |  | Need Dismantle 1 Pcs VEMc 1 | Release | Release | Release | Release |  |  |  |  | DOEID260218C7 | DOEID260218C8 | NO NEED | DNWID0682026021806 | DNWID0712026021801 | NO NEED | 2026-02-21 | [7 empty] | La Sanudi | 2026-02-21 | 2026-02-21 | 2026-02-21 | 2026-02-22 | 100% | 2026-02-22 |  |  | 2026-02-23 | Connected | Connected | [8 empty] | 2026-02-23 |  |  |  |  | 2026-02-22 | [22 empty] | PO Confirmed | S1ID2023070102WBF1-9473 | 2026-03-29
150 | 2026-02-22 | 2602-U32T32R-4G#RO-KGN069-030046-S2 |  |  | KGN069 | KGN069M41 | YPTT | SEKOLAHNEGARADMT | BANJARMASIN | HULU SUNGAI | HULU SUNGAI SELATAN | DMT | 2026 CP1 PART 3 | 115103178 | -2632483 | Jl. Sekolah islam RT 01 RW 01 Desa Sungai Pinang Kec. Daha Selatan, Negara Prop. Kalimantan Selatan | BBU Board VEMc4(1), BBU VBPe2q(1), A9652D M2326(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Need Dismantle 1 Pcs VEMc1 | Release | Release | Release | Release |  |  |  |  | DOEID260220FG | NO NEED | NO NEED | DNWID0662026022004 | NO NEED | NO NEED | 2026-02-22 | [7 empty] | Yoga | 2026-02-22 | 2026-02-22 | 2026-02-23 | 2026-02-22 | 100% | 2026-02-22 |  |  | 2026-02-23 | Connected | Connected | [8 empty] | 2026-02-23 |  |  |  |  | 2026-02-22 | [22 empty] | PO Confirmed | S1ID2023070102WBF1-9491 | 2026-04-04
151 | 2026-02-24 | 2602-ADSTR-4G#RO-STA034-060082 |  |  | STA034 | STA034M41 | YPTT | Addsect_SIMPANGNANGAPINOH | PONTIANAK | SINTANG | SINTANG | TSEL | Capacity Upgrade 4G | 11144637 | -2824 | JL PONTIANAK SINTANG DSN. SIMPANG TIGA RT.02 RW.01 KEL. SUNGAI UKOI KEC. SUNGAI TEBLIAN KAB. SINTANG | Reuse 1 Pcs Pole Mounting Use Ex Dismantle, BBU Board VEMc4(1), R9264M M7290(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1) | L900 | EQP Add Sector LTE 900 2T2R | Need Dismantle 1 Pcs VEMc 1, 1 pcs R8852 S9000 incude SFP, Bracket, conector Power, 50m RRU PWR Cable 2 core Type-D 6mm², 1 Pcs RRU Fiber LC-LC 70m | Release | Release | Release | Release |  |  |  |  | DOEID26022148 | DOEID26022149 | NO NEED | DNWID0682026022107 | DNWID0712026022103 | NO NEED | 2026-02-24 | [7 empty] | La Sanudi | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 100% | 2026-02-24 |  |  | 2026-02-26 | Connected | Connected | [8 empty] | 2026-02-28 |  |  |  |  | 2026-02-24 | [22 empty] | PO Confirmed | S1ID2023070102WBF1-9473 | 2026-03-29
152 | 2026-02-23 | 2602-ADSTR-4G#RO-BRI021-060113 |  |  | BRI021 | BRI021M41 | YPTT | Addsect_TLKMASJID | BANJARMASIN | HULU SUNGAI | HULU SUNGAI TENGAH | TSEL | Capacity Upgrade 4G | 11534300 | -266870 | JL. KH Moh. Taher RT.07 RW.04 Kel. Teluk Masjid Kec. haruyan Kab. Hulu Sungai Tengah Kalsel | Reuse 1 Pcs Pole Mounting Use Ex Dismantle / Buffer , BBU Board VEMc4(1), R9264M M7290(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1) | L900 | EQP Add Sector LTE 900 2T2R | Reuse 1 Pcs Pole Mounting Use Ex Dismantle / Buffer , Need Dismantle 1 Pcs VEMc 1, 1 pcs R8852 S9000 incude SFP, Bracket, conector Power, 40m RRU PWR Cable 2 core Type-D 6mm², 1 Pcs RRU Fiber LC-LC 60m | Release | Release | Release | Release |  |  |  |  | DOEID260220FE | DOEID260220FF | NO NEED | DNWID0662026022005 | DNWID0692026022003 | NO NEED | 2026-02-23 | [7 empty] | Yoga | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 100% | 2026-02-24 |  |  | 2026-02-25 | Connected | Connected | [8 empty] | 2026-02-25 |  |  |  |  | 2026-02-24 | [22 empty] | PO Confirmed | S1ID2023070102WBF1-9491 | 2026-04-04
153 | 2026-02-25 | 2602-NNE4G-4G#RO-PTS030-060065 |  |  | PTS030 | PTS030M41 | YPTT | MIAUMERAHTBG | PONTIANAK | SINTANG | KAPUAS HULU | TBG | New NE 4G | 11178474 | 25313 | SUKA DAMAI, SILAT HILIR, KAPUAS HULU, KALIMANTAN BARAT | BBU Board VEMc4(1), BBU VBPe1p(1), R9264M M7290(1) | L900 | EQP New NE 4G LTE 900 10 MHz | - | Release | Release | Release | Release |  |  |  |  | DOEID260223B5 | NO NEED | NO NEED | DNWID0682026022301 | NO NEED | NO NEED | 2026-02-25 | [7 empty] | La Sanudi | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 100% | 2026-02-26 |  |  | 2026-02-26 | Connected | Connected | [8 empty] | 2026-02-28 | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9493 | 2026-04-04
154 | 2026-02-26 | 2602-4GGSM-4G#RO-BEK027-060001 |  |  | BEK027 | BEK027M41 | YPTT | GUA_DUGINANGSTP | PONTIANAK | SAMBAS | BENGKAYANG | STP | CP#1 Part 2 2026_New NE 4G | 10966645 | 117026 | KALIMANTAN BARAT, BENGKAYANG, SANGGAU LEDO, GUA | VC9910 Package with DCPD10B & LPU2(1), BBU V9200 Package with VeMc4(1), VSWd1(1), VBPe3p(1), R9264M M7290(2), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(3), 7090C filter(3) | L900 | EQP New NE 4G LTE 900 10 Mhz | - | Release | Release | Release | Release |  |  |  |  | DOEID260224AW | NO NEED | NO NEED | DNWID0682026022401 | NO NEED | NO NEED | 2026-02-26 | [7 empty] | Rizki | 2026-02-26 | 2026-02-26 | 2026-02-28 | 2026-02-28 | 100% | 2026-03-14 |  |  | 2026-03-14 | Connected | Connected | waiting TRM | [7 empty] | Waiting TRM | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9493 | 2026-04-04
155 | 2026-02-26 | 2602-NNE4G-4G#RO-BEK027-060034 |  |  | BEK027 | BEK027M41 | YPTT | GUA_DUGINANGSTP | PONTIANAK | SAMBAS | BENGKAYANG | STP | CP#1 Part 2 2026_New NE 4G | 10966645 | 117026 | KALIMANTAN BARAT, BENGKAYANG, SANGGAU LEDO, GUA | DCPD10B Suit(1), RRU R9264 M1821(2) | L1800 | EQP New NE 4G LTE 1800 10 Mhz | - | Release | Release | Release | Release |  |  |  |  | DOEID260224AX | NO NEED | NO NEED | DNWID0682026022402 | NO NEED | NO NEED | 2026-02-26 | [7 empty] | Rizki | 2026-02-26 | 2026-02-26 | 2026-02-28 | 2026-02-28 | 100% | 2026-03-14 |  |  | 2026-03-14 | Connected | Connected | waiting TRM | [7 empty] | Waiting TRM | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9493 | 2026-04-04
156 | 2026-02-28 | 2602-NNE4G-4G#RO-NGP024-060067 |  |  | NGP024 | NGP024MT1 | YPTT | KELAKIKPTI | PONTIANAK | SINTANG | MELAWI | PTI | New NE 4G | 111.7595 | -0.36026 | KALIMANTAN BARAT. MELAWI, NANGA PINOH,KELAKIK | R9264M M7290(2) | L900 | EQP New NE 4G LTE 900 10 MHz | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26022679 | NO NEED | NO NEED | DNWID0682026022602 | NO NEED | NO NEED | 2026-02-28 | [7 empty] | La Sanudi | 2026-02-28 | 2026-02-28 | 2026-03-02 | 2026-03-02 | 100% | 2026-03-02 |  |  | 2026-03-02 | Connected | Connected | [8 empty] | 2026-03-03 | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9493 | 2026-04-04
157 | 2026-02-27 | 2602-ADSTR-4G#RO-STA120-060134 |  |  | STA120 | STA120MT1 | YPTT | Addsect_MELAWIDMT | PONTIANAK | SINTANG | MELAWI | DMT | Capacity Upgrade 4G | 111.7448 | -0.34499 | DUSUN TANAH TINGGI, RT. 06/04, KEL. TANJUNG NIAGA, KEC. NANGAPINOH, KAB MELAWI. | Reuse 1 Pcs Pole Mounting Use Ex Dismantle / Buffer, BBU Board VEMc4(1), R9264M M7290(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1) | L900 | EQP Add Sector LTE 900 2T2R | Need Dismantle 1 Pcs VEMc 1, 1 pcs R8852 S9000 incude SFP, Bracket, conector Power, 40m RRU PWR Cable 2 core Type-D 6mm², 1 Pcs RRU Fiber LC-LC 60m | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26022152 | DOEID26022153 | NO NEED | DNWID0682026022106 | DNWID0712026022102 | NO NEED | 2026-02-27 | [7 empty] | La Sanudi | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-28 | 100% | 2026-02-28 |  |  | 2026-02-28 | Connected | Connected | [8 empty] | 2026-03-03 | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9493 | 2026-04-04
158 | 2026-02-26 | 2602-ADSTR-4G#RO-EPQ210-060031 |  |  | EPQ210 | EPQ210EL1 | YPTT | PRG010_KUPANGOlegPTI | BANJARMASIN | NEW HULU SUNGAI | BALANGAN | PTI | CP#1 Part 2 2026_Capacity Upgrade 4G | 115.387 | -2.3275 | KALIMANTAN SELATAN, BALANGAN, LAMPIHONG, SUNGAI AWANG | BBU VBPe3p(1), RRU R9264 M1821(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1) | L1800 | EQP Add Sector LTE 1800 2T2R | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID260224CZ | NO NEED | NO NEED | DNWID0662026022404 | NO NEED | NO NEED | 2026-02-26 | [7 empty] | Yoga | 2026-02-26 | 2026-02-26 | 2026-02-27 | 2026-02-27 | 100% | 2026-03-14 |  |  | 2026-03-14 | Connected | Connected | waiting Rect Batt dan OTB | [7 empty] | 2026-03-14 | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9541 | 2026-04-10
159 | 2026-02-28 | 2602-ADSTR-4G#RO-KGN060-060117 |  |  | KGN060 | KGN060MT1 | YPTT | Addsect_JOHANSYAHPTI | BANJARMASIN | HULU SUNGAI | HULU SUNGAI SELATAN | PTI | Capacity Upgrade 4G | 115.2414 | -2.8042 | Ds. Kapuh RT004, Kec. Simpur, Kab. Hulu Sungai Selatan | BBU Board VEMc4(1), R9264M M7290(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1), | L900 | EQP Add Sector LTE 900 2T2R | Need Dismantle 1 Pcs VEMc 1, 1 pcs R8852 S9000 incude SFP, Bracket, conector Power, 50m RRU PWR Cable 2 core Type-D 6mm², 1 Pcs RRU Fiber LC-LC 50m | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26022690 | NO NEED | NO NEED | DNWID0662026022606 | NO NEED | NO NEED | 2026-02-28 | [7 empty] | Yoga | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-02-28 | 100% | 2026-02-28 |  |  | 2026-02-28 | Connected | Connected | [8 empty] | 2026-03-13 | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9541 | 2026-04-10
160 | 2026-03-03 | 2602-NNE5G-5G#RO-MTP054-250003 |  |  | MTP054 | MTP054VP1 | YPTT | STADAMJW-TBG | BANJARMASIN | BATULICIN | MARTAPURA | TBG | 5G MV | 114.8504 | -3.4119 | Jl. Sultan Adam No.8 Rt.03/02 Kel. Jawa Kec. Martapura Kab. Banjar Baru | DCPD10B Suit(1), VEMc4(1), VBPe2q(1), A9652D M2326(3), Pole for new antenna (3m)(3) | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Need Dismantle 1 pcs VEMc1, 1 pcs R8998G S2300 inlude SFP, Bracket, Conector Power, 40m RRU PWR Cable 2 core Type-D 10mm² ,1 pcs RRU Fiber LC-LC 60m | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26030256 | NO NEED | NO NEED | DNWID0662026030202 | NO NEED | NO NEED | 2026-03-03 | [7 empty] | Yoga | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-05 | 100% | 2026-03-05 |  |  | 2026-03-05 | Connected | Connected | [8 empty] | 2026-03-17 | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9541 | 2026-04-10
161 | 2026-03-04 | 2602-4GDCS-4G#RO-SHR033-250010 |  |  | SHR033 | SHR033ML1 | YPTT | IAAS_GUM_MULAU | PONTIANAK | SINTANG | SEKADAU | Corporate | Only L1800 is activated | 111.1281 | 0.53126 | KALIMANTAN BARAT, SEKADAU, BELITANG HULU, BATUK MULAU | RBS, BBU V9200 Package with VeMc4(1), VSWd1(1), VBPe3p(1), RRU R9264 M1821(2), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(3) | L1800 | EQP New NE 4G LTE 1800 10 Mhz | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID260302B6 | NO NEED | NO NEED | DNWID0682026030202 | NO NEED | NO NEED | 2026-03-04 | [7 empty] | Del Piero | 2026-03-04 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 100% | waiting TRM |  |  |  | waiting TRM | Work Not Start | waiting TRM | [7 empty] | waiting TRM | [27 empty] | PO Confirmed | S1ID2023070102WBF1-9493 | 2026-04-04
162 | 2026-03-15 | 2602-4GGSM-4G#RO-PTS042-060020 |  |  | PTS042 | PTS042ML1 | YPTT | MELAPIDMT | PONTIANAK | SINTANG | KAPUAS HULU | DMT | 2026 - Batch#1 (56) | 112969693 | 819 | KALIMANTAN BARAT, KAPUAS HULU, KOTAWARINGIN TIMUR, MENTAYA HULU | VC9910 Package with DCPD10B & LPU2(1), BBU V9200 Package with VeMc4(1), VSWd1(1), VBPe3p(1), R9264M M7290(2), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(3), 7090C filter(3) | L900 | EQP New NE 4G LTE 900 10 Mhz |  | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26031345 | NO NEED | NO NEED | DNWID0682026031301 | NO NEED | NO NEED | 2026-03-15 | [7 empty] | Arya | 2026-03-15 | 2026-03-15 | 2026-03-16 | 2026-03-18 | 100% | 2026-04-13 |  |  | 2026-04-11 | Connected | Connected | [8 empty] | reviewing | [27 empty] | #N/A | #N/A | #N/A
163 | 2026-03-15 | 2602-NNE4G-4G#RO-PTS042-060054 |  |  | PTS042 | PTS042MT1 | YPTT | MELAPIDMT | PONTIANAK | SINTANG | KAPUAS HULU | DMT | 2026 - Batch#1 (56) | 112969693 | 819 | KALIMANTAN BARAT, KAPUAS HULU, KOTAWARINGIN TIMUR, MENTAYA HULU | DCPD10B Suit(1), RRU R9264 M1821(2) | L1800 | EQP New NE 4G LTE 1800 10 Mhz |  | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26031346 | NO NEED | NO NEED | DNWID0682026031302 | NO NEED | NO NEED | 2026-03-15 | [7 empty] | Arya | 2026-03-15 | 2026-03-15 | 2026-03-16 | 2026-03-18 | 100% | 2026-04-13 |  |  | 2026-04-11 | Connected | Connected | [8 empty] | reviewing | [27 empty] | #N/A | #N/A | #N/A
164 | 2026-04-21 | 2604-U32T32R-4G#RO-BBR055-200106-S1 |  |  | BBR055 | BBR055VR1 | YPTT | KURNIA-TBG | BANJARMASIN | BANJAR | KOTA BANJARBARU | TBG | CP2 Part 2 2026 | 114744006 | -3417219 | Jl.Golf Rt. 12/003 Kel.Syamsudin Noer Kec.Landasan Ulin Kab.Banjarbaru | BBU VBPe2q(1), A9752 M1821(1), Pole for new antenna (3m)(1) | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26042121 | NO NEED | NO NEED | DNWID0662026042101 | NO NEED | NO NEED | 2026-04-21 | [7 empty] | Yoga | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-22 | 100% | 2026-04-22 |  |  | 2026-04-22 | Connected | Connected | [8 empty] | waiting ticket ineom
165 | 2026-04-23 | 2604-U32T32R-4G#RO-SAG014-200058-S2 |  |  | SAG014 | SAG014VV1 | YPTT | TERAJU | PONTIANAK | SINTANG | SANGGAU | TSEL | CP2 Part 2 2026 | 110100692 | -241589 | JL. PATTIMURA DUSUN TAJERAJU BARAT RT 01DESA TERAJU KEC. TOBA, KAB. SANGGAU PROP. KALIMANTAN BARAT | BBU VBPe2q(1), A9652D M2326(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Need dismantle 1 Pcs R8998 S2300 inlude SFP, bracket. Conector power, 100m RRU PWR Cable 2 core Type-D 10mm², 1 pcs RRU Fiber LC-LC 120m | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID260420EU | NO NEED | NO NEED | DNWID0682026042003 | NO NEED | NO NEED | 2026-04-23 | [7 empty] | Djamali | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 100% | 2026-04-24 |  |  | 2026-04-24 | Connected | Connected | [8 empty] | OG
166 | 2026-04-22 | 2604-U32T32R-4G#RO-PTS018-200069-S1 |  |  | PTS018 | PTS018VV1 | YPTT | LANJAKBADAU | PONTIANAK | SINTANG | KAPUAS HULU | TSEL | CP2 Part 2 2026 | 112227285 | 1037457 | JL. LINTAS UTARA, LANJAK, DS SEPADAN, KEC. BATANG LUPAR, KAPUAS HULU | DCPD10B Suit(1), BBU VBPe2q(1), A9652D M2326(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Need dismantle 1 Pcs R9614 S23 inlude SFP, bracket. Conector power, 70m RRU PWR Cable 2 core Type-D 10mm², 1 pcs RRU Fiber LC-LC 90m | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID260420EW | NO NEED | NO NEED | DNWID06820260420001 | NO NEED | NO NEED | 2026-04-23 | [7 empty] | Arya | 2026-04-22 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 |  |  | 2026-04-23 | Connected | Connected | [8 empty] | OG
167 | 2026-04-23 | 2604-U32T32R-4G#RO-PLI020-200038-S3 |  |  | PLI020 | PLI020VR1 | YPTT | YONIFPLEIHARITSEL | BANJARMASIN | BANJAR | TANAH LAUT | TSEL | CP2 Part 2 2026 | 114776752 | -3789345 | JL. JEND A YANI, RT 13/III, KEL ANGSAU-PLEIHARI, KAB. TANAH LAUT | BBU VBPe2q(1), A9752 M1821(1), Pole for new antenna (3m)(1) | L2100 | QP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26042283 | NO NEED | NO NEED | DNWID0662026042201 | NO NEED | NO NEED | 2026-04-23 | [7 empty] | Yoga | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 |  |  | 2026-04-23 | Connected | Connected | [8 empty] | 2026-04-24
168 | 2026-04-22 | 2604-U32T32R-4G#RO-KGN017-200003-S1 |  |  | KGN017 | KGN017M41 | YPTT | SAMUDANEGARATSEL | BANJARMASIN | HULU SUNGAI | HULU SUNGAI SELATAN | TSEL | CP2 Part 2 2026 | 115067368 | -2633109 | JL.SAMUDA RT07 RW04, KELURAHAN SAMUDA, KECAMATAN DAHA SELATAN, HULU SUNGAI SELATAN | VBPe2q(1), A9752 M1821(1), Pole for new antenna (3m) | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID260422AO | DOEID26042282 | NO NEED | DNWID0692026042201 | DNWID0662026042204 | NO NEED | 2026-04-22 | [7 empty] | Puguh | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-25 | 100% | 2026-04-25 |  |  | 2026-04-25 | Connected | Connected | [8 empty] | OG, rektifikasi 1
169 | 2026-04-22 | 2604-ADSTR-4G#RO-KGN017-200117 |  |  | KGN017 | KGN017M41 | YPTT | SAMUDANEGARATSEL | BANJARMASIN | HULU SUNGAI | HULU SUNGAI SELATAN | TSEL | CP2 Part 2 2026 | 115067368 | -2633109 | JL.SAMUDA RT07 RW04, KELURAHAN SAMUDA, KECAMATAN DAHA SELATAN, HULU SUNGAI SELATAN | RRU R9614 S2300(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1) | L2300 | EQP Add Sector LTE 2300 4T4R | Need Dismantle 1 pcs antenaKathrein 80010123, 1 Pcs antena Tongyu TDQ-182020DE-65F | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID260422AN | NO NEED | NO NEED | DNWID0662026042202 | NO NEED | NO NEED | 2026-04-22 | [7 empty] | Puguh | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-25 | 100% | 2026-04-25 |  |  | 2026-04-25 | Connected | Connected | [8 empty] | OG, rektifikasi 1
170 | 2026-04-25 | 2604-ADSTR-4G#RO-SAG089-200034 |  |  | SAG089 | SAG089M41 | YPTT | TBGSUMATERAAGROLESTARITBG | PONTIANAK | SINTANG | SANGGAU | TBG | CP2 Part 2 2026 | 11018308 | -40801 | Dusun Modang Rt02, Desa Bagan Asam, Kecamatan Toba, Kabupaten Sanggau, KaltimDesa Bagan AsamKeamatan Toba | RRU R9264 M1821(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1), | L1800 | EQP Add Sector LTE 1800 4T4R | Need Dismantle 1 Pcs antena 2 port Low band, 1 Pcs R8894E M1821 inlucde sfp, bracket, conector power, 70m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 90m | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID260423BV | NO NEED | NO NEED | DNWID0682026042301 | NO NEED | NO NEED | 2026-04-24 | [7 empty] | Djamali | 2026-04-25 | 2026-04-24 | 2026-04-25 | 2026-04-25 | 100% | 2026-04-25 |  |  | 2026-04-25 | Connected | Connected | [8 empty] | OG
171 | 2026-04-25 | 2604-NNE4G-4G#RO-PTS034-200097 |  |  | PTS034 | PTS034M41 | YPTT | CENDANAPANGSUMAPTI | PONTIANAK | NEW SINTANG | KAPUAS HULU | PTI | CP2 Part 2 2026 | 11292764 | 83287 | KALIMANTAN BARAT, KAPUAS HULU, PUTUSSIBAU SELATAN, KEDAMIN HULU | BBU VBPe3p(1), RRU R9614 S2300(2) | L2300 | EQP New NE 4G LTE 2300 50 Mhz | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26042210 | NO NEED | NO NEED | DNWID0682026042201 | NO NEED | NO NEED | 2026-04-24 | [7 empty] | Arya | 2026-04-25 | 2026-04-24 | 2026-04-26 | 2026-04-26 | 100% | 2026-04-26 |  |  | 2026-04-26 | Connected | Connected | [8 empty] | OG
172 | 2026-04-24 | 2604-NNE4G-4G#RO-COH657-200109 |  |  | COH657 | COH657M41 | YPTT | MICFPTSAP12TERAJUTSEL | PONTIANAK | SINTANG | SANGGAU | TSEL | CP2 Part 2 2026 | 11007577 | -30502 | Bagan Asam, Kec. Toba, Kabupaten Sanggau, Kalimantan Barat | BBU VBPe3p(1), RRU R9614 S2300(1) | L2300 | EQP New NE 4G LTE 2300 50 Mhz | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26042443 | NO NEED | NO NEED | DNWID0682026040202 | NO NEED | NO NEED | 2026-04-24 | [7 empty] | Djamali | 2026-04-24 | 2026-04-24 | 2026-04-26 | 2026-04-27 | 100% | 2026-04-27 |  |  | 2026-04-27 | Connected | Connected | [8 empty] | OG
173 | 2026-04-27 | 2604-NNE4G-4G#RO-PTS031-200088 |  |  | PTS031 | PTS031MV1 | YPTT | SUNGAIBESARTBG | PONTIANAK | SINTANG | KAPUAS HULU | TBG | CP2 Part 2 2026 | 11263979 | 46302 | SUNGAI BESAR, BUNUT HULUT, KAPUAS HULU, KALIMANTAN BARAT | BBU VBPe3p(1), RRU R9614 S2300(1) | L2300 | EQP New NE 4G LTE 2300 50 Mhz | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26042524 | NO NEED | NO NEED | DNWID0682026042502 | NO NEED | NO NEED | 2026-04-27 | [7 empty] | Arya | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-28 |  |  | 2026-04-28 | Connected | Connected | [8 empty] | OG
174 | 2026-04-28 | 2604-U32T32R-4G#RO-STA193-200016-S2 |  |  | STA193 | STA193VL1 | YPTT | PENGKADANBARUTSEL | PONTIANAK | SINTANG | KAPUAS HULU | TSEL | CP2 Part 2 2026 | 111674643 | 1718 | DUSUN PANGKADAN KAPUAK RT.004 RW.03 DESA PANGKADAN BARU KEC. DEDAI KABUPATEN SINTANG | VBPd2(1), A9752 M1821(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26042780 | NO NEED | NO NEED | DNWID0682026042705 | NO NEED | NO NEED | 2026-04-28 | [7 empty] | Djamali | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 100% | 2026-04-30 |  |  | 2026-04-30 | Connected | Connected | [8 empty] | OG
175 | 2026-04-28 | 2604-ADSTR-4G#RO-BRI050-200066 |  |  | BRI050 | BRI050MV1 | YPTT | BRBMURAKATABARATTSEL | BANJARMASIN | HULU SUNGAI | HULU SUNGAI TENGAH | TSEL | CP2 Part 2 2026 | 115381 | -25875 | Jalan Pasar Baru II RT 002 /RW - , Desa Barabai Utara, Kecamatan Barbai , Kabupaten Hulu Sungai Tengah,Propinsi Kalimantan Selatan | BBU VBPe3p(1), RRU R9614 S2300(1), | L2300 | EQP Add Sector LTE 2300 4T4R | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID260427BN | NO NEED | NO NEED | DNWID0662026042706 | NO NEED | NO NEED | 2026-04-28 | [7 empty] | Puguh | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 100% | 2026-04-29 |  |  | 2026-04-29 | Connected | Connected | [8 empty] | 2026-04-30
176 | 2026-04-29 | 2604-NNE4G-4G#RO-MRB061-200103 |  |  | MRB061 | MRB061MV1 | YPTT | ULUBENTENGPTI | BANJARMASIN | HULU SUNGAI | BARITO KUALA | PTI | CP2 Part 2 2026 | 11474357 | -297943 | Jl. Asdi Suryadi, Poros Pesantren RT015/RW001, Ds. Ulu Benteng, Kec. Marabahan, Kab. Barito Kuala | RRU R9614 S2300(1), Antena 12 ports ( Mobi MB4BMFMF-65-171818DDE-IN-TSL High Gain )(1) | L2300 | EQP New NE 4G LTE 2300 50 Mhz | Need Dismantle 1 pcs antena Commscope DBXLH-6565C-VTM, 1 Pcs antena Tongyu TDQ-182020DE-65F | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID260428C3 | DOEID260428C2 | NO NEED | DNWID0662026042806 | DNWID0692026042801 | NO NEED | 2026-04-29 | [7 empty] | Yoga | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-29 |  |  | 2026-04-29 | Connected | Connected | [8 empty] | OG
177 | 2026-04-30 | 2604-U32T32R-4G#RO-NGP014-200024-S3 |  |  | NGP014 | NGP014VL1 | YPTT | NANGASOKANTSEL | PONTIANAK | KETAPANG | MELAWI | TSEL | CP2 Part 2 2026 | 111501246 | -90226 | JL.PROPINSI KOTA BARU - NANGA SOKAN DS.PANDAN KEC.NANGA SOKAN KAB.MELAWI | Add VBPe2q (1) | L1800 | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Dismantle R9224E M1821 (1) | Release | Release | Release | Release |  |  |  | Permit NY Requested | - | NO NEED | NO NEED | - | NO NEED | NO NEED | 2026-04-29 | [7 empty] | Arya | 2026-04-30 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 100% | 2026-04-30 |  |  | 2026-04-30 | Connected | Connected | [8 empty] | OG
178 | 2026-04-30 | 2604-NNE4G-4G#RO-MRB017-200100 |  |  | MRB017 | MRB017MV1 | YPTT | SIDOMULYOBATOLADMT | BANJARMASIN | BANJAR | BARITO KUALA | DMT | CP2 Part 2 2026 | 11460005 | -30123 | MUARA BUMBAN, WANARAYA, BARITO KUALA, KALIMANTAN SELATAN | BBU VBPe3p(1), RRU R9614 S2300(1), | L2300 | EQP New NE 4G LTE 2300 50 Mhz | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID260428C1 | NO NEED | NO NEED | DNWID0662026042604 | NO NEED | NO NEED | 2026-04-30 | [7 empty] | Yoga | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 100% | 2026-04-30 |  |  | 2026-04-30 | Connected | Connected | [8 empty] | OG
179 | 2026-05-01 | 2604-ADSTR-4G#RO-STA210-200044 |  |  | STA210 | STA210MV1 | YPTT | WAHANAPLANTATIONDMT | PONTIANAK | SINTANG | SINTANG | DMT | CP2 Part 2 2026 | 11147619 | 6755 | JL.MT.HARYONO GG.TRANSITO 1 RT.015 RW.04 KELURAHAN KAPUAS KANAN HULU KEC SINTANG KAB.SINTANG | BBU VBPe1p(1), Jumper | L2300 | EQP Add Sector LTE 2300 4T4R | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | - | NO NEED | NO NEED | - | NO NEED | NO NEED | 01-May-26 | [7 empty] | Djamali | 2026-05-01 | 01-May-26 | 01-May-26 | 02-May-26 | 100% | 02-May-26 |  |  | 02-May-26 | Connected | Connected | [8 empty] | OG
180 | 2026-05-03 | 2604-ADSTR-4G#RO-STA120-200026 |  |  | STA120 | STA120ML1 | YPTT | Addsect_MELAWIDMT | PONTIANAK | KETAPANG | MELAWI | DMT | CP2 Part 2 2026 | 11174483 | -34499 | DUSUN TANAH TINGGI, RT. 06/04, KEL. TANJUNG NIAGA, KEC. NANGAPINOH, KAB MELAWI. | RRU R9264 M1821(1) | L1800 | EQP Add Sector LTE 1800 4T4R | - | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26042781 | NO NEED | NO NEED | DNWID0682026042707 | NO NEED | NO NEED | 03-May-26 | [7 empty] | Djamali | 2026-05-03 | 03-May-26 | 03-May-26 | 03-May-26 | 100% | 03-May-26 |  |  | 03-May-26 | Connected | Connected | [8 empty] | OG
181 | 2026-05-04 | 2604-ADSTR-4G#RO-STA091-200079 |  |  | STA091 | STA091ML1 | YPTT | SUKAUHULUTSEL | PONTIANAK | SINTANG | SINTANG | TSEL | CP2 Part 2 2026 | 11131042 | 10325 | DUSUN SUKAU HULU RT 04 RW 03 DESA SUKA BERSATU KEC SEPAUK SINTANG | RRU R9264 M1821(1), | L1800 | EQP Add Sector LTE 1800 4T4R | Need disamntle 1 Pcs R8894E M1821 inlucde sfp, bracket, conector power, 70m RRU PWR Cable 2 core Type-D 10mm², 1 Pcs RRU Fiber LC-LC 90m | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26042898 | NO NEED | NO NEED |  |  |  | waiting OB today | [7 empty] | Djamali | 2026-05-04 | [9 empty] | Work Not Start
182 | 2026-05-04 | 2604-U32T32R-4G#RO-NGP012-200017-S2 |  |  | NGP012 | NGP012VV1 | YPTT | ISTANAKAYANTSEL | PONTIANAK | KETAPANG | MELAWI | TSEL | CP2 Part 2 2026 | 111694524 | -168798 | DUSUN ISTANA KAYAN RT 02 KAB. SINTANG | A9652D M2326(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Need dismantle 1 Pcs R8998 S2300 inlude SFP, bracket. Conector power, 70m RRU PWR Cable 2 core Type-D 10mm², 1 pcs RRU Fiber LC-LC 90m | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26042899 | NO NEED | NO NEED |  |  |  | waiting OB today | [7 empty] | Arya | 2026-05-04 | [9 empty] | Work Not Start
183 | 2026-05-05 | 2604-U32T32R-4G#RO-STA044-200015-S1 |  |  | STA044 | STA044VV1 | YPTT | KAHAYANHILIRTSEL | PONTIANAK | SINTANG | SINTANG | TSEL | CP2 Part 2 2026 | 111922477 | -111119 | DS2 NANGA MAU RT01 DS NANGA MAU KEC KAYAN HILIR KAB.SINTANG | BBU VBPe2q(1), A9652D M2326(1), Pole for new antenna (3m)(1) | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Need dismantle 1 Pcs R8978 S2300 inlude SFP, bracket. Conector power, 100m RRU PWR Cable 2 core Type-D 10mm², 1 pcs RRU Fiber LC-LC 100m | Release | Release | Release | Release |  |  |  | Permit NY Requested | DOEID26042779 | NO NEED | NO NEED |  |  |  | waiting OB today | [7 empty] | Arya | 2026-05-05 | [9 empty] | Work Not Start

## Site_SUL
No. | WID | Program CAPEX | SOW Details | Work Type | Site ID Impl | Site Name Impl | Band | Daily REMARK | ZTE ZONE | Lat | Long | Partner Actual | Monthly Target | Monthly Assignment | PO Year | Years Assigned | WID Recti | Remark | Type Antenna BOQ | Qty BOQ Antenna | Mounting Bracket | RRU Type | Qty RRU | Cabinet | BBU | CCE1B | CCF0 | BPN2 | BPQ2 | GPS | PM5 | DCPD7 | DCPD10 | CR0 | optic | Filter | Dismentle Antenna BOQ | Qty Antenna | Mounting Bracker | Dismentel Filter | Qty Filter | Dismentle RRU | Qty RRU | Dismentle Board | TP | Status Permit | Permit Release | Permit Ineom | DOID | PIC Muver | PIC TI | TI Engineer | Site Productivity Status | Addcost Productivity Status | Add Cost Amount | Add Cost Description | Total PO Amt (IDR) No Tax | MOS | MOS Info | HI Start | HI Done | HI Info | HI Progress | Installation Start | Installation Finished | Connected Date | Connected Info | GAP Analysis | Blocking Issues | SM Status | SM Kitting, PTW & EHS | SM Dismantle | SM ATP | ATP Passed | FI Ineom | Ineom Passed | Asset Ineom | Ineom Dismentel | Blocking SM & Ineom | Status Dismentle | Dismantle Date | Status Material | DR & LDM Status | Date Inbond | DRID | PIC Mover | Remark INBOUND | Date Upload | Blocking BARA | eATP Submit Date | eATP Approve TSEL Date | eATP Status | PO Status | PO Number | PO Release Date | BAUT Approved by Tsel | BAUT Status | BAST SAP Status | YPMS Status | inv status | BOQ Source
1 | 2602-4GGSM-4G#RO-MGN012-0073 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | MGN012 | PANTUGE_DMT | L900 |  | MANADO | 126791 | 383659 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | In Progress for Productivity | Approval Completed (PR NY) | 16400000 | additional cost special transportation from Manado to Talaud island & continue Talaud island to kabaruang | 9214574 | 2026-06-28 | Done | 2026-06-30 | 2026-07-02 | Done | 100% | 2026-06-30 | 2026-07-02 |  | NY |  | waitting TRM | Progress | Progress | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need |  | No Need | No Need
2 | 1804-NNE4G-4G#RO-KDI253-1626 | 0 | EQP New NE 4G LTE 2300 40 Mhz | Add RRU and Module BBU | KDI253 | DprdKotaKendari-DMT |  | ALL CLOSE | KENDARI | -3.9629 | 122.3558 | YPTT | October-23 |  | 2023 | 2023 |  |  | Mobi 10 Port | 1 | 0 | R8998G S2300 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | TBXLHA 6 Port | 1 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Partner | MAMAN | Done Productivity 90 % |  |  |  |  | 2023-11-10 | Done | Done |  | Done | 100% | 2023-11-10 | 2023-11-11 | 2023-11-11 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-11-13 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-11-22 | 5-Dec-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2130 | 2023-11-18 | 17-Dec-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
3 | 1910-4GGSM-4G#RO-DGL077-0459 | RO Acceleration CP#2 | EQP New NE 4G LTE 900 5 MHz | Add RRU | DGL077 | JonoOge-DMT |  |  | PALU | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 | [28 empty] | TBG (PT. TOWER BERSAMA GROUP) | [5 empty] | Rental Resaource | ALDI | Done Productivity 90 % |  |  |  |  | 2023-06-11 | Done | Done |  | Done | 100% | 2023-06-11 | 2023-06-12 | 2023-06-12 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-06-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-04-07 | 2023-07-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5944 | 2023-06-22 | 2023-07-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
4 | 2203-4GGSM-4G#1222-NTI008-0050 | CAPEX RAN 1 2022 FOR DESA NON 3T BATCH 1 NATIONWIDE | EQP New Site 4G LTE 900 10 Mhz | New Infra | NTI008 | N3TPATUA |  |  | KENDARI | -5.7252 | 123.9351 | YPTT | January-23 |  | 2023 | 2023 |  |  | ANTENA MOBI 10 PORT | 3 | 3 | R8852E S900 | 3 |  | 1 | VBPc0 | 0 | VSWc0 | 0 | 1 | VEMc1 | 0 | 1 |  |  | VPDc1 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | TBG |  |  |  |  | SCHANKER | partner | RUSLAN | Done Productivity 90 % |  |  |  |  | 27-Dec-22 | Done | Done |  | Done | 100% | 27-Dec-22 | 29-Dec-22 | 2023-01-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-04-01 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-06-03 | 2023-03-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-4974 | 2023-02-10 | 2023-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
5 | 2206-4GGSM-4G#1651-NTI002-0174 | CAPEX RAN 2 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and Module BBU and Add RRU | LBA109 | Desa Kawasi 2 CR fr N3TPONDOA |  |  | TERNATE | #N/A | #N/A | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-03-01 | Done | Done |  | Done | 100% | 2024-03-01 | 2024-03-02 | 2024-03-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-08 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3251 | 2024-03-21 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
6 | 2206-4GGSM-4G#1651-NTI011-0130 | CAPEX RAN 2 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE | EQP New Site 4G LTE 900 10 Mhz | New Infra | NTI011 | N3TTALAGA BESAR |  | ALL CLOSE | KENDARI | -5.4744 | 122.0753 | YPTT | March-23 |  | 2023 | 2023 |  |  | MOBI 10port | 3 | 0 | R8852E S9000 | 3 |  | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 3 | 3 | FS5(1) | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [5 empty] | DHL TRANS | partner | RUSLAN | Done Productivity 90 % |  |  |  |  | 2023-03-14 | Done | Done |  | Done | 100% | 2023-03-14 | 2023-03-14 | 2023-03-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-03-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 04-Oct-23 | 23-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5446 | 2023-03-31 | 31-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
7 | 2206-4GGSM-4G#1651-NTI066-0161 | CAPEX RAN 2 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE | EQP New Site 4G LTE 900 10 Mhz | New Infra (Add Antenna, Add RRU and module BBU) | NTI066 | N3TDONGKALAN |  |  | PALU | #N/A | #N/A | YPTT | January-23 |  | 2023 | 2023 | [34 empty] | Intenal | Adriyanto | Done Productivity 100 % |  |  |  |  | 2023-02-20 | Done | Done |  | Done | 100% | 2023-02-20 | 2023-02-20 | 2023-02-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-02-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-02-25 | 2023-03-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5375 | 2023-03-21 | 2023-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
8 | 2206-4GGSM-4G#1651-NTI082-0152 | CAPEX RAN 2 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE | EQP New NE 4G LTE 900 5 Mhz | New Infra | NTI082 | N3TBATU ATAS BARAT |  | ALL CLOSE | KENDARI | -6190000 | 122.6803 | YPTT | February-23 |  | 2023 | 2023 |  |  | Rosen 10 Port(2),Mobi 10 port(1) | 3 | 0 | R8852E S9000 | 3 |  | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 3 | 3 | FS5(1) | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [5 empty] | DHL TRANS | partner | RUSLAN | Done Productivity 90 % |  |  |  |  | 2023-02-27 | Done | Done |  | Done | 100% | 2023-02-27 | 2023-02-27 | 2023-03-03 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-03-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-03-20 | 2023-03-21 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5473 | 2023-04-05 | 2023-04-29 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
9 | 2206-4GGSM-4G#1651-NTI282-0132 | CAPEX RAN 2 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and Module BBU and Add RRU | LBA111 | Mining Area 2 CR fr N3T RAE |  |  | TERNATE | #N/A | #N/A | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-02-23 | Done | Done |  | Done | 100% | 2024-02-23 | 2024-02-27 | 2024-02-27 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-10 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-18 | 2024-03-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5627 | 11-May-23 | 2024-06-06 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | NEW PO
10 | 2209-4GDCS-4G#RO-LGR001-0310 | RO IWIP | EQP New Site 4G LTE 1800 20 Mhz | New Infra | WTG084 | PTI Baringeng Sembada CR fr Mess harita Wawoni |  |  | MAKASSAR | -429213 | 12000975 | YPTT | December-23 |  | 2023 | 2023 | [28 empty] | PTI | [5 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 27-Dec-23 | Done | Done | 31-Dec-23 | Done | 100% | 27-Dec-23 | 27-Dec-23 | 2024-02-02 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-02-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-15 | 2024-03-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6129 | 2025-03-10 | 28-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
11 | 2210-4GDCS-4G#RO-MRW249-0398 | RO Corporate | EQP New Site 4G LTE 1800 20 Mhz | New Infra (Add Antenna, Add RRU and module BBU) | MRW249 | New Mess DCI |  |  | PALU | #N/A | #N/A | YPTT | May-23 |  | 2023 | 2023 | [34 empty] | Intenal | Adriyanto | Done Productivity 90 % |  |  |  |  | 08-May-23 | Done | Done |  | Done | 100% | 08-May-23 | 09-May-23 | 10-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 12-May-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-01-06 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5637 | 11-May-23 | 2023-06-11 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
12 | 2212-4GGSM-4G#2735-NTI349-0319 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | New Infra | NTI112 | N3T BULUDE |  |  | MANADO | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Noris | Done Productivity 100 % |  |  |  |  | 2024-03-18 | Done | Done |  | Done | 100% | 2024-03-18 | 2024-03-19 | 2024-03-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-21 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-30 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3274 | 2024-03-25 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
13 | 2212-4GGSM-4G#2735-NTI355-0325 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | L900 | New Infra | NTI124 | N3T TAWALIAN TIMUR |  |  | PARE PARE | #N/A | #N/A | YPTT | July-24 |  | 2024 | 2024 | NTI124-N-3M2B | [33 empty] | PT. Djaya Sukses Pratama | Andika | Done Productivity 100 % |  |  |  |  | 2024-07-19 | Done | Done |  | Done | 100% | 2024-07-19 | 2024-07-23 | 2024-07-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 22-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-11 | 2024-11-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4553 | 7-Aug-24 | 2025-01-07 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
14 | 2212-4GGSM-4G#2735-NTI359-0329 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New NE 4G LTE 900 10 Mhz | New Infra | NTI104 | DMT N3T Runduma |  | NY Ineom | KENDARI | -5348860 | 124347300 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 0 | R8852E S9000 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2024-03-25 | Done | Done |  | Done | 100% | 2024-03-25 | 2024-03-27 | 2024-03-27 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-29 |  | Done Tagging |  | Done Tagging | No Need | Waiting Permit | [10 empty] | 2024-09-09 | 2024-09-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3440 | 6-May-24 | 2024-09-17 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
15 | 2212-4GGSM-4G#2735-NTI360-0330 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | New Infra | NTI105 | N3T RAE SELATAN |  |  | MANADO | #N/A | #N/A | YPTT | August-24 |  | 2024 | 2024 | NTI105-N-3M2P | [28 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Noris | Done Productivity 100 % |  |  |  |  | 19-Aug-24 | Done | Done |  | Done | 100% | 19-Aug-24 | 30-Aug-24 | 2024-09-05 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-09-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-30 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5086 | 2024-09-23 | 24-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
16 | 2212-4GGSM-4G#2735-NTI367-0337 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | New Infra | NTI106 | N3T TARUAN |  |  | MANADO | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-03-19 | Done | Done |  | Done | 100% | 2024-03-19 | 2024-03-20 | 2024-03-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-30 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3274 | 2024-03-25 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
17 | 2212-4GGSM-4G#2735-NTI377-0347 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | New Infra | NTI125 | N3T LAMBANAN |  |  | TERNATE | #N/A | #N/A | YPTT | August-24 |  | 2024 | 2024 | NTI125-N-3M2B | [28 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 30-Aug-24 | Done | Done |  | Done | 100% | 30-Aug-24 | 31-Aug-24 | 2024-09-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-26 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5128 | 2024-09-27 | 2025-01-07 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
18 | 2212-4GGSM-4G#2735-NTI381-0351 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | New Infra | NTI108 | N3T TANDA OLEO |  |  | PALU | #N/A | #N/A | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-01-19 | Done | Done |  | Done | 100% | 2024-01-19 | 2024-11-21 | 2024-02-17 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-02-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-24 | 2024-03-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2910 | 2024-02-02 | 2024-06-06 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
19 | 2212-4GGSM-4G#2735-NTI391-0361 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | New Infra | NTI115 | N3T ARALLE UTARA |  |  | TERNATE | #N/A | #N/A | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-09-07 | Done | Done |  | Done | 100% | 2024-09-07 | 2024-09-09 | 2024-09-12 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 12-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-11 | 2024-11-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5195 | 10-Oct-24 | 2025-01-07 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
20 | 2212-4GGSM-4G#2735-NTI393-0363 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and Module BBU and Add RRU | LBA112 | Desa EcoVillage CR fr N3TLIMBORORAMBU2 |  |  | TERNATE | #N/A | #N/A | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-02-25 | Done | Done |  | Done | 100% | 2024-02-25 | 2024-02-26 | 2024-02-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-22 | 2024-03-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3159 | 2024-03-02 | 2025-01-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
21 | 2212-4GGSM-4G#2735-NTI394-0364 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | New Infra | NTI122 | N3TPATAMBANUA |  |  | TERNATE | #N/A | #N/A | YPTT | August-24 |  | 2024 | 2024 | NTI122-N-3M2B | [27 empty] | TELKOMSEL | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 23-Aug-24 | Done | Done |  | Done | 100% | 23-Aug-24 | 24-Aug-24 | 2025-02-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-11-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5086 | 2024-09-23 | 2025-03-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
22 | 2212-4GGSM-4G#2735-NTI396-0366 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New NE 4G LTE 900 10 MHz + GSM | Add Antenna and RRU and Module BBU(New Infra) | NTI120 | DMT N3T Kasakamu |  | ALL CLOSE | KENDARI | -4.7458 | 122.5101 | YPTT | July-24 |  | 2024 | 2024 | NTI120-N-3M2B |  | Mobi 10 Port | 3 | 0 | R8852E S9000 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-07-16 | Done | Done |  | Done | 100% | 2024-07-16 | 2024-07-17 | 2024-09-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-13 |  | Done Tagging |  | Done Tagging | No Need | Waiting Permit | [10 empty] | 24-Oct-24 | 25-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4553 | 7-Aug-24 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
23 | 2212-4GGSM-4G#2735-NTI397-0367 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New NE 4G LTE 900 10 MHz | Add Antenna and RRU and Module BBU(New Infra) | NTI118 | DMT N3T Lombu Jaya |  | ALL CLOSE | KENDARI | -4.7929 | 122.4825 | YPTT | August-24 |  | 2024 | 2024 | NTI118-N-3M2B |  | Mobi 10 Port | 3 | 0 | R8852E S9000 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 09-Aug-24 | Done | Done |  | Done | 100% | 09-Aug-24 | 10-Aug-24 | 2024-09-11 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-16 |  | Done Tagging |  | Done Tagging | No Need | Waiting Permit | [10 empty] | 24-Oct-24 | 25-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5389 | 2024-11-03 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
24 | 2212-4GGSM-4G#2735-NTI398-0368 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New NE 4G LTE 900 10 MHz | Add Antenna and RRU and Module BBU(New Infra) | NTI117 | DMT N3T Lawada Jaya |  | ALL CLOSE | KENDARI | -4.8429 | 122.4468 | YPTT | August-24 |  | 2024 | 2024 | NTI117-N-3M2B |  | Mobi 10 Port | 3 | 0 | R8852E S9000 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 12-Aug-24 | Done | Done |  | Done | 100% | 12-Aug-24 | 13-Aug-24 | 2024-09-11 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-16 |  | Done Tagging |  | Done Tagging | No Need | Waiting Permit | [10 empty] | 24-Oct-24 | 25-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5389 | 2024-11-03 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
25 | 2212-4GGSM-4G#2735-NTI401-0371 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | Add RRU | TER214 | Maliaoro |  |  | TERNATE | #N/A | #N/A | YPTT | October-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 18-Oct-24 | Done | Done |  | Done | 100% | 18-Oct-24 | 19-Oct-24 | 19-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 20-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 28-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5388 | 2024-11-03 | 24-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
26 | 2212-4GGSM-4G#2735-NTI402-0372 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | Swap Antenna and Module BBU and Add RRU | COI583 | C_COI583M41_CombatMVSalumanurung |  |  | PARE PARE | #N/A | #N/A | YPTT | October-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Aswin | Done Productivity 100 % |  |  |  |  | 18-Oct-24 | Done | Done |  | Done | 100% | 18-Oct-24 | 19-Oct-24 | 19-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 21-Oct-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-11-28 | 2024-11-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5388 | 2024-11-03 | 2025-01-07 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
27 | 2212-4GGSM-4G#2735-NTI403-0373 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and Module BBU(New Infra) | NTI119 | DMT N3T Masara |  | ALL CLOSE | KENDARI | -4.6941 | 122.5809 | YPTT | July-24 |  | 2024 | 2024 | NTI119-N-3M2B |  | Prose 10 port | 3 | 0 | R8852E S9000 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2024-07-13 | Done | Done |  | Done | 100% | 2024-07-13 | 2024-07-14 | 2024-09-09 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-16 |  | Done Tagging |  | Done Tagging | No Need | Waiting Permit | [10 empty] | 24-Oct-24 | 25-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4378 | 2024-07-20 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
28 | 2212-4GGSM-4G#2735-NTI404-0374 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | New Infra | NTI404 | N3TKELAPADUA |  |  | MAKASSAR | #N/A | #N/A | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-11-01 | Done | Done |  | Done | 100% | 2024-11-01 | 2024-11-02 | 2024-11-28 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 30-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 01-Aug-25 | 2025-01-14 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5405 | 2024-11-06 | 2025-02-06 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
29 | 2212-4GGSM-4G#2735-NTI405-0375 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna,Add RRU and Swap Module BBU | COI582 | Combat MV Molore Pantai |  | NY Ineom | KENDARI | -331032 | 12227639 | YPTT | March-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 0 | R9224E M1821 | 3 | 1 | 1 | 0 | VBpd0p(2) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | Rosenberger 10 Port(2),Mobi 10 port(1) | 3 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),Cabinet(1),PM5(1),SA(1),BPN2(2),CC1B(1),FA0(1),CR0(1),DCPD7(1) | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-03-30 | Done | Done |  | Done | 100% | 2024-03-30 | 2024-03-30 | 2024-03-30 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-04-01 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-07-17 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3440 | 6-May-24 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
30 | 2212-4GGSM-4G#2735-NTI408-0378 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | Add RRU and Module BBU | RHA031 | DMT RSUD Muna - Permanenisasi COI844 - Combat Alun Alun Raha |  | ALL CLOSE | KENDARI | -4.8354 | 122.7258 | YPTT | October-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M7290 | 3 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-11-10 | Done | Done |  | Done | 100% | 2024-11-10 | 2024-11-10 | 2024-11-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-11-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-11-13 | 2024-11-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5423 | 2024-11-12 | 24-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
31 | 2212-4GGSM-4G#2735-NTI410-0380 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | Add RRU and Module BBU | RHA062 | DMT Wanseriwu |  | ALL CLOSE | KENDARI | -4.7936 | 122.3769 | YPTT | October-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R8852E S9000 | 3 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 23-Oct-24 | Done | Done |  | Done | 100% | 23-Oct-24 | 23-Oct-24 | 23-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 24-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-11 | 2024-11-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5284 | 24-Oct-24 | 24-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
32 | 2212-4GGSM-4G#2735-NTI418-0388 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | Add RRU and Module BBU | MMS009 | N_MMS009M41_Pambe-DMT |  |  | PARE PARE | #N/A | #N/A | YPTT | October-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 16-Oct-24 | Done | Done |  | Done | 100% | 16-Oct-24 | 18-Oct-24 | 18-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | NO NEED | 19-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-11 | 2024-11-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5388 | 2024-11-03 | 24-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
33 | 2212-4GGSM-4G#2735-NTI427-0397 | CAPEX RAN 3 2022 FOR DESA NON 3T BATCH 2 NATIONWIDE 2022 | EQP New Site 4G LTE 900 10 Mhz | Add RRU and Module BBU | MMS004 | N_MMS004M41_RanteKamase-TBG |  |  | PARE PARE | #N/A | #N/A | YPTT | October-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 20-Oct-24 | Done | Done |  | Done | 100% | 20-Oct-24 | 21-Oct-24 | 21-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 23-Oct-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-01-11 | 2024-11-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5388 | 2024-11-03 | 24-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
34 | 2212-4GGSM-4G#RO-COI528-0304 | CAPEX RAN 1 PART 1 2023 | EQP New NE 4G LTE 900 5 Mhz | Swap Antenna, Add RRU and module BBU | COI528 | CombatPT.SJU-ADT |  |  | TERNATE | #N/A | #N/A | YPTT | January-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 100 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 16-May-23 | 16-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5473 | 2023-04-05 | 2023-06-06 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
35 | 2212-4GGSM-4G#RO-MRW360-0308 | RO Corporate | EQP New NE 4G LTE 900 5 Mhz | New Infra | MRW360 | Baoshuo Office |  |  | PALU | #N/A | #N/A | YPTT | January-23 |  | 2023 | 2023 | [34 empty] | Rental Resaource | Fadli | Done Productivity 100 % |  |  |  |  | 2023-01-17 | Done | Done |  | Done | 100% | 2023-01-17 | 2023-01-18 | 2023-02-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-02-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-06-26 | 2023-06-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-4973 | 2023-02-10 | 2023-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
36 | 2212-U8T8R-4G#RO-BAU025-0167 | CAPEX RAN 1 PART 1 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna, Add RRU and Swap module BBU | BAU025 | Wanci2 |  | ALL CLOSE | KENDARI | -5.3451 | 123.5443 | YPTT | March-23 |  | 2023 | 2023 |  |  | Rosenberger 12 port | 2 | 0 | R8978 S2300 | 1 |  | 1 | VBPd2 (1) | 0 | VSWD1 (1) | 0 | 0 | 0 | 0 | 0 |  |  | VBPd2p (1) | MOBI 10 Port | 2 | 0 | No Need | 0 | NO Need RRU | 0 | BBU(1), SA(1), FAN(1), CCE1B(2), BPN2(4), CR0(2), PM5(2) | TELKOMSEL |  |  |  |  | DHL TRANS | partner | RUSLAN | Done Productivity 100 % |  |  |  |  | 2023-01-29 | Done | Done |  | Done | 100% | 2023-01-29 | 2023-01-30 | 2023-01-30 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-01-31 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-09-18 | 2023-03-15 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-4982 | 2023-02-12 | 2023-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
37 | 2302-4GDCS-4G#RO-TOB084-0045 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 1800 5 Mhz | Add RRU and Module BBU | TOB084 | DMT Lalonga |  |  | TERNATE | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 100 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 05-Dec-23 | 15-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5734 | 19-May-23 | 18-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
38 | 2302-4GGSM-4G#RO-BIT104-0005 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 900 5 MHz | Swap Antenna and Add RRU | BIT104 | MCR Manembonembo |  |  | MANADO | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 100 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 01-Passed | SM Passed | 2023-07-17 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 26-Oct-23 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5622 | 11-May-23 | 2023-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
39 | 2302-4GGSM-4G#RO-KDI247-0019 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 900 5 Mhz | Swap Antenna and Add RRU and Module BBU | KDI247 | DMT Bonggoeya |  | ALL CLOSE | KENDARI | -4.0032 | 122.5066 | YPTT | March-23 |  | 2023 | 2023 |  |  | Prose 10 port | 1 | 0 | R8852E S9000 | 1 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | Mobi 8 port | 1 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RANDI | Done Productivity 100 % |  |  |  |  | 2023-04-30 | Done | Done |  | Done | 100% | 2023-04-30 | 01-May-23 | 01-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 8-May-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2023-09-26 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5628 | 11-May-23 | 2023-06-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
40 | 2302-4GGSM-4G#RO-LBA017-0024 | CAPEX RAN 1 PART 2 2023 | L900 | Swap Antenna and Add RRU | LBA017 | DMT Mandaong |  |  | TERNATE | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [34 empty] | Intenal | sulaiman | Done Productivity 100 % |  |  |  |  | 14-May-23 | Done | Done |  | Done | 100% | 14-May-23 | 14-May-23 | 14-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 18-May-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 09-Oct-23 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5625 | 11-May-23 | 2023-06-11 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
41 | 2302-ADSTR-4G#RO-BAU090-0006 | CAPEX RAN 1 PART 2 2023 | EQP Add Sector LTE | Add Antenna and RRU (Add Sector Vertical) | BAU090 | TBG Patuno Resort |  | ALL CLOSE | KENDARI | -5.247 | 123.5823 | YPTT | March-23 |  | 2023 | 2023 |  |  | Prose 10 port | 1 | 0 | R8852E S1800 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [5 empty] | DHL TRANS | partner | RUSLAN | Done Productivity 100 % |  |  |  |  | 2023-04-02 | Done | Done |  | Done | 100% | 2023-04-02 | 2023-04-03 | 2023-04-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-04-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-01-05 | 3-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5628 | 11-May-23 | 10-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
42 | 2302-ADSTR-4G#RO-BAU210-0076 | CAPEX RAN 1 PART 2 2023 | EQP Add Sector LTE | Add RRU | BAU210 | DMT Waturombe |  | ALL CLOSE | KENDARI | -5.3696 | 122.3765 | YPTT | March-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8978 S2300 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Intenal | LA ODE SALNI | Done Productivity 90 % |  |  |  |  | 2023-06-21 | Done | Done |  | Done | 100% | 2023-06-21 | 2023-06-22 | 2023-06-22 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 12-May-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 29-May-23 | 31-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5628 | 11-May-23 | 2023-06-06 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
43 | 2302-ADSTR-4G#RO-BIT086-0078 | CAPEX RAN 1 PART 2 2023 | EQP Add Sector LTE 2300 | Swap Antenna and Reconfigure RRU and Add Jumper Cable for Add Sector | BIT086 | Protelindo Sagerat Bitung |  |  | MANADO | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 100 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2023-07-06 | 2023-06-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5622 | 11-May-23 | 2023-06-11 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
44 | 2302-ADSTR-4G#RO-MRW093-0063 | CAPEX RAN 1 PART 2 2023 | EQP Add Sector LTE 2100 (Horisontal) | Add Antenna and Add RRU and Swap Module BBU | MRW093 | IMIP Rusunawa & Apartement |  |  | PALU | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [34 empty] | Rental Resaource | Fadli | Done Productivity 100 % |  |  |  |  | 2023-04-14 | Done | Done |  | Done | 100% | 2023-04-14 | 2023-04-14 | 2023-04-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-04-30 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 06-Dec-23 | 2023-06-13 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5637 | 11-May-23 | 2023-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
45 | 2302-ADSTR-4G#RO-TOB017-0143 | CAPEX RAN 1 PART 2 2023 | EQP Add Sector LTE | Add RRU | TOB017 | DMT Gorua Selatan |  |  | TERNATE | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 100 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 05-Aug-23 | 9-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5731 | 19-May-23 | 16-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
46 | 2302-MSCTR-4G#RO-ADL091-0002 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade Multisector LTE | Add Antenna, RRU and Module BBU | ADL091 | DMT Pasar Baruga |  | ALL CLOSE | KENDARI | -4.0437 | 122.4766 | YPTT | 2026-04-23 |  | 2023 | 2023 |  |  | MOBI 4port | 1 | 1 | R9224E M1821 | 1 |  | 0 | VBPD0P(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800 | 1 | No Need Board | [6 empty] | partner | RANDI | Done Productivity 90 % |  |  |  |  | 2023-04-30 | Done | Done |  | Done | 100% | 2023-04-30 | 2023-04-30 | 2023-04-30 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 5-May-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-09-27 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5628 | 11-May-23 | 2023-06-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
47 | 2302-MSCTR-4G#RO-MRW117-0049 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade Multisector LTE | Add Antenna and RRU and Swap Module BBU | MRW117 | TBG Fatufia |  |  | PALU | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [34 empty] | Intenal | Hendro | Done Productivity 90 % |  |  |  |  | 2023-04-18 | Done | Done |  | Done | 100% | 2023-04-18 | 2023-04-18 | 2023-04-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 12-May-23 |  | Done Tagging |  | Done Tagging | [12 empty] | 06-Dec-23 | 2023-06-13 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5637 | 11-May-23 | 2023-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
48 | 2302-MSCTR-4G#RO-TER002-0074 | CAPEX RAN 1 PART 2 2023 | MS 2100 | Add Antenna and RRU and Swap Module BBU | TER002 | Airport Ternate |  |  | MANADO | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [34 empty] | Intenal | Syahril | Done Productivity 100 % |  |  |  |  | 01-May-23 | Done | Done |  | Done | 100% | 01-May-23 | 02-May-23 | 02-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 17-May-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2023-01-08 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5668 | 13-May-23 | 2023-06-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
49 | 2302-NNE4G-4G#RO-BAU013-0304 | CAPEX RAN 1 PART 2 2023 | EQP New NE 4G LTE 2300 10 Mhz | Swap Antenna and Add RRU and Module BBU | BAU013 | DMT Lakudo |  | ALL CLOSE | KENDARI | -5.3127 | 122.53 | YPTT | March-23 |  | 2023 | 2023 |  |  | Prose 10 port | 3 | 3 | R8978 S2300 | 1 |  | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  |  | 0 | Kathrein 4 port (3) | 3 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Intenal | ALADIN | Done Productivity 100 % |  |  |  |  | 14-May-23 | Done | Done |  | Done | 100% | 14-May-23 | 15-May-23 | 15-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 16-May-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-09-21 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5628 | 11-May-23 | 2023-06-11 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
50 | 2302-NNE4G-4G#RO-BAU219-0145 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 2100 5 Mhz | Add RRU and module BBU | BAU219 | DMT Todanga |  | ALL CLOSE | KENDARI | -510875 | 12279111 | YPTT | March-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8852E S2100 | 2 |  | 0 | vbpd0p (1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | VPDc1 (1) | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Intenal | KARIMUDDIN | Done Productivity 90 % |  |  |  |  | 20-May-23 | Done | Done |  | Done | 100% | 20-May-23 | 20-May-23 | 20-May-23 | Connected | Connected | Ineom & ATP NY | 01-Passed | 01-Passed | No Need | 21-May-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 30-May-23 | 31-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5628 | 11-May-23 | 2023-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
51 | 2302-NNE4G-4G#RO-BAU222-0146 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 2100 5 Mhz | Swap RRU (Configure 2 UBR for 3 sector) and Add Module BBU | BAU222 | DMT KANCINA |  | ALL CLOSE | KENDARI | -5.4322 | 122.8942 | YPTT | March-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 2 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |  | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800 | 3 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 90 % |  |  |  |  | 03-May-23 | Done | Done |  | Done | 100% | 03-May-23 | 04-May-23 | 04-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 20-May-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2023-09-18 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5628 | 11-May-23 | 2023-06-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
52 | 2302-NNE4G-4G#RO-BAU243-0312 | CAPEX RAN 1 PART 2 2023 | EQP New NE 4G LTE 2300 10 Mhz | Add RRU | BAU243 | DMT SP Lasalimu |  | ALL CLOSE | KENDARI | -5.3074 | 123.1303 | YPTT | March-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8978 S2300 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 90 % |  |  |  |  | 01-May-23 | Done | Done |  | Done | 100% | 01-May-23 | 02-May-23 | 02-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 27-May-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 06-May-23 | 2023-06-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5628 | 11-May-23 | 2023-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
53 | 2302-NNE4G-4G#RO-BIT039-0286 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 900 5 Mhz | Swap RRU | BIT039 | Protelindo Naimundung |  |  | MANADO | #N/A | #N/A | YPTT | March-23 |  | 2023 | 2023 | [34 empty] | Intenal | Vendi | Cancel |  |  |  |  | 2023-03-21 | Done | Done |  | Done | 100% | 2023-03-21 | 2023-03-21 | 2023-03-21 | Connected | Connected |  | 04-No Need | 01-Passed | No Need | 2023-03-21 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 04-May-23 | 2023-04-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023071503WBF1-48 | 30-Aug-23 | 2023-04-29 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
54 | 2302-NNE4G-4G#RO-DGL093-0166 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 2100 5 Mhz | Swap RRU and Module BBU | DGL093 | TBG Sidondo |  |  | PALU | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [34 empty] | Intenal | Hendro | Done Productivity 90 % |  |  |  |  | 2023-04-27 | Done | Done |  | Done | 100% | 2023-04-27 | 2023-04-28 | 2023-04-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 5-May-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 06-Dec-23 | 2023-06-13 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5637 | 11-May-23 | 2023-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
55 | 2302-NNE4G-4G#RO-KDI234-0354 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 2300 10 Mhz | Swap Antenna and Add RRU and Module BBU | KDI234 | DMT Andonouhu |  | ALL CLOSE | KENDARI | -4.0106 | 122.5398 | YPTT | March-23 |  | 2023 | 2023 |  |  | Prose 10 port | 1 | 0 | R8978 S2300 | 1 |  | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | Extream 12 Port | 1 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RANDI | Done Productivity 90 % |  |  |  |  | 2023-04-29 | Done | Done |  | Done | 100% | 2023-04-29 | 2023-04-29 | 2023-04-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 5-May-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2023-09-20 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5628 | 11-May-23 | 2023-06-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
56 | 2302-NNE4G-4G#RO-KDI277-0175 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 2100 5 Mhz | Add RRU | KDI277 | Anugerah Poasia |  | ALL CLOSE | KENDARI | -4.0399 | 122.5546 | YPTT | March-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8852E S2100 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [5 empty] | DHL TRANS | Rental Resaource | ANTO/Syamsuddin | Done Productivity 100 % |  |  |  |  | 2023-03-28 | Done | Done |  | Done | 100% | 2023-03-28 | 2023-03-28 | 2023-03-28 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-04-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 05-May-23 | 5-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5670 | 13-May-23 | 16-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
57 | 2302-NNE4G-4G#RO-KKA006-0356 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 2300 10 Mhz | Swap Antenna and Add RRU and Module BBU | KKA006 | Dawi Dawi |  | ALL CLOSE | KENDARI | -4.1708 | 121.6169 | YPTT | March-23 |  | 2023 | 2023 |  |  | Prose 10 port | 2 | 2 | R8978 S2300 | 1 |  | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Kathrein 2 port | 3 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Rental Resaource | ANTO/Syamsuddin | Done Productivity 100 % |  |  |  |  | 2023-03-18 | Done | Done |  | Done | 100% | 2023-03-18 | 2023-03-18 | 2023-03-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-03-21 |  | Done Tagging |  | Done Tagging | NY Ineom Reutilise | [11 empty] | 2023-06-14 | 2023-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5472 | 2023-04-05 | 2023-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
58 | 2302-NNE4G-4G#RO-LBA003-0366 | CAPEX RAN 1 PART 2 2023 | L2300 | Swap Antenna and Add RRU and Module BBU | LBA003 | Pelabuhan Bacan |  |  | TERNATE | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 100 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 06-Oct-23 | 2023-06-13 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5625 | 11-May-23 | 2023-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
59 | 2302-NNE4G-4G#RO-MGN004-0198 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 2100 5 Mhz | Swap RRU and Add Module BBU | MGN004 | Kolongan |  |  | MANADO | #N/A | #N/A | YPTT | March-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 100 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2023-04-21 | 2023-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5468 | 2023-04-05 | 16-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
60 | 2302-NNE4G-4G#RO-MGN019-0200 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 2100 5 Mhz | Swap Antenna And Add RRU | MGN019 | DMT Tabang |  |  | MANADO | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [34 empty] | Intenal | Risal | Done Productivity 100 % |  |  |  |  | 05-May-23 | Done | Done |  | Done | 100% | 05-May-23 | 05-May-23 | 05-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 06-May-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2023-07-31 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5622 | 11-May-23 | 2023-06-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
61 | 2302-NNE4G-4G#RO-MGN031-0400 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 2300 10 Mhz | Swap Antenna and Add RRU and Module BBU | MGN031 | Salebabu |  |  | MANADO | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 100 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2023-07-06 | 2023-06-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5622 | 11-May-23 | 2023-06-11 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
62 | 2302-NNE4G-4G#RO-MGN038-0401 | CAPEX RAN 1 PART 2 2023 | EQP New NE 4G LTE 2300 10 Mhz | Add RRU and Module BBU | MGN038 | DMT Bitunuris |  |  | MANADO | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 100 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 03-NY SM | 03-NY SM | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 23-Oct-23 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5622 | 11-May-23 | 2023-06-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
63 | 2302-NNE4G-4G#RO-MGN039-0105 | CAPEX RAN 1 PART 2 2023 | EQP New NE 4G LTE 2100 5 Mhz | Swap RRU and Add Module BBU | MGN039 | TBG Pulutan Talaud |  |  | MANADO | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [34 empty] | Intenal | Risal | Done Productivity 100 % |  |  |  |  | 04-May-23 | Done | Done |  | Done | 100% | 04-May-23 | 07-May-23 | 07-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 11-May-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2023-09-26 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5622 | 11-May-23 | 2023-06-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
64 | 2302-NNE4G-4G#RO-TDE029-0083 | CAPEX RAN 1 PART 2 2023 | EQP New NE 4G LTE 2100 5 Mhz | Swap RRU | TDE029 | DMT Dowara |  |  | TERNATE | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [34 empty] | Intenal | sulaiman | Done Productivity 100 % |  |  |  |  | 06-May-23 | Done | Done |  | Done | 100% | 06-May-23 | 07-May-23 | 07-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 09-May-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2023-09-26 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5731 | 19-May-23 | 2023-06-11 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
65 | 2302-NNE4G-4G#RO-TDE053-0243 | CAPEX RAN 1 PART 2 2023 | L2100 | Swap RRU and Module BBU | TDE053 | PST MM Goto Tidore |  |  | TERNATE | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [34 empty] | Intenal | sulaiman | Done Productivity 100 % |  |  |  |  | 02-May-23 | Done | Done |  | Done | 100% | 02-May-23 | 02-May-23 | 02-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 04-May-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2023-09-26 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5668 | 13-May-23 | 2023-06-11 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
66 | 2302-NNE4G-4G#RO-THN015-0530 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 2300 10 Mhz | Add RRU and Module BBU | THN015 | Manalu |  |  | MANADO | #N/A | #N/A | YPTT | March-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 100 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 05-Oct-23 | 12-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5622 | 11-May-23 | 17-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
67 | 2302-NNE4G-4G#RO-THN039-0034 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 1800 5 Mhz | Swap RRU and Module BBU | THN039 | TBG Siau Timur |  |  | MANADO | #N/A | #N/A | YPTT | March-23 |  | 2023 | 2023 | [34 empty] | Intenal | Nopik | Done Productivity 100 % |  |  |  |  | 2023-03-23 | Done | Done |  | Done | 100% | 2023-03-23 | 2023-03-25 | 2023-03-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-03-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 06-Aug-23 | 2023-06-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5793 | 25-May-23 | 2023-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
68 | 2302-NNE4G-4G#RO-THN074-0532 | CAPEX RAN 1 PART 2 2023 | EQP New Site 4G LTE 2300 10 Mhz | Swap Antenna and Add RRU and Module BBU | THN074 | MCR Soataloara |  |  | MANADO | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 100 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 06-Aug-23 | 2023-06-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5622 | 11-May-23 | 2023-06-11 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
69 | 2302-NNE4G-4G#RO-THN083-0129 | CAPEX RAN 1 PART 2 2023 | EQP New NE 4G LTE 2100 5 Mhz | Swap RRU and Add Module BBU | THN083 | TBG Nusa Tabukan |  |  | MANADO | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [34 empty] | Intenal | Vendi | Done Productivity 100 % |  |  |  |  | 05-May-23 | Done | Done |  | Done | 100% | 05-May-23 | 06-May-23 | 06-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 09-May-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 13-Oct-23 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5622 | 11-May-23 | 2023-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
70 | 2302-NNE4G-4G#RO-THN110-0533 | CAPEX RAN 1 PART 2 2023 | EQP New NE 4G LTE 2300 10 Mhz | Add RRU and Module BBU | THN110 | COMBATMANENTE |  |  | MANADO | #N/A | #N/A | YPTT | March-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 100 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2023-01-05 | 9-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5622 | 11-May-23 | 17-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
71 | 2302-U8T8R-4G#RO-BAU105-0006 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna and Reconfigure RRU with Add Jumper Cable and FO Kit | BAU105 | TBG Poros Wandoka |  | ALL CLOSE | KENDARI | -5.3198 | 123.535 | YPTT | March-23 |  | 2023 | 2023 |  |  | Rosenberger 12 port | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | MOBI 10 Port | 1 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 100 % |  |  |  |  | 2023-03-10 | Done | Done |  | Done | 100% | 2023-03-10 | 2023-03-13 | 2023-03-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-04-04 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-06-06 | 2023-06-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5472 | 2023-04-05 | 2023-06-11 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
72 | 2302-U8T8R-4G#RO-BAU140-0007 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna and Module BBU and Reconfigure RRU with Add Jumper Cable and FO Kit | BAU140 | TBG Mandati |  | ALL CLOSE | KENDARI | -5.3351 | 123.5418 | YPTT | March-23 |  | 2023 | 2023 |  |  | Rosenberger 12 port | 1 | 0 | 0 | 0 |  | 1 | VBPD2P(1) | 0 | VSWD1 (1) | 0 | 0 | 0 | 0 | 0 |  |  | 0 | MOBI 10 Port | 1 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),BPN2(4),CCE1B(2),CR0(2),PM5(2) | [5 empty] | SCHANKER | partner | RUSLAN | Done Productivity 100 % |  |  |  |  | 2023-03-15 | Done | Done |  | Done | 100% | 2023-03-15 | 2023-03-15 | 2023-03-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-04-03 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 13-May-23 | 15-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5472 | 2023-04-05 | 18-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
73 | 2302-U8T8R-4G#RO-KDI008-0014 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna and Module BBU and Reconfigure RRU with Add Jumper Cable and FO Kit | KDI008 | Wanci |  | ALL CLOSE | KENDARI | -5.3265 | 123.5419 | YPTT | 2026-04-23 |  | 2023 | 2023 |  |  | Prose 12 port | 1 | 0 | 0 | 0 |  | 1 | VBPD2P(1) | 0 | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | MOBI 10 Port | 1 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),CCE1B(2),BPN2(4),CR0(2),FA0(1),PM5(2),DCPD7(1) | [6 empty] | partner | RUSLAN | Done Productivity 90 % |  |  |  |  | 2023-04-15 | Done | Done |  | Done | 100% | 2023-04-15 | 2023-04-16 | 2023-04-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 10-May-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-06-13 | 2023-06-14 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5626 | 11-May-23 | 2023-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
74 | 2302-U8T8R-4G#RO-KKA004-0033 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna and Module BBU and Reconfigure RRU with Add Jumper Cable and FO Kit | KKA004 | Kolaka Utara |  | ALL CLOSE | KENDARI | -3.5058 | 120.8897 | YPTT | March-23 |  | 2023 | 2023 |  |  | Rosenberger 12 port | 1 | 1 | 0 | 0 |  | 1 | VBPD2p(1) | 0 | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | MOBI 10 Port | 1 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),CCE1B(2),BPN(4),CR0(2),PM5(2) | [6 empty] | Rental Resaource | ANTO/Syamsuddin | Done Productivity 90 % |  |  |  |  | 03-May-23 | Done | Done |  | Done | 100% | 03-May-23 | 04-May-23 | 04-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 4-May-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-09-27 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5626 | 11-May-23 | 2023-06-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
75 | 2302-U8T8R-4G#RO-LBA005-0038 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna and Reconfigure RRU | LBA005 | Bacan 2 |  |  | TERNATE | #N/A | #N/A | YPTT | March-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 90 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2023-02-05 | 3-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5467 | 2023-04-05 | 10-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
76 | 2302-U8T8R-4G#RO-LBA027-0039 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna and Reconfigure RRU with Add Jumper Cable and FO Kit | LBA027 | PT. GPS Kawasi |  |  | TERNATE | #N/A | #N/A | YPTT | March-23 |  | 2023 | 2023 | [34 empty] | Intenal | Hendra | Done Productivity 100 % |  |  |  |  | 2023-03-29 | Done | Done |  | Done | 100% | 2023-03-29 | 2023-03-30 | 2023-03-30 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2023-03-30 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 06-Aug-23 | 2023-06-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5605 | 10-May-23 | 2023-06-11 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
77 | 2302-U8T8R-4G#RO-LBA052-0040 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna and Reconfigure RRU | LBA052 | Smelter HJF |  |  | TERNATE | #N/A | #N/A | YPTT | March-23 |  | 2023 | 2023 | [34 empty] | Intenal | Hendra | Done Productivity 90 % |  |  |  |  | 2023-03-27 | Done | Done |  | Done | 100% | 2023-03-27 | 2023-03-28 | 2023-03-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2023-03-28 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 13-May-23 | 15-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5605 | 10-May-23 | 18-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
78 | 2302-U8T8R-4G#RO-LBA080-0041 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna and Reconfigure RRU with Add Jumper Cable and FO Kit | LBA080 | Harita Losari |  |  | TERNATE | #N/A | #N/A | YPTT | March-23 |  | 2023 | 2023 | [34 empty] | Intenal | Hendra | Done Productivity 100 % |  |  |  |  | 2023-03-26 | Done | Done | 2023-03-26 | Done | 100% | 2023-03-26 | 2023-03-26 | 2023-03-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2023-03-26 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 16-May-23 | 16-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5605 | 10-May-23 | 18-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
79 | 2302-U8T8R-4G#RO-MRW122-0062 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna and Reconfigure RRU | MRW122 | Combat Fatufia |  |  | PALU | #N/A | #N/A | YPTT | May-23 |  | 2023 | 2023 | [34 empty] | Rental Resaource | Fadli | Done Productivity 90 % |  |  |  |  | 10-May-23 | Done | Done |  | Done | 100% | 10-May-23 | 10-May-23 | 10-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 12-May-23 |  | Done Tagging |  | Done Tagging | [12 empty] | 13-Oct-23 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5637 | 11-May-23 | 2023-06-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
80 | 2302-U8T8R-4G#RO-MRW123-0063 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna, Add FO Kit and Reconfigure RRU | MRW123 | COMBAT TUGU BAHOMAKMUR |  |  | PALU | #N/A | #N/A | YPTT | May-23 |  | 2023 | 2023 | [28 empty] | Telkomsel | [5 empty] | Intenal | Hendro | Done Productivity 90 % |  |  |  |  | 10-May-23 | Done | Done |  | Done | 100% | 10-May-23 | 10-May-23 | 10-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 17-May-23 |  | Done Tagging |  | Done Tagging | [12 empty] | 2023-07-24 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5637 | 11-May-23 | 2023-06-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
81 | 2302-U8T8R-4G#RO-MRW227-0067 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna and Reconfigure RRU with Add Jumper Cable and FO Kit | MRW227 | PLTU Terminal - IMIP |  |  | PALU | #N/A | #N/A | YPTT | March-23 |  | 2023 | 2023 | [34 empty] | Intenal | Hendro | Done Productivity 90 % |  |  |  |  | 2023-03-15 | Done | Done |  | Done | 100% | 2023-03-15 | 2023-03-15 | 2023-03-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-03-27 |  | Done Tagging |  | Done Tagging | [12 empty] | 2023-04-18 | 2023-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5471 | 2023-04-05 | 9-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
82 | 2302-U8T8R-4G#RO-MRW914-0070 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna and Reconfigure RRU with Add Jumper Cable and FO Kit | MRW914 | COMBAT SWADAYA BAHOMAKMUR |  |  | PALU | #N/A | #N/A | YPTT | March-23 |  | 2023 | 2023 | [34 empty] | Rental Resaource | Fadli | Done Productivity 90 % |  |  |  |  | 2023-04-16 | Done | Done |  | Done | 100% | 2023-04-16 | 2023-04-17 | 2023-04-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-04-19 |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 2023-06-16 | 2023-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5637 | 11-May-23 | 2023-06-20 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
83 | 2302-U8T8R-4G#RO-TER071-0093 | CAPEX RAN 1 PART 2 2023 | 8T8R | Swap Antenna and Module BBU and Reconfigure RRU with Add Jumper Cable and FO Kit | TER071 | TBG Jambu Ternate |  |  | TERNATE | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [34 empty] | Intenal | sulaiman | Done Productivity 90 % |  |  |  |  | 13-May-23 | Done | Done |  | Done | 100% | 13-May-23 | 13-May-23 | 13-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 13-May-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2023-09-21 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5625 | 11-May-23 | 2023-06-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
84 | 2302-U8T8R-4G#RO-THN057-0095 | CAPEX RAN 1 PART 2 2023 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna and Reconfigure RRU | THN057 | Protelindo Tatehadeng |  |  | MANADO | #N/A | #N/A | YPTT | March-23 |  | 2023 | 2023 | [36 empty] | Done Productivity 100 % | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 05-May-23 | 5-May-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5468 | 2023-04-05 | 16-May-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
85 | 2303-REENG-4G#RO-BAU141-0052 | CAPEX RAN 1 PART 2 2023 | EQP Enode B Relocation Service | Swap Antenna and Add RRU and Module BBU | BAU141 | DMT Wandoka Selatan |  | ALL CLOSE | KENDARI | -531212 | 12353092 | YPTT | March-23 |  | 2023 | 2023 |  |  | Prose 10 port | 3 | 0 | R8978 S2300 | 1 |  | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | DBXLH-9090C-VTM | 3 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 100 % |  |  |  |  | 05-May-23 | Done | Done |  | Done | 100% | 05-May-23 | 07-May-23 | 07-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 26-May-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 23-Oct-23 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5626 | 11-May-23 | 2023-06-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
86 | 2303-REENG-4G#RO-BIT013-0054 | CAPEX RAN 1 PART 2 2023 | EQP eNode B Relocation Service | Swap Antenna and Add RRU and Module BBU | BIT013 | Girian Weru-DMT |  |  | MANADO | #N/A | #N/A | YPTT | March-23 |  | 2023 | 2023 | [34 empty] | Intenal | Haris | Done Productivity 100 % |  |  |  |  | 14-May-23 | Done | Done |  | Done | 100% | 14-May-23 | 15-May-23 | 15-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-07-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-May-23 | 2023-06-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5622 | 11-May-23 | 2023-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
87 | 2304-4GDCS-4G#RO-BAU289-0059 | RO Acceleration CP#2 | EQP New NE 4G LTE 1800 5 Mhz | New Infra | BAU289 | Palatiga |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | Prose 10 port | 3 | 0 | R9224E M1821 | 3 | 1 | 1 | VBPD0P(1) | 0 | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 90 % |  |  |  |  | 2023-06-17 | Done | Done |  | Done | 100% | 2023-06-17 | 2023-06-18 | 2023-06-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2-Oct-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-11-29 | 5-Dec-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5665 | 13-May-23 | 17-Dec-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
88 | 2304-4GDCS-4G#RO-COI368-0057 | Activity Non MPSL_CP2 ADD RCI RAFI 2023 | EQP New NE 4G LTE 1800 5 Mhz | New Infra (Add Antenna, Add RRU and module BBU) | COI368 | CombatARRPlan29-MRW002-Ex-COD028 |  |  | PALU | #N/A | #N/A | YPTT | May-23 |  | 2023 | 2023 | [28 empty] | IMIP | [5 empty] | Rental Resaource | Fadli | Done Productivity 90 % |  |  |  |  | 16-May-23 | Done | Done |  | Done | 100% | 16-May-23 | 17-May-23 | 2023-06-27 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-07-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-07-26 | 2023-07-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5794 | 25-May-23 | 10-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
89 | 2304-4GDCS-4G#RO-COI382-0063 | Activity Non MPSL_CP2 ADD RCI RAFI 2023 | EQP New NE 4G LTE 1800 5 Mhz | New Infra | COI382 | MARINA TOGO |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | Prose 10 port | 3 | 0 | R9224E M1821 | 3 | 1 | 1 | VBPD0P(1) | 0 | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 100 % |  |  |  |  | 09-Aug-23 | Done | Done |  | Done | 100% | 09-Aug-23 | 11-Aug-23 | 11-Aug-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 18-Aug-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-04-09 | 2023-09-13 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-6049 | 2023-06-27 | 2023-09-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
90 | 2304-4GDCS-4G#RO-MRW921-0081 | RO Acceleration CP#2 | EQP New NE 4G LTE 1800 5 Mhz | New Infra | MRW921 | Puungkoilu |  |  | PALU | #N/A | #N/A | YPTT | May-23 |  | 2023 | 2023 | [34 empty] | Rental Resaource | Fadli | Done Productivity 90 % |  |  |  |  | 2023-06-22 | Done | Done |  | Done | 100% | 2023-06-22 | 2023-06-23 | 2023-06-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-07-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-01-08 | 4-Aug-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5942 | 2023-06-22 | 28-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
91 | 2304-4GGSM-4G#RO-TDO356-0105 | RO Acceleration CP#2 | L900 | New Infra | TDO356 | Permanenisasi COI034 - Combat CRURSI Sentra Medika |  |  | MANADO | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 | [34 empty] | Intenal | Agim | Done Productivity 90 % |  |  |  |  | 2023-06-05 | Done | Done |  | Done | 100% | 2023-06-05 | 2023-06-08 | 2023-07-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 03-Aug-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-01-09 | 2023-09-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5902 | 2023-06-14 | 2023-09-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
92 | 2304-4GGSM-4G#RO-WGI001-0089 | RO Acceleration CP#2 | EQP New NE 4G LTE 900 5 Mhz | New Infra | WGI001 | Permanenisasi COI246 - COMBAT DESA USUKU |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | Prose 10 port | 3 | 0 | R8852E S9000 | 3 | 1 | 1 | VBPD0P(1),VBPD2P(1) | 0 | VSWD1(1) | 0 | 1 | 0 | 0 | 2 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 90 % |  |  |  |  | 2023-06-06 | Done | Done |  | Done | 100% | 2023-06-06 | 2023-06-07 | 2023-06-07 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 6-Aug-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 27-Oct-23 | 2023-06-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5942 | 2023-06-22 | 20-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
93 | 2304-ADSTR-4G#RO-BIT030-0194 | RO Acceleration CP#2 | EQP Add Sector L2300 | Swap Antenna and Reconfigure RRU With Add Jumper Cable for Add Sector | BIT030 | DMT SAGERAT WERU |  |  | MANADO | #N/A | #N/A | YPTT | 2026-04-23 |  | 2023 | 2023 | [34 empty] | Intenal | Aditiaia | Done Productivity 90 % |  |  |  |  | 09-Aug-23 | Done | Done |  | Done | 100% | 09-Aug-23 | 09-Aug-23 | 09-Aug-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 10-Aug-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-09-13 | 2023-09-15 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-6001 | 2023-06-26 | 2023-09-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
94 | 2304-U8T8R-4G#RO-KDI035-0099 | Activity Non MPSL_CP2 RAFI 2023 | EQP upgrade BW 4G LTE 2300 U8T8R 30mhz | Swap Antenna and Add RRU | KDI035 | DMT Plaza Inn |  | NY Ineom Dismantle | KENDARI | -3.9803 | 122.5135 | YPTT | 2026-04-23 |  | 2023 | 2023 |  |  | Rosenberger 12 port | 2 | 2 | R8998G S2300 | 1 |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 |  |  | 0 | MOBI 10 port | 2 | 2 | No Need | 0 | No Need RRU | 0 | BPN2(1),PM3(1) | [6 empty] | Rental Resaource | ANTO/Syamsuddin | Done Productivity 90 % |  |  |  |  | 2023-04-13 | Done | Done |  | Done | 100% | 2023-04-13 | 2023-04-13 | 2023-04-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-04-16 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2023-11-15 | 2023-06-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5626 | 11-May-23 | 2023-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
95 | 2305-4GDCS-4G#RO-SSU047-0110 | RO Acceleration CP#2 | EQP New Site 4G LTE 1800 5 Mhz | Add RRU | LBA113 | Bandara Soligi 1 |  | Imp by YPTT (Mapping site), PR to Tritell_PO No : S1ID2023070108WBF1-4 | TERNATE | #N/A | #N/A | YPTT | January-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE | Done Req ZTE |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-02-10 | Done | Done |  | Done | 100% | 2024-02-10 | 2024-02-10 | 2024-02-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-11 | 2024-11-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9463 | 2026-03-25 | 19-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | NEW PO
96 | 2305-4GGSM-4G#RO-COI151-0127 | RO Acceleration CP#2 | EQP New NE 4G LTE 900 5 Mhz | Swap Antenna and Add RRU | COI151 | CombatARRNumana |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | TBXLHA 6 Port | 3 | 0 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | TDQ 4 Port | 1 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 90 % |  |  |  |  | 2023-06-27 | Done | Done |  | Done | 100% | 2023-06-27 | 2023-06-28 | 2023-06-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-07-10 |  | Done Tagging |  | Done Tagging | Waiting Permit | [11 empty] | 24-Aug-23 | 29-Aug-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5942 | 2023-06-22 | 31-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
97 | 2305-4GGSM-4G#RO-JLO009-0245 | RO Acceleration CP#2 | EQP New Site 4G LTE 900 10 Mhz | ATP Only | JLO009 | Repeater Loloda |  | Take over closing ATP to YPTT d/t GMI no team | TERNATE | #N/A | #N/A | YPTT | December-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  | 1920499 | 18-Dec-24 | Done | Done |  | Done | 100% | 18-Dec-24 | 20-Dec-24 | 20-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need | [11 empty] | 24-Dec-24 | 24-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9463 | 2026-03-25 | 2025-01-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | NEW PO
98 | 2305-4GGSM-4G#RO-KDI046-0134 | RO Acceleration CP#2 | EQP New NE 4G LTE 900 5 MHz | Swap Antenna and Module BBU and Add RRU | KDI046 | Saranani |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | Prose 10 port | 1 | 1 | R8852E S9000 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | Kathrein 2 port(1),Kathrein 4 port(1) | 2 | 1 | No Need | 0 | No Need RRU | 0 | PM3(2) | [6 empty] | partner | RANDI | Done Productivity 90 % |  |  |  |  | 2023-06-25 | Done | Done |  | Done | 100% | 2023-06-25 | 2023-06-26 | 2023-06-26 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-07-06 |  | Done Tagging |  | Done Tagging | Waiting Permit | [11 empty] | 23-Aug-23 | 29-Aug-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-6001 | 2023-06-26 | 31-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
99 | 2305-4GGSM-4G#RO-KDI250-0135 | RO Acceleration CP#2 | EQP New NE 4G LTE 900 5 MHz | Swap Antenna and Module BBU and Add RRU | KDI250 | Pondambia-DMT |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | Prose 10 port | 1 | 1 | R8852E S9000 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | Amphenol 8 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | PM3(1) | [6 empty] | partner | RANDI | Done Productivity 90 % |  |  |  |  | 2023-06-21 | Done | Done |  | Done | 100% | 2023-06-21 | 2023-06-22 | 2023-06-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-06-24 |  | Done Tagging |  | Done Tagging | Waiting Permit | [11 empty] | 22-Aug-23 | 23-Aug-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5955 | 2023-06-23 | 28-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
100 | 2305-4GGSM-4G#RO-TDO260-0217 | RO Acceleration CP#2 | L900 | Swap Antenna and Add RRU and Module BBU | TDO260 | TonseaTondano-DMT |  |  | MANADO | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 | [34 empty] | Intenal | Agim | Done Productivity 90 % |  |  |  |  | 2023-06-27 | Done | Done |  | Done | 100% | 2023-06-27 | 2023-07-04 | 2023-07-04 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 11-Aug-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 09-Dec-23 | 2023-09-15 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-6001 | 2023-06-26 | 2023-09-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
101 | 2305-ADSTR-4G#RO-KDI272-0252 | RO Acceleration CP#2 | EQP Add Sector LTE 2300 | Add RRU and Module BBU | KDI272 | Mokoau Kambu-DMT |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8998G S2300 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RANDI | Done Productivity 90 % |  |  |  |  | 2023-06-16 | Done | Done |  | Done | 100% | 2023-06-16 | 2023-06-17 | 2023-06-17 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-06-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-07-18 | 2023-07-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5955 | 2023-06-23 | 2023-07-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
102 | 2305-NNE4G-4G#RO-BAU022-0828 | RO Acceleration CP#2 | EQP New NE 4G LTE 2300 10 Mhz | Add RRU and Module BBU | BAU022 | Umalaoge |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8978 S2300 | 1 |  | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 100 % |  |  |  |  | 2023-06-16 | Done | Done |  | Done | 100% | 2023-06-16 | 2023-06-17 | 2023-06-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-07-20 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-02-08 | 4-Aug-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5961 | 2023-06-24 | 16-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
103 | 2305-NNE4G-4G#RO-BAU048-0861 | RO Acceleration CP#2 | EQP New NE 4G LTE 2300 10 Mhz | Swap Antenna and Add RRU and Module BBU | BAU048 | Bandara Matohara Wanci |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | Prose 10 port | 3 | 0 | R8998G S2300 | 1 |  | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | TDQ 4 port(1),K742352(2),TBXLHA 6 port(3) | 6 | 2 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 90 % |  |  |  |  | 2023-06-23 | Done | Done |  | Done | 100% | 2023-06-23 | 2023-06-24 | 2023-06-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-07-11 |  | Done Tagging |  | Done Tagging | Waiting Permit | [11 empty] | 23-Aug-23 | 23-Aug-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5960 | 2023-06-24 | 28-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
104 | 2305-NNE4G-4G#RO-BAU090-0866 | RO Acceleration CP#2 | EQP New NE 4G LTE 2300 10 Mhz | Add RRU and Module BBU | BAU090 | PatunoResort-TBG |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8998G S2300 | 1 |  | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 100 % |  |  |  |  | 2023-06-26 | Done | Done |  | Done | 100% | 2023-06-26 | 2023-06-27 | 2023-06-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-07-11 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-07-27 | 4-Aug-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5955 | 2023-06-23 | 28-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
105 | 2305-NNE4G-4G#RO-DGL057-0648 | RO Acceleration CP#2 | EQP New NE 4G LTE 1800 5 Mhz | Swap Antenna and RRU | DGL057 | DoloBarat-DMT |  |  | PALU | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 | [28 empty] | IMIP | [5 empty] | Rental Resaource | ALDI | Done Productivity 90 % |  |  |  |  | 2023-06-05 | Done | Done |  | Done | 100% | 2023-06-05 | 2023-06-06 | 2023-06-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-06-24 |  | Done Tagging |  | Done Tagging | [12 empty] | 30-Aug-23 | 2023-06-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5946 | 2023-06-22 | 20-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
106 | 2305-NNE4G-4G#RO-KDI279-1225 | RO Acceleration CP#2 | EQP New Site 4G LTE 2300 10 Mhz | Swap Antenna and Add RRU and Module BBU | KDI279 | MCR Budi Utomo Kendari |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | Prose 10 port | 1 | 0 | R8998G S2300 | 1 |  | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | TBXLHA 6 Port | 1 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RANDI | Done Productivity 90 % |  |  |  |  | 2023-06-19 | Done | Done |  | Done | 100% | 2023-06-19 | 2023-06-20 | 2023-06-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-06-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 18-Aug-23 | 21-Aug-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5955 | 2023-06-23 | 28-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
107 | 2305-NNE4G-4G#RO-KDI322-0698 | RO Acceleration CP#2 | EQP New NE 4G LTE 2100 5 Mhz | Add Module BBU | KDI322 | Labibia-PTI |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | 0 | 0 |  | 0 | VBPD2p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RANDI | Done Productivity 100 % |  |  |  |  | 27-May-23 | Done | Done |  | Done | 100% | 27-May-23 | 27-May-23 | 27-May-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 28-May-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-06-23 | 2023-06-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5943 | 2023-06-22 | 2023-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
108 | 2305-NNE4G-4G#RO-LBA091-1229 | RO Acceleration CP#2 | EQP New Site 4G LTE 2300 10 Mhz | Add RRU and Module BBU | LBA091 | Laiwui-DMT |  |  | TERNATE | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 | [34 empty] | Rental Resaource | Sulaiman | Done Productivity 100 % |  |  |  |  | 2023-07-01 | Done | Done |  | Done | 100% | 2023-07-01 | 2023-07-01 | 2023-07-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-07-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-07-25 | 2023-07-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-6001 | 2023-06-26 | 2024-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
109 | 2305-NNE4G-4G#RO-RHA034-1058 | RO Acceleration CP#2 | EQP New NE 4G LTE 2300 10 Mhz | Swap Antenna and Add RRU and Module BBU | RHA034 | Wakadia-DMT |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8998G S2300 | 1 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Rental Resaource | ANTO/Syamsuddin | Done Productivity 90 % |  |  |  |  | 2023-06-20 | Done | Done |  | Done | 100% | 2023-06-20 | 2023-06-21 | 2023-06-21 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-06-22 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-07-24 | 2023-07-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5953 | 2023-06-23 | 2023-07-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
110 | 2305-NNE4G-4G#RO-RHA049-1062 | RO Acceleration CP#2 | EQP New NE 4G LTE 2300 10 Mhz | Swap Antenna and Module BBU and Add RRU | RHA049 | Labunti-DMT |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | Prose 10 port | 3 | 3 | R8998G S2300 | 1 |  | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | DBXLH 4 port | 3 | 3 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Rental Resaource | ANTO/Syamsuddin | Done Productivity 90 % |  |  |  |  | 2023-06-25 | Done | Done |  | Done | 100% | 2023-06-25 | 2023-06-26 | 2023-06-26 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-06-27 |  | Done Tagging |  | Done Tagging | Waiting Permit | [11 empty] | 2023-11-08 | 15-Aug-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-6005 | 2023-06-26 | 28-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
111 | 2305-U8T8R-4G#RO-ADL272-0121 | RO Acceleration CP#2 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna, Add RRU and Module BBU | ADL272 | B2B.PT.OSSJetty |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | Prose 12 port | 2 | 1 | R8998G S2300 | 1 |  | 0 | VBPD0P(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | MOBI 12 port | 2 | 1 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RANDI | Done Productivity 100 % |  |  |  |  | 2023-06-03 | Done | Done |  | Done | 100% | 2023-06-03 | 2023-06-04 | 2023-06-04 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-06-04 |  | Done Tagging |  | Done Tagging | Waiting Permit | [11 empty] | 2023-06-12 | 2023-06-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5943 | 2023-06-22 | 2023-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
112 | 2305-U8T8R-4G#RO-MRW912-0118 | RO Acceleration CP#2 | EQP Upgrade BW LTE 2300 30 - 30Mhz 8T8R | Swap Antenna and Reconfigure RRU with Add Jumper Cable and FO Kit | MRW912 | Keurea-DMT |  |  | PALU | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 | [28 empty] | DMT (PT. DAYA MITRA TELEKOMUNIKASI) | [5 empty] | Rental Resaource | imam | Done Productivity 90 % |  |  |  |  | 2023-07-03 | Done | Done |  | Done | 100% | 2023-07-03 | 2023-07-03 | 2023-07-03 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-07-17 |  | Done Tagging |  | Done Tagging | [12 empty] | 21-Aug-23 | 21-Aug-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-6031 | 2023-06-26 | 28-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
113 | 2306-REENG-4G#RO-WGI001-0105 | Re-Eng Permanenisasi Combat 2023 | EQP New NE 4G LTE 1800 5 Mhz | Add RRU | WGI001 | Permanenisasi COI246 - COMBAT DESA USUKU |  | NR Ineom | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8872 S1800 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 100 % |  |  |  |  | 2023-06-17 | Done | Done |  | Done | 100% | 2023-06-17 | 2023-06-18 | 2023-06-18 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 9-Aug-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-11-08 | 15-Aug-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5954 | 2023-06-23 | 28-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
114 | 2306-REENG-4G#RO-WGI001-0112 | Re-Eng Permanenisasi Combat 2023 | EQP New NE 4G LTE 2100 5 Mhz | Add RRU | WGI001 | Permanenisasi COI246 - COMBAT DESA USUKU |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8852E S2100 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 100 % |  |  |  |  | 2023-06-17 | Done | Done |  | Done | 100% | 2023-06-17 | 2023-06-18 | 2023-06-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 9-Aug-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-11-08 | 15-Aug-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5954 | 2023-06-23 | 28-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
115 | 2306-REENG-4G#RO-WGI001-0118 | Re-Eng Permanenisasi Combat 2023 | EQP New NE 4G LTE 2300 10 Mhz | Add RRU | WGI001 | Permanenisasi COI246 - COMBAT DESA USUKU |  | ALL CLOSE | KENDARI | #N/A | #N/A | YPTT | June-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8978 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | partner | RUSLAN | Done Productivity 100 % |  |  |  |  | 2023-06-17 | Done | Done |  | Done | 100% | 2023-06-17 | 2023-06-18 | 2023-06-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 9-Aug-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-11-08 | 15-Aug-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2021040102WBF1-5954 | 2023-06-23 | 28-Aug-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
116 | 2309-4GDCS-4G#RO-NTI306-0158 | CAPEX RAN 3 ACCELERATION SUPPORT 2023 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | NTI386 | DMT N3T Sani-Sani |  | HI Done by GMI in Pare but PO mapping to Kendari due to PLN issue and imp by YPTT at acceptor (Mapping site), PR to GMI_PO No : S1ID2023070107WBF1-104 | KENDARI | -3.98 | 121.4349 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Herdianto | [5 empty] | 2025-03-27 | Done | Done | 2025-03-27 | Done | 100% | 2025-03-27 | 2025-03-27 | 2025-04-22 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-04-17 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 05-May-25 | 8-May-25 |  | PO NY Release |  |  | 2025-07-07 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload
117 | 2309-NNE4G-4G#RO-KDI050-1432 | CAPEX RAN 3 ACCELERATION SUPPORT 2023 | EQP New NE 4G LTE 2300 10 Mhz | Swap Antenna and Add RRU and Module BBU | KDI050 | DMT Purirano |  |  | KENDARI | -3.9601 | 122.6179 | YPTT | 2026-09-23 |  | 2023 | 2023 |  |  | Mobi 10 Port | 1 | 1 | R8998 S2300 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | TDQ 4 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Partner | Indra | Done Productivity 90 % |  |  |  |  | 2023-09-23 | Done | Done |  | Done | 100% | 2023-09-23 | 2023-09-23 | 2023-09-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-09-28 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-09-10 | 9-Oct-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-1437 | 9-Oct-23 | 26-Oct-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
118 | 2309-NNE4G-4G#RO-KDI241-1599 | CAPEX RAN 3 ACCELERATION SUPPORT 2023 | EQP New NE 4G LTE 2300 40 Mhz Massive MIMO | Swap Antenna and Add RRU and Module BBU | KDI241 | DMT Hotel Azahra |  |  | KENDARI | -3.974 | 122.5254 | YPTT | 2026-09-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8998 S2300 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | DCPD7(1) | [6 empty] | Partner | Indra | Done Productivity 90 % |  |  |  |  | 2023-09-22 | Done | Done |  | Done | 100% | 2023-09-22 | 2023-09-22 | 2023-09-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-09-28 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 10-May-23 | 9-Oct-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-1437 | 9-Oct-23 | 26-Oct-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
119 | 2309-NNE4G-4G#RO-KDI310-1353 | CAPEX RAN 3 ACCELERATION SUPPORT 2023 | EQP New NE 4G LTE 2100 5 Mhz | Swap RRU and Add Module BBU | KDI310 | KDI MM Bumi Wanggu |  |  | KENDARI | -4.0275 | 122.5127 | YPTT | 2026-09-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800 | 1 | No Need Board | [6 empty] | Partner | Indra | Done Productivity 100 % |  |  |  |  | 2023-09-18 | Done | Done |  | Done | 100% | 2023-09-18 | 2023-09-19 | 2023-09-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-09-20 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 10-May-23 | 9-Oct-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-1437 | 9-Oct-23 | 18-Oct-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
120 | 2309-NNE4G-4G#RO-MGN019-1474 | CAPEX RAN 3 ACCELERATION SUPPORT 2023 | EQP New NE 4G LTE 2300 10 Mhz | Add RRU and Module BBU | MGN019 | DMT TABANG |  |  | MANADO | #N/A | #N/A | YPTT | 2026-09-23 |  | 2023 | 2023 | [34 empty] | Partner | noris | Done Productivity 100 % |  |  |  |  | 2023-09-21 | Done | Done |  | Done | 100% | 2023-09-21 | 2023-09-21 | 2023-09-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 03-Oct-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2023-07-10 | 10-Oct-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-1437 | 9-Oct-23 | 26-Oct-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
121 | 2309-NNE4G-4G#RO-MGN051-1476 | CAPEX RAN 3 ACCELERATION SUPPORT 2023 | EQP New NE 4G LTE 2300 10 Mhz | Add RRU and Module BBU | MGN051 | DMT MELONGUANE BARAT |  |  | MANADO | #N/A | #N/A | YPTT | 2026-09-23 |  | 2023 | 2023 | [34 empty] | Partner | Noris | Done Productivity 90 % |  |  |  |  | 2023-09-23 | Done | Done |  | Done | 100% | 2023-09-23 | 2023-09-23 | 2023-09-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-09-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-03-10 | 9-Oct-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-1437 | 9-Oct-23 | 26-Oct-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
122 | 2309-NNE4G-4G#RO-TDO069-1548 | CAPEX RAN 3 ACCELERATION SUPPORT 2023 | EQP New NE 4G LTE 2300 10 Mhz | Swap Antenna and Add RRU and Module BBU | TDO069 | MSI TOMPASSO |  |  | MANADO | #N/A | #N/A | YPTT | 2026-09-23 |  | 2023 | 2023 | [34 empty] | Partner | Aditia | Done Productivity 90 % |  |  |  |  | 19-Oct-23 | Done | Done |  | Done | 100% | 19-Oct-23 | 20-Oct-23 | 20-Oct-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 23-Oct-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-01-11 | 2023-11-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-1785 | 2023-11-02 | 2023-11-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
123 | 2309-NNE4G-4G#RO-TDO230-1552 | CAPEX RAN 3 ACCELERATION SUPPORT 2023 | EQP New NE 4G LTE 2300 10 Mhz | Add RRU and Module BBU | TDO230 | DMT ISAT LEMBEAN |  |  | MANADO | #N/A | #N/A | YPTT | 2026-09-23 |  | 2023 | 2023 | [34 empty] | Partner | Aditia | Done Productivity 90 % |  |  |  |  | 17-Oct-23 | Done | Done |  | Done | 100% | 17-Oct-23 | 17-Oct-23 | 17-Oct-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 18-Oct-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 26-Oct-23 | 2023-11-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-1785 | 2023-11-02 | 2023-11-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
124 | 2309-NNE4G-4G#RO-TDO232-1554 | CAPEX RAN 3 ACCELERATION SUPPORT 2023 | EQP New NE 4G LTE 2300 10 Mhz | Swap Antena and Add RRU and Module BBU | TDO232 | DMT ISAT SONDAR |  |  | MANADO | #N/A | #N/A | YPTT | 2026-09-23 |  | 2023 | 2023 | [34 empty] | Partner | Aditia | Done Productivity 90 % |  |  |  |  | 24-Oct-23 | Done | Done |  | Done | 100% | 24-Oct-23 | 25-Oct-23 | 25-Oct-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 26-Oct-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-02-11 | 2023-11-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2020 | 2023-11-14 | 17-Dec-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
125 | 2309-NNE4G-4G#RO-TMH032-1572 | CAPEX RAN 3 ACCELERATION SUPPORT 2023 | EQP New NE 4G LTE 2300 10 Mhz | Add RRU and Module BBU | TMH032 | PROTELINDO KAYAWU |  |  | MANADO | #N/A | #N/A | YPTT | 2026-09-23 |  | 2023 | 2023 | [34 empty] | Partner | Aditia | Done Productivity 90 % |  |  |  |  | 2023-09-22 | Done | Done |  | Done | 100% | 2023-09-22 | 2023-09-23 | 2023-09-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-09-27 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-04-10 | 9-Oct-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-1437 | 9-Oct-23 | 26-Oct-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
126 | 2309-NNE4G-4G#RO-TMH074-1575 | CAPEX RAN 3 ACCELERATION SUPPORT 2023 | EQP New NE 4G LTE 2300 10 Mhz | Add RRU and Module BBU | TMH074 | DMT MM KAKASKASEN |  |  | MANADO | #N/A | #N/A | YPTT | 2026-09-23 |  | 2023 | 2023 | [34 empty] | Partner | Aditia | Done Productivity 90 % |  |  |  |  | 2023-09-25 | Done | Done |  | Done | 100% | 2023-09-25 | 2023-09-26 | 2023-09-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-09-27 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-06-10 | 10-Oct-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-1437 | 9-Oct-23 | 30-Oct-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
127 | 2310-4GDCS-4G#RO-BAU273-0242 | 0 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | RHA067 | DMT Wadolao Marobo |  | ALL CLOSE | KENDARI | -5.1009 | 122.3614 | YPTT | May-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 3 | 3 | R9224E M1821 | 3 | 1 | 1 | 0 | VBPd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 16-May-24 | Done | Done |  | Done | 100% | 16-May-24 | 17-May-24 | 17-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 22-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 27-May-24 | 22-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3546 | 31-May-24 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
128 | 2310-4GDCS-4G#RO-KDI349-0183 | 0 | EQP New Site 4G LTE 1800 20 Mhz | Add Antenna and RRU and Module BBU (New Infra) | KDI349 | Desa Baruga |  | ALL CLOSE | KENDARI | -4.0422 | 122.5025 | YPTT | October-23 |  | 2023 | 2023 |  |  | Prose 10 port | 3 | 3 | R9224E M1821 | 3 | 1 | 1 | VBPd0P(1) | 0 | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Partner | MAMAN | Done Productivity 90 % |  |  |  |  | 31-Oct-23 | Done | Done |  | Done | 100% | 31-Oct-23 | 2023-11-02 | 2023-11-27 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 9-Dec-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-11-12 | 12-Dec-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2215 | 2023-11-23 | 17-Dec-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
129 | 2310-4GDCS-4G#RO-KDI350-0247 | 0 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | KDI350 | BTN Dewi Bunga |  | ALL CLOSE | KENDARI | -4.0317 | 122.5566 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 0 | R9224E M1821 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-02-22 | Done | Done |  | Done | 100% | 2024-02-22 | 2024-02-23 | 03-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 3-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-05 | 16-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3159 | 2024-03-02 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
130 | 2310-4GDCS-4G#RO-LBA123-0251 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add Module BBU | LBA123 | Kampung Makian |  |  | TERNATE | #N/A | #N/A | YPTT | October-23 |  | 2023 | 2023 | [28 empty] | New Infra | 14-Dec-23 | 14-Dec-23 |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-04-29 | Done | Done |  | Done | 100% | 2024-04-29 | 01-May-24 | 2024-06-02 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 10-Aug-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 26-Aug-24 | 2024-09-02 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3510 | 23-May-24 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
131 | 2310-4GDCS-4G#RO-MRW381-0258 | 0 | EQP New Site 4G LTE 1800 20 Mhz | New Infra | MRW381 | CombatFUNMiniGrapariMorowali |  |  | PALU | #N/A | #N/A | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-04-30 | Done | Done |  | Done | 100% | 2024-04-30 | 01-May-24 | 06-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 18-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 21-May-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3510 | 23-May-24 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
132 | 2310-4GDCS-4G#RO-MRW924-0259 | 0 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | MRW924 | DMT Tangofa Choirul |  |  | PALU | #N/A | #N/A | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-03-16 | Done | Done |  | Done | 100% | 2024-03-16 | 2024-03-17 | 2024-03-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2026-03-27 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-31 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3159 | 2024-03-02 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
133 | 2310-4GDCS-4G#RO-MRW925-0260 | 0 | EQP New Site 4G LTE 1800 20 Mhz | New Infra | MRW925 | CombatPermanenisasi_MRW925 |  |  | PALU | #N/A | #N/A | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-04-20 | Done | Done |  | Done | 100% | 2024-04-20 | 2024-04-24 | 2024-04-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-05 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3463 | 15-May-24 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
134 | 2310-4GDCS-4G#RO-MRW926-0261 | 0 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | MRW926 | JalanMerpatiLalampu-DMT |  |  | PALU | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [28 empty] | IMIP | [5 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-04-02 | Done | Done |  | Done | 100% | 2024-04-02 | 2024-04-05 | 2024-04-03 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-04-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-05 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3250 | 2024-03-21 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
135 | 2310-4GDCS-4G#RO-MRW928-0262 | 0 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | MRW928 | Perumahan Jl Pelangi |  |  | PALU | #N/A | #N/A | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-04-30 | Done | Done |  | Done | 100% | 2024-04-30 | 2024-04-29 | 02-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 6-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 17-May-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3510 | 23-May-24 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
136 | 2310-4GDCS-4G#RO-NTI081-0236 | 0 | EQP New NE 4G LTE 1800 5 Mhz | Add Antenna and RRU and Module BBU | NTI081 | N3TMatahit-DMT |  |  | MANADO | #N/A | #N/A | YPTT | October-23 |  | 2023 | 2023 | [29 empty] | Release | Done Req ZTE |  |  |  | Partner | Noris | Done Productivity 100 % |  |  |  |  | 2023-11-18 | Done | Done |  | Done | 100% | 2023-11-18 | 2023-11-20 | 2023-11-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-11-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 01-Dec-23 | 1-Dec-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2347 | 3-Dec-23 | 17-Dec-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
137 | 2310-4GDCS-4G#RO-SSU131-0265 | 0 | EQP New Site 4G LTE 1800 20 Mhz (DCS Activation) | New Infra | SSU131 | Split Lokolamo |  |  | TERNATE | #N/A | #N/A | YPTT | 2026-04-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-04-21 | Done | Done |  | Done | 100% | 2024-04-21 | 2024-04-22 | 25-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 05 August 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 17-Dec-24 | 17-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3463 | 15-May-24 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
138 | 2310-4GDCS-4G#RO-SSU132-0266 | 0 | EQP New Site 4G LTE 1800 20 Mhz (DCS Activation) | New Infra | SSU132 | Lelilef Utara |  |  | TERNATE | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-04-11 | Done | Done |  | Done | 100% | 2024-04-11 | 2024-04-11 | 24-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 14 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 27-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3463 | 15-May-24 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
139 | 2310-4GDCS-4G#RO-SSU136-0267 | 0 | EQP New Site 4G LTE 1800 20 Mhz (DCS Activation) | New Infra | SSU136 | Weda City |  |  | TERNATE | #N/A | #N/A | YPTT | 2026-04-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-04-18 | Done | Done |  | Done | 100% | 2024-04-18 | 2024-04-19 | 18-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 8-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 27-Aug-24 | 2024-09-02 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3463 | 15-May-24 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
140 | 2310-4GDCS-4G#RO-SSU138-0269 | 0 | EQP New Site 4G LTE 1800 20 Mhz (DCS Activation) | New Infra | SSU138 | Perumahan Fidi Jaya |  |  | TERNATE | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-03-30 | Done | Done |  | Done | 100% | 2024-03-30 | 2024-03-30 | 18-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 14 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 27-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3440 | 6-May-24 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
141 | 2310-4GDCS-4G#RO-SSU139-0270 | 0 | EQP New Site 4G LTE 1800 20 Mhz (DCS Activation) | New Infra | SSU139 | TK Gemaf |  |  | TERNATE | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-04-17 | Done | Done |  | Done | 100% | 2024-04-17 | 2024-04-18 | 2024-07-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 10 August 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 28-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3463 | 15-May-24 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
142 | 2310-4GDCS-4G#RO-SSU140-0271 | 0 | EQP New Site 4G LTE 1800 20 Mhz (DCS Activation) | New Infra | SSU140 | Permanenisasi Kobe |  |  | TERNATE | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-03-31 | Done | Done |  | Done | 100% | 2024-03-31 | 2024-03-31 | 2024-03-31 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 18 August 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 29-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3440 | 6-May-24 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
143 | 2310-4GDCS-4G#RO-TDE070-0272 | 0 | EQP New Site 4G LTE 1800 20 Mhz (DCS Activation) | Add Antenna and RRU and module BBU | TDE070 | Ampera Sofifi |  |  | TERNATE | #N/A | #N/A | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-03-05 | Done | Done |  | Done | 100% | 2024-03-05 | 2024-03-06 | 2024-03-12 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 06-Dec-24 | 22-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3264 | 2024-03-22 | 17-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
144 | 2310-4GDCS-4G#RO-TDE071-0273 | 0 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | TDE071 | Alun Alun Sofifi |  |  | TERNATE | #N/A | #N/A | YPTT | October-23 |  | 2023 | 2023 | [28 empty] | New Infra | 14-Dec-23 | 14-Dec-23 |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 28-May-24 | Done | Done |  | Done | 100% | 28-May-24 | 30-May-24 | 30-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-06 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3902 | 2024-06-13 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
145 | 2310-4GDCS-4G#RO-TER214-0274 | 0 | EQP New Site 4G LTE 1800 20 Mhz (DCS Activation) | New Infra | TER214 | Maliaoro |  |  | TERNATE | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-04-12 | Done | Done |  | Done | 100% | 2024-04-12 | 2024-04-14 | 07-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 06-Dec-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3463 | 15-May-24 | 2-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
146 | 2310-4GDCS-4G#RO-UNH005-0278 | 0 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | UNH005 | DMT Pohara Laosu |  | MOS by CCSI but imp take over to YPTT due to CCSI no team to continue imp, PR to CCSI_PO No : S1ID2023070101WBF1-1023 | KENDARI | -391072 | 12243258 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 0 | R9224E M1821 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | [5 empty] | 2024-03-06 | Done | Done |  | Done | 100% | 2024-03-06 | 2024-03-07 | 2024-03-07 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 05-Aug-24 | 16-May-24 |  | PO NY Release |  |  | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload
147 | 2310-4GGSM-4G#RO-AMR118-0373 | 0 | EQP New Site 4G LTE 900 10 Mhz (GSM Activation) | New Infra | AMR118 | NIB#3_00579 |  |  | MANADO | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-04-13 | Done | Done |  | Done | 100% | 2024-04-13 | 2024-04-14 | 2024-04-17 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-18 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-29 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3463 | 15-May-24 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
148 | 2310-4GGSM-4G#RO-BOB001-0375 | 0 | EQP New Site 4G LTE 900 10 Mhz (GSM Activation) | Add Antenna and RRU and module BBU | BOB001 | Desa Todoli |  |  | TERNATE | #N/A | #N/A | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-04-26 | Done | Done |  | Done | 100% | 2024-04-26 | 2024-04-29 | 01-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 21-May-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3462 | 15-May-24 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
149 | 2310-4GGSM-4G#RO-KKA259-0380 | 0 | EQP New NE 4G LTE 900 10 Mhz | New Infra | KKA259 | DMT Lapao Pao |  | ALL CLOSE | KENDARI | -3.8944 | 121.3369 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 0 | R8852E S9000 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-03-16 | Done | Done |  | Done | 100% | 2024-03-16 | 2024-03-17 | 2024-03-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 7-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 16-May-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3263 | 2024-03-22 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
150 | 2310-4GGSM-4G#RO-KKA260-0381 | 0 | EQP New NE 4G LTE 900 10 Mhz | New Infra | KKA260 | DMT Pesouha |  | ALL CLOSE | KENDARI | -417829 | 12163552 | YPTT | 2026-04-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 3 | R8852E S9000 | 3 | 1 | 1 | 0 | VBPd0P(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-04-24 | Done | Done |  | Done | 100% | 2024-04-24 | 2024-04-26 | 2024-04-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 25-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 16-May-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3462 | 15-May-24 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
151 | 2310-4GGSM-4G#RO-KKA261-0382 | 0 | EQP New NE 4G LTE 900 10 Mhz | New Infra | KKA261 | NIB#3 Tambea |  | NY Ineom | KENDARI | -420271 | 12158571 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 0 | R8852E S9000 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-03-22 | Done | Done |  | Done | 100% | 2024-03-22 | 2024-03-23 | 2024-03-23 | Connected | Connected |  | 01-Passed | 01-Passed | no Need | 2024-03-23 |  | Done Tagging |  | Done Tagging | No Need | Waiting Permit | [10 empty] | 2024-03-06 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3250 | 2024-03-21 | 2-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
152 | 2310-4GGSM-4G#RO-LBA075-0383 | 0 | EQP New Site 4G LTE 900 10 Mhz (GSM Activation) | New Infra | LBA075 | CombatMOPLaromabatiKayoa |  |  | TERNATE | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-04-27 | Done | Done |  | Done | 100% | 2024-04-27 | 16-May-24 | 16-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 19 May 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 27-May-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3462 | 15-May-24 | 2-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
153 | 2310-4GGSM-4G#RO-LBA076-0384 | 0 | EQP New Site 4G LTE 900 10 Mhz (GSM Activation) | New Infra | LBA076 | CombatFUNAirportBacan |  |  | TERNATE | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-04-25 | Done | Done |  | Done | 100% | 2024-04-25 | 2024-04-25 | 26-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 8-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 27-Aug-24 | 2024-09-02 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3462 | 15-May-24 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
154 | 2310-4GGSM-4G#RO-LBA077-0385 | 0 | EQP New Site 4G LTE 900 10 Mhz (GSM Activation) | New Infra | LBA077 | NIB#3_00253 |  |  | TERNATE | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-04-29 | Done | Done |  | Done | 100% | 2024-04-29 | 04-May-24 | 12-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 05 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-06 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3510 | 23-May-24 | 2-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
155 | 2310-4GGSM-4G#RO-LBA107-0386 | 0 | EQP New Site 4G LTE 900 10 Mhz (GSM Activation) | New Infra | LBA107 | Sambiki |  |  | TERNATE | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 22-May-24 | Done | Done |  | Done | 100% | 22-May-24 | 24-May-24 | 26-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 30 May 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 31-May-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3546 | 31-May-24 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
156 | 2310-4GGSM-4G#RO-MRW380-0390 | 0 | EQP New NE 4G LTE 900 10 Mhz | New Infra | RHA059 | DMT Wulanga Jaya |  | ALL CLOSE | KENDARI | -4.8291 | 12243420 | YPTT | 2026-04-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 3 | R8852E S9000 | 3 | 1 | 1 | 0 | VBPd0P(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-04-30 | Done | Done |  | Done | 100% | 2024-04-30 | 01-May-24 | 01-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 8-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 20-May-24 | 22-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3510 | 23-May-24 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
157 | 2310-4GGSM-4G#RO-MRW929-0391 | 0 | EQP New Site 4G LTE 900 10 Mhz | New Infra | MRW929 | Topogaro-UmpangaSamsir-DMT |  |  | PALU | #N/A | #N/A | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-02-27 | Done | Done |  | Done | 100% | 2024-02-27 | 2024-02-29 | 2024-03-29 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-04-18 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3250 | 2024-03-21 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
158 | 2310-4GGSM-4G#RO-PSW001-0396 | 0 | EQP New NE 4G LTE 900 10 Mhz | New Infra | PSW001 | Ambuau Indah |  | NY ATP & Ineom | KENDARI | -5.3176 | 123.1687 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 0 | R8852E S9000 | 3 | 1 | 1 | 0 | VBpd0P(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-03-15 | Done | Done |  | Done | 100% | 2024-03-15 | 2024-03-16 | 2024-03-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-23 |  | Done Tagging |  | Done Tagging | No Need | Waiting Permit | [10 empty] | 27-May-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3263 | 2024-03-22 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
159 | 2310-4GGSM-4G#RO-RHA152-0397 | 0 | EQP New NE 4G LTE 900 10 Mhz | New Infra | RHA152 | DMT Oensuli Kabangka |  | ALL CLOSE | KENDARI | -4.9474 | 122383900 | YPTT | May-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 3 | 3 | R8852E S9000 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 30-May-24 | Done | Done |  | Done | 100% | 30-May-24 | 31-May-24 | 31-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-15 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-24 | 2024-09-02 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3902 | 2024-06-13 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
160 | 2310-4GGSM-4G#RO-SKG205-0401 | 0 | EQP New NE 4G LTE 900 10 Mhz | New Infra | SKG205 | Tengnga |  |  | MAKASSAR | -4061300 | 120182320 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Very | Done Productivity 100 % |  |  |  |  | 2024-02-20 | Done | Done |  | Done | 100% | 2024-02-20 | 2024-02-21 | 2024-02-29 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 04-May-24 | 2024-04-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3159 | 2024-03-02 | 13-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
161 | 2310-4GGSM-4G#RO-SSU133-0408 | 0 | EQP New Site 4G LTE 900 10 Mhz (GSM Activation) | New Infra | SSU133 | Trans Lelilef |  |  | TERNATE | #N/A | #N/A | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 26-May-24 | Done | Done |  | Done | 100% | 26-May-24 | 27-May-24 | 27-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 16 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-19 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3902 | 2024-06-13 | 16-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
162 | 2310-4GGSM-4G#RO-TDE073-0410 | 0 | EQP New Site 4G LTE 900 10 Mhz (GSM Activation) | New Infra | TDE073 | Pasigau |  |  | TERNATE | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-04-20 | Done | Done |  | Done | 100% | 2024-04-20 | 2024-04-21 | 06-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 10 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 06-Dec-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3463 | 15-May-24 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
163 | 2310-4GGSM-4G#RO-TDE074-0411 | 0 | EQP New Site 4G LTE 900 10 Mhz (GSM Activation) | Add Antenna and RRU and module BBU | TDE074 | Togeme |  |  | TERNATE | #N/A | #N/A | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-02-29 | Done | Done |  | Done | 100% | 2024-02-29 | 2024-03-01 | 2024-03-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-22 | 2024-11-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3250 | 2024-03-21 | 18-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
164 | 2310-4GGSM-4G#RO-TDE075-0412 | 0 | EQP New Site 4G LTE 900 10 Mhz (GSM Activation) | Add Antenna and RRU and module BBU | TDE075 | Change 3 |  |  | TERNATE | #N/A | #N/A | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-03-04 | Done | Done |  | Done | 100% | 2024-03-04 | 2024-03-15 | 2024-03-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-28 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-04 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3250 | 2024-03-21 | 2024-07-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
165 | 2310-ADSTR-4G#RO-MRW239-0311 | 0 | EQP Add Sector LTE 2300 Massive Mimo | Add RRU and Module BBU | MRW239 | IMIP-LHMI |  |  | PALU | -2.8598 | 122.1581 | YPTT | 2026-11-23 |  | 2023 | 2023 | [34 empty] | Partner | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2023-11-20 | Done | Done |  | Done | 100% | 2023-11-20 | 2023-11-20 | 2023-11-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-11-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-23 | 2024-04-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2347 | 3-Dec-23 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
166 | 2310-ADSTR-4G#RO-MRW247-0313 | 0 | EQP Add Sector LTE 2300 Massive Mimo | Add RRU and Module BBU | MRW247 | HCAI2Renom |  |  | PALU | -2.8642 | 122.1756 | YPTT | 2026-11-23 |  | 2023 | 2023 | [34 empty] | Partner | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2023-11-18 | Done | Done |  | Done | 100% | 2023-11-18 | 2023-11-18 | 2023-11-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-11-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-23 | 2024-04-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2347 | 3-Dec-23 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
167 | 2310-MODRN-4G#RO-KDI090-0062 | 0 | BBU Modernization | Swap Module BBU | KDI090 | Padaleu-TBG |  | NY Ineom Dismantle | KENDARI | -3.9986 | 122.5208 | YPTT | October-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 1 | VBPD2P(2) | 0 | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),DCPD7(1),BPN2(2),BPQ(2),CCE1B(2),SA(1),PM5(2),FA0(1),CR0(2)MCB 63A(3) | [6 empty] | partner | MAMAN | Done Productivity 100 % |  |  |  |  | 2023-11-14 | Done | Done |  | Done | 100% | 2023-11-14 | 2023-11-14 | 2023-11-14 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-11-18 |  | Done Tagging |  | Done Tagging | Work Not Start | NY Tag Dismantle | [10 empty] | 2025-01-06 | 2025-01-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2215 | 2023-11-23 | 2025-01-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
168 | 2310-MODRN-4G#RO-KDI207-0069 | 0 | BBU Modernization | Swap Module BBU | KDI207 | MCRKampusUnhalu |  | NY Ineom Dismantle | KENDARI | -4.0073 | 122.5279 | YPTT | October-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 1 | VBPD2P(1) | 0 | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),FA0(1),PM5(2),SA(1),CCE1B(1),BPN2(3),CR0(2) | [6 empty] | Partner | MAMAN | Done Productivity 100 % |  |  |  |  | 2023-11-15 | Done | Done |  | Done | 100% | 2023-11-15 | 2023-11-15 | 2023-11-15 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-11-15 |  | Done Tagging |  | Done Tagging | Work Not Start | NY Tag Dismantle | [10 empty] | 2025-01-06 | 2025-01-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2215 | 2023-11-23 | 2025-01-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
169 | 2310-NNE4G-4G#RO-ADL155-1445 | 0 | EQP New NE 4G LTE 2300 40 Mhz | Add RRU and Module BBU | ADL155 | MMRanomeeto-DMT |  | ALL CLOSE | KENDARI | -4.0521 | 122.4517 | YPTT | October-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8998G S2300 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Partner | MAMAN | Done Productivity 90 % |  |  |  |  | 2023-11-14 | Done | Done |  | Done | 100% | 2023-11-14 | 2023-11-16 | 2023-11-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-11-17 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-11-24 | 12-Dec-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2130 | 2023-11-18 | 17-Dec-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
170 | 2310-NNE4G-4G#RO-ADL158-1446 | 0 | EQP New NE 4G LTE 2300 40 Mhz | Add RRU and Module BBU | ADL158 | PoeaBombana-TBG |  | ALL CLOSE | KENDARI | -4.7815 | 122.0497 | YPTT | October-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8998G S2300 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Partner | MAMAN | Done Productivity 90 % |  |  |  |  | 2023-11-21 | Done | Done |  | Done | 100% | 2023-11-21 | 2023-11-22 | 2023-11-22 | Connected | Connected |  | 01-Passed | 01-Passed | no Need | 2023-11-22 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2023-11-29 | 9-Dec-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2130 | 2023-11-18 | 17-Dec-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
171 | 2310-NNE4G-4G#RO-BAU115-1485 | 0 | EQP New NE 4G LTE 2300 40 Mhz | Add RRU and Module BBU | BAU115 | PasarWajo-BTC |  |  | KENDARI | -5.5101 | 122.8411 | YPTT | October-23 |  | 2023 | 2023 | [34 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2024-01-29 | Done | Done |  | Done | 100% | 2024-01-29 | 2024-01-29 | 2024-01-30 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-31 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-04-28 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2911 | 2024-02-02 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
172 | 2310-NNE4G-4G#RO-BIT017-1448 | 0 | EQP New Site 4G LTE 2300 40 Mhz | Swap Antenna and Add RRU and Module BBU | BIT017 | Rinondoran |  |  | MANADO | #N/A | #N/A | YPTT | July-24 |  | 2024 | 2024 | [28 empty] | DMT | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Sulaiman | Done Productivity 100 % |  |  |  |  | 2025-02-13 | Done | Done | 2025-02-15 | Done | 100% | 2025-02-13 | 2025-02-13 | 2025-02-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-20 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6054 | 2025-02-25 | 2025-04-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
173 | 2310-NNE4G-4G#RO-COI151-1429 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Swap Antenna and Add RRU and Module BBU | COI151 | CombatARRNumana |  |  | KENDARI | -5.3563 | 123.5562 | YPTT | October-23 |  | 2023 | 2023 |  |  | TBXLHA 6 Port | 1 | 1 | R8852E S2100 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | TDQ 4 Port | 1 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Partner | RUSLAN | Done Productivity 90 % |  |  |  |  | 2023-11-11 | Done | Done |  | Done | 100% | 2023-11-11 | 2023-11-12 | 2023-11-12 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 8-Dec-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 08-May-25 | 9-Dec-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2130 | 2023-11-18 | 17-Dec-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
174 | 2310-NNE4G-4G#RO-COI225-1430 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Swap Antenna and Add RRU and Module BBU | COI225 | CombatARRSaronsongSukur |  |  | MANADO | #N/A | #N/A | YPTT | October-23 |  | 2023 | 2023 |  |  |  | 1 | 1 | R8852E S2100 | 1 | [9 empty] | 1 |  |  |  | TDQ-182020DE-65F | 1 | 1 | [6 empty] | 2023-11-13 | Done Req ZTE |  |  |  | Partner | Aditia | Done Productivity 90 % |  |  |  |  | 28-Oct-23 | Done | Done |  | Done | 100% | 28-Oct-23 | 31-Oct-23 | 31-Oct-23 | Connected | Connected |  | 01-Passed | 01-Passed | 2023-11-01 | 2023-11-01 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-11-23 | 2023-11-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2020 | 2023-11-14 | 17-Dec-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
175 | 2310-NNE4G-4G#RO-KDI104-1456 | 0 | EQP New NE 4G LTE 2300 40 Mhz | Swap Antenna and Add RRU and Module BBU | KDI104 | MandongaMallKendari-MSD |  | ALL CLOSE | KENDARI | -3.9643 | 122.519 | YPTT | October-23 |  | 2023 | 2023 |  |  | Mobi 10 Port | 1 | 1 | R8998G S2300 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | DBXLH 4 port | 1 | 1 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Partner | MAMAN | Done Productivity 90 % |  |  |  |  | 2023-11-12 | Done | Done |  | Done | 100% | 2023-11-12 | 2023-11-13 | 2023-11-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-11-13 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2023-11-24 | 5-Dec-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2130 | 2023-11-18 | 17-Dec-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | NY Upload | Invoiced 100%
176 | 2310-NNE4G-4G#RO-UPD279-1388 | 0 | New NE 4G+5G 2.3G TMM 64TR | Add iMacro and Swap Module BBU | UPD279 | TBG Manggala Antang |  |  | MAKASSAR | -516297 | 119498 | YPTT | October-23 |  | 2023 | 2023 | [34 empty] | Partner | Muslimin | Done Productivity 100 % |  |  |  |  | 26-Oct-23 | Done | Done |  | Done | 100% | 26-Oct-23 | 27-Oct-23 | 27-Oct-23 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2023-11-04 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-07-30 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2020 | 2023-11-14 | 2024-09-12 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
177 | 2310-NNE5G-5G#RO-COI097-0033 | 0 | EQP New NE 5G DS 2100 20 Mhz | Swap RRU | COI097 | CombatMICMorowali |  |  | PALU | #N/A | #N/A | YPTT | 2026-11-23 |  | 2023 | 2023 | [34 empty] | Partner | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2023-11-15 | Done | Done |  | Done | 100% | 2023-11-15 | 2023-11-17 | 2023-11-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-11-17 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 01-Oct-24 | 4-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2215 | 2023-11-23 | 9-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
178 | 2310-NNE5G-5G#RO-MRW072-0036 | 0 | EQP New NE 5G DS 2100 20 Mhz | Swap RRU and Module BBU | MRW072 | IMIPFerrochromeFactory |  |  | PALU | -2.8272 | 122.1681 | YPTT | October-23 |  | 2023 | 2023 | [34 empty] | Partner | Herianto | Done Productivity 100 % |  |  |  |  | 2023-11-15 | Done | Done |  | Done | 100% | 2023-11-15 | 2023-11-16 | 2023-11-17 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2023-11-17 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 00-Jan-00 | 10-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2215 | 2023-11-23 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
179 | 2310-NNE5G-5G#RO-MRW107-0042 | 0 | EQP New NE 5G DSS 2100 20 Mhz | Add RRU and Swap Module BBU | MRW107 | IMIPGuestHouse |  |  | PALU | -2.8156 | 122.1667 | YPTT | October-23 |  | 2023 | 2023 | [34 empty] | Partner | Herianto | Done Productivity 100 % |  |  |  |  | 2023-11-18 | Done | Done |  | Done | 100% | 2023-11-18 | 2023-11-23 | 2023-11-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-11-25 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 00-Jan-00 | 10-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2347 | 3-Dec-23 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
180 | 2310-NNE5G-5G#RO-UPX074-0018 | 0 | EQP New NE 5G NR 2300 30 Mhz 64T64R | Add iMacro and Swap Module BBU | UPX074 | DMT MCP Inspeksi PAM |  |  | MAKASSAR | -5.165 | 119.5008 | YPTT | October-23 |  | 2023 | 2023 | [34 empty] | Partner | Ashan Kamal | Done Productivity 100 % |  |  |  |  | 2023-11-24 | Done | Done |  | Done | 100% | 2023-11-24 | 2023-11-25 | 2023-11-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-11-27 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-07-30 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2347 | 3-Dec-23 | 2024-09-12 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
181 | 2310-U8T8R-4G#RO-UPD209-0140 | 0 | EQP Upgrade BW LTE 2300 20 Mhz 8T8R | Swap Antenna and Module BBU and Add RRU | UPD209 | SKP Nipa-Nipa |  |  | MAKASSAR | -5.1578 | 119.4916 | YPTT | October-23 |  | 2023 | 2023 | [34 empty] | Partner | Muslimin | Done Productivity 100 % |  |  |  |  | 28-Oct-23 | Done | Done |  | Done | 100% | 28-Oct-23 | 30-Oct-23 | 30-Oct-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-11-07 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 14-Dec-23 | 27-Dec-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2020 | 2023-11-14 | 2024-02-02 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
182 | 2310-UMIMO-4G#RO-COI097-0019 | 0 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | COI097 | CombatMICMorowali |  |  | PALU | -2.8364 | 122.1646 | YPTT | 2026-11-23 |  | 2023 | 2023 | [34 empty] | Partner | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2023-11-15 | Done | Done |  | Done | 100% | 2023-11-15 | 2023-11-17 | 2023-11-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-11-17 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 07-Aug-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2215 | 2023-11-23 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
183 | 2310-UMIMO-4G#RO-MRW072-0028 | 0 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU and Swap Module BBU | MRW072 | IMIPFerrochromeFactory |  |  | PALU | -2.8272 | 122.1681 | YPTT | 2026-11-23 |  | 2023 | 2023 | [34 empty] | Partner | Herianto | Done Productivity 100 % |  |  |  |  | 2023-11-15 | Done | Done |  | Done | 100% | 2023-11-15 | 2023-11-16 | 2023-11-17 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2023-11-17 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 00-Jan-00 | 10-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2347 | 3-Dec-23 | 16-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
184 | 2310-UMIMO-4G#RO-MRW099-0022 | 0 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Module BBU | MRW099 | BDMMessBlokM |  |  | PALU | -2.8242 | 122.1654 | YPTT | 2026-11-23 |  | 2023 | 2023 | [34 empty] | Partner | Herlianto Ali Sahfi | Done Productivity 100 % |  |  |  |  | 2023-11-15 | Done | Done |  | Done | 100% | 2023-11-15 | 2023-11-19 | 2023-11-19 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2023-11-19 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 00-Jan-00 | 10-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2215 | 2023-11-23 | 16-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
185 | 2310-UMIMO-4G#RO-MRW107-0023 | 0 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Module BBU | MRW107 | IMIPGuestHouse |  |  | PALU | -2.8156 | 122.1667 | YPTT | 2026-11-23 |  | 2023 | 2023 | [34 empty] | Partner | Herianto | Done Productivity 90 % |  |  |  |  | 2023-11-18 | Done | Done |  | Done | 100% | 2023-11-18 | 2023-11-23 | 2023-11-24 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2023-11-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 00-Jan-00 | 10-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2347 | 3-Dec-23 | 16-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
186 | 2310-UMIMO-4G#RO-MRW158-0014 | 0 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Module BBU | LBA049 | DMT Wanatiara |  |  | TERNATE | -1.4716 | 127.4453 | YPTT | May-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | ahmad | Done Productivity 100 % |  |  |  |  | 17-May-25 | Done | Done | 19-May-25 | Done | 100% | 17-May-25 | 18-May-25 | 19-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 13-May-25 |  | Done Tagging |  | Done Tagging | 21-May-25 | Done Tagging | Done Tagging | Work Not Start | [8 empty] | 2025-07-24 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6512 | 29-May-25 | 19-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
187 | 2310-UMIMO-4G#RO-MRW218-0005 | 0 | EQP Upgrade L2300 Massive Mimo | Add RRU and Module BBU | MRW218 | IMIPWalsinLabota |  |  | PALU | -2.8776 | 122.1716 | YPTT | 2026-11-23 |  | 2023 | 2023 | [34 empty] | Partner | Herlianto Ali Sahfi | Done Productivity 100 % |  |  |  |  | 2023-11-18 | Done | Done |  | Done | 100% | 2023-11-18 | 2023-11-18 | 2023-11-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-11-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-22 | 2024-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2347 | 3-Dec-23 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
188 | 2310-UMIMO-4G#RO-MRW230-0008 | 0 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU and Module BBU | MRW230 | HCAI-IMIP |  |  | PALU | -2.9049 | 122.0105 | YPTT | 2026-11-23 |  | 2023 | 2023 | [34 empty] | Partner | Herlianto Ali Sahfi | Done Productivity 100 % |  |  |  |  | 2023-11-17 | Done | Done |  | Done | 100% | 2023-11-17 | 2023-11-17 | 2023-11-17 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-11-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 10-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2347 | 3-Dec-23 | 16-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
189 | 2310-UMIMO-4G#RO-MRW237-0009 | 0 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU and Module BBU | MRW237 | NewMessLabota2IMIP |  |  | PALU | -2.8737 | 122.1678 | YPTT | 2026-11-23 |  | 2023 | 2023 | [34 empty] | Partner | Herdianto | Done Productivity 100 % |  |  |  |  | 2023-11-17 | Done | Done |  | Done | 100% | 2023-11-17 | 2023-11-17 | 2023-11-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-11-24 |  | Done Tagging |  | Done Tagging | pending asset storing | [11 empty] | 2024-04-19 | 2024-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2215 | 2023-11-23 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
190 | 2310-UMIMO-4G#RO-MRW249-0010 | 0 | EQP Upgrade L2300 Massive Mimo | Add RRU and Module BBU | MRW249 | NewMessDCI |  |  | PALU | -2.8774 | 122.1544 | YPTT | 2026-11-23 |  | 2023 | 2023 | [34 empty] | Partner | Herianto | Done Productivity 100 % |  |  |  |  | 2023-11-27 | Done | Done |  | Done | 100% | 2023-11-27 | 2023-11-28 | 2023-11-28 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-11-28 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-18 | 2024-04-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2516 | 13-Dec-23 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
191 | 2310-UMIMO-4G#RO-MRW251-0011 | 0 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU and Module BBU | MRW251 | PLTU-DCI |  |  | PALU | -2.8761 | 122.1589 | YPTT | 2026-11-23 |  | 2023 | 2023 | [34 empty] | Partner | Herdianto | Done Productivity 100 % |  |  |  |  | 2023-11-15 | Done | Done |  | Done | 100% | 2023-11-15 | 2023-11-16 | 2023-11-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2023-11-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-22 | 2024-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2215 | 2023-11-23 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
192 | 2310-UMIMO-4G#RO-MRW903-0012 | 0 | EQP Upgrade L2300 Massive Mimo | Add RRU and Swap Module BBU | MRW903 | IMIPITSSDXSI1 |  |  | PALU | -2.8355 | 122.1737 | YPTT | 2026-11-23 |  | 2023 | 2023 | [34 empty] | Partner | Herdianto | Done Productivity 100 % |  |  |  |  | 2023-11-19 | Done | Done |  | Done | 100% | 2023-11-19 | 2023-11-19 | 2023-11-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2023-11-22 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-04-19 | 2024-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2347 | 3-Dec-23 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
193 | 2311-ADSTR-4G#RO-ADL080-0338 | 0 | EQP Add Sector LTE 2100 20 Mhz | Swap Antenna and RRU | ADL080 | Pudambu-DMT |  | ALL CLOSE | KENDARI | -4.1868 | 122.0893 | YPTT | December-23 |  | 2023 | 2023 |  |  | Prose 10 port | 1 | 1 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | DBXLH 4 port | 1 | 1 | No Need | 0 | R8872A S1800 | 1 | SFP 2,5G (2) | [6 empty] | Partner | NUSMIN SAMIL | Done Productivity 100 % |  |  |  |  | 15-Dec-23 | Done | Done |  | Done | 100% | 15-Dec-23 | 15-Dec-23 | 15-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 16-Dec-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-01-22 | 2024-01-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2687 | 27-Dec-23 | 2024-02-02 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
194 | 2311-ADSTR-4G#RO-ADL261-0316 | 0 | EQP Add Sector LTE 2300 40 Mhz | Swap Antenna and Reconfigure RRU With Add Jumper Cable for Add Sector | ADL261 | Lantari Jaya-TBG |  | ALL CLOSE | KENDARI | -4.6158 | 122.0048 | YPTT | December-23 |  | 2023 | 2023 |  |  | Prose 10 port | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | TBXLHA 6 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Partner | NUSMIN SAMIL | Done Productivity 100 % |  |  |  |  | 10-Dec-23 | Done | Done |  | Done | 100% | 10-Dec-23 | 10-Dec-23 | 10-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 11-Dec-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-01-22 | 2024-01-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2518 | 13-Dec-23 | 2024-02-02 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
195 | 2311-ADSTR-4G#RO-ADL274-0354 | 0 | EQP Add Sector LTE 1800 20 Mhz | Add Antenna and RRU | ADL274 | PT. PAG 1 |  | ALL CLOSE | KENDARI | -4.5845 | 121.8798 | YPTT | December-23 |  | 2023 | 2023 |  |  | Prose 10 port | 1 | 1 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | PT. PAG | [5 empty] | Partner | NUSMIN SAMIL | Done Productivity 100 % |  |  |  |  | 08-Dec-23 | Done | Done | 08-Dec-23 | Done | 100% | 08-Dec-23 | 08-Dec-23 | 08-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 11-Dec-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-04 | 2025-03-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2518 | 13-Dec-23 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
196 | 2311-ADSTR-4G#RO-BAU075-0317 | 0 | EQP Add Sector LTE 900 5 Mhz | Add RRU | BAU075 | Wakeakea-STP |  | ALL CLOSE | KENDARI | -5.288 | 122.5034 | YPTT | December-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-01-08 | Done | Done |  | Done | 100% | 2024-01-08 | 2024-01-08 | 2024-01-08 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-16 | 2024-01-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2860 | 2024-01-23 | 2024-02-02 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
197 | 2311-NNE4G-4G#RO-LBA085-1508 | 0 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | LBA085 | Bukit Tinggi Harita |  |  | TERNATE | -1.5115 | 127.4288 | YPTT | December-23 |  | 2023 | 2023 | [28 empty] | TELKOMSEL | Release | Release |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-01-13 | Done | Done | 2024-01-15 | Done | 100% | 2024-01-13 | 2024-01-13 | 2024-01-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 15-May-24 | 15-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2860 | 2024-01-23 | 17-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
198 | 2311-NNE5G-5G#RO-TDO429-0042 | 0 | EQP New Site 4G LTE 2100 5G NR | Swap Module BBU | TDO429 | DMT PULISAN LIKUPANG |  |  | MANADO | #N/A | #N/A | YPTT | December-23 |  | 2023 | 2023 | [28 empty] | DMT | Release | Release |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 06-Dec-23 | Done | Done |  | Done | 100% | 06-Dec-23 | 06-Dec-23 | 11-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 6-Dec-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 29-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2518 | 13-Dec-23 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
199 | 2311-UPBWL-4G#4029-BAU114-6808 | 0 | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU | BAU114 | Lakudo-STP |  | ALL CLOSE | KENDARI | -5.3179 | 122.5291 | YPTT | December-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800 | 1 | SFP 6,144G (2) | [6 empty] | YPTT | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-01-06 | Done | Done |  | Done | 100% | 2024-01-06 | 2024-01-06 | 2024-01-06 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-07 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 02-May-24 | 2024-02-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2837 | 2024-01-17 | 2024-02-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
200 | 2311-UPBWL-4G#4029-KKA055-6819 | 0 | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU | KKA055 | Lalembuu-TBG |  | ALL CLOSE | KENDARI | -4.3654 | 122.0093 | YPTT | December-23 |  | 2023 | 2023 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800 | 1 | SFP 10G(2) | [6 empty] | Partner | NUSMIN SAMIL | Done Productivity 100 % |  |  |  |  | 14-Dec-23 | Done | Done |  | Done | 100% | 14-Dec-23 | 14-Dec-23 | 14-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 14-Dec-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-01-18 | 2024-01-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2688 | 27-Dec-23 | 2024-01-31 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
201 | 2311-UPBWL-4G#4029-LBA082-6823 | 0 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU | LBA082 | PT.HPALObiHaritaKonstruksi |  |  | TERNATE | -1.5483 | 127.4195 | YPTT | December-23 |  | 2023 | 2023 | [28 empty] | TELKOMSEL | Release | Release |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-01-05 | Done | Done | 2024-01-05 | Done | 100% | 2024-01-05 | 2024-01-05 | 2024-01-05 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | July-26 | Done Tagging | July-26 | Done Tagging | waiting tiket | [11 empty] | 15-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2837 | 2024-01-17 | 18-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
202 | 2311-UPBWL-4G#RO-COI168-6873 | 0 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU and Swap Module BBU | COI168 | Combat Kawasi |  |  | TERNATE | -1.5346 | 127.4225 | YPTT | December-23 |  | 2023 | 2023 | [28 empty] | TELKOMSEL | Release | Release |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-01-07 | Done | Done | 2024-01-08 | Done | 100% | 2024-01-07 | 2024-01-08 | 2024-01-08 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-01-24 |  | Done Tagging |  | Done Tagging | [12 empty] | 15-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2860 | 2024-01-23 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
203 | 2311-UPBWL-4G#RO-LBA052-6875 | 0 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU | LBA052 | Smelter HJF |  |  | TERNATE | -1.5664 | 127.4216 | YPTT | December-23 |  | 2023 | 2023 | [28 empty] | TELKOMSEL | Release | Release |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-01-03 | Done | Done | 2024-01-03 | Done | 100% | 2024-01-03 | 2024-01-03 | 2024-01-03 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-05 |  | Done Tagging |  | Done Tagging | [12 empty] | 15-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2837 | 2024-01-17 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
204 | 2311-UPBWL-4G#RO-LBA073-6876 | 0 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Module BBU | LBA073 | KawasiLama-GPS |  |  | TERNATE | -1.5772 | 127.4423 | YPTT | December-23 |  | 2023 | 2023 | [28 empty] | PT. GPS Kawasi | Release | Release |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-01-16 | Done | Done | 2024-01-17 | Done | 100% | 2024-01-16 | 2024-01-17 | 2024-01-17 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | July-26 | Done Tagging | July-26 | Done Tagging | [12 empty] | 15-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2860 | 2024-01-23 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
205 | 2311-UPBWL-4G#RO-LBA080-6878 | 0 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Module BBU | LBA080 | Harita Losari |  |  | TERNATE | -1.5265 | 127.4143 | YPTT | December-23 |  | 2023 | 2023 | [28 empty] | TELKOMSEL | Release | Release |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-01-09 | Done | Done | 2024-01-22 | Done | 100% | 2024-01-09 | 2024-01-09 | 2024-01-22 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-01-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-06-19 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2860 | 2024-01-23 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
206 | 2312-4GDCS-4G#RO-COI546-0283 | Acceleration CP#1 2024 | EQP New NE 4G LTE 1800 20 Mhz | Swap Antenna and Add RRU and Module BBU | COI546 | COMBAT PANGGONA RAYA |  |  | PALU | -0.86907 | 119.8948 | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | Partner | ALEX | Done Productivity 100 % |  |  |  |  | 30-Dec-23 | Done | Done |  | Done | 100% | 30-Dec-23 | 31-Dec-23 | 31-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-12 |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 2024-03-13 | 2024-03-14 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
207 | 2312-4GDCS-4G#RO-MRW364-0288 | Acceleration CP#1 2024 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | MRW364 | EMA HARAPAN |  |  | PALU | -2.2466 | 121.7282 | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-01-19 | Done | Done | 2024-01-21 | Done | 100% | 2024-01-19 | 2024-01-20 | 2024-01-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-11-21 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-26 | 2024-02-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 2024-03-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
208 | 2312-4GDCS-4G#RO-NTI317-0291 | Acceleration CP#1 2024 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | SSU013 | Permanenisasi SSU053 |  | HI Done by GIT in Pare but PO mapping to Ternate due to PLN issue and imp by YPTT at acceptor (Mapping site), PR to GIT_PO No : S1ID2023070105WBF-981 & S1ID2023070105WBF-2428 | TERNATE | #N/A | #N/A | YPTT | May-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-04-30 | Done | Done | 05-May-25 | Done | 100% | 2025-04-30 | 06-May-25 | 06-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 13-May-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 15-May-25 | 27-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9550 | 2026-04-13 | 2025-07-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Workoad 100%
209 | 2312-4GGSM-4G#RO-BAU289-0450 | Acceleration CP#1 2024 | EQP New NE 4G LTE 900 10 Mhz 4T4R | Add RRU and Module BBU | BAU289 | DMT Palatiga |  | ALL CLOSE | KENDARI | -5.4771 | 122.6169 | YPTT | January-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R8852E S9000 | 3 | 0 | 0 | VBPd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-01-06 | Done | Done | 2024-01-06 | Done | 100% | 2024-01-06 | 2024-01-06 | 2024-01-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-29 | 2024-03-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
210 | 2312-4GGSM-4G#RO-LBA114-0434 | Acceleration CP#1 2024 | EQP New NE 4G LTE 900 10 Mhz | Add RRU and Module BBU | LBA114 | HARITA BANDARA SOLIGI 2 |  |  | TERNATE | -1.648 | 127.4147 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-02-06 | Done | Done | 2024-02-06 | Done | 100% | 2024-02-06 | 2024-02-06 | 2024-02-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-13 | 2024-03-14 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
211 | 2312-4GGSM-4G#RO-MRW252-0435 | Acceleration CP#1 2024 | EQP New NE 4G LTE 900 10 MHz | Add RRU and Module BBU | LBA127 | ONC Smelter 2 |  |  | TERNATE | #N/A | #N/A | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-03-03 | Done | Done | 2025-03-04 | Done | 100% | 2025-03-03 | 2025-03-04 | 2025-03-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-18 | 2025-03-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6094 | 2025-03-06 | 2025-06-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
212 | 2312-4GGSM-4G#RO-PAL434-0439 | Acceleration CP#1 2024 | EQP New NE 4G LTE 900 10 MHz | Add RRU and Module BBU | PAL434 | DMT MERPATI DENGELO |  |  | PALU | #N/A | #N/A | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | ALEX | Done Productivity 100 % |  |  |  |  | 2024-01-06 | Done | Done |  | Done | 100% | 2024-01-06 | 2024-01-06 | 2024-01-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 01-Oct-24 | 2024-01-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 2024-02-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
213 | 2312-4GGSM-4G#RO-TDE014-0444 | Acceleration CP#1 2024 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | TDE014 | Dokiri |  |  | TERNATE | #N/A | #N/A | YPTT | January-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-08 | Done | Done |  | Done | 100% | 2024-01-08 | 2024-01-10 | 2024-01-10 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-01-11 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-02-24 | 2024-02-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 2024-03-10 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
214 | 2312-4GGSM-4G#RO-TDE032-0445 | Acceleration CP#1 2024 | EQP New NE 4G LTE 900 10 MHz | Add RRU and Module BBU | TDE032 | Protelindo Tidore Selatan |  |  | TERNATE | #N/A | #N/A | YPTT | January-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-23 | Done | Done |  | Done | 100% | 2024-01-23 | 2024-01-23 | 2024-01-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-15 | 2024-02-21 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3191 | 2024-03-08 | 2024-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
215 | 2312-4GGSM-4G#RO-TER048-0446 | Acceleration CP#1 2024 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | TER048 | FLEXI KALUMATA |  |  | TERNATE | 0.77021 | 127.3641 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-30 | Done | Done | 2024-01-30 | Done | 100% | 2024-01-30 | 2024-01-30 | 2024-01-30 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-03-07 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-20 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3190 | 2024-03-08 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
216 | 2312-ADSTR-4G#RO-KKA031-0381 | Acceleration CP#1 2024 | EQP Add Sector LTE 900 10 MHz | Add Antenna and RRU and Module BBU | KKA031 | Rep. Panre |  | Pending Tag Dismantle | KENDARI | -3.8611 | 121.3239 | YPTT | January-24 |  | 2024 | 2024 |  |  | Prose 10 port | 1 | 1 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | UBPG3(1) | [6 empty] | Partner | NUSMIN SAMIL | Done Productivity 100 % |  |  |  |  | 24-Dec-23 | Done | Done |  | Done | 100% | 24-Dec-23 | 25-Dec-23 | 25-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 25-Dec-23 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2024-03-21 | 2024-03-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 3-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
217 | 2312-ADSTR-4G#RO-LBA013-0367 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Add Sector LTE | Swap RRU | LBA013 | Rep.Kayoa |  |  | TERNATE | -0.0040833 | 127.4584 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-01-29 | Done | Done | 2024-01-29 | Done | 100% | 2024-01-29 | 2024-01-29 | 2024-01-29 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-01-30 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 03-Oct-25 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3176 | 2024-03-07 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
218 | 2312-ADSTR-4G#RO-SKG019-0389 | Acceleration CP#1 2024 | EQP Add Sector LTE | Add RRU | SKG019 | DMT KEERA 2 |  |  | MAKASSAR | -3.7451 | 120.3663 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-01-04 | Done | Done | 2024-01-05 | Done | 100% | 2024-01-04 | 2024-01-04 | 2024-01-05 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-04 | 2024-04-03 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
219 | 2312-ADSTR-4G#RO-SKG029-0390 | Acceleration CP#1 2024 | EQP Add Sector LTE | Reconfigure RRU With Add Jumper Cable and FO Kit for Add Sector | SKG029 | DMT ONGKOE |  |  | MAKASSAR | -3.9547 | 119.9428 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | Partner | Muh Asdi | Done Productivity 100 % |  |  |  |  | 29-Dec-23 | Done | Done |  | Done | 100% | 29-Dec-23 | 29-Dec-23 | 29-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-31 | 2024-04-03 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
220 | 2312-ADSTR-4G#RO-SKG037-0391 | Acceleration CP#1 2024 | EQP Add Sector LTE | Add RRU | SKG037 | DMT BULETE |  |  | MAKASSAR | -3.7181 | 120.4027 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-01-04 | Done | Done | 2024-01-06 | Done | 100% | 2024-01-04 | 2024-01-06 | 2024-01-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-04 | 2024-04-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
221 | 2312-ADSTR-4G#RO-SKG051-0430 | Acceleration CP#1 2024 | EQP Add Sector LTE | Swap RRU | SKG051 | E_SKG051M41_Lalliseng-DMT |  |  | MAKASSAR | -3.8985 | 120.2805 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | Partner | Fhandi | Done Productivity 100 % |  |  |  |  | 30-Dec-23 | Done | Done |  | Done | 100% | 30-Dec-23 | 30-Dec-23 | 30-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-11 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-03-21 | 2024-03-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 2024-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
222 | 2312-ADSTR-4G#RO-SKG145-0443 | Acceleration CP#1 2024 | EQP Add Sector LTE | Swap RRU | SKG145 | E_SKG145M41_LagosiPammana-TBG |  |  | MAKASSAR | -4.15 | 120.1595 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | Partner | Fhandi | Done Productivity 100 % |  |  |  |  | 29-Dec-23 | Done | Done |  | Done | 100% | 29-Dec-23 | 29-Dec-23 | 29-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-12 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-03-21 | 2024-03-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 2024-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
223 | 2312-ADSTR-4G#RO-SKG165-0371 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Add Sector LTE | Swap RRU | SKG165 | TawaroeMakmur-TBG |  |  | MAKASSAR | -4.0182 | 120.265 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | Partner | Muh Asdi | Done Productivity 100 % |  |  |  |  | 17-Dec-23 | Done | Done |  | Done | 100% | 17-Dec-23 | 17-Dec-23 | 17-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 18-Dec-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-02-20 | 2024-02-21 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2689 | 27-Dec-23 | 2024-03-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
224 | 2312-ADSTR-4G#RO-TDE033-0445 | Acceleration CP#1 2024 | EQP Add Sector LTE | Swap RRU | TDE033 | Protelindo Ome Utara |  |  | TERNATE | 0.70956 | 127.3821 | YPTT | January-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-31 | Done | Done | 2024-01-31 | Done | 100% | 2024-01-31 | 2024-01-31 | 2024-01-31 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-02 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 05-Oct-24 | 15-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3190 | 2024-03-08 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
225 | 2312-ADSTR-4G#RO-TDE045-0431 | Acceleration CP#1 2024 | EQP Add Sector LTE | Swap antenna and RRU | TDE045 | MMObaUtaraSofifi-DMT |  |  | TERNATE | 0.73769 | 127.5583 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Risal | Done Productivity 100 % |  |  |  |  | 2024-01-18 | Done | Done | 2024-01-19 | Done | 100% | 2024-01-18 | 2024-01-20 | 2024-01-20 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-19 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-20 | 2024-07-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
226 | 2312-ADSTR-4G#RO-TDE059-0393 | Acceleration CP#1 2024 | EQP Add Sector LTE | Swap RRU | TDE059 | DMT FANAHA |  |  | TERNATE | 0.4865 | 127.569 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Risal | Done Productivity 100 % |  |  |  |  | 2024-01-22 | Done | Done | 2024-01-22 | Done | 100% | 2024-01-22 | 2024-01-22 | 2024-01-22 | Connected | Connected |  | 03-NY SM | 01-Passed | Passed | 2024-02-14 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 27-May-24 | 27-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-03-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
227 | 2312-ADSTR-4G#RO-TDE069-0446 | Acceleration CP#1 2024 | EQP Add Sector LTE | Swap RRU | TDE069 | Gura-bunga |  |  | TERNATE | 0.67346 | 127.4197 | YPTT | January-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-25 | Done | Done | 2024-01-26 | Done | 100% | 2024-01-25 | 2024-01-26 | 2024-01-26 | Connected | Connected |  | 03-NY SM | 01-Passed | Passed | 2024-02-02 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 2024-06-20 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3191 | 2024-03-08 | 2024-03-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
228 | 2312-ADSTR-4G#RO-TDO287-0447 | Acceleration CP#1 2024 | EQP Add Sector LTE | Swap Antenna and RRU | TDO287 | ISATKombi-DMT |  |  | MANADO | 1.2364 | 124.977 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-01-26 | Done | Done | 2024-01-26 | Done | 100% | 2024-01-26 | 2024-01-26 | 2024-01-26 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-29 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 2024-06-20 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3191 | 2024-03-08 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
229 | 2312-ADSTR-4G#RO-TER021-0418 | Acceleration CP#1 2024 | EQP Add Sector LTE | Add RRU | TER021 | Maliaro |  |  | TERNATE | 0.78275 | 127.3785 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-19 | Done | Done | 2024-01-19 | Done | 100% | 2024-01-19 | 2024-01-19 | 2024-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-27 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-17 | 2024-04-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
230 | 2312-ADSTR-4G#RO-TER053-0419 | Acceleration CP#1 2024 | EQP Add Sector LTE | Swap Antenna and Reconfigure RRU With Add Jumper Cable and FO Kit for Add Sector | TER053 | HotelCorner |  |  | TERNATE | 0.78496 | 127.3827 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-19 | Done | Done | 2024-01-19 | Done | 100% | 2024-01-19 | 2024-01-19 | 2024-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-03-17 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-13 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
231 | 2312-ADSTR-4G#RO-TER069-0362 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Add Sector LTE | Swap Antenna and Add RRU | TER069 | TBG DUFA DUFA |  |  | TERNATE | 0.81444 | 127.3876 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-04 | Done | Done | 2024-01-04 | Done | 100% | 2024-01-04 | 2024-01-04 | 2024-01-04 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-03-31 | 2024-04-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
232 | 2312-ADSTR-4G#RO-TER091-0420 | Acceleration CP#1 2024 | EQP Add Sector LTE | Reconfigure RRU With Add Jumper Cable for Add Sector | TER091 | ManggaDuaUtara-PTI |  |  | TERNATE | 0.77464 | 127.3826 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Risal | Done Productivity 100 % |  |  |  |  | 2024-01-06 | Done | Done | 2024-01-06 | Done | 100% | 2024-01-06 | 2024-01-06 | 2024-01-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 27-May-24 | 27-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
233 | 2312-ADSTR-4G#RO-TER127-0426 | Acceleration CP#1 2024 | EQP Add Sector LTE | Add Antenna and RRU | TER127 | BandaraSultanBabullah-TBG |  |  | TERNATE | 0.83141 | 127.3772 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-13 | Done | Done | 2024-01-13 | Done | 100% | 2024-01-13 | 2024-01-13 | 2024-01-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 17-May-24 | 19-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
234 | 2312-ADSTR-4G#RO-TER130-0398 | Acceleration CP#1 2024 | EQP Add Sector LTE | Reconfigure RRU With Add Jumper Cable and FO Kit for Add Sector | TER130 | TBG MCP HASAN BOSOERI |  |  | TERNATE | 0.79219 | 127.3872 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-06 | Done | Done | 2024-01-06 | Done | 100% | 2024-01-06 | 2024-01-06 | 2024-01-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-17 | 2024-04-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
235 | 2312-ADSTR-4G#RO-TER136-0399 | Acceleration CP#1 2024 | EQP Add Sector LTE | Swap RRU | TER136 | MCR SEROJA TERNATE |  |  | TERNATE | 0.76281 | 127.3691 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Risal | Done Productivity 100 % |  |  |  |  | 2024-01-07 | Done | Done | 2024-01-07 | Done | 100% | 2024-01-07 | 2024-01-07 | 2024-01-07 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-01-09 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-05 | 7-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
236 | 2312-ADSTR-4G#RO-TER182-0400 | Acceleration CP#1 2024 | EQP Add Sector LTE | Add RRU and Module BBU | TER182 | DMT MALL JATILAND |  |  | TERNATE | 0.79217 | 127.3904 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-19 | Done | Done | 2024-01-18 | Done | 100% | 2024-01-19 | 2024-01-19 | 2024-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-27 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-27 | 2024-04-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
237 | 2312-ADSTR-4G#RO-UNH068-0374 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Add Sector LTE 2100 20 Mhz | Swap RRU | UNH068 | DMT Puriala |  | ALL CLOSE | KENDARI | -4.1114 | 122.0846 | YPTT | January-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8852E S1800 | 1 | SFP 10G(2) | [6 empty] | Partner | NUSMIN SAMIL | Done Productivity 100 % |  |  |  |  | 22-Dec-23 | Done | Done |  | Done | 100% | 22-Dec-23 | 23-Dec-23 | 23-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 23-Dec-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-02-29 | 2024-03-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 2024-03-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
238 | 2312-MSCTR-4G#RO-KKA100-0123 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Upgrade Multisector LTE 2100 | Add Antenna and RRU | KKA100 | Protelindo Poros Kolaka Bombana |  | ALL CLOSE | KENDARI | -4.1975 | 121.9094 | YPTT | January-24 |  | 2024 | 2024 |  |  | Mobi 4 Port | 1 | 1 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Partner | NUSMIN SAMIL | Done Productivity 100 % |  |  |  |  | 20-Dec-23 | Done | Done |  | Done | 100% | 20-Dec-23 | 21-Dec-23 | 21-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 21-Dec-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-29 | 2024-03-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 2024-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
239 | 2312-MSCTR-4G#RO-LBA007-0132 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Upgrade Multisector LTE | Add RRU and Antenna | LBA007 | Kayoa-DMT |  |  | TERNATE | 0.01583 | 127.4064 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-01-20 | Done | Done | 2024-01-22 | Done | 100% | 2024-01-20 | 2024-01-22 | 2024-01-22 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-26 | 2024-02-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
240 | 2312-MSCTR-4G#RO-LBA067-0133 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Upgrade Multisector LTE | Add Antenna and RRU | LBA067 | Laluin-DMT |  |  | TERNATE | -0.040446 | 127.4263 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-01-16 | Done | Done | 2024-01-16 | Done | 100% | 2024-01-16 | 2024-01-16 | 2024-01-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-17 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-26 | 2024-02-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
241 | 2312-MSCTR-4G#RO-PLP085-0125 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Upgrade Multisector LTE L2100 | Add Antenna and RRU | PLP085 | DMT BINTURU |  |  | PARE PARE | -354435 | 120316 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | Partner | Muh Asdi | Done Productivity 100 % |  |  |  |  | 21-Dec-23 | Done | Done |  | Done | 100% | 21-Dec-23 | 22-Dec-23 | 22-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 26-Dec-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 10-Tagging New Asset & SM ATP Done, Wait BAPA | PO Confirmed | S1ID2023070102WBF1-3026 | 2024-02-20 |  | #N/A |  | Done Upload | Invoiced 100%
242 | 2312-MSCTR-4G#RO-PLP085-0140 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Upgrade Multisector LTE L2100 | Add Antenna and Swap RRU | PLP085 | E_PLP085M41_Binturu-DMT |  |  | PARE PARE | -3544787 | 120315546 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | Partner | Muh Asdi | Done Productivity 100 % |  |  |  |  | 21-Dec-23 | Done | Done |  | Done | 100% | 21-Dec-23 | 22-Dec-23 | 22-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 26-Dec-23 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-02-21 | 2024-02-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
243 | 2312-MSCTR-4G#RO-TER072-0126 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Upgrade Multisector LTE | Add Antenna and Swap RRU | TER072 | TBG SANTIONG TERNATE |  |  | TERNATE | 0.78949 | 127.3875 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-02 | Done | Done | 2024-01-03 | Done | 100% | 2024-01-02 | 2024-01-03 | 2024-01-03 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-01-12 |  | Done Tagging |  | Done Tagging | [12 empty] | 2024-07-05 | 8-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 15-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
244 | 2312-NNE4G-4G#RO-ADL274-1713 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | ADL274 | PT. PAG 1 |  | Pending Tag Dismantle | KENDARI | -4.5845 | 121.8798 | YPTT | January-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R8978 S2300 | 1 | 0 | 1 | VBPdop(1),VBPD2P(1) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),FA0(1),PM5(2),CCE1B(1)CR0(2),BPN2(3) | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-01-12 | Done | Done | 2024-01-12 | Done | 100% | 2024-01-12 | 2024-01-12 | 2024-01-12 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-14 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2024-07-24 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
245 | 2312-NNE4G-4G#RO-BAU116-1572 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | BAU116 | Villa Pantai Nirwana |  | ALL CLOSE | KENDARI | -5.5211 | 122.565 | YPTT | January-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 2 | 0 | 1 | VBPd0p(),VBPd2p(1) | 0 | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),BPN2(2),PM5(2),CCE1B(1),CR0(2),FA0(1) | [6 empty] | YPTT | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-01-07 | Done | Done | 2024-01-07 | Done | 100% | 2024-01-07 | 2024-01-07 | 2024-01-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-10 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 05-Aug-24 | 15-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
246 | 2312-NNE4G-4G#RO-BAU130-1573 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | BAU130 | DMT MCP Wangkanapi |  | ALL CLOSE | KENDARI | -5.4657 | 122.615 | YPTT | January-24 |  | 2024 | 2024 |  |  | Prose 10 port | 1 | 1 | R9614 S2300 | 1 | 0 | 1 | VBPd0p(),VBPd2p(1) | 0 | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | TBXLHA 6 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | BBU(1),PM5(2),CR0(1),FS5(1),CCE1b(1),BPN2(2),FA0(1) | [6 empty] | YPTT | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-01-04 | Done | Done |  | Done | 100% | 2024-01-04 | 2024-01-05 | 2024-01-05 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-11 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2024-02-20 | 2024-02-21 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 2024-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
247 | 2312-NNE4G-4G#RO-BGA003-1530 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU | BGA003 | DMT Non 3T Bumi Lapero |  | ALL CLOSE | KENDARI | -4.7124 | 123.0668 | YPTT | January-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8852E S1800 | 1 | SFP 10G(2) | [6 empty] | YPTT | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-01-17 | Done | Done | 2024-01-17 | Done | 100% | 2024-01-17 | 2024-01-17 | 2024-01-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-17 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2024-07-22 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
248 | 2312-NNE4G-4G#RO-BIT017-1567 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2100 20 MHz | Swap Antenna and RRU | BIT017 | Rinondoran |  |  | MANADO | 1.6014 | 125.127 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | PT. Djaya Sukses Pratama | Nopik | Done Productivity 100 % |  |  |  |  | 2024-01-05 | Done | Done | 2024-01-07 | Done | 100% | 2024-01-05 | 2024-01-07 | 2024-01-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-12 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-03-05 | 6-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 8-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
249 | 2312-NNE4G-4G#RO-BIT801-1531 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU | BIT801 | DMT BATU PUTIH BAWAH |  |  | MANADO | #N/A | #N/A | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | PT. DJAYA SUKSES PRATAMA | Nopik | Done Productivity 100 % |  |  |  |  | 29-Dec-23 | Done | Done |  | Done | 100% | 29-Dec-23 | 29-Dec-23 | 29-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 30-Dec-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-12 | 2024-06-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 2024-03-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
250 | 2312-NNE4G-4G#RO-COI101-1519 | Acceleration CP#1 2024 | EQP New NE 4G LTE 1800 20 MHz | Add RRU | ADL004 | Lapulu Tinanggea-TBG |  | ALL CLOSE | KENDARI | -4.4787 | 122.2578 | YPTT | June-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-07-05 | Done | Done | 2024-07-05 | Done | 100% | 2024-07-05 | 2024-07-05 | 2024-07-05 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-09 | 2024-09-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4492 | 2024-07-30 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
251 | 2312-NNE4G-4G#RO-COI397-1509 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP New NE 4G LTE 2300 20 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | LBA123 | Kampung Makian |  |  | TERNATE | -0.64885 | 127.4907 | YPTT | December-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 14-Dec-24 | Done | Done | 14-Dec-24 | Done | 100% | 14-Dec-24 | 14-Dec-24 | 14-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 14-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 18-Dec-24 | 2025-01-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5722 | 24-Dec-24 | 2025-03-04 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
252 | 2312-NNE4G-4G#RO-KKA159-1599 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | KKA159 | Anugerah Samaturu |  | Pending Tag Dismantle | KENDARI | -3.9303 | 121.331 | YPTT | January-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 2 | 0 | 1 | VBPD0P(1),VBPD2P(1) | 0 | VSWD1(1) | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),FAN(1),PM5(2),CCE1B(1),CR0(1),BPN2(1) | [6 empty] | Partner | NUSMIN SAMIL | Done Productivity 100 % |  |  |  |  | 29-Dec-23 | Done | Done |  | Done | 100% | 29-Dec-23 | 30-Dec-23 | 30-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-10 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2024-02-17 | 2024-02-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 2024-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
253 | 2312-NNE4G-4G#RO-KKA194-1600 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | KKA194 | TBG Pasar Lambai |  | ALL CLOSE | KENDARI | -3.6315 | 120.9783 | YPTT | January-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 2 | 0 | 0 | VBPd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | Partner | NUSMIN SAMIL | Done Productivity 100 % |  |  |  |  | 30-Dec-23 | Done | Done |  | Done | 100% | 30-Dec-23 | 31-Dec-23 | 31-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 31-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-10 | 2024-01-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 2024-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
254 | 2312-NNE4G-4G#RO-LBA009-1603 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Module BBU and Add RRU | LBA009 | DMT REPEATER SAKETA |  |  | TERNATE | -0.31831 | 127.7528 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Risal | Done Productivity 100 % |  |  |  |  | 2024-01-31 | Done | Done | 2024-01-31 | Done | 100% | 2024-01-31 | 2024-01-31 | 2024-01-31 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-05 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 2024-06-19 | 2024-07-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3190 | 2024-03-08 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
255 | 2312-NNE4G-4G#RO-LBA018-1604 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Add RRU and Module BBU | LBA018 | DMT JIKO |  |  | TERNATE | #N/A | #N/A | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-03-20 | Done | Done |  | Done | 100% | 2024-03-20 | 2024-03-20 | 2024-03-20 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-03-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-19 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5724 | 24-Dec-24 | 2025-04-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
256 | 2312-NNE4G-4G#RO-LBA041-1605 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | LBA041 | DMT MADOPOLO BARAT |  |  | TERNATE | #N/A | #N/A | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-02-08 | Done | Done |  | Done | 100% | 2024-02-08 | 2024-02-10 | 2024-02-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-10 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-19 | 2024-09-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
257 | 2312-NNE4G-4G#RO-LBA108-1717 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | LBA108 | DesaKawasi1-HARITA |  |  | TERNATE | -1.5409 | 127.4087 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-01-23 | Done | Done | 2024-01-23 | Done | 100% | 2024-01-23 | 2024-01-23 | 2024-01-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-30 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-17 | 8-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
258 | 2312-NNE4G-4G#RO-LBA109-1727 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | LBA109 | Harita Kawasi 2 |  |  | TERNATE | -1.5635 | 127.4151 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-01-24 | Done | Done | 2024-01-24 | Done | 100% | 2024-01-24 | 2024-01-24 | 2024-01-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-17 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-18 | 8-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 19-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
259 | 2312-NNE4G-4G#RO-LBA110-1726 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | LBA110 | SmelterArea-HARITA |  |  | TERNATE | -1.5556 | 127.425 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-01-28 | Done | Done | 2024-01-28 | Done | 100% | 2024-01-28 | 2024-01-28 | 2024-01-28 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-01 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-18 | 2-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3191 | 2024-03-08 | 19-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
260 | 2312-NNE4G-4G#RO-LBA111-1606 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | LBA111 | Harita Mining Area |  |  | TERNATE | -1.5697 | 127.4589 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-01-26 | Done | Done | 2024-01-26 | Done | 100% | 2024-01-26 | 2024-01-26 | 2024-01-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-17 | 8-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 19-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
261 | 2312-NNE4G-4G#RO-LBA112-1607 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | LBA112 | Harita Desa Eco Village |  |  | TERNATE | -1.5909 | 127.4174 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-01-27 | Done | Done | 2024-01-27 | Done | 100% | 2024-01-27 | 2024-01-27 | 2024-01-27 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-16 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-17 | 14-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 19-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
262 | 2312-NNE4G-4G#RO-MAS012-1611 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | MAS012 | DMT BAEBUNTA BAJO |  |  | PARE PARE | -2.6744 | 120.3478 | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-01-10 | Done | Done | 2024-01-11 | Done | 100% | 2024-01-10 | 2024-01-10 | 2024-01-11 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-15 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 05-Oct-24 | 13-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
263 | 2312-NNE4G-4G#RO-MAS106-1613 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | MAS106 | DMT MUNTE TANA LILI |  |  | PARE PARE | -2.6775 | 120.6014 | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-01-12 | Done | Done |  | Done | 100% | 2024-01-12 | 2024-01-12 | 2024-01-12 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-23 | 2024-01-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 2024-02-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
264 | 2312-NNE4G-4G#RO-MDO367-1740 | Acceleration CP#1 2024 | 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Swap Module BBU | MDO367 | MC Fekon Unsrat |  |  | MANADO | 1.4596 | 124.8263 | YPTT | January-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-01-19 | Done | Done | 2024-01-20 | Done | 100% | 2024-01-19 | 2024-01-20 | 2024-01-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-30 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 14-May-24 | 15-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
265 | 2312-NNE4G-4G#RO-MGN017-1742 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Swap Module BBU | MGN017 | Lahu-DMT |  |  | MANADO | 4.4571 | 126.8633 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Noris | Done Productivity 100 % |  |  |  |  | 2024-01-12 | Done | Done | 2024-01-15 | Done | 100% | 2024-01-12 | 2024-01-16 | 2024-01-16 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-31 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 23-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
266 | 2312-NNE4G-4G#RO-MGN050-1619 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | MGN050 | DMT N3T_NIAMPAK |  |  | MANADO | #N/A | #N/A | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Noris | Done Productivity 100 % |  |  |  |  | 2024-01-09 | Done | Done |  | Done | 100% | 2024-01-09 | 2024-01-09 | 2024-01-09 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-30 | 2024-01-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 2024-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
267 | 2312-NNE4G-4G#RO-MRW377-1512 | Acceleration CP#1 2024 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | MRW377 | MakartiJaya-DMT |  |  | PALU | -2.8914 | 122.1745 | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-01-01 | Done | Done | 2024-01-01 | Done | 100% | 2024-01-01 | 2024-01-01 | 2024-01-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-29 | 2024-03-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 2024-03-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
268 | 2312-NNE4G-4G#RO-MRW918-1749 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | MRW918 | Labota2-DMT |  |  | PALU | -2.8673 | 122.1824 | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-01-18 | Done | Done | 2024-01-18 | Done | 100% | 2024-01-18 | 2024-01-18 | 2024-01-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 04-May-24 | 10-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
269 | 2312-NNE4G-4G#RO-MRW922-1750 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | MRW922 | Bahomoahi-TBG |  |  | PALU | -2.7077 | 122.0056 | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-01-06 | Done | Done | 2024-01-06 | Done | 100% | 2024-01-06 | 2024-01-06 | 2024-01-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-17 | 2024-04-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
270 | 2312-NNE4G-4G#RO-NTI042-1627 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | NTI042 | DMT N3T Wagari |  | ALL CLOSE | KENDARI | -5.189 | 122.9185 | YPTT | January-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 2 | 0 | 0 | VBPd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-01-13 | Done | Done | 2024-01-13 | Done | 100% | 2024-01-13 | 2024-01-14 | 2024-01-14 | Connected | Connected |  | 01-Passed | 01-Passed | no Need | 2024-01-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-25 | 8-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 16-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
271 | 2312-NNE4G-4G#RO-NTI337-1633 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | NTI337 | DMT NON 3T TULAK TALLU |  |  | PARE PARE | #N/A | #N/A | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-01-16 | Done | Done |  | Done | 100% | 2024-01-16 | 2024-01-16 | 2024-01-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-16 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-23 | 2024-01-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-02-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
272 | 2312-NNE4G-4G#RO-PAL099-1751 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | PAL099 | DMT Watusampu |  |  | PALU | -0.81361 | 119.8097 | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | ALEX | Done Productivity 100 % |  |  |  |  | 2024-01-26 | Done | Done | 2024-01-27 | Done | 100% | 2024-01-26 | 2024-01-27 | 2024-01-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-31 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 14-May-24 | 16-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3176 | 2024-03-07 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
273 | 2312-NNE4G-4G#RO-PAL268-1646 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Module BBU and Add RRU | PAL268 | UNTAD 2 KEDOKTERAN |  |  | PALU | -0.84286 | 119.8967 | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | ALEX | Done Productivity 100 % |  |  |  |  | 31-Dec-23 | Done | Done |  | Done | 100% | 31-Dec-23 | 2024-01-02 | 2024-01-02 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-17 |  | Done Tagging |  | Done Tagging | Done Tagging | Done | Done | 2026-01-17 | Done Inbound |  | 2026-01-19 |  | HC |  |  |  | 13-May-24 | 16-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
274 | 2312-NNE4G-4G#RO-PLP181-1650 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | PLP181 | DMT MCP SAKOTAE PALOPO |  |  | PARE PARE | -2.996 | 120.1876 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-01-20 | Done | Done | 2024-01-21 | Done | 100% | 2024-01-20 | 2024-01-20 | 2024-01-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-22 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 05-Oct-24 | 15-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3191 | 2024-03-08 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
275 | 2312-NNE4G-4G#RO-PLP192-1720 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | PLP192 | E_PLP192M41_MCPRatulangiTemmalebba-LSP |  |  | PARE PARE | -296464 | 120182 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-01-03 | Done | Done | 2024-01-03 | Done | 100% | 2024-01-03 | 2024-01-03 | 2024-01-03 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-15 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 05-Oct-24 | 15-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
276 | 2312-NNE4G-4G#RO-RBI001-1721 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | RBI001 | Permanenisasi COI767 - CombatFUNKabaena |  | ALL CLOSE | KENDARI | -5.2631 | 121.7952 | YPTT | January-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R8978 S2300 | 1 | 0 | 0 | VBPd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-01-03 | Done | Done | 2024-01-04 | Done | 100% | 2024-01-03 | 2024-01-04 | 2024-01-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-04 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 04-May-24 | 2024-04-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3026 | 2024-02-20 | 2024-11-08 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
277 | 2312-NNE4G-4G#RO-SKG002-1661 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | SKG002 | DMT SIWA |  |  | MAKASSAR | -3.6961 | 120.4117 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | Partner | Fhandi | Done Productivity 100 % |  |  |  |  | 30-Dec-23 | Done | Done |  | Done | 100% | 30-Dec-23 | 31-Dec-23 | 31-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-03 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-02-05 | 2024-03-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
278 | 2312-NNE4G-4G#RO-SKG004-1662 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | SKG004 | BELAWA |  |  | MAKASSAR | -3.9943 | 119.9363 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 31-Dec-23 | Done | Done |  | Done | 100% | 31-Dec-23 | 31-Dec-23 | 2024-01-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-09 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 13-May-24 | 16-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
279 | 2312-NNE4G-4G#RO-SKG038-1759 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Swap Module BBU | SKG038 | E_SKG038M41_Simpellu-DMT |  |  | MAKASSAR | -3.7497 | 120.2911 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-01-01 | Done | Done | 2024-01-01 | Done | 100% | 2024-01-01 | 2024-01-01 | 2024-01-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-10 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 14-May-24 | 16-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
280 | 2312-NNE4G-4G#RO-SKG055-1663 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | SKG055 | PROTELINDO MATTIROWALIE |  |  | MAKASSAR | -3.6926 | 120.3876 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-01-04 | Done | Done | 2024-01-07 | Done | 100% | 2024-01-04 | 2024-01-04 | 2024-01-05 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-10 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 13-May-24 | 15-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
281 | 2312-NNE4G-4G#RO-SKG064-1664 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | SKG064 | DELTACOMSEL MAJAULUNG |  |  | MAKASSAR | -4.1193 | 120.1177 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-01-17 | Done | Done |  | Done | 100% | 2024-01-17 | 2024-01-17 | 2024-01-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-19 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-02-17 | 2024-02-21 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
282 | 2312-NNE4G-4G#RO-SKG098-1665 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | SKG098 | TBG KAMPUNG MENGE |  |  | MAKASSAR | -4.0028 | 119.9363 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | Partner | Muh Asdi | Done Productivity 100 % |  |  |  |  | 30-Dec-23 | Done | Done |  | Done | 100% | 30-Dec-23 | 30-Dec-23 | 30-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-08 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-02-05 | 2024-02-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 2024-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
283 | 2312-NNE4G-4G#RO-SKG145-1666 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | SKG145 | TBG LAGOSI PAMMANA |  |  | MAKASSAR | -4.15 | 120.1595 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | Partner | Fhandi | Done Productivity 100 % |  |  |  |  | 29-Dec-23 | Done | Done |  | Done | 100% | 29-Dec-23 | 29-Dec-23 | 29-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-16 | 2024-01-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
284 | 2312-NNE4G-4G#RO-SKG165-1667 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | SKG165 | TBG TAWAROE MAKMUR |  |  | MAKASSAR | -4.0194 | 120.2815 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-01-01 | Done | Done |  | Done | 100% | 2024-01-01 | 2024-01-01 | 2024-01-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-02 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-02-17 | 2024-02-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
285 | 2312-NNE4G-4G#RO-SKG201-1668 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | SKG201 | TBG PANTAI TIMUR |  |  | MAKASSAR | -4.1875 | 120.3567 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-01-03 | Done | Done |  | Done | 100% | 2024-01-03 | 2024-01-03 | 2024-01-03 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-04 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-01 | 2024-01-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 2024-02-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
286 | 2312-NNE4G-4G#RO-TDE013-1680 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | TDE013 | Protelindo Bobo Toloa |  |  | TERNATE | #N/A | #N/A | YPTT | January-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-24 | Done | Done |  | Done | 100% | 2024-01-24 | 2024-01-24 | 2024-01-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-16 | 2024-03-13 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3191 | 2024-03-08 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
287 | 2312-NNE4G-4G#RO-TDE033-1681 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | TDE033 | Protelindo Ome Utara |  |  | TERNATE | #N/A | #N/A | YPTT | January-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-25 | Done | Done |  | Done | 100% | 2024-01-25 | 2024-01-25 | 2024-01-25 | Connected | Connected |  | 03-NY SM | 01-Passed | Passed | 2024-02-02 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 2024-02-20 | 2024-02-21 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3191 | 2024-03-08 | 2024-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
288 | 2312-NNE4G-4G#RO-TDE045-1682 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | TDE045 | DMT MM OBA UTARA SOFIFI |  |  | TERNATE | #N/A | #N/A | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Risal | Done Productivity 100 % |  |  |  |  | 2024-01-18 | Done | Done |  | Done | 100% | 2024-01-18 | 2024-01-20 | 2024-01-20 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-18 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-02-20 | 2024-02-21 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
289 | 2312-NNE4G-4G#RO-TDE061-1683 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | TDE061 | TBG KOSA |  |  | TERNATE | #N/A | #N/A | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Risal | Done Productivity 100 % |  |  |  |  | 2024-01-25 | Done | Done |  | Done | 100% | 2024-01-25 | 2024-01-25 | 2024-01-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-08 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-02-20 | 2024-02-21 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
290 | 2312-NNE4G-4G#RO-TDE069-1684 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | TDE069 | Gura-bunga |  |  | TERNATE | #N/A | #N/A | YPTT | January-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-25 | Done | Done |  | Done | 100% | 2024-01-25 | 2024-01-26 | 2024-01-26 | Connected | Connected |  | 03-NY SM | 01-Passed | Passed | 2024-02-02 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 2024-02-20 | 2024-02-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3191 | 2024-03-08 | 2024-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
291 | 2312-NNE4G-4G#RO-TDO011-1685 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Module BBU and Add RRU | TDO011 | DMT TATELU |  |  | MANADO | 1.5711 | 125.003 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | PT. Djaya Sukses Pratama | nopik | Done Productivity 100 % |  |  |  |  | 30-Dec-23 | Done | Done |  | Done | 100% | 30-Dec-23 | 31-Dec-23 | 31-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-04 |  | Done Tagging |  | Done Tagging | Work Not Start | waiting tiket dismantle | [10 empty] | 13-May-24 | 15-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
292 | 2312-NNE4G-4G#RO-TER102-1689 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | TER102 | MC Sasa Gambesi |  |  | TERNATE | 0.75811 | 127.3241 | YPTT | May-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | ahmad | Done Productivity 100 % |  |  |  |  | 21-May-25 | Done | Done | 22-May-25 | Done | 100% | 21-May-25 | 22-May-25 | 22-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 13-May-25 |  | Done Tagging |  | Done Tagging | Work Not Start | Work Not Start | Work Not Start | Work Not Start | [8 empty] | 2025-07-26 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6770 | 2025-06-21 | 2025-07-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
293 | 2312-NNE4G-4G#RO-THN019-1691 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | THN019 | DMT KENDAHE |  |  | MANADO | #N/A | #N/A | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Haris | Done Productivity 100 % |  |  |  |  | 2024-01-24 | Done | Done |  | Done | 100% | 2024-01-24 | 2024-01-24 | 2024-01-24 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2024-02-09 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 2024-03-05 | 6-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 8-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
294 | 2312-NNE4G-4G#RO-THN072-1763 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | THN072 | TolaMarange-TBG |  |  | MANADO | 3.6388 | 125.5305 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Haris | Done Productivity 100 % |  |  |  |  | 2024-01-10 | Done | Done | 2024-01-13 | Done | 100% | 2024-01-10 | 2024-01-13 | 2024-01-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-07 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-04-18 | 2024-04-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
295 | 2312-NNE4G-4G#RO-THN087-1693 | Acceleration CP#1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | THN087 | DMT MM BUNGALAWANG |  |  | MANADO | #N/A | #N/A | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Haris | Done Productivity 100 % |  |  |  |  | 2024-01-17 | Done | Done |  | Done | 100% | 2024-01-17 | 2024-01-17 | 2024-01-17 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-30 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-05 | 7-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 13-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
296 | 2312-REENG-4G#RO-COI245-0140 | Acceleration CP#1 2024 | EQP eNode B Modular Relocation Service New NE LTE 1800 | Swap Antenna and Add RRU and Module BBU | COI245 | COMBAT RSUD KOLAKA |  | NY Tag Asset Reutilise | KENDARI | -4.0795 | 121.6109 | YPTT | January-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 0 | R8872 S1800 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 0 | TBXLHA 6 Port | 3 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-01-08 | Done | Done | 2024-01-09 | Done | 100% | 2024-01-08 | 2024-01-09 | 2024-01-09 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-10 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2025-03-03 | 2025-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 2024-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
297 | 2312-REENG-4G#RO-COI356-0156 | Acceleration CP#1 2024 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Add RRU and Module BBU | COI356 | CombatMOPLaromabatiKayoa |  |  | TERNATE | 0.12512 | 127.4441 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-03-30 | Done | Done | 2024-03-30 | Done | 100% | 2024-03-30 | 2024-03-30 | 2024-03-30 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-31 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 06-Dec-24 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
298 | 2312-REENG-4G#RO-MAS139-0145 | Acceleration CP#1 2024 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Add RRU and Module BBU | MAS139 | DMT BUNGADIDI |  |  | PARE PARE | -26189 | 120622 | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-01-08 | Done | Done | 2024-01-08 | Done | 100% | 2024-01-08 | 2024-01-08 | 2024-01-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-01-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-24 | 2024-03-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
299 | 2312-U4T4R-4G#RO-KDI028-0056 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU | KDI028 | Kaledupa |  | ALL CLOSE | KENDARI | -5.5031 | 123.7525 | YPTT | January-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800(1),R8852E S2100(1) | 2 | SFP 10G(4) | [6 empty] | Partner | RUSLAN | Done Productivity 100 % |  |  |  |  | 17-Dec-23 | Done | Done |  | Done | 100% | 17-Dec-23 | 18-Dec-23 | 18-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 20-Dec-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-02-27 | 2024-02-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2689 | 27-Dec-23 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
300 | 2312-U4T4R-4G#RO-KKA100-0073 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU | KKA100 | Protelindo Poros Kolaka Bombana |  | ALL CLOSE | KENDARI | -4.1975 | 121.9094 | YPTT | January-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800(1),R8852E S2100(1) | 2 | SFP 10G (2) | [6 empty] | Partner | NUSMIN SAMIL | Done Productivity 100 % |  |  |  |  | 20-Dec-23 | Done | Done |  | Done | 100% | 20-Dec-23 | 21-Dec-23 | 21-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 21-Dec-23 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-02-29 | 2024-03-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 2024-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
301 | 2312-U4T4R-4G#RO-LBA021-0031 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU | LBA021 | JIKOTAMO |  |  | TERNATE | -1.345 | 127.6566 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-01-04 | Done | Done | 2024-01-04 | Done | 100% | 2024-01-04 | 2024-01-04 | 2024-01-04 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-01-10 |  | Done Tagging |  | Done Tagging | [12 empty] | 2024-04-30 | 2-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 2024-06-20 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
302 | 2312-U4T4R-4G#RO-SNN004-0074 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU | ADL017 | DMT Angata |  | NY ATP & Ineom | KENDARI | -4.1377 | 122.1247 | YPTT | 2026-11-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800 (1),R8863 S2100(1) | 2 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-11-30 | Done | Done | 2024-11-30 | Done | 100% | 2024-11-30 | 2024-11-30 | 2024-11-30 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 03-Dec-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 13-Dec-24 | 16-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5726 | 24-Dec-24 | 24-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
303 | 2312-U4T4R-4G#RO-TDE003-0090 | Acceleration CP#1 2024 | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU | TDE003 | Gurabati |  |  | TERNATE | 0.62706 | 127.4205 | YPTT | January-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-08 | Done | Done | 2024-01-09 | Done | 100% | 2024-01-08 | 2024-01-09 | 2024-01-09 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-01-11 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 27-May-24 | 27-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3025 | 2024-02-20 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
304 | 2312-U4T4R-4G#RO-TDO316-0092 | Acceleration CP#1 2024 | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Dismantle RRU and Reconfigure UBR Sector-1 | TDO316 | TBG RERER |  |  | MANADO | 103879 | 12437371 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | PT. Djaya Sukses Pratama | nopik | Done Productivity 100 % |  |  |  |  | 31-Dec-23 | Done | Done |  | Done | 100% | 31-Dec-23 | 31-Dec-23 | 31-Dec-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-01 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-25 | 2024-03-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
305 | 2312-U4T4R-4G#RO-TER034-0094 | Acceleration CP#1 2024 | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU | TER034 | PROTELINDO SULAMADAHA |  |  | TERNATE | 0.85795 | 127.3448 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-21 | Done | Done | 2024-01-21 | Done | 100% | 2024-01-21 | 2024-01-21 | 2024-01-21 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-05 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 06-Dec-24 | 2024-06-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3191 | 2024-03-08 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
306 | 2312-U8T8R-4G#RO-TDE018-0142 | Acceleration CP#1 2024 | EQP Upgrade BW LTE 2300 40 - 40Mhz 8T8R | Swap Antenna and Module BBU and Add RRU | TDE018 | DMT BALE OBA |  |  | TERNATE | 0.39552 | 127.6965 | YPTT | December-23 |  | 2023 | 2023 | [28 empty] | DMT | Release | Release |  |  |  | YPTT | Risal | Done Productivity 100 % |  |  |  |  | 2024-01-26 | Done | Done | 2024-01-26 | Done | 100% | 2024-01-26 | 2024-01-26 | 2024-01-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-15 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 2024-06-13 | 2024-06-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
307 | 2312-UMIMO-4G#RO-LBA103-0044 | Acceleration CP#1 2024 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU | LBA103 | MessHJF-P2-HaritaObi |  |  | TERNATE | -1.5576 | 127.4296 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-03-16 | Done | Done | 2024-03-17 | Done | 100% | 2024-03-16 | 2024-03-16 | 2024-03-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-22 | 2024-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3262 | 2024-03-22 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
308 | 2312-UMIMO-4G#RO-TER028-0043 | Acceleration CP#1 2024 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | TER028 | DMT GAMBESI |  |  | TERNATE | 0.76005 | 127.3321 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-17 | Done | Done | 2024-01-17 | Done | 100% | 2024-01-17 | 2024-01-17 | 2024-01-17 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-03-13 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-19 | 2024-07-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
309 | 2312-UMIMO-4G#RO-TER083-0039 | Activity Non MPSL_CP1 Acceleration Capacity Issue | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU and Swap Module BBU | TER083 | PROTELINDO GAMBESI KOTA |  |  | TERNATE | 0.75791 | 127.3406 | YPTT | December-23 |  | 2023 | 2023 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-01-06 | Done | Done | 2024-01-06 | Done | 100% | 2024-01-06 | 2024-01-06 | 2024-01-06 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-01-15 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 13-May-24 | 14-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
310 | 2312-UPPWR-4G#RO-BAU076-0002 | Acceleration CP#1 2024 | EQP eNode B Power Upgrade LTE 900 | Swap RRU | BAU076 | Deltacomsel Waara Muna |  | ALL CLOSE | KENDARI | -5.4157 | 122.5823 | YPTT | January-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8862 S9000 | 1 | SFP 2,67G (2) | [6 empty] | YPTT | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-01-05 | Done | Done | 2024-01-05 | Done | 100% | 2024-01-05 | 2024-01-05 | 2024-01-05 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2024-01-05 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2024-03-21 | 2024-03-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2868 | 2024-01-24 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
311 | 2312-UPPWR-4G#RO-SKG073-0006 | Acceleration CP#1 2024 | EQP eNode B Power Upgrade | Swap RRU | SKG073 | TBG PATILA PAMMANA |  |  | MAKASSAR | -4.1812 | 120.0742 | YPTT | December-23 |  | 2023 | 2023 | [34 empty] | Partner | Muh Asdi | Done Productivity 100 % |  |  |  |  | 29-Dec-23 | Done | Done |  | Done | 100% | 29-Dec-23 | 29-Dec-23 | 29-Dec-23 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2024-01-09 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-03-22 | 2024-03-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-2869 | 2024-01-24 | 2024-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
312 | 2401-4GDCS-4G#RO-COI013-0122 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | COI013 | IAAS Combat Mess Karo |  |  | TERNATE | -1.516 | 127.4462 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-07-07 | Done | Done | 2024-07-13 | Done | 100% | 2024-07-07 | 2024-07-09 | 2024-07-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-09 | 2024-09-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4332 | 2024-07-12 | 2024-09-12 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
313 | 2401-4GDCS-4G#RO-COI015-0123 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | COI015 | IAAS Combat ONC Limonite |  |  | TERNATE | -1.5683 | 127.4259 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-07-20 | Done | Done | 2024-07-23 | Done | 100% | 2024-07-20 | 2024-07-22 | 2024-07-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-09 | 2024-09-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4492 | 2024-07-30 | 5-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
314 | 2401-4GDCS-4G#RO-COI016-0124 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | COI016 | IAAS Combat Mess & Lab Tondano |  |  | TERNATE | -1.5555 | 127.4443 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-06-30 | Done | Done | 2024-07-04 | Done | 100% | 2024-06-30 | 2024-07-02 | 2024-07-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 20-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 21-Aug-24 | 22-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4332 | 2024-07-12 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
315 | 2401-4GDCS-4G#RO-COI017-0125 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | COI017 | IAAS Combat Mess Kontruksi Central LQ |  |  | TERNATE | -1.5692 | 127.4429 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-07-17 | Done | Done | 2024-07-23 | Done | 100% | 2024-07-17 | 2024-07-18 | 2024-07-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 26-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 08-May-24 | 22-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4348 | 2024-07-15 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
316 | 2401-4GDCS-4G#RO-COI018-0126 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | COI018 | IAAS Combat MTI |  | ATP iNEoM by Comap | PALU | -2.8845 | 122.1817 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 24-May-24 | Done | Done | 30-May-24 | Done | 100% | 24-May-24 | 28-May-24 | 2024-07-28 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 11-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 26-Aug-24 | 27-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
317 | 2401-4GDCS-4G#RO-COI019-0127 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | COI019 | IAAS Combat BTIIG 1 |  | PR/PO released under WID : 2401-4GDCS-4G#RO-COI019-0127_PO No : S1ID2023070102WBF1-3969 | PALU | -2.2849 | 121.7858 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Adriyanto | [5 empty] | 2024-06-08 | Done | Done | 2024-06-08 | Done | 100% | 2024-06-08 | 2024-06-09 | 2024-09-09 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-26 | 4-Oct-24 |  | PO Confirmed | S1ID2023070102WBF1-3969 | 2024-06-14 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | NEW PO
318 | 2401-4GDCS-4G#RO-COI022-0128 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | COI022 | IAAS Combat HSM ex Wanatiara |  |  | TERNATE | 0.61466 | 127.9536 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 17-Aug-24 | Done | Done | 23-Aug-24 | Done | 100% | 17-Aug-24 | 19-Aug-24 | 27-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 12-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 24-Oct-24 | 25-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4916 | 2024-09-06 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
319 | 2401-4GDCS-4G#RO-COI026-0129 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | COI026 | IAAS Combat BTIIG 2 |  | Integrasi | PALU | -2.2566 | 121.7696 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-06-03 | Done | Done | 2024-06-04 | Done | 100% | 2024-06-03 | 2024-06-04 | 2024-09-05 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-09-15 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-23 | 2024-09-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
320 | 2401-4GDCS-4G#RO-COI036-0135 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | COI036 | IAAS Combat SJU |  |  | TERNATE | -1.7326 | 124.4564 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-07-05 | Done | Done | 2024-07-06 | Done | 100% | 2024-07-05 | 2024-07-07 | 2024-07-07 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 13 July 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-29 | 7-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4348 | 2024-07-15 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
321 | 2401-4GDCS-4G#RO-COI769-0058 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 1800 20 Mhz | Swap Antenna and Add RRU and Module BBU | COI769 | Combat MOP Sampuabalo Ambuau Indah |  | NY Tag Asset Reutilise | KENDARI | -5.434 | 123.0121 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-02-07 | Done | Done | 2024-02-08 | Done | 100% | 2024-02-07 | 2024-02-08 | 2024-02-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-09 |  | Done Tagging |  | Done Tagging | No Need | Waiting Tag Asset Reutile | [10 empty] | 16-May-24 | 16-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
322 | 2401-4GDCS-4G#RO-COI920-0030 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 1800 20 Mhz | ATP Only | COI920 | COMBAT RUSUNAWA |  | Take over closing ATP to YPTT d/t GMI no team | TERNATE | 1.0921 | 127.4789 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-02-26 | Done | Done | 2025-02-26 | Done | 100% | 2025-02-26 | 2025-02-26 | 2025-02-26 | Connected | Connected |  | 03-NY SM | 01-Passed | Work Not Start | 2025-02-26 |  | Work Not Start |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-25 | 2025-04-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9550 | 2026-04-13 | 2025-07-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Workoad 100%
323 | 2401-4GDCS-4G#RO-COI939-0069 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | COI939 | Combat CRU Langke Ereke |  | ALL CLOSE | KENDARI | -4.7662 | 123.1785 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-03-08 | Done | Done | 2024-03-09 | Done | 100% | 2024-03-08 | 2024-03-09 | 2024-03-09 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-26 | 2024-04-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
324 | 2401-4GDCS-4G#RO-DGL011-0096 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | DGL011 | Permanenisasi COI703 - Combat Fun Rujab Bupati Donggala |  |  | PALU | -0.68033 | 119.7545 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-04-08 | Done | Done | 2024-04-19 | Done | 100% | 2024-04-08 | 2024-04-10 | 2024-04-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 09-May |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 13-May-24 | 15-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
325 | 2401-4GDCS-4G#RO-KDI038-0100 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | KDI038 | DMT Matabubu |  | ALL CLOSE | KENDARI | -4001352 | 122570640 | YPTT | 2026-04-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 3 | R9224E M1821 | 3 | 1 | 1 | 0 | VBPd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 1 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-04-22 | Done | Done | 2024-04-23 | Done | 100% | 2024-04-22 | 2024-04-23 | 2024-04-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 3-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-05 | 8-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3464 | 15-May-24 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
326 | 2401-4GDCS-4G#RO-KTG027-0007 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | KTG027 | Permanenisasi COI364 - Combat Pole Pusian |  |  | MANADO | 0.6536 | 124.1683 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Sergi | Done Productivity 100 % |  |  |  |  | 2024-03-27 | Done | Done | 2024-03-26 | Done | 100% | 2024-03-27 | 2024-03-27 | 2024-03-30 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-01 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-29 | 2-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3406 | 2024-04-19 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
327 | 2401-4GDCS-4G#RO-LBA117-0035 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | LBA117 | BANDARA SOLIGI 3 |  |  | TERNATE | -1.6546 | 127.4159 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-02-11 | Done | Done | 2024-02-11 | Done | 100% | 2024-02-11 | 2024-02-11 | 2024-02-11 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-13 | 8-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
328 | 2401-4GDCS-4G#RO-MAS031-0105 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | MAS031 | Desa Laba, Kec. |  |  | PARE PARE | -2.5793 | 120.3272 | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-04-22 | Done | Done | 2024-04-24 | Done | 100% | 2024-04-22 | 2024-04-22 | 02-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 5-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 05-Aug-24 | 21-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3465 | 15-May-24 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
329 | 2401-4GDCS-4G#RO-MAS058-0010 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | MAS058 | Tamuku LUWU UTARA |  |  | PARE PARE | -2.6478 | 120.5344 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-01-27 | Done | Done | 2024-01-29 | Done | 100% | 2024-01-27 | 2024-01-27 | 2024-01-29 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-01-30 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-02 | 2024-02-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3176 | 2024-03-07 | 2024-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
330 | 2401-4GDCS-4G#RO-MRW012-0011 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | MRW012 | Permanenisasi COI396 - Onepute |  |  | PALU | -2.7374 | 122.0124 | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-01-26 | Done | Done | 2024-01-27 | Done | 100% | 2024-01-26 | 2024-01-27 | 2024-01-01 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2024-02-02 |  | Done Tagging |  | Done Tagging | [12 empty] | 2024-07-02 | 2024-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3176 | 2024-03-07 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
331 | 2401-4GDCS-4G#RO-MRW013-0012 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | MRW013 | IMIP Hotel Sejahtera |  |  | PALU | -2.7898 | 122.1158 | YPTT | January-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-01-28 | Done | Done | 2024-01-31 | Done | 100% | 2024-01-28 | 2024-01-29 | 2024-01-31 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-01 |  | Done Tagging |  | Done Tagging | [12 empty] | 02-May-24 | 2024-03-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3190 | 2024-03-08 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
332 | 2401-4GDCS-4G#RO-MRW366-0071 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | MRW366 | Badspot 5 - Pelabuhan Bahomante |  |  | PALU | -2.4379 | 121.9016 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-02-08 | Done | Done | 2024-02-08 | Done | 100% | 2024-02-08 | 2024-02-08 | 2024-02-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-29 | 2024-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
333 | 2401-4GDCS-4G#RO-PAL018-0014 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | RHA062 | DMT Wanseriwu |  | ALL CLOSE | KENDARI | -4.7936 | 122.3769 | YPTT | May-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 3 | R9224E M1821 | 3 | 1 | 1 | 0 | VBPd0P(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-04-30 | Done | Done | 10-May-24 | Done | 100% | 2024-04-30 | 01-May-24 | 01-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-17 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 20-May-24 | 2024-06-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 28-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
334 | 2401-4GDCS-4G#RO-PLP182-0085 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 1800 20 Mhz | Swap Antenna and Add RRU | PLP182 | DMT ISAT BUNTU MATABING |  |  | PARE PARE | -3.5395 | 120.4004 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Very | Done Productivity 100 % |  |  |  |  | 2024-02-29 | Done | Done | 2024-02-29 | Done | 100% | 2024-02-29 | 2024-02-29 | 2024-02-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-02 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 27-May-24 | 29-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
335 | 2401-4GDCS-4G#RO-RHA031-0112 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | RHA031 | DMT RSUD Muna - Permanenisasi COI844 - Combat Alun Alun Raha |  | ALL CLOSE | KENDARI | -4.8354 | 122.7258 | YPTT | May-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 3 | 3 | R9224E M1821 | 3 | 1 | 1 | 0 | VBPd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 17-May-24 | Done | Done | 17-May-24 | Done | 100% | 17-May-24 | 18-May-24 | 18-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 20-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-06 | 9-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
336 | 2401-4GDCS-4G#RO-SKG001-0019 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | SKG034 | DMT ALEWADENG |  |  | MAKASSAR | -3.3979 | 119.9363 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-04-03 | Done | Done | 2024-03-04 | Done | 100% | 2024-04-03 | 2024-04-03 | 15-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-16 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 28-Aug-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 16-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
337 | 2401-4GDCS-4G#RO-SKG203-0092 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | SKG203 | CEMPALAGI |  |  | MAKASSAR | -4.1254 | 120.0411 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-02-04 | Done | Done | 2024-02-05 | Done | 100% | 2024-02-04 | 2024-02-04 | 2024-02-05 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-21 | 2024-03-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
338 | 2401-4GDCS-4G#RO-TDO052-0115 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | TDO052 | Permanenisasi COI612 - Combat Malendeng Warem |  |  | MANADO | 1.4212 | 124.8114 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 08-May-24 | Done | Done | 12-May-24 | Done | 100% | 08-May-24 | 27-May-24 | 27-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-24 | 5-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 17-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
339 | 2401-4GDCS-4G#RO-TDO113-0034 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 1800 20 Mhz | Swap RRU | TDO113 | PROTELINDO LIHUNU |  |  | MANADO | 1.7589 | 125.1482 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Sergi | Done Productivity 100 % |  |  |  |  | 2024-02-22 | Done | Done | 2024-02-22 | Done | 100% | 2024-02-22 | 2024-02-23 | 2024-02-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-20 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
340 | 2401-4GDCS-4G#RO-TDO393-0062 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | TDO393 | DesaLibas-DMT |  |  | MANADO | 1.8266 | 125.1379 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-03-25 | Done | Done | 2024-03-26 | Done | 100% | 2024-03-25 | 2024-03-26 | 2024-03-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-28 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-05 | 8-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
341 | 2401-4GDCS-4G#RO-TER032-0059 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap module BBU | COI070 | COI070 CR fr Loloda |  |  | PARE PARE | -3.9761 | 119.6118 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Narfin | Done Productivity 100 % |  |  |  |  | 29-May-25 | Done | Done | 30-May-25 | Done | 100% | 29-May-25 | 30-May-25 | 30-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-07-02 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-09-02 | 2025-06-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6868 | 2025-06-30 | 6-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
342 | 2401-4GDCS-4G#RO-THN020-0116 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | THN020 | Permanenisasi COI541 - Combat FUN Perkantoran Tahuna |  |  | MANADO | 3.6048 | 125.5108 | YPTT | 2026-04-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 21-May-24 | Done | Done | 23-May-24 | Done | 100% | 21-May-24 | 23-May-24 | 2024-06-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 19 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-Oct-24 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
343 | 2401-4GDCS-4G#RO-WTG064-0120 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | WTG064 | Permanenisasi COI312 - Combat Jolle Pangkep2 |  |  | MAKASSAR | -4.3292 | 119.9802 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-03-31 | Done | Done | 2024-04-06 | Done | 100% | 2024-03-31 | 2024-04-05 | 2024-04-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-17 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-22 | 8-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
344 | 2401-4GGSM-4G#RO-ADL004-0489 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | ADL004 | Lapulu |  | ALL CLOSE | KENDARI | -4.4787 | 122.2578 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 0 | R8852E S9000 | 3 | 1 | 1 | 0 | VBPd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-03-04 | Done | Done | 2024-03-07 | Done | 100% | 2024-03-04 | 2024-03-05 | 2024-04-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 6-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 05-Oct-24 | 14-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
345 | 2401-4GGSM-4G#RO-BAU011-0496 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | BAU011 | TBG Kadolo Katapi |  | ALL CLOSE | KENDARI | -5.4662 | 122.6418 | YPTT | May-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 3 | R8852E S9000 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-04-13 | Done | Done | 2024-04-19 | Done | 100% | 2024-04-13 | 2024-04-13 | 08-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 31-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-06 | 2024-06-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3464 | 15-May-24 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
346 | 2401-4GGSM-4G#RO-BAU016-0497 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | BAU016 | Permanenisasi COI255 - Combat CRU Gonda Baru |  | ALL CLOSE | KENDARI | -5.4759 | 12272700 | YPTT | May-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 3 | 0 | R8852E S9000 | 3 | 1 | 1 | 0 | VBPd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 22-May-24 | Done | Done | 25-May-24 | Done | 100% | 22-May-24 | 23-May-24 | 26-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 24-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 06-Dec-24 | 2024-06-15 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-06-20 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
347 | 2401-4GGSM-4G#RO-BAU029-0498 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | TWA007 | Permanenisasi COI490 - Polenga Jaya |  | ALL CLOSE | KENDARI | -4.2397 | 121.9417 | YPTT | May-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 3 | 3 | R8852E S9000 | 3 | 1 | 1 | 0 | VBPd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | TBG | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 22-May-24 | Done | Done | 23-May-24 | Done | 100% | 22-May-24 | 23-May-24 | 23-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-18 | 2024-07-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 28-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
348 | 2401-4GGSM-4G#RO-BAU095-0230 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap antenna and Add RRU and Module BBU | BAU095 | Bure Bau Bau |  | Pending Tag Dismantle | KENDARI | -5.46 | 122.6224 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 1 | 0 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | TDQ 6 port | 2 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),CCE1B(1),CR0(2),BPN2(3),PM(2),SA(1) | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-02-28 | Done | 100% | 2024-02-28 | 2024-02-28 | 2024-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-03 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2024-07-08 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
349 | 2401-4GGSM-4G#RO-BAU117-0112 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz 4T4R | Swap Antenna and Add RRU and Module BBU | BAU117 | BO Star |  | Pending Tag Dismantle | KENDARI | -5.4657 | 122.6067 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 1 | 0 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | TDQ 6 port | 1 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-02-27 | Done | Done | 2024-02-27 | Done | 100% | 2024-02-27 | 2024-02-27 | 2024-02-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-04 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2024-07-22 | 2024-07-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
350 | 2401-4GGSM-4G#RO-BAU130-0452 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU | BAU130 | DMT MCP Wangkanapi |  | ALL CLOSE | KENDARI | -5.4657 | 122.615 | YPTT | February-24 |  | 2024 | 2024 |  |  | MOBI 10port | 1 | 1 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | TBXLHA 6 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-02-19 | Done | Done | 2024-02-19 | Done | 100% | 2024-02-19 | 2024-02-19 | 2024-02-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-22 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-22 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
351 | 2401-4GGSM-4G#RO-BAU132-0235 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | BAU132 | DMT Kambumbulana |  | Pending Tag Dismantle | KENDARI | -5.4998 | 122.8427 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 1 | 1 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | TBXLHA 6 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-03-02 | Done | Done | 2024-03-03 | Done | 100% | 2024-03-02 | 2024-03-03 | 2024-03-03 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-04 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2024-07-26 | 2024-07-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
352 | 2401-4GGSM-4G#RO-BAU135-0231 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap antenna and Add RRU and Module BBU | BAU135 | MC Erlangga Bau Bau |  | Pending Tag Dismantle | KENDARI | -5.4614 | 122.5964 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 1 | 0 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | TBXLHA 6 Port | 1 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-02-23 | Done | Done | 2024-02-23 | Done | 100% | 2024-02-23 | 2024-02-23 | 2024-02-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-16 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 08-Aug-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
353 | 2401-4GGSM-4G#RO-BAU137-0236 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | BAU137 | TBG Bukit Wolio Indah |  | ALL CLOSE | KENDARI | -5.466 | 122.6184 | YPTT | February-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 1 | 1 | R8852E S9000 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | Rosenberger 8 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | AISG(1) | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-02-10 | Done | Done | 2024-02-10 | Done | 100% | 2024-02-10 | 2024-02-10 | 2024-02-10 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-19 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-03-14 | 2025-03-15 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
354 | 2401-4GGSM-4G#RO-BAU181-0238 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | BAU181 | MCP Pasar Nugraha-DMT |  | ALL CLOSE | KENDARI | -5.4745 | 122.5913 | YPTT | February-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 1 | 1 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | TBXLHA 6 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-02-18 | Done | Done | 2024-02-18 | Done | 100% | 2024-02-18 | 2024-02-18 | 2024-02-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-22 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-03-03 | 2025-03-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
355 | 2401-4GGSM-4G#RO-BAU186-0113 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz 4T4R | Swap Antenna and Add RRU and Module BBU | BAU186 | MCR Benteng Keraton |  | ALL CLOSE | KENDARI | -5.4783 | 122.6012 | YPTT | February-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 1 | 1 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | TBXLHA 6 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-02-10 | Done | Done | 2024-02-10 | Done | 100% | 2024-02-10 | 2024-02-10 | 2024-02-10 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-22 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-22 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
356 | 2401-4GGSM-4G#RO-BAU191-0125 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | BAU191 | TBG MCP SMP2 Bau Bau |  | ALL CLOSE | KENDARI | -5.4689 | 122.6009 | YPTT | February-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 1 | 1 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | TBXLHA 6 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-02-11 | Done | Done | 2024-02-11 | Done | 100% | 2024-02-11 | 2024-02-11 | 2024-02-11 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-22 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 26-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
357 | 2401-4GGSM-4G#RO-BAU193-0193 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Add RRU and Module BBU | BAU193 | TBG MCP Unismuh Buton |  | ALL CLOSE | KENDARI | -5.4633 | 122.5997 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-02-11 | Done | Done | 2024-02-11 | Done | 100% | 2024-02-11 | 2024-02-11 | 2024-02-11 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-21 |  | Done Tagging |  | Done Tagging | No Need | Waiting Tag Asset Reutile | [10 empty] | 17-May-24 | 19-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
358 | 2401-4GGSM-4G#RO-BAU197-0116 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Add RRU | BAU197 | TBG MCP Sdn3 Wameo |  | ALL CLOSE | KENDARI | -5.4644 | 122.5923 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-02-19 | Done | Done | 2024-02-20 | Done | 100% | 2024-02-19 | 2024-02-19 | 2024-02-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-15 | 2024-03-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
359 | 2401-4GGSM-4G#RO-BAU201-0126 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | BAU201 | DMT MCP Waode Wau |  | Pending Tag Dismantle | KENDARI | -5.4731 | 122.5975 | YPTT | February-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 1 | 0 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | TBXLHA 6 Port | 1 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-02-23 | Done | Done | 2024-02-23 | Done | 100% | 2024-02-23 | 2024-02-23 | 2024-02-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-04 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2024-07-22 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
360 | 2401-4GGSM-4G#RO-BAU204-0194 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Add RRU and Module BBU | BAU204 | TBG MCP Cemara Wangkanapi |  | ALL CLOSE | KENDARI | -5.4633 | 122.6128 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-02-22 | Done | Done | 2024-02-11 | Done | 100% | 2024-02-22 | 2024-02-22 | 2024-02-22 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-22 |  | Done Tagging |  | Done Tagging | No Need | Waiting Tag Asset Store | [10 empty] | 17-May-24 | 19-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
361 | 2401-4GGSM-4G#RO-BAU207-0241 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | BAU207 | DMT MCP Wale Wolio |  | Pending Tag Dismantle | KENDARI | -5.4692 | 122.62 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 1 | 0 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | TBXLHA 6 Port | 1 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-02-28 | Done | 100% | 2024-02-28 | 2024-02-28 | 2024-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-04 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 29-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
362 | 2401-4GGSM-4G#RO-BAU213-0127 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | BAU213 | TBG MCP Jalan Labuke |  | ALL CLOSE | KENDARI | -5.4752 | 122.6002 | YPTT | February-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 1 | 1 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | TBXLHA 6 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-02-10 | Done | Done | 2024-02-10 | Done | 100% | 2024-02-10 | 2024-02-10 | 2024-02-10 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-22 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-26 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
363 | 2401-4GGSM-4G#RO-BAU222-0117 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Add RRU and Module BBU | BAU222 | DMT Kancina |  | ALL CLOSE | KENDARI | -5.4378 | 122.8952 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-02-18 | Done | Done | 2024-02-18 | Done | 100% | 2024-02-18 | 2024-02-18 | 2024-02-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-19 | 2024-03-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
364 | 2401-4GGSM-4G#RO-BAU224-0242 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | BAU224 | DMT Holimombo |  | ALL CLOSE | KENDARI | -5.564 | 122.8911 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-02-18 | Done | Done | 2024-02-18 | Done | 100% | 2024-02-18 | 2024-02-18 | 2024-02-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-15 | 2024-03-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
365 | 2401-4GGSM-4G#RO-BIT007-0002 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | BIT007 | Permanenisasi COI360 - Combat Manembo-nemboTangkoko |  |  | MANADO | 1.425 | 125.1168 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-04-09 | Done | Done | 2024-04-22 | Done | 100% | 2024-04-09 | 2024-04-11 | 09-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 12 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-19 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
366 | 2401-4GGSM-4G#RO-BIT028-0196 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | BIT028 | Kekenturan-DMT |  |  | MANADO | 1.4589 | 125.1933 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-02-27 | Done | Done | 2024-02-27 | Done | 100% | 2024-02-27 | 2024-02-27 | 2024-02-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-18 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-07-30 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
367 | 2401-4GGSM-4G#RO-BIT049-0232 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | BIT049 | PROTELINDO PATETEN |  |  | MANADO | 1.4545 | 125.1962 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-03-19 | Done | Done | 2024-03-19 | Done | 100% | 2024-03-19 | 2024-03-19 | 2024-03-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-20 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-07-30 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
368 | 2401-4GGSM-4G#RO-BIT052-0197 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | BIT052 | BitungTengah-PTI |  |  | MANADO | 1.4369 | 125.1337 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-02-27 | Done | Done | 2024-02-27 | Done | 100% | 2024-02-27 | 2024-02-27 | 2024-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-30 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-14 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
369 | 2401-4GGSM-4G#RO-BIT089-0233 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | BIT089 | MC TANGKILISAN |  |  | MANADO | 1.4454 | 125.1797 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-02-29 | Done | Done | 2024-02-29 | Done | 100% | 2024-02-29 | 2024-02-29 | 2024-02-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-05 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-07-30 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
370 | 2401-4GGSM-4G#RO-BIT103-0198 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap antenna and Add RRU and Module BBU | BIT103 | MCRSamuelLanguyu |  |  | MANADO | 1.4473 | 125.2055 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-02-08 | Done | Done | 2024-02-08 | Done | 100% | 2024-02-08 | 2024-02-08 | 2024-02-08 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-19 | 2024-06-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
371 | 2401-4GGSM-4G#RO-BIT110-0245 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | BIT110 | DMT MCP BITUNG BARAT DUA |  |  | MANADO | 1.4481 | 125.1872 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-03-01 | Done | Done | 2024-03-01 | Done | 100% | 2024-03-01 | 2024-03-01 | 2024-03-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-09 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-07-30 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
372 | 2401-4GGSM-4G#RO-BUA002-0006 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | BUA002 | DMT Gunung Sejuk |  | ALL CLOSE | KENDARI | -5540196 | 12269515 | YPTT | 2026-04-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 3 | 0 | R8852E S9000 | 3 | 1 | 1 | 0 | VBPd0P(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-04-29 | Done | Done | 04-May-24 | Done | 100% | 2024-04-29 | 01-May-24 | 04-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 24-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 30-May-24 | 31-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3509 | 23-May-24 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
373 | 2401-4GGSM-4G#RO-COI007-0548 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 MHz | Add Antenna and RRU and Module BBU(New Infra) | COI007 | Combat CRU Sabulakoa |  | ALL CLOSE | KENDARI | -4.0078 | 122.2697 | YPTT | June-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 2 | 3 | R8852E S9000 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-07-02 | Done | Done | 2024-07-03 | Done | 100% | 2024-07-02 | 2024-07-02 | 2024-09-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-26 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4332 | 2024-07-12 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
374 | 2401-4GGSM-4G#RO-COI160-0056 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Add RRU and Module BBU | COI160 | C_COI160M41_CombatDesa Tampa |  |  | PARE PARE | -3182379 | 120232166 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-03-19 | Done | Done | 2024-03-24 | Done | 100% | 2024-03-19 | 2024-03-20 | 2024-03-22 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-03-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-27 | 10-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3406 | 2024-04-19 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
375 | 2401-4GGSM-4G#RO-COI213-0153 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Add RRU | COI213 | COMBAT BACAN |  |  | TERNATE | -0.64239 | 127.4908 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-02-28 | Done | 100% | 2024-02-28 | 2024-02-28 | 2024-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-03-01 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-19 | 2024-07-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
376 | 2401-4GGSM-4G#RO-COI239-0128 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | COI239 | Combat RSUD Baubau |  | ALL CLOSE | KENDARI | -5.483 | 122.5919 | YPTT | February-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 1 | 1 | R8852E S9000 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | TBXLHA 6 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-02-10 | Done | Done | 2024-02-10 | Done | 100% | 2024-02-10 | 2024-02-10 | 2024-02-10 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-21 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2025-03-03 | 2025-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
377 | 2401-4GGSM-4G#RO-COI367-0436 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New Site 4G LTE 900 10 Mhz | Swap Antenna and Add RRU | COI367 | C_COI367M41_CombatMOPHuntapPombewe |  |  | PALU | -0.9865 | 119.9396 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | ALEX | Done Productivity 100 % |  |  |  |  | 2024-02-03 | Done | Done | 2024-02-03 | Done | 100% | 2024-02-03 | 2024-02-03 | 2024-02-03 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-02-07 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 2024-09-23 | 2024-09-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3190 | 2024-03-08 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
378 | 2401-4GGSM-4G#RO-COI368-0266 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New Site 4G LTE 900 10 Mhz | Add RRU and Module BBU | COI368 | Combat Arr Plan 29- MRW002 EX_COD028 |  |  | PALU | -2.5594 | 121.9618 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-02-04 | Done | Done | 2024-02-04 | Done | 100% | 2024-02-04 | 2024-02-04 | 2024-02-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2026-02-04 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-29 | 2024-04-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3190 | 2024-03-08 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
379 | 2401-4GGSM-4G#RO-COI370-0156 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New Site 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | COI370 | PLAN 5-MRW095 |  |  | PALU | -2.811963 | 122133156 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-02-08 | Done | Done | 2024-02-08 | Done | 100% | 2024-02-08 | 2024-02-08 | 2024-02-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2026-02-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-29 | 2024-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
380 | 2401-4GGSM-4G#RO-COI398-0058 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Add RRU and Module BBU | UNH005 | DMT Pohara Laosu |  | ALL CLOSE | KENDARI | -391072 | 12243258 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R8852E S9000 | 3 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-03-15 | Done | Done | 2024-03-15 | Done | 100% | 2024-03-15 | 2024-03-16 | 2024-03-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-17 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 31-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3262 | 2024-03-22 | 24-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
381 | 2401-4GGSM-4G#RO-COI541-0130 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | COI541 | CombatPerkantoranTahuna |  |  | MANADO | 3.6047 | 125.5115 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-02-17 | Done | Done | 2024-02-17 | Done | 100% | 2024-02-17 | 2024-02-17 | 2024-02-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-19 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 23-Aug-24 | 27-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
382 | 2401-4GGSM-4G#RO-COI703-0474 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Add RRU | MRW012 | Permanenisasi COI396 - Onepute |  | Req New permit Wait BA Mapping | PALU | -2.7374 | 122.0124 | YPTT | July-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 2024-07-14 | Done | Done | 2024-07-15 | Done | 100% | 2024-07-14 | 2024-07-18 | 2024-07-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 18-Dec-24 | 23-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 2025-01-07 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
383 | 2401-4GGSM-4G#RO-COI725-0131 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | COI725 | CombatFUNTamanVictory |  |  | MANADO | 1.3043 | 124.832 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-02-08 | Done | Done | 2024-02-09 | Done | 100% | 2024-02-08 | 2024-02-09 | 2024-02-09 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-19 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
384 | 2401-4GGSM-4G#RO-DGL020-0499 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | DGL020 | KolaKolaDonggala-TBG |  |  | PALU | -0.73177 | 119.7114 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-04-22 | Done | Done | 2024-04-30 | Done | 100% | 2024-04-22 | 2024-04-24 | 2024-06-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2026-07-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-24 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3464 | 15-May-24 | 13-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
385 | 2401-4GGSM-4G#RO-KKA008-0504 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | KKA008 | TOLOWE PONREWARU |  | ALL CLOSE | KENDARI | -3.8356 | 121.307 | YPTT | May-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 3 | R8852E S9000 | 3 | 1 | 1 | 0 | VBPd0P(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 14-May-24 | Done | Done | 15-May-24 | Done | 100% | 14-May-24 | 15-May-24 | 15-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-22 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
386 | 2401-4GGSM-4G#RO-KKA009-0505 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | KKA009 | Lambolemo |  | NY Ineom | KENDARI | -3.9397 | 121.3503 | YPTT | March-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 3 | R8852E S9000 | 3 | 1 | 1 | 0 | VBPd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-04-02 | Done | Done | 2024-04-08 | Done | 100% | 2024-04-02 | 2024-04-08 | 2024-04-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-23 |  | Done Tagging |  | Done Tagging | No Need | Waiting Permit | [10 empty] | 27-May-24 | 27-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
387 | 2401-4GGSM-4G#RO-KKA015-0506 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | KKA015 | Permanenisasi COI604 - Combat FUN Balandete |  | ALL CLOSE | KENDARI | -4.0615 | 121.6223 | YPTT | May-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 3 | R8852E S9000 | 3 | 1 | 1 | 0 | VBPd0P(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 06-May-24 | Done | Done | 07-May-24 | Done | 100% | 06-May-24 | 07-May-24 | 07-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 25-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 30-May-24 | 31-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
388 | 2401-4GGSM-4G#RO-KNL003-0508 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | KNL003 | Permanenisasi COI298 - Combat Fun Tompira |  |  | PALU | -2.0138 | 121.3324 | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 29-May-24 | Done | Done | 30-May-24 | Done | 100% | 29-May-24 | 30-May-24 | 31-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2026-07-18 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 08-May-24 | 7-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3509 | 23-May-24 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
389 | 2401-4GGSM-4G#RO-KTG017-0509 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | TDO028 | DMT Sonsilo |  |  | MANADO | 1.7129 | 124.9889 | YPTT | March-24 |  | 2024 | 2024 | [28 empty] | DMT | Done Req ZTE |  |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-04-28 | Done | Done | 2024-04-30 | Done | 100% | 2024-04-28 | 01-May-24 | 22-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-08 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3465 | 15-May-24 | 28-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
390 | 2401-4GGSM-4G#RO-KTG034-0010 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | KTG034 | Permanenisasi COI717 - Combat GYD Desa Manembo |  |  | MANADO | 0.77812 | 124.3481 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-03-31 | Done | Done | 2024-03-31 | Done | 100% | 2024-03-31 | 2024-04-15 | 2024-03-31 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-21 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-05 | 8-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
391 | 2401-4GGSM-4G#RO-LBA014-0510 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | LBA014 | Pertambangan Obi Anggai |  |  | TERNATE | -1.3622 | 127.7287 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 08-May-24 | Done | Done | 09-May-24 | Done | 100% | 08-May-24 | 10-May-24 | 10-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 12-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 31-May-24 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3509 | 23-May-24 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
392 | 2401-4GGSM-4G#RO-LBA023-0511 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | LBA023 | Permanenisasi MXW047 - Nain |  |  | TERNATE | -0.74515 | 127.645 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-04-30 | Done | Done | 01-May-24 | Done | 100% | 2024-04-30 | 01-May-24 | 03-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 05-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 27-May-24 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3509 | 23-May-24 | 13-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
393 | 2401-4GGSM-4G#RO-LBA024-0512 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | LBA024 | Permanenisasi COI927 - Combat Fun Perkantoran Bupati Halsel |  | All Close | TERNATE | -0.64996 | 127.5007 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-04-26 | Done | Done | 09-May-24 | Done | 100% | 2024-04-26 | 2024-04-27 | 2024-06-05 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 12 August 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 20-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3465 | 15-May-24 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
394 | 2401-4GGSM-4G#RO-LBA060-0252 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap antenna and Add RRU and Module BBU | LBA060 | TBG BABANG BACAN |  |  | TERNATE | -0.63059 | 127.6073 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-02-13 | Done | Done | 2024-02-12 | Done | 100% | 2024-02-13 | 2024-02-13 | 2024-02-13 | Connected | Connected |  | 03-NY SM | 01-Passed | Passed | 2024-02-14 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 2024-06-19 | 2024-06-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
395 | 2401-4GGSM-4G#RO-LBA091-0164 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Add RRU | LBA091 | DMT LAIWUI |  |  | TERNATE | -1.3402 | 127.6406 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-03-03 | Done | Done | 2024-03-03 | Done | 100% | 2024-03-03 | 2024-03-03 | 2024-03-03 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-04 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-22 | 2024-03-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
396 | 2401-4GGSM-4G#RO-MAS017-0014 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | MAS017 | Permanenisasi COI499 - Combat Desa Parara |  |  | PARE PARE | -2.626 | 120.1182 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-01-28 | Done | Done | 2024-02-01 | Done | 100% | 2024-01-28 | 2024-01-28 | 2024-01-31 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-02-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-13 | 2024-02-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3176 | 2024-03-07 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
397 | 2401-4GGSM-4G#RO-MDO364-0095 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | MDO364 | MCMaumbi |  |  | MANADO | 1.4655 | 124.9262 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-03-16 | Done | Done | 2024-03-19 | Done | 100% | 2024-03-16 | 2024-03-19 | 2024-03-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-04-03 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 08-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3262 | 2024-03-22 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
398 | 2401-4GGSM-4G#RO-MGN051-0175 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Add RRU and Module BBU | MGN051 | MelonguaneBarat-DMT |  |  | MANADO | 4.0003 | 126.676 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Noris | Done Productivity 100 % |  |  |  |  | 2024-02-20 | Done | Done | 2024-02-20 | Done | 100% | 2024-02-20 | 2024-02-20 | 2024-02-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-22 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-13 | 2024-03-14 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
399 | 2401-4GGSM-4G#RO-MRW104-0073 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU | MRW104 | TBG Koromatantu |  |  | PALU | -2.0369 | 121.3301 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-02-27 | Done | Done | 2024-03-01 | Done | 100% | 2024-02-27 | 18-Aug-24 | 19-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 21-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-19 | 2024-09-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
400 | 2401-4GGSM-4G#RO-OSU010-0019 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | OSU010 | Permanenisasi COI931 - Combat Fun Kisihang |  |  | MANADO | 2.3184 | 125.4418 | YPTT | January-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-01-25 | Done | Done | 2024-01-26 | Done | 100% | 2024-01-25 | 2024-01-25 | 30-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-01 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 06-May-24 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3192 | 2024-03-08 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
401 | 2401-4GGSM-4G#RO-OSU011-0020 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | TDO057 | DMT Palaes |  |  | MANADO | 1.6602 | 124.9692 | YPTT | 2026-04-24 |  | 2024 | 2024 | [28 empty] | DMT | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 04-May-24 | Done | Done | 06-May-24 | Done | 100% | 04-May-24 | 07-May-24 | 24-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 27-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-09 | 2024-09-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 90%
402 | 2401-4GGSM-4G#RO-PAL009-0428 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New Site 4G LTE 900 10 Mhz | Swap antenna and Add RRU | PAL009 | DMT Tanjung Satu |  |  | PALU | -0.90709 | 119.8856 | YPTT | February-24 |  | 2024 | 2024 | [20 empty] | 1 | [13 empty] | CV. Puri Tepule Abadi | ALEX | Done Productivity 100 % |  |  |  |  | 2024-02-09 | Done | Done | 2024-02-15 | Done | 100% | 2024-02-09 | 2024-02-09 | 2024-02-15 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-03-05 |  | Done Tagging |  | Done Tagging | Done tagging |  | Done | 2026-02-15 | 1*Antena Rosenberger 8port | [7 empty] | 2025-03-03 | 2025-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-03-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
403 | 2401-4GGSM-4G#RO-PAL136-0240 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap antenna and Add RRU | PAL136 | LereRahman-PTI |  |  | PALU | -0.89158 | 119.8347 | YPTT | February-24 |  | 2024 | 2024 | [28 empty] | IMIP | [5 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-03-10 | Done | Done | 2024-03-11 | Done | 100% | 2024-03-10 | 2024-03-11 | 2024-03-11 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-20 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-08 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
404 | 2401-4GGSM-4G#RO-PAL157-0243 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New Site 4G LTE 900 10 Mhz | Swap Antenna and Add RRU | PAL157 | ManondaDuyu-DMT |  |  | PALU | -0.90949 | 119.8444 | YPTT | February-24 |  | 2024 | 2024 | [20 empty] | 1 | [13 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-02-13 | Done | Done | 2024-02-12 | Done | 100% | 2024-02-13 | 2024-02-13 | 2024-02-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-02-15 |  | Done Tagging |  | Done Tagging | Done tagging |  | Done | 2026-02-15 | 1*Antena TDQ 4*Jumper 1*Mounting Antena 2*Bracket Mounting | [7 empty] | 2024-07-08 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
405 | 2401-4GGSM-4G#RO-PAL164-0048 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | PAL164 | DMT TALISE RUSA |  |  | PALU | -0.8781 | 119.8733 | YPTT | March-24 |  | 2024 | 2024 | [28 empty] | IMIP | [5 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-03-06 | Done | Done | 2024-03-07 | Done | 100% | 2024-03-06 | 2024-03-06 | 2024-03-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-03-31 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-06 | 2024-06-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
406 | 2401-4GGSM-4G#RO-PAL390-0262 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU | PAL390 | EBT MCP KAWATUNA |  |  | PALU | -0.90865 | 119.923 | YPTT | March-24 |  | 2024 | 2024 | [28 empty] | IMIP | [5 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-03-06 | Done | Done | 2024-03-07 | Done | 100% | 2024-03-06 | 2024-03-06 | 2024-03-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-10 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-08 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
407 | 2401-4GGSM-4G#RO-PIN022-0524 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | PIN022 | LETTA |  |  | PARE PARE | -3.5013 | 119.6451 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-01 | Done | Done | 31-May-24 | Done | 100% | 2024-06-01 | 2024-06-01 | 2024-06-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-22 | 2024-07-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3969 | 2024-06-14 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
408 | 2401-4GGSM-4G#RO-PLP021-0027 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | PLP021 | LatuppaPalopo-DMT |  |  | PARE PARE | -3.0315 | 120.1222 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-04-15 | Done | Done | 2024-04-21 | Done | 100% | 2024-04-15 | 2024-04-20 | 2024-04-21 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-05 | 10-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
409 | 2401-4GGSM-4G#RO-PLP022-0028 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | PLP022 | Permanenisasi COI472 - Combat Fun Tirowali |  |  | PARE PARE | -3.198 | 120.2647 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-02-01 | Done | Done | 2024-02-08 | Done | 100% | 2024-02-01 | 2024-02-02 | 2024-02-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-26 | 2024-03-13 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3190 | 2024-03-08 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
410 | 2401-4GGSM-4G#RO-PLP097-0250 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 900 10 MHz | Add RRU and Module BBU | PLP097 | TBG BTN LIBUKANG PERMAI |  |  | PARE PARE | -29844 | 120182 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-02-08 | Done | Done | 2024-02-08 | Done | 100% | 2024-02-08 | 2024-02-08 | 2024-02-08 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-02-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-26 | 2024-03-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
411 | 2401-4GGSM-4G#RO-PLP122-0275 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap antenna and Add RRU and Module BBU | PLP122 | N_PLP122M41_OpuAmmasangan-DMT |  |  | PARE PARE | -299526 | 120196 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-02-26 | Done | Done | 2024-02-26 | Done | 100% | 2024-02-26 | 2024-02-26 | 2024-02-26 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-04 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 28-May-24 | 29-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-06 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
412 | 2401-4GGSM-4G#RO-PLP130-0047 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | PLP130 | TBG RAMPOANG BARA |  |  | PARE PARE | -2.9505 | 120.1805 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-03-07 | Done | Done | 2024-03-07 | Done | 100% | 2024-03-07 | 2024-03-07 | 2024-03-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-09 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 28-May-24 | 29-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 2024-06-06 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
413 | 2401-4GGSM-4G#RO-PLP170-0473 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU | PLP170 | N_PLP170ML1_REP_PALO AMENSANG |  |  | PARE PARE | -285892 | 120177 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-02-16 | Done | Done | 2024-02-17 | Done | 100% | 2024-02-16 | 2024-02-17 | 2024-02-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-18 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-07-22 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
414 | 2401-4GGSM-4G#RO-PLP178-0465 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | PLP178 | E_PLP178M41_Salokoe-DMT |  |  | PARE PARE | -299221 | 120.19 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-02-17 | Done | Done | 2024-02-17 | Done | 100% | 2024-02-17 | 2024-02-17 | 2024-02-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-19 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2025-03-03 | 2025-03-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
415 | 2401-4GGSM-4G#RO-PLP188-0441 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Add RRU and Module BBU | PLP188 | N_PLP188M41_MCPTemmalebbaPalopo-TBG |  |  | PARE PARE | -295787 | 120183 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-02-09 | Done | Done | 2024-02-10 | Done | 100% | 2024-02-09 | 2024-02-10 | 2024-02-10 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-02-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-26 | 2024-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
416 | 2401-4GGSM-4G#RO-PLP191-0442 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Add RRU | PLP191 | E_PLP191M41_MCPSalekkoe-LSP |  |  | PARE PARE | -3.0094 | 120.2074 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-02-26 | Done | Done | 2024-02-27 | Done | 100% | 2024-02-26 | 2024-02-26 | 2024-02-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-03-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-20 | 2024-03-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
417 | 2401-4GGSM-4G#RO-PLP198-0273 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Add RRU and Module BBU | PLP198 | N_PLP198M41_MCPSalobuluWara-TBG |  |  | PARE PARE | -298131 | 120183 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-02-08 | Done | Done | 2024-02-10 | Done | 100% | 2024-02-08 | 2024-02-08 | 2024-02-08 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-02-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-26 | 2024-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
418 | 2401-4GGSM-4G#RO-PLP200-0276 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Add RRU and Module BBU | PLP200 | PLP200ML1_ TBG MCP TERMINAL DANGERAKKO |  |  | PARE PARE | -300367 | 120196 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-02-09 | Done | Done | 2024-02-10 | Done | 100% | 2024-02-09 | 2024-02-09 | 2024-02-09 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-02-18 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-26 | 2024-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
419 | 2401-4GGSM-4G#RO-PLP223-0081 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU | PLP223 | E_PLP223M41_SaluparemangSelatan-DMT |  |  | PARE PARE | -323574 | 120.3 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-03-07 | Done | Done | 2024-03-14 | Done | 100% | 2024-03-07 | 2024-03-07 | 2024-03-08 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-18 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 28-May-24 | 29-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 2024-06-06 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
420 | 2401-4GGSM-4G#RO-PSK018-0526 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | PSK018 | DMT Kasoloang |  |  | PALU | -1.0095 | 119.4878 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 09-May-24 | Done | Done | 10-May-24 | Done | 100% | 09-May-24 | 10-May-24 | 2024-06-06 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2026-07-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-24 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
421 | 2401-4GGSM-4G#RO-PSK028-0527 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | PSK028 | Desa Doda, Kec. Sarudu |  |  | PALU | -1.6366 | 119.3089 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 19-May-24 | Done | Done | 26-May-24 | Done | 100% | 19-May-24 | 20-May-24 | 2024-06-03 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-31 |  | Done Tagging |  | Done Tagging | No need | [11 empty] | 2024-07-08 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 18-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
422 | 2401-4GGSM-4G#RO-PSK030-0528 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | PSK030 | DMT Kasano |  |  | PALU | -1.542 | 119.346 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-04-28 | Done | Done | 2024-04-30 | Done | 100% | 2024-04-28 | 2024-04-29 | 2024-04-30 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 01-May |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 27-May-24 | 27-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3509 | 23-May-24 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
423 | 2401-4GGSM-4G#RO-RHA053-0530 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | RHA053 | TBG Banggai Duruka |  | ALL CLOSE | KENDARI | -4.876 | 122.7176 | YPTT | May-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 3 | R8852E S9000 | 3 | 1 | 1 | 0 | VBPd0P(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-04-29 | Done | Done | 04-May-24 | Done | 100% | 2024-04-29 | 2024-04-30 | 08-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 12-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 20-May-24 | 21-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 2024-06-20 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
424 | 2401-4GGSM-4G#RO-RTN003-0029 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | AMR009 | TBG Elusan |  | Imp by YPTT (Mapping site), PR to CCSI_PO No : S1ID2023070107WBF1-495 | MANADO | 1.1229 | 124.533 | YPTT | May-24 |  | 2024 | 2024 | [28 empty] | TBG | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 90 % |  |  |  |  | 13-May-24 | Done | Done | 19-May-24 | Done | 100% | 13-May-24 | 16-May-24 | 2024-06-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 25 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-09 | 2024-09-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9462 | 2026-03-25 | 28-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Reject Workload 70%, (quality self check ny finished)
425 | 2401-4GGSM-4G#RO-SKG010-0031 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | SKG010 | PENRANG |  |  | MAKASSAR | -4.1133 | 120.1744 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Very | Done Productivity 100 % |  |  |  |  | 2024-03-29 | Done | Done | 2024-03-30 | Done | 100% | 2024-03-29 | 2024-03-31 | 2024-04-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-22 | 8-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
426 | 2401-4GGSM-4G#RO-SKG107-0300 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | SKG107 | MCR Lapangan Merdeka |  |  | MAKASSAR | -4.1392 | 120.0317 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-02-10 | Done | Done | 2024-02-10 | Done | 100% | 2024-02-10 | 2024-02-11 | 2024-02-11 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-19 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-07-24 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-03-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
427 | 2401-4GGSM-4G#RO-SKG111-0466 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU | SKG111 | MCR Terminal Tempe |  |  | MAKASSAR | -4.1307 | 120.0269 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-02-12 | Done | Done | 2024-02-12 | Done | 100% | 2024-02-12 | 2024-02-12 | 2024-02-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-18 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-07-24 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-03-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
428 | 2401-4GGSM-4G#RO-SKG113-0301 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | SKG113 | MCR Wolter Monginsidi |  |  | MAKASSAR | -4.1462 | 120.0341 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-02-09 | Done | Done | 2024-02-09 | Done | 100% | 2024-02-09 | 2024-02-09 | 2024-02-09 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-15 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-07-23 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
429 | 2401-4GGSM-4G#RO-SKG114-0151 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | SKG114 | MCR Serikaya |  |  | MAKASSAR | -4.1426 | 120.0419 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-02-10 | Done | Done | 2024-02-10 | Done | 100% | 2024-02-10 | 2024-02-10 | 2024-02-10 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-18 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-07-23 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
430 | 2401-4GGSM-4G#RO-SKG124-0107 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | SKG124 | MCR Pasar Siwa |  |  | MAKASSAR | -3.7016 | 120.417 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Very | Done Productivity 100 % |  |  |  |  | 2024-02-09 | Done | Done | 2024-02-11 | Done | 100% | 2024-02-09 | 2024-02-10 | 2024-02-11 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-07 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2025-11-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
431 | 2401-4GGSM-4G#RO-TDE007-0533 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | TDE007 | Permanenisasi COI522 - Combat Pole Tugulupa (Support Event Sail Tidore) |  |  | TERNATE | 0.66994 | 127.4545 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-07-11 | Done | Done | 2024-07-23 | Done | 100% | 2024-07-11 | 2024-07-12 | 16-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-09-22 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-19 | 2024-09-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4380 | 2024-07-20 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
432 | 2401-4GGSM-4G#RO-TDE010-0534 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 MHz | New Infra | TDE010 | Desa Maidi |  |  | TERNATE | 0.13391 | 127.7117 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 16-May-24 | Done | Done | 18-May-24 | Done | 100% | 16-May-24 | 18-May-24 | 18-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 26 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 20-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
433 | 2401-4GGSM-4G#RO-TDE053-0248 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | TDE053 | PST MM GOTO TIDORE |  |  | TERNATE | 0.67957 | 127.4521 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Risal | Done Productivity 100 % |  |  |  |  | 2024-02-24 | Done | Done | 2024-02-25 | Done | 100% | 2024-02-24 | 2024-02-25 | 2024-02-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-26 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 28-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
434 | 2401-4GGSM-4G#RO-TDO034-0036 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | TDO034 | Permanenisasi COI530 - Combat Pole Geovani Matungkas |  |  | MANADO | 1.4713 | 124.9841 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 04-May-24 | Done | Done | 06-May-24 | Done | 100% | 04-May-24 | 08-May-24 | 08-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 07-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 21-May-24 | 27-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
435 | 2401-4GGSM-4G#RO-TDO035-0037 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | TDO035 | Permanenisasi COI575 - Combat Dimembe Nyiur |  |  | MANADO | 1.5186 | 124.9657 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-04-22 | Done | Done | 2024-04-28 | Done | 100% | 2024-04-22 | 2024-04-28 | 2024-04-28 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 02-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 27-May-24 | 27-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3465 | 15-May-24 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
436 | 2401-4GGSM-4G#RO-TDO049-0038 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | TDO049 | Permanenisasi COI037 - Combat CRU Tulap |  |  | MANADO | 1.2023 | 124.9846 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Aditia | Done Productivity 100 % |  |  |  |  | 10-May-24 | Done | Done | 12-May-24 | Done | 100% | 10-May-24 | 12-May-24 | 12-May-24 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 29 May 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 31-May-24 | 31-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 2024-06-20 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
437 | 2401-4GGSM-4G#RO-TDO055-0537 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | TDO055 | KALI |  |  | MANADO | 1.4106 | 124.8457 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-04-06 | Done | Done | 2024-04-08 | Done | 100% | 2024-04-06 | 2024-04-08 | 2024-04-30 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 12-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 21-May-24 | 27-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
438 | 2401-4GGSM-4G#RO-TDO141-0307 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | TDO141 | Warukapas-PTI |  |  | MANADO | 1.5122 | 124.9884 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Sergi | Done Productivity 100 % |  |  |  |  | 2024-03-02 | Done | Done | 2024-03-03 | Done | 100% | 2024-03-02 | 2024-03-03 | 2024-03-03 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-04-21 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-14 | 2024-07-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
439 | 2401-4GGSM-4G#RO-TDO246-0171 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | TDO246 | AirMadidi-DMT |  |  | MANADO | 1.4169 | 124.9879 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Sergi | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-03-01 | Done | 100% | 2024-02-28 | 2024-03-01 | 2024-03-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 08-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
440 | 2401-4GGSM-4G#RO-TER073-0313 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | TER073 | TBG TABONA |  |  | TERNATE | 0.77288 | 127.366 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-02-16 | Done | Done | 2024-02-17 | Done | 100% | 2024-02-16 | 2024-02-17 | 2024-02-17 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-26 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-19 | 2024-06-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
441 | 2401-4GGSM-4G#RO-TER086-0114 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 900 10 MHz | Add RRU | TER086 | TBG PERUMNAS TERNATE |  |  | TERNATE | 0.77638 | 127.364 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-02-20 | Done | Done | 2024-02-20 | Done | 100% | 2024-02-20 | 2024-02-20 | 2024-02-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-21 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-13 | 2024-03-14 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
442 | 2401-4GGSM-4G#RO-TER092-0443 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap antenna and Add RRU and Module BBU | TER092 | JUMAT PUASA |  |  | TERNATE | 0.79083 | 127.3852 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-02-16 | Done | Done | 2024-02-18 | Done | 100% | 2024-02-16 | 2024-02-18 | 2024-02-18 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 15-May-24 | 16-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
443 | 2401-4GGSM-4G#RO-TER101-0427 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap antenna and Add RRU and Module BBU | TER101 | MC SALAHUDDIN |  |  | TERNATE | 0.79307 | 127.3802 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-02-24 | Done | Done | 2024-02-24 | Done | 100% | 2024-02-24 | 2024-02-24 | 2024-02-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-26 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-14 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
444 | 2401-4GGSM-4G#RO-TER134-0314 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | TER134 | TBG MCP PEMUDA SANGAJI |  |  | TERNATE | 0.81089 | 127.3857 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-02-19 | Done | Done | 2024-02-19 | Done | 100% | 2024-02-19 | 2024-02-19 | 2024-02-19 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-02-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 14-May-24 | 15-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 17-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
445 | 2401-4GGSM-4G#RO-WGI002-0543 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | WGI002 | TBG Numana |  | ALL CLOSE | KENDARI | -535628 | 1235562 | YPTT | 2026-04-24 |  | 2024 | 2024 |  |  | Prose 10 port | 3 | 3 | R8852E S9000 | 3 | 1 | 1 | 0 | VBPd0P(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 02-May-24 | Done | Done | 2024-04-19 | Done | 100% | 02-May-24 | 03-May-24 | 03-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 11-May-24 |  | Done Tagging |  | Done Tagging | No Need | Waiting Permit | [10 empty] | 30-May-24 | 31-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3464 | 15-May-24 | 2024-06-20 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
446 | 2401-4GGSM-4G#RO-WTG051-0191 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | WTG051 | MC Kalino Soppeng |  |  | MAKASSAR | -4.3512 | 119.8863 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-02-20 | Done | Done | 2024-02-20 | Done | 100% | 2024-02-20 | 2024-02-20 | 2024-02-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-04 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-07-22 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-03-17 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
447 | 2401-4GGSM-4G#RO-WTG056-0040 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | WTG056 | Permanenisasi COI510 - Combat Cruiser Jampu Soppeng |  |  | MAKASSAR | -4.4011 | 119.9805 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-03-29 | Done | Done | 2024-03-31 | Done | 100% | 2024-03-29 | 2024-03-30 | 2024-04-03 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-17 | 14-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
448 | 2401-4GGSM-4G#RO-WTG057-0544 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | WTG057 | Desa Abbanuange, Kec. Lilirilau |  |  | MAKASSAR | -4.3672 | 120.0662 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Very | Done Productivity 100 % |  |  |  |  | 2024-04-05 | Done | Done | 2024-04-17 | Done | 100% | 2024-04-05 | 2024-04-05 | 2024-04-17 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-29 | 8-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
449 | 2401-4GGSM-4G#RO-WTG065-0041 | CAPEX RAN 1 PART 2 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | WTG065 | DONRI DONRI |  |  | MAKASSAR | -4.2403 | 119.9241 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-03-24 | Done | Done | 2024-03-27 | Done | 100% | 2024-03-24 | 2024-03-25 | 2024-04-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-17 | 8-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
450 | 2401-4GGSM-4G#RO-WTG066-0545 | CAPEX RAN 1 PART 3 2024 | EQP New NE 4G LTE 900 10 Mhz | New Infra | WTG066 | BC_SOPPENG_MASING |  |  | MAKASSAR | -4297030 | 120041020 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Very | Done Productivity 100 % |  |  |  |  | 2024-03-22 | Done | Done | 2024-03-27 | Done | 100% | 2024-03-22 | 2024-03-24 | 2024-03-30 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-17 | 2024-04-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3406 | 2024-04-19 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
451 | 2401-NNE4G-4G#RO-ADL050-0217 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2100 20 Mhz | Swap Antenna and Add RRU and Module BBU | ADL050 | TBG Sawei |  | ALL CLOSE | KENDARI | -4.6957 | 121.8447 | YPTT | February-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 1 | 1 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | TBXLHA 6 Port | 1 | 1 | No Need | 0 | R8872A S1800 | 1 | SFP 10G(2) | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-02-06 | Done | Done | 2024-02-06 | Done | 100% | 2024-02-06 | 2024-02-07 | 2024-02-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-07 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-03-14 | 2025-03-15 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
452 | 2401-NNE4G-4G#RO-ADL095-0001 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | ADL095 | DMT Lalonggasu |  | Pending Tag Dismantle | KENDARI | -4.4107 | 122.2294 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 2 | 2 | R8978 S2300 | 2 | 0 | 1 | 0 | Vbpdop(1),VBPd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | DBXRHA 4 Port | 2 | 2 | No Need | 0 | No Need RRU | 0 | BBU(1),UBGP3(1),BPN2(2),CC16B(1),CR0(1)FS5(1),PM3(1),PM5(1),SA(1)FA0(1) | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-03-19 | Done | Done | 2024-03-20 | Done | 100% | 2024-03-19 | 2024-03-20 | 2024-03-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-21 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2025-03-17 | 2025-03-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3352 | 2024-04-17 | 2024-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
453 | 2401-NNE4G-4G#RO-BAU014-0265 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | BAU014 | Mawasangka |  | ALL CLOSE | KENDARI | -5.2913 | 122.2972 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-03-03 | Done | Done | 2024-03-04 | Done | 100% | 2024-03-03 | 2024-03-04 | 2024-03-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-04 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-22 | 2024-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
454 | 2401-NNE4G-4G#RO-BAU027-0266 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | BAU027 | Repeater Lakudo |  | ALL CLOSE | KENDARI | -5.275 | 122.5428 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-02-29 | Done | Done | 2024-02-29 | Done | 100% | 2024-02-29 | 2024-02-29 | 2024-02-29 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-22 | 2024-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-20 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
455 | 2401-NNE4G-4G#RO-BAU052-0007 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | BAU052 | DMT ISAT Boneatiro |  | Pending Tag Dismantle | KENDARI | -5.2456 | 122.7444 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 1 | 1 | R9614 S2300 | 1 | 0 | 1 | 0 | Vbpdop(1),VBPd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | TBXLHA 6 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | BBU(1),Fa0(1),SA(1),PM4(2),CCE1b(1),CR0(1),FS5(1),BPN2(3),DCPD7(1) | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-03-27 | Done | Done | 2024-03-29 | Done | 100% | 2024-03-27 | 2024-03-28 | 2024-03-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-29 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2024-07-23 | 2024-07-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
456 | 2401-NNE4G-4G#RO-BAU075-0267 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Swap Antenna and Add RRU and Module BBU | BAU075 | Deltacomsel Wakeakea |  | ALL CLOSE | KENDARI | -5.2881 | 122.5037 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-03-02 | Done | Done | 2024-03-03 | Done | 100% | 2024-03-02 | 2024-03-03 | 2024-03-03 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-04 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-22 | 2024-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
457 | 2401-NNE4G-4G#RO-BAU089-0008 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | BAU089 | TBG Wungka |  | Pending Tag Dismantle | KENDARI | -5.3046 | 123.5858 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 2 | 0 | R9614 S2300 | 1 | 0 | 1 | 0 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | TDQ 4 Port | 2 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),CCE1B(1),CR0(2),BPN(2),PM(2),SA(1) | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2024-03-02 | Done | Done | 2024-03-02 | Done | 100% | 2024-03-02 | 2024-03-02 | 2024-03-02 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-15 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 29-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
458 | 2401-NNE4G-4G#RO-BAU106-0331 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | BAU106 | DMT Labalawa Bau-Bau |  | Pending Tag Dismantle | KENDARI | -5.5125 | 122.5959 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 1 | 1 | R9614 S2300 | 1 | 0 | 0 | 0 | VBpd0p(3) | VSWD1(1) | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | TDQ 4 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | BBU(1),CCE1B(1),CR0(2),FS5(1),PM5(2),BPN2(3),FA0(1) | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-02-29 | Done | Done | 2024-02-29 | Done | 100% | 2024-02-29 | 2024-02-29 | 2024-02-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-04 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 29-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
459 | 2401-NNE4G-4G#RO-BAU179-0009 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Module BBU and Add RRU | BAU179 | LMA Batauga |  | Pending Tag Dismantle | KENDARI | -5.6766 | 122.6261 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 1 | 0 | VBpd2p(2) | VSWD1(1) | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),CCE1b(1),CR0(2),BPN2(4),PM5(2),Sa(1),FA0(1) | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2024-03-06 | Done | Done | 2024-03-06 | Done | 100% | 2024-03-06 | 2024-03-06 | 2024-03-06 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-11 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 26-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
460 | 2401-NNE4G-4G#RO-BAU194-0010 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | BAU194 | TBG MCP SDN Ngangana |  | Pending Tag Dismantle | KENDARI | -5.4603 | 122.5995 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 2 | 0 | R9614 S2300 | 1 | 0 | 1 | 0 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | TDQ 4 Port | 2 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),CCE1B(1)CR0(2)BPN(3),PM(2),SA(1) | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2024-02-26 | Done | Done | 2024-02-27 | Done | 100% | 2024-02-26 | 2024-02-27 | 2024-02-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-14 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 26-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
461 | 2401-NNE4G-4G#RO-BAU220-0164 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Module BBU and Add RRU | BAU220 | DMT Mantowu |  | Pending Tag Dismantle | KENDARI | -5.409 | 122.8835 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 1 | 0 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | DCPD7(1),BBU(1),CCE1(1),PM5(2)FA0(1),SA(1),BPN(2),CR0(1) | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-03-01 | Done | Done | 2024-03-01 | Done | 100% | 2024-03-01 | 2024-03-01 | 2024-03-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-02 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 08-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
462 | 2401-NNE4G-4G#RO-BAU289-0165 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Add RRU and Module BBU | BAU289 | DMT Perumahan Palatiga |  | ALL CLOSE | KENDARI | -5.2842 | 122.3654 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-02-29 | Done | Done | 2024-03-02 | Done | 100% | 2024-02-29 | 2024-02-29 | 2024-02-29 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 04-May-24 | 2024-04-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
463 | 2401-NNE4G-4G#RO-BIT051-0014 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Module BBU | BIT051 | PROTELINDO MADIDIR UNET |  |  | MANADO | 1.4492 | 125.1658 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-03-03 | Done | Done | 2024-03-04 | Done | 100% | 2024-03-03 | 2024-03-04 | 2024-03-04 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-28 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 23-Aug-24 | 27-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
464 | 2401-NNE4G-4G#RO-BIT068-0086 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | BIT068 | PimpinTanjungMerah-PTI |  |  | MANADO | 1.3973 | 125.0988 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Sergi | Done Productivity 100 % |  |  |  |  | 2024-02-26 | Done | Done | 2024-02-27 | Done | 100% | 2024-02-26 | 2024-02-27 | 2024-02-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 4-May-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-03 | 2025-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
465 | 2401-NNE4G-4G#RO-BIT104-0012 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | BIT104 | MCR Manembonembo |  |  | MANADO | 1.4338 | 125.1208 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-02-28 | Done | 100% | 2024-02-28 | 2024-02-28 | 2024-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-07 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-06-24 | 2024-07-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
466 | 2401-NNE4G-4G#RO-BUA001-0332 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | BUA001 | DMT Busoa Batauga |  | ALL CLOSE | KENDARI | -5.5891 | 122.5975 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-03-01 | Done | Done | 2024-03-01 | Done | 100% | 2024-03-01 | 2024-03-01 | 2024-03-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-01 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-22 | 2024-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
467 | 2401-NNE4G-4G#RO-COI163-0090 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | COI163 | E_COI163M41_CombatARRLarompong |  |  | PARE PARE | -3.4761 | 120.3673 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-02-06 | Done | Done | 2024-03-03 | Done | 100% | 2024-02-06 | 2024-02-06 | 2024-02-06 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-04 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 30-May-24 | 31-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
468 | 2401-NNE4G-4G#RO-COI167-0045 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU | COI167 | Combat ARR Kadolo Katapi |  | ALL CLOSE | KENDARI | -5.4662 | 122.6418 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-03-06 | Done | Done | 2024-03-06 | Done | 100% | 2024-03-06 | 2024-03-06 | 2024-03-06 | Connected | Connected |  | 01-Passed | 01-Passed | no Need | 2024-03-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-26 | 2024-03-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 8-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
469 | 2401-NNE4G-4G#RO-COI446-0028 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | COI446 | COMBAT LATUPPA PALOPO |  |  | PARE PARE | -3.0316 | 120.1223 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-02-06 | Done | Done | 2024-02-07 | Done | 100% | 2024-02-06 | 2024-02-07 | 2024-02-07 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-02-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-27 | 2024-03-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
470 | 2401-NNE4G-4G#RO-COI528-0334 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Swap Module BBU | COI528 | CombatPT.SJU-ADT |  |  | TERNATE | -1.7448 | 124.4629 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 12-May-24 | Done | Done | 18-May-24 | Done | 100% | 12-May-24 | 12-May-24 | 17-May-24 | Connected | Connected |  | 03-NY SM | 01-Passed | Passed | 17-May-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-09 | 2024-09-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3465 | 15-May-24 | 2024-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
471 | 2401-NNE4G-4G#RO-COI551-0282 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU and Module BBU | COI551 | COMBAT TUBO |  |  | TERNATE | 0.82569 | 127.3736 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-02-26 | Done | 100% | 2024-02-28 | 2024-02-28 | 2024-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-15 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 14-May-24 | 15-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
472 | 2401-NNE4G-4G#RO-DGL016-0335 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | DGL016 | DMT Namo |  |  | PALU | -1.4111 | 119.9779 | YPTT | February-24 |  | 2024 | 2024 | [28 empty] | IMIP | [5 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-03-01 | Done | Done | 2024-03-01 | Done | 100% | 2024-03-01 | 2024-03-01 | 2024-03-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-04-03 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 26-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
473 | 2401-NNE4G-4G#RO-DGL103-0039 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Module BBU and Add RRU | DGL103 | DMT Gumbasa Kulawi |  |  | PALU | -1.3055 | 119.9508 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-02-29 | Done | Done | 2024-02-29 | Done | 100% | 2024-02-29 | 2024-02-29 | 2024-02-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-04-26 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-08 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
474 | 2401-NNE4G-4G#RO-DGL141-0273 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | DGL141 | Quattro Berdikari Palolo |  |  | PALU | -1.1246 | 120.0849 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-04-07 | Done | Done | 2024-04-07 | Done | 100% | 2024-04-07 | 2024-04-07 | 2024-04-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-04-25 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 26-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
475 | 2401-NNE4G-4G#RO-KKA048-0052 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | KKA048 | DMT Samaturu |  | Pending Tag Dismantle | KENDARI | -3.9258 | 121.3446 | YPTT | February-24 |  | 2024 | 2024 |  |  | Prose 10 port | 2 | 2 | R9614 S2300 | 1 | 0 | 1 | 1 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | Kathrein 4 Port,Mobi 8 Port | 2 | 2 | No Need | 0 | No Need RRU | 0 | BBU(1),FA0(1),PM5(2),CCE1B(1),CR0(2),BPN2(4),DCPD7(1) | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-02-25 | Done | Done | 2024-02-26 | Done | 100% | 2024-02-25 | 2024-02-26 | 2024-02-26 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-27 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 27-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
476 | 2401-NNE4G-4G#RO-KKA068-0340 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | KKA068 | DMT Pakue Utara |  | Pending Tag Dismantle | KENDARI | -3.1073 | 121.0658 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 1 | 0 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | DCPD7(1),BBU(1),FA0(1),SA(1),PM5(2),CCE1B(1),CR0(1),FS5(1),BPN2(2),UBPG3(1) | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-03-01 | Done | Done | 2024-03-01 | Done | 100% | 2024-03-01 | 2024-03-02 | 2024-03-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-02 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2024-07-24 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
477 | 2401-NNE4G-4G#RO-KKA069-0053 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Module BBU and Add RRU | KKA069 | DMT Rantelimbong |  | Pending Tag Dismantle | KENDARI | -3.5264 | 120.9148 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 1 | 1 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-02-28 | Done | 100% | 2024-02-28 | 2024-02-28 | 2024-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-29 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 08-Aug-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
478 | 2401-NNE4G-4G#RO-LBA022-0230 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU | LBA022 | DMT AMASING KALI |  |  | TERNATE | -0.599 | 127.4747 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-02-25 | Done | Done | 2024-02-25 | Done | 100% | 2024-02-25 | 2024-02-25 | 2024-02-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 26-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
479 | 2401-NNE4G-4G#RO-LBA047-0281 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Swap Module BBU | LBA047 | Anggai Obi |  |  | TERNATE | -1.3487 | 127.7334 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-03-25 | Done | Done | 2024-03-26 | Done | 100% | 2024-03-25 | 2024-03-26 | 2024-03-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-03-28 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-19 | 2024-06-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5520 | 2024-11-30 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
480 | 2401-NNE4G-4G#RO-LBA086-0341 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | LBA086 | Repeater Harita 2 |  |  | TERNATE | -0.73487 | 127.452 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-02-26 | Done | Done | 2024-02-27 | Done | 100% | 2024-02-26 | 2024-02-27 | 2024-02-27 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-04-01 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-30 | 10-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 19-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
481 | 2401-NNE4G-4G#RO-LBA119-0342 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | LBA119 | Mess DCM |  |  | TERNATE | -1.553 | 127.4293 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-02-28 | Done | 100% | 2024-02-28 | 2024-02-28 | 2024-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-04 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-30 | 2-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 19-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
482 | 2401-NNE4G-4G#RO-MDO052-0285 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Swap Module BBU | MDO052 | Bunaken |  |  | MANADO | 1.6242 | 124.751 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Sergi | Done Productivity 100 % |  |  |  |  | 2024-03-14 | Done | Done | 2024-03-13 | Done | 100% | 2024-03-14 | 2024-03-15 | 2024-03-15 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-16 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-19 | 2024-07-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
483 | 2401-NNE4G-4G#RO-MDO243-0124 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | MDO243 | MatungkasResident-DMT |  |  | MANADO | 1.4556 | 124.9295 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-02-29 | Done | Done | 2024-02-29 | Done | 100% | 2024-02-29 | 2024-02-29 | 2024-02-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-15 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-07-19 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
484 | 2401-NNE4G-4G#RO-MDO604-0126 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | MDO604 | BunakenSelatan-PTI |  |  | MANADO | 1.5978 | 124.7798 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Sergi | Done Productivity 100 % |  |  |  |  | 2024-03-16 | Done | Done | 2024-03-17 | Done | 100% | 2024-03-16 | 2024-03-17 | 2024-03-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-18 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 08-Dec-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3262 | 2024-03-22 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
485 | 2401-NNE4G-4G#RO-MDO614-0216 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | MDO614 | BunakenTengah-PTI |  |  | MANADO | 1.6225 | 124.7662 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Sergi | Done Productivity 100 % |  |  |  |  | 2024-03-16 | Done | Done | 2024-03-16 | Done | 100% | 2024-03-16 | 2024-03-16 | 2024-03-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-16 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-27 | 2024-04-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3262 | 2024-03-22 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
486 | 2401-NNE4G-4G#RO-MGN049-0264 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU and Module BBU | MGN049 | Non3TEssangSelatan-DMT |  |  | MANADO | 4.4505 | 126.7258 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Noris | Done Productivity 100 % |  |  |  |  | 2024-02-15 | Done | Done | 2024-02-16 | Done | 100% | 2024-02-15 | 2024-02-16 | 2024-02-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-28 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-13 | 2024-03-14 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
487 | 2401-NNE4G-4G#RO-MRW100-0293 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | MRW100 | DMT ISAT Moahino |  |  | PALU | -2.2092 | 121.5915 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-03-22 | Done | Done | 2024-03-23 | Done | 100% | 2024-03-22 | 2024-03-22 | 2024-03-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-03-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 26-Aug-24 | 27-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3406 | 2024-04-19 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
488 | 2401-NNE4G-4G#RO-MRW362-0347 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | MRW362 | PuntariMakmur-DMT |  |  | PALU | -2.2406 | 121.6591 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-02-25 | Done | Done | 2024-02-25 | Done | 100% | 2024-02-25 | 2024-02-25 | 2024-02-25 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-02-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-18 | 2024-04-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
489 | 2401-NNE4G-4G#RO-MRW364-0184 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | MRW364 | EMA Harapan |  |  | PALU | -2.2466 | 121.7282 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-02-10 | Done | Done | 2024-02-10 | Done | 100% | 2024-02-10 | 2024-02-10 | 2024-02-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-10 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-29 | 2024-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
490 | 2401-NNE4G-4G#RO-MRW367-0348 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | MRW367 | Protelindo Dampala |  |  | PALU | -2.7535 | 122.0319 | YPTT | February-24 |  | 2024 | 2024 | [28 empty] | IMIP | [5 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-03-02 | Done | Done | 2024-03-02 | Done | 100% | 2024-03-02 | 2024-03-02 | 2024-03-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-18 | 2024-04-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
491 | 2401-NNE4G-4G#RO-PAL028-0084 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PAL028 | DMT Kayu Malue |  |  | PALU | -0.75586 | 119.862 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-02-28 | Done | 100% | 2024-02-28 | 2024-02-28 | 2024-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-04-16 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-08 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
492 | 2401-NNE4G-4G#RO-PAL189-0085 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Module BBU and Add RRU | PAL189 | TBG Layana Tondo |  |  | PALU | -0.81936 | 119.8808 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-02-27 | Done | Done | 2024-02-27 | Done | 100% | 2024-02-27 | 2024-02-27 | 2024-02-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-03-05 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-08 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3252 | 2024-03-21 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
493 | 2401-NNE4G-4G#RO-PLP015-0297 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Swap Antenna and Module BBU and Add RRU | PLP015 | DMT Bajo Belopa |  |  | PARE PARE | -338139 | 120318 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Very | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-02-28 | Done | 100% | 2024-02-28 | 2024-02-28 | 2024-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-05 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 30-May-24 | 31-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 2024-06-20 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
494 | 2401-NNE4G-4G#RO-PLP024-0239 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Module BBU | PLP024 | COMBAT BATARA |  |  | PARE PARE | -2.9981 | 120.1915 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-02-06 | Done | Done | 2024-02-07 | Done | 100% | 2024-02-06 | 2024-02-07 | 2024-02-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-20 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 08-Dec-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
495 | 2401-NNE4G-4G#RO-PLP025-0298 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Swap Module BBU | PLP025 | DMT Rante Belu |  |  | PARE PARE | -3552954 | 120400 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Very | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-03-03 | Done | 100% | 2024-02-28 | 2024-03-03 | 2024-03-03 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-04 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-03-06 | 2024-06-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 2024-06-12 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
496 | 2401-NNE4G-4G#RO-PLP044-0299 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Swap Antenna and Module BBU and Add RRU | PLP044 | DMT Ponrang |  |  | PARE PARE | -322269 | 120.32 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-02-29 | Done | Done | 2024-02-29 | Done | 100% | 2024-02-29 | 2024-02-29 | 2024-02-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-06 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 30-May-24 | 31-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 2024-06-12 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
497 | 2401-NNE4G-4G#RO-PLP047-0300 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Swap Module BBU | PLP047 | DMT Pongrakka |  |  | PARE PARE | -2.883 | 120.1978 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-03-01 | Done | Done | 2024-03-01 | Done | 100% | 2024-03-01 | 2024-03-01 | 2024-03-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-04 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 30-May-24 | 31-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 2024-06-06 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
498 | 2401-NNE4G-4G#RO-PLP088-0150 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap Antenna and RRU and Add Module BBU | PLP088 | E_PLP088M41_Bolong-PTI |  |  | PARE PARE | -281795 | 120135 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-02-28 | Done | 100% | 2024-02-28 | 2024-02-28 | 2024-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-03-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 06-Dec-24 | 2024-06-15 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
499 | 2401-NNE4G-4G#RO-PLP091-0153 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | PLP091 | E_PLP091M41_Bonglo-PTI |  |  | PARE PARE | -306231 | 120094 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-02-28 | Done | 100% | 2024-02-28 | 2024-02-28 | 2024-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-03-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-18 | 2024-03-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
500 | 2401-NNE4G-4G#RO-PLP094-0156 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | PLP094 | E_PLP094M41_PadangDurian-TBG |  |  | PARE PARE | -284999 | 120099 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-02-08 | Done | Done | 2024-02-09 | Done | 100% | 2024-02-08 | 2024-02-08 | 2024-02-08 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-09 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 08-Dec-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
501 | 2401-NNE4G-4G#RO-PLP132-0159 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU | PLP132 | E_PLP132M41_MurantePalopo-TBG |  |  | PARE PARE | -3.0089 | 120.177 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-02-06 | Done | Done | 2024-02-06 | Done | 100% | 2024-02-06 | 2024-02-06 | 2024-02-06 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-18 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-07-22 | 2024-07-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
502 | 2401-NNE4G-4G#RO-PLP140-0161 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | PLP140 | E_PLP140M41_PangaliWalenrang-PTI |  |  | PARE PARE | -2.8502 | 120.1732 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-02-26 | Done | Done | 2024-02-26 | Done | 100% | 2024-02-26 | 2024-02-26 | 2024-02-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-03-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-20 | 2024-03-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
503 | 2401-NNE4G-4G#RO-PLP231-0175 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU and Add Module BBU | PLP231 | E_PLP231M41_Paconne-DMT |  |  | PARE PARE | -3.3667 | 120.3846 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-02-22 | Done | Done | 2024-02-22 | Done | 100% | 2024-02-22 | 2024-02-22 | 2024-02-22 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-02-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-18 | 2024-03-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
504 | 2401-NNE4G-4G#RO-PLP255-0311 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU | PLP255 | DMT SALU PAO |  |  | PARE PARE | -282391 | 120233 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-02-22 | Done | Done | 2024-02-22 | Done | 100% | 2024-02-22 | 2024-02-22 | 2024-02-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-08 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-07-22 | 2024-07-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
505 | 2401-NNE4G-4G#RO-PLP256-0302 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | PLP256 | TBG PONGKO |  |  | PARE PARE | -2.7417 | 120.1581 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Muh Asdi | Done Productivity 100 % |  |  |  |  | 2024-02-29 | Done | Done | 2024-02-29 | Done | 100% | 2024-02-29 | 2024-02-29 | 2024-02-29 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-03-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-31 | 2024-04-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
506 | 2401-NNE4G-4G#RO-PLP257-0095 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | PLP257 | Desa Jambu |  |  | PARE PARE | -3.3569 | 120.3188 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-03-01 | Done | Done | 2024-03-01 | Done | 100% | 2024-03-01 | 2024-03-01 | 2024-03-01 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-03-04 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-31 | 2024-04-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
507 | 2401-NNE4G-4G#RO-PLP259-0182 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | PLP259 | N_PLP259M41_Setiarejo-CMI |  |  | PARE PARE | -2.8047 | 120.2012 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-02-27 | Done | Done | 2024-02-27 | Done | 100% | 2024-02-27 | 2024-02-27 | 2024-02-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-06 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 31-May-24 | 2024-06-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-12 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
508 | 2401-NNE4G-4G#RO-RHA045-0304 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | RHA045 | TBG Lakandito |  | ALL CLOSE | KENDARI | -4.965 | 122.4787 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-02-28 | Done | 100% | 2024-02-28 | 2024-02-28 | 2024-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-04 | 2024-04-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
509 | 2401-NNE4G-4G#RO-RHA114-0194 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | RHA114 | Oempu-BMT |  | ALL CLOSE | KENDARI | -5.1905 | 122.5848 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-02-16 | Done | Done | 2024-02-17 | Done | 100% | 2024-02-16 | 2024-02-17 | 2024-02-17 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-15 | 2024-03-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
510 | 2401-NNE4G-4G#RO-RHA124-0195 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | RHA124 | Protelindo Wantimoro |  | NY Tag Asset Reutilise | KENDARI | -5.027 | 122.4975 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-02-23 | Done | Done | 2024-02-25 | Done | 100% | 2024-02-23 | 2024-02-24 | 2024-02-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 23-Aug-24 | 27-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
511 | 2401-NNE4G-4G#RO-SKG043-0107 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Module BBU and Add RRU | SKG043 | DMT Lamata |  |  | MAKASSAR | -3.9479 | 120.1219 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-02-29 | Done | Done | 2024-03-01 | Done | 100% | 2024-02-29 | 2024-03-01 | 2024-03-01 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2024-03-04 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 30-May-24 | 31-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 2024-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
512 | 2401-NNE4G-4G#RO-SKG050-0308 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | SKG050 | DMT Akkajeng |  |  | MAKASSAR | -4.0391 | 120.3285 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-03-02 | Done | Done | 2024-03-05 | Done | 100% | 2024-03-02 | 2024-03-02 | 2024-03-05 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-07 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 30-May-24 | 31-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 2024-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
513 | 2401-NNE4G-4G#RO-SKG063-0108 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | SKG063 | Deltacomsel Barutancung Tanah Sitolo |  |  | MAKASSAR | -4.0603 | 120.0272 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-03-01 | Done | Done | 2024-03-01 | Done | 100% | 2024-03-01 | 2024-03-01 | 2024-03-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-02 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 30-May-24 | 30-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 2024-06-06 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
514 | 2401-NNE4G-4G#RO-SKG074-0178 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap Antenna and RRU and Add Module BBU | SKG074 | TBG SIDUNTUNG BELAWA |  |  | MAKASSAR | -396611 | 119938 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Very | Done Productivity 100 % |  |  |  |  | 2024-02-08 | Done | Done | 2024-02-08 | Done | 100% | 2024-02-08 | 2024-02-08 | 2024-02-08 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-17 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-07-23 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
515 | 2401-NNE4G-4G#RO-SKG108-0245 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | SKG108 | LMA PAJALELE |  |  | MAKASSAR | -408966 | 120023 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-02-08 | Done | Done | 2024-02-08 | Done | 100% | 2024-02-08 | 2024-02-08 | 2024-02-08 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-13 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-07-22 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-03-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
516 | 2401-NNE4G-4G#RO-SKG160-0111 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Module BBU and Add RRU | SKG160 | DMT Wiring Palennae |  |  | MAKASSAR | -4.1428 | 120.0143 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-02-24 | Done | Done | 2024-02-24 | Done | 100% | 2024-02-24 | 2024-02-24 | 2024-02-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-25 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 30-May-24 | 31-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-06 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
517 | 2401-NNE4G-4G#RO-SKG164-0112 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Module BBU and Add RRU | SKG164 | Lompoloan |  |  | MAKASSAR | -3.7267 | 120.3348 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-02-22 | Done | Done | 2024-02-22 | Done | 100% | 2024-02-22 | 2024-02-22 | 2024-02-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-26 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 30-May-24 | 30-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-06 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
518 | 2401-NNE4G-4G#RO-SNN018-0309 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | SNN018 | DMT Mangoli |  |  | TERNATE | -1.9298 | 125.9283 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 29-May-24 | Done | Done | 29-May-24 | Done | 100% | 29-May-24 | 29-May-24 | 29-May-24 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 30-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-06 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
519 | 2401-NNE4G-4G#RO-SRI001-0317 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU and Module BBU | SRI001 | Bakaremba |  | ALL CLOSE | KENDARI | -4.7279 | 122.5292 | YPTT | February-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-02-08 | Done | Done | 2024-02-08 | Done | 100% | 2024-02-08 | 2024-02-08 | 2024-02-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-02-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-15 | 2024-03-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3194 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
520 | 2401-NNE4G-4G#RO-TDE004-0326 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | TDE004 | Soadara |  |  | TERNATE | 0.66521 | 127.4482 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-03-08 | Done | Done | 2024-03-08 | Done | 100% | 2024-03-08 | 2024-03-08 | 2024-03-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 27-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
521 | 2401-NNE4G-4G#RO-TDE042-0314 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Swap Antenna and Add RRU and Module BBU | TDE042 | DMT Lola Oba Tengah |  |  | TERNATE | 0.43135 | 127.5835 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-03-02 | Done | Done | 2024-03-06 | Done | 100% | 2024-03-02 | 2024-03-06 | 2024-03-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-22 | 2024-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
522 | 2401-NNE4G-4G#RO-TDE063-0350 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Add RRU and Module BBU | TDE063 | DMT Lifofa |  |  | TERNATE | 0.0859 | 127.7207 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-03-02 | Done | Done | 2024-03-02 | Done | 100% | 2024-03-02 | 2024-03-02 | 2024-03-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-05 | 10-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 29-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
523 | 2401-NNE4G-4G#RO-TDO081-0119 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | TDO081 | DMT Kaweng |  |  | MANADO | 1.1695 | 124.9017 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-03-05 | Done | Done | 2024-03-06 | Done | 100% | 2024-03-05 | 2024-03-05 | 2024-03-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-10 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-22 | 2024-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
524 | 2401-NNE4G-4G#RO-TDO146-0120 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | TDO146 | TBG Tandengan |  |  | MANADO | 1.2345 | 124.9267 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-03-07 | Done | Done | 2024-03-20 | Done | 100% | 2024-03-07 | 2024-03-08 | 2024-03-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-24 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
525 | 2401-NNE4G-4G#RO-TDO154-0121 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | TDO154 | Protelindo Pelelean |  |  | MANADO | 1.2548 | 124.8979 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-03-04 | Done | Done | 2024-03-04 | Done | 100% | 2024-03-04 | 2024-03-04 | 2024-03-04 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-30 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-07-30 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
526 | 2401-NNE4G-4G#RO-TDO287-0125 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | TDO287 | DMT ISAT Kombi |  |  | MANADO | 1.2364 | 124.977 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Sergi | Done Productivity 100 % |  |  |  |  | 2024-03-23 | Done | Done | 2024-03-23 | Done | 100% | 2024-03-23 | 2024-03-23 | 2024-03-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-04-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 06-Dec-24 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5732 | 25-Dec-24 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
527 | 2401-NNE4G-4G#RO-TDO288-0248 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | TDO288 | DMT PANTAI KINUNANG |  |  | MANADO | 1.6649 | 125.1617 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-02-15 | Done | Done | 2024-02-15 | Done | 100% | 2024-02-15 | 2024-02-15 | 2024-02-15 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-21 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-07-05 | 7-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3193 | 2024-03-09 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
528 | 2401-NNE4G-4G#RO-TDO336-0127 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | TDO336 | TBG Treman Kauditan |  |  | MANADO | 1.3931 | 125.0336 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Sergi | Done Productivity 100 % |  |  |  |  | 2024-03-04 | Done | Done | 2024-03-04 | Done | 100% | 2024-03-04 | 2024-03-04 | 2024-03-04 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-09 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 14-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
529 | 2401-NNE4G-4G#RO-TDO357-0082 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU and Module BBU | TDO357 | Lansa-DMT |  |  | MANADO | 1.6435 | 124.9298 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-03-01 | Done | Done | 2024-03-01 | Done | 100% | 2024-03-01 | 2024-03-01 | 2024-03-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 29-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
530 | 2401-NNE4G-4G#RO-TDO405-0316 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | TDO405 | DMT Serei Jaga |  |  | MANADO | 1.7371 | 125.0061 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Sergi | Done Productivity 100 % |  |  |  |  | 2024-03-05 | Done | Done | 2024-03-05 | Done | 100% | 2024-03-05 | 2024-03-05 | 2024-03-05 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-23 | 2024-04-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
531 | 2401-NNE4G-4G#RO-TER046-0128 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | TER046 | Jl. Ubo Ubo |  |  | TERNATE | 0.76821 | 127.3718 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-03-05 | Done | Done | 2024-03-06 | Done | 100% | 2024-03-05 | 2024-03-06 | 2024-03-06 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-03-11 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-13 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
532 | 2401-NNE4G-4G#RO-TER155-0129 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | TER155 | Tataleka |  |  | TERNATE | 0.9566 | 127.5159 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 2024-02-28 | Done | Done | 2024-03-01 | Done | 100% | 2024-02-28 | 2024-03-09 | 2024-03-09 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-03-13 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-19 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
533 | 2401-NNE4G-4G#RO-THN017-0351 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | THN017 | Bebu |  |  | MANADO | 3.4239 | 125.5337 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-03-25 | Done | Done | 2024-03-24 | Done | 100% | 2024-03-25 | 2024-03-26 | 2024-03-26 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-26 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-06-19 | 2024-06-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3406 | 2024-04-19 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
534 | 2401-NNE4G-4G#RO-THN102-0352 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | THN102 | Ngalipaeng Makro |  |  | MANADO | 3.3891 | 125.6238 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-03-24 | Done | Done | 2024-03-24 | Done | 100% | 2024-03-24 | 2024-03-24 | 2024-03-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-30 | 10-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3406 | 2024-04-19 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
535 | 2401-NNE4G-4G#RO-TKA034-0353 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | LBA118 | Apartement 14-15 |  |  | TERNATE | -1.5319 | 127.4091 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-09-08 | Done | Done | 2024-09-16 | Done | 100% | 2024-09-08 | 2024-09-09 | 2024-09-09 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-10 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-25 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
536 | 2401-NNE4G-4G#RO-TOB103-0356 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | BAU095 | Bure Bau Bau-DMT |  | ALL CLOSE | KENDARI | -5.46 | 122.6224 | YPTT | August-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 1 | 0 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),PM5(2),BPN2(3),CCE1B(1),FS5(1),CR0(1),SA(1),FA0(1) | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 21-Aug-24 | Done | Done | 21-Aug-24 | Done | 100% | 21-Aug-24 | 21-Aug-24 | 21-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 22-Aug-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-18 | 2024-09-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4913 | 2024-09-05 | 17-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
537 | 2401-NNE4G-4G#RO-UNH051-0322 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 MHz | Swap Antenna and Module BBU and Add RRU | COI370 | PLAN 5-MRW095 |  |  | PARE PARE | -296111 | 1222928 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Suardi | Done Productivity 100 % |  |  |  |  | 01-Aug-24 | Done | Done | 04-Aug-24 | Done | 100% | 01-Aug-24 | 02-Aug-24 | 04-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 4-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 27-Aug-24 | 2024-09-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 17-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
538 | 2401-NNE4G-4G#RO-WTG033-0141 | CAPEX RAN 1 2024 Acceleration Support Part 5 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | WTG033 | Deltacomsel Mario Riwa |  |  | MAKASSAR | -4.1195 | 119.8614 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-02-29 | Done | Done | 2024-02-29 | Done | 100% | 2024-02-29 | 2024-02-29 | 2024-02-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-04 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 30-May-24 | 31-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3247 | 2024-03-21 | 2024-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
539 | 2401-NNE4G-4G#RO-WTG035-0271 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap Antenna and Add RRU and Module BBU | WTG035 | Protelindo Apanam |  |  | MAKASSAR | -4.3557 | 119.9533 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Very | Done Productivity 100 % |  |  |  |  | 2024-03-16 | Done | Done | 2024-03-16 | Done | 100% | 2024-03-16 | 2024-03-16 | 2024-03-16 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-17 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-03-06 | 2024-06-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3262 | 2024-03-22 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
540 | 2401-NNE4G-4G#RO-WTG036-0253 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | WTG036 | Protelindo Tallepu |  |  | MAKASSAR | -4.3673 | 119.9885 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-02-26 | Done | Done | 2024-02-26 | Done | 100% | 2024-02-26 | 2024-02-26 | 2024-02-26 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-27 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-03-06 | 2024-06-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-12 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
541 | 2401-NNE4G-4G#RO-WTG040-0180 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2100 20 Mhz | Swap Antenna and RRU and Add Module BBU | WTG040 | TBG LALABBATA RIAJA |  |  | MAKASSAR | -424661 | 119883 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-02-02 | Done | Done | 2024-02-03 | Done | 100% | 2024-02-02 | 2024-02-03 | 2024-02-03 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-02-06 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2025-11-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3190 | 2024-03-08 | 2024-04-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
542 | 2401-NNE4G-4G#RO-WTG044-0044 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Module BBU | WTG044 | DMT JENNAE LILIRIAJA |  |  | MAKASSAR | -441208 | 119945 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-03-16 | Done | Done | 2024-03-16 | Done | 100% | 2024-03-16 | 2024-03-16 | 2024-03-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-18 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 23-Aug-24 | 22-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3262 | 2024-03-22 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
543 | 2401-REEENG-4G#RO-COI160-0010 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Swap Antenna and RRU and Add Module BBU | COI160 | COMBAT Desa Tampa |  |  | PARE PARE | -3182379 | 120232166 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-03-19 | Done | Done | 2024-06-05 | Done | 100% | 2024-03-19 | 2024-03-20 | 2024-06-05 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-06 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 09-Dec-24 | 2024-09-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3969 | 2024-06-14 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
544 | 2401-REEENG-4G#RO-COI545-0017 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Swap Antenna and RRU and Add Module BBU | COI545 | COMBAT AIRMADIDI ATAS |  |  | MANADO | 1.473 | 124.9755 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | CV. Puri Tepule Abadi | Aditia | Done Productivity 100 % |  |  |  |  | 18-May-24 | Done | Done | 19-May-24 | Done | 100% | 18-May-24 | 18-May-24 | 18-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 22-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 14-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-06-20 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
545 | 2401-REEENG-4G#RO-PLP165-0059 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Swap Antenna and RRU and Add Module BBU | PLP165 | MC PATENE |  |  | PARE PARE | -2.997 | 120.185 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-03-09 | Done | Done | 2024-03-09 | Done | 100% | 2024-03-09 | 2024-03-09 | 2024-03-09 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-16 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-03-06 | 2024-06-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
546 | 2401-REEENG-4G#RO-SKG062-0056 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Swap Antenna and RRU and Add Module BBU | SKG062 | ProtelindoSalojampu |  |  | MAKASSAR | -4.2223 | 120.0111 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-02-20 | Done | Done | 2024-02-21 | Done | 100% | 2024-02-20 | 2024-02-21 | 2024-02-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-06 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 03-Oct-25 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3197 | 2024-03-11 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
547 | 2401-REEENG-4G#RO-SKG110-0038 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Swap Antenna and RRU and Add Module BBU | SKG110 | MCR Bau Mahmud |  |  | MAKASSAR | -4.1274 | 120.0293 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-03-16 | Done | Done | 2024-03-16 | Done | 100% | 2024-03-16 | 2024-03-16 | 2024-03-16 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-18 |  | Done Tagging |  | Done Tagging | Request Nodin | [11 empty] | 2024-07-19 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3262 | 2024-03-22 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
548 | 2401-REEENG-4G#RO-TDO089-0048 | CAPEX RAN 1 2024 Acceleration Support Part 3 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Swap RRU | TDO089 | DMT TEREMAAL |  |  | MANADO | 1.7032 | 124.9768 | YPTT | February-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-03-16 | Done | Done | 2024-03-16 | Done | 100% | 2024-03-16 | 2024-03-16 | 2024-03-16 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-03-17 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-05 | 8-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3262 | 2024-03-22 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
549 | 2401-REEENG-4G#RO-WTG047-0053 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Swap RRU and Module BBU | WTG047 | PROTELINDO SANUALE SOPPENG |  |  | MAKASSAR | -449238 | 119947 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Fhandi | Done Productivity 100 % |  |  |  |  | 2024-03-09 | Done | Done | 2024-03-10 | Done | 100% | 2024-03-09 | 2024-03-09 | 2024-03-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-03-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-04 | 2024-04-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 30-May-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
550 | 2401-REEENG-4G#RO-WTG071-0054 | CAPEX RAN 1 2024 Acceleration Support Part 2 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Swap RRU and Add Module BBU | WTG071 | LSP MCP Jalan Kayangan |  |  | MAKASSAR | -4.3573 | 119.8825 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Very | Done Productivity 100 % |  |  |  |  | 2024-03-09 | Done | Done | 2024-03-09 | Done | 100% | 2024-03-09 | 2024-03-09 | 2024-03-09 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 06-May-24 | 2024-06-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3261 | 2024-03-22 | 13-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
551 | 2403-NNE4G-4G#RO-KTG158-0363 | Activity Non MPSL RAFI 2024 SUL | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | KTG158 | TBG Passi |  |  | MANADO | 0.76787 | 124.3014 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Sergi | Done Productivity 100 % |  |  |  |  | 2024-03-28 | Done | Done | 2024-03-28 | Done | 100% | 2024-03-28 | 2024-03-28 | 2024-03-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-04-02 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 13-Aug-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 18-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
552 | 2403-OPTIC-4G#RO-ADL111-0023 | #N/A | L2300 | Move the optical port on the RRU | ADL111 | CMI MCP Tapuahi |  | Done | KENDARI | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-03-30 | Done | Done |  | Done | 100% | 2024-03-30 | 2024-03-30 | 2024-03-30 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-30 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
553 | 2403-OPTIC-4G#RO-BAU010-0013 | #N/A | L2300 | Move the optical port on the RRU | BAU010 | Liabuku |  | Done | KENDARI | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-03-29 | Done | Done |  | Done | 100% | 2024-03-29 | 2024-03-29 | 2024-03-29 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
554 | 2403-OPTIC-4G#RO-BAU012-0034 | #N/A | L2300 | Move the optical port on the RRU | BAU012 | DMT Betoambari |  | Done | KENDARI | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-03-29 | Done | Done |  | Done | 100% | 2024-03-29 | 2024-03-29 | 2024-03-29 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
555 | 2403-OPTIC-4G#RO-BAU021-0010 | #N/A | L2300 | Move the optical port on the RRU | BAU021 | Sandang Pangan |  | Done | KENDARI | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-03-29 | Done | Done |  | Done | 100% | 2024-03-29 | 2024-03-29 | 2024-03-29 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
556 | 2403-OPTIC-4G#RO-BAU030-0038 | #N/A | L2300 | Move the optical port on the RRU | BAU030 | Keraton Bau-Bau |  | Done | KENDARI | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-03-29 | Done | Done |  | Done | 100% | 2024-03-29 | 2024-03-29 | 2024-03-29 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
557 | 2403-OPTIC-4G#RO-BAU100-0044 | #N/A | L2300 | Move the optical port on the RRU | BAU100 | DMT Nganganaumala |  | Done | KENDARI | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-03-29 | Done | Done |  | Done | 100% | 2024-03-29 | 2024-03-29 | 2024-03-29 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
558 | 2403-OPTIC-4G#RO-BAU197-0017 | #N/A | L2300 | Move the optical port on the RRU | BAU197 | TBG MCP Sdn3 Wameo |  | Done | KENDARI | -5.4644 | 122.5923 | YPTT | March-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-03-29 | Done | Done |  | Done | 100% | 2024-03-29 | 2024-03-29 | 2024-03-29 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
559 | 2403-OPTIC-4G#RO-KDI276-0047 | #N/A | L2300 | Move the optical port on the RRU | KDI276 | TBG Labengki |  | Done | KENDARI | -3483081 | 122484514 | YPTT | March-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-04-30 | Done | Done |  | Done | 100% | 2024-04-30 | 2024-04-30 | 2024-04-30 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-04-30 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
560 | 2403-OPTIC-4G#RO-KKA014-0016 | #N/A | L2300 | Move the optical port on the RRU | KKA014 | Wolo |  | Done | KENDARI | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-03-28 | Done | Done |  | Done | 100% | 2024-03-28 | 2024-03-28 | 2024-03-28 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-28 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
561 | 2403-OPTIC-4G#RO-KKA189-0003 | #N/A | L2300 | Move the optical port on the RRU | KKA189 | TBG Jabal Kubis |  | Done | KENDARI | -3352390 | 120.944 | YPTT | March-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-03-28 | Done | Done |  | Done | 100% | 2024-03-28 | 2024-03-28 | 2024-03-28 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-28 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
562 | 2403-OPTIC-4G#RO-PLP014-0004 | #N/A | EQP New NE 4G LTE 2300 40 Mhz | Swicth Optic Cable | PLP014 | Larompong-DMT |  |  | PARE PARE | -3.5289 | 120.3667 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-03-21 | Done | Done |  | Done | 100% | 2024-03-21 | 2024-03-21 | 2024-03-21 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-21 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
563 | 2403-OPTIC-4G#RO-PLP061-0008 | #N/A | EQP New NE 4G LTE 2300 10 Mhz | Swicth Optic Cable | PLP061 | Balobalo-TBG |  |  | PARE PARE | -3.383 | 120.3554 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-03-21 | Done | Done |  | Done | 100% | 2024-03-21 | 2024-03-21 | 2024-03-21 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-21 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
564 | 2403-OPTIC-4G#RO-PLP095-0058 | #N/A | EQP New NE 4G LTE 2300 10 Mhz | Swicth Optic Cable | PLP095 | Bupon-TBG |  |  | PARE PARE | 0 | 0 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-03-21 | Done | Done |  | Done | 100% | 2024-03-21 | 2024-03-21 | 2024-03-21 | Connected | Connected |  | 03-NY SM | 03-NY SM | No Need | 2024-03-21 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
565 | 2403-OPTIC-4G#RO-PLP175-0006 | #N/A | EQP New NE 4G LTE 2300 10 Mhz | Swicth Optic Cable | PLP175 | Bajo-STP |  |  | PARE PARE | 0 | 0 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-03-21 | Done | Done |  | Done | 100% | 2024-03-21 | 2024-03-21 | 2024-03-21 | Connected | Connected |  | 03-NY SM | 03-NY SM | No Need | 2024-03-21 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
566 | 2403-OPTIC-4G#RO-RHA004-0015 | #N/A | L2300 | Move the optical port on the RRU | RHA004 | Labunia |  | Done | KENDARI | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin S | Done Productivity 100 % |  |  |  |  | 2024-03-27 | Done | Done |  | Done | 100% | 2024-03-27 | 2024-03-27 | 2024-03-27 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-27 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
567 | 2403-OPTIC-4G#RO-RHA027-0057 | #N/A | L2300 | Move the optical port on the RRU | RHA027 | DMT Kombikuno |  | Done | KENDARI | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-03-30 | Done | Done |  | Done | 100% | 2024-03-30 | 2024-03-30 | 2024-03-30 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-30 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
568 | 2403-OPTIC-4G#RO-RHA039-0035 | #N/A | L2300 | Move the optical port on the RRU | RHA039 | DMT Kontomolepe |  | Done | KENDARI | -511381 | 122.5116 | YPTT | March-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-03-27 | Done | Done |  | Done | 100% | 2024-03-27 | 2024-03-27 | 2024-03-27 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-27 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
569 | 2403-OPTIC-4G#RO-SKG053-0054 | #N/A | EQP New NE 4G LTE 2300 10 Mhz | Swicth Optic Cable | SKG053 | Tajo-DMT |  |  | MAKASSAR | -4.0991 | 120.1565 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-03-22 | Done | Done |  | Done | 100% | 2024-03-22 | 2024-03-22 | 2024-03-22 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-22 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
570 | 2403-OPTIC-4G#RO-SKG075-0031 | #N/A | EQP New NE 4G LTE 2300 10 Mhz | Swicth Optic Cable | SKG075 | BelawaCity-TBG |  |  | MAKASSAR | -4.0051 | 119.9287 | YPTT | February-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-03-22 | Done | Done |  | Done | 100% | 2024-03-22 | 2024-03-22 | 2024-03-22 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-03-22 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
571 | 2403-OPTIC-4G#RO-TDE068-0043 | #N/A | 2300 | Change port optic | TDE068 | Aketobololo |  |  | TERNATE | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-04-08 | Done | Done |  | Done | 100% | 2024-04-08 | 2024-04-08 | 2024-04-08 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-04-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
572 | 2403-OPTIC-4G#RO-TER062-0020 | #N/A | 2300 | Change port optic | TER062 | Salero Ternate |  |  | TERNATE | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-04-07 | Done | Done |  | Done | 100% | 2024-04-07 | 2024-04-07 | 2024-04-07 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-04-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
573 | 2403-OPTIC-4G#RO-TER142-0048 | #N/A | 2300 | Change port optic | TER142 | MCPTobenga-PST |  |  | TERNATE | #N/A | #N/A | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-04-07 | Done | Done |  | Done | 100% | 2024-04-07 | 2024-04-07 | 2024-04-07 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-04-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-3495 | 17-May-24 |  | #N/A |  | Done Upload | Invoiced 100%
574 | 2403-UMIMO-4G#667-MRW046-0014 | CAPEX RAN 1 PART 2D 2024 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | MRW046 | DMT Fatufia |  |  | PALU | -2.8193 | 122.1579 | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 30-May-24 | Done | Done | 31-May-24 | Done | 100% | 30-May-24 | 31-May-24 | 31-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-06-16 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-17 | 2024-07-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
575 | 2403-UMIMO-4G#RO-LBA073-0008 | Activity Non MPSL NVEEH SUL | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU | LBA073 | GPS Kawasi Lama |  |  | TERNATE | -1.5772 | 127.4423 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-03-26 | Done | Done | 2024-03-27 | Done | 100% | 2024-03-26 | 2024-03-26 | 2024-03-27 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | July-26 | Done Tagging | July-26 | Done Tagging | Work Not Start | [11 empty] | 13-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3406 | 2024-04-19 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
576 | 2403-UMIMO-4G#RO-LBA082-0009 | Activity Non MPSL NVEEH SUL | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU | LBA082 | PT. HPAL OBI Harita Konstruksi |  |  | TERNATE | -1.5483 | 127.4195 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Aditia | Done Productivity 100 % |  |  |  |  | 2024-03-23 | Done | Done | 2024-03-23 | Done | 100% | 2024-03-23 | 2024-03-23 | 2024-03-23 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | July-26 | Done Tagging | July-26 | Done Tagging | waiting tiket | [11 empty] | 15-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3406 | 2024-04-19 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
577 | 2403-UMIMO-4G#RO-MRW016-0012 | Activity Non MPSL RAFI 2024 SUL | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU | MRW016 | Bahodopi |  |  | PALU | -2.7953 | 122.129 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-03-28 | Done | Done | 2024-03-28 | Done | 100% | 2024-03-28 | 2024-03-28 | 2024-03-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-03-28 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 31-May-24 | 31-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
578 | 2403-UMIMO-4G#RO-MRW370-0013 | Activity Non MPSL RAFI 2024 SUL | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | MRW370 | PenginapanPelangi-PTI |  |  | PALU | -2.7913 | 122.1233 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-04-05 | Done | Done | 2024-04-07 | Done | 100% | 2024-04-05 | 2024-04-06 | 2024-04-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 3-May-24 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 27-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
579 | 2403-UMIMO-4G#RO-MRW378-0010 | Activity Non MPSL NVEEH SUL | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU | MRW378 | BTII G2 - Baoshuo |  |  | PALU | -2.2619 | 121.7714 | YPTT | March-24 |  | 2024 | 2024 | [28 empty] | Hold issue akses imip | [5 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-03-20 | Done | Done | 2024-03-20 | Done | 100% | 2024-03-20 | 2024-03-20 | 2024-03-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-03-24 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 2025-07-01 | 2025-01-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3352 | 2024-04-17 | 2025-01-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
580 | 2403-UMIMO-4G#RO-MRW379-0002 | Activity Non MPSL NVEEH SUL | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU and Add Module BBU | MRW379 | BTII G3 - Baoshuo |  |  | PALU | -2.2658 | 121.759 | YPTT | March-24 |  | 2024 | 2024 | [28 empty] | IMIP | [5 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-03-21 | Done | Done | 2024-03-21 | Done | 100% | 2024-03-21 | 2024-03-21 | 2024-03-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-03-21 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 2024-06-08 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3352 | 2024-04-17 | 13-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
581 | 2403-UMIMO-4G#RO-SSU075-0004 | Activity Non MPSL NVEEH SUL | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | TER071 | TBG Jambu Ternate |  |  | TERNATE | 0.79781 | 127.3862 | YPTT | December-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 11-Dec-24 | Done | Done | 11-Dec-24 | Done | 100% | 11-Dec-24 | 11-Dec-24 | 11-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 16-Dec-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 22-May-25 | 23-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5723 | 24-Dec-24 | 2025-03-10 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
582 | 2403-UMIMO-4G#RO-TER072-0014 | Activity Non MPSL RAFI 2024 SUL | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Module BBU | TER072 | TBG Santiong Ternate |  |  | TERNATE | 0.78949 | 127.3875 | YPTT | March-24 |  | 2024 | 2024 | [29 empty] | Release | Release |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-04-04 | Done | Done | 2024-04-04 | Done | 100% | 2024-04-04 | 2024-04-04 | 2024-04-04 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-04-06 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 20-May-24 | 21-May-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3439 | 6-May-24 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
583 | 2404-4GDCS-4G#RO-COI246-0138 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | COI246 | Combat Burangasi Kontu |  | ALL CLOSE | KENDARI | -5673279 | 122787111 | YPTT | 2026-04-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2024-04-25 | Done | Done | 2024-04-26 | Done | 100% | 2024-04-25 | 2024-04-26 | 2024-04-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 6-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-25 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3465 | 15-May-24 | 2024-07-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
584 | 2404-4GDCS-4G#RO-COI593-0139 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | COI593 | Combat MV Desa Lantula 2 |  |  | PALU | -2.2266 | 121.6224 | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 08-May-24 | Done | Done | 10-May-24 | Done | 100% | 08-May-24 | 16-May-24 | 16-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-16 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-22 | 2024-07-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
585 | 2404-4GDCS-4G#RO-COI594-0140 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | COI594 | Combat MV Petasia Timur |  |  | PALU | -2.0802 | 121.4203 | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 07-May-24 | Done | Done | 10-May-24 | Done | 100% | 07-May-24 | 10-May-24 | 10-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 29-Aug-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-11-25 | 2024-11-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
586 | 2404-4GDCS-4G#RO-MRW376-0145 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | MRW376 | Badspot 12 - Molino |  |  | PALU | -2.3963 | 121.87 | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 09-May-24 | Done | Done | 09-May-24 | Done | 100% | 09-May-24 | 09-May-24 | 09-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 9-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 08-Aug-24 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 17-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
587 | 2404-4GDCS-4G#RO-MRW927-0167 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | MRW927 | Labota |  |  | PALU | -2.876 | 122.1827 | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 06-May-24 | Done | Done | 06-May-24 | Done | 100% | 06-May-24 | 06-May-24 | 06-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Aug-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 16-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
588 | 2404-4GDCS-4G#RO-NTI108-0157 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | NTI108 | N3T TANDA OLEO |  |  | PALU | -2.996 | 122.2741 | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 11-May-24 | Done | Done | 11-May-24 | Done | 100% | 11-May-24 | 11-May-24 | 11-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 12-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-15 | 2024-06-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 2024-06-20 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
589 | 2404-4GGSM-4G#RO-PLP111-0563 | Risk Order - Blacksite | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | PLP111 | DMT Pasar Lama Palopo |  |  | PARE PARE | -2.9915 | 120.1949 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 26-May-24 | Done | Done | 27-May-24 | Done | 100% | 26-May-24 | 27-May-24 | 27-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 5-May-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 18-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
590 | 2404-4GGSM-4G#RO-PLP196-0564 | Risk Order - Blacksite | EQP New NE 4G LTE 900 10 Mhz | Add RRU | PLP196 | LSP MCP Tanjung Ringgit |  |  | PARE PARE | -2.9874 | 120.1996 | YPTT | March-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 22-May-24 | Done | Done | 23-May-24 | Done | 100% | 22-May-24 | 23-May-24 | 23-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 5-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-15 | 2024-06-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-06-20 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
591 | 2404-UPMod-4G#672-ADL075-0003 | CAPEX RAN 1 PART 2E 2024 | MODERNIZATION ONLY | Add BBU | ADL075 | PTI Awalo |  | ALL CLOSE | KENDARI | -425952 | 12218887 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 1 | 1 | 0 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),BFAN(1),FA0(1),DCPD7(1),SA(1),CCF0(1),CCE1B(1),CR0(2),BPN2(3),PM5(2) | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 09-May-24 | Done | Done | 10-May-24 | Done | 100% | 09-May-24 | 10-May-24 | 10-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 11-May-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 26-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
592 | 2404-UPMod-4G#672-BAU090-0041 | CAPEX RAN 1 PART 2E 2024 | MODERNIZATION ONLY | Add BBU | BAU090 | TBG Patuno Resort |  | ALL CLOSE | KENDARI | -5.247 | 123.5823 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 1 | 1 | 0 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),CC16B(1),CCE1B(1),UBPG3(1),CR0(2),BPN2(3),SA(1),PM5(2),FA0(1) | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 09-May-24 | Done | Done | 10-May-24 | Done | 100% | 09-May-24 | 10-May-24 | 10-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 16-May-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-30 | 6-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 2024-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
593 | 2404-UPMod-4G#672-BIT070-0022 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Add BBU and RRU | BIT070 | TBG Matuari Stadion |  |  | MANADO | 1.4412 | 125.1048 | YPTT | 2026-04-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Aditia | Done Productivity 100 % |  |  |  |  | 27-May-24 | Done | Done | 27-May-24 | Done | 100% | 27-May-24 | 27-May-24 | 27-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-08 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-23 | 2024-09-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
594 | 2404-UPMod-4G#672-COI610-0011 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Add BBU and RRU | COI610 | Combat Perum Koka ADP |  |  | MANADO | 1.4345 | 124.8543 | YPTT | 2026-04-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 22-May-24 | Done | Done | 23-May-24 | Done | 100% | 22-May-24 | 25-May-24 | 25-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-07 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-23 | 2024-09-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
595 | 2404-UPMod-4G#672-DGL078-0027 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Add BBU and RRU | DGL078 | Protelindo Tenggede Selatan |  |  | PALU | -0.9407 | 119.8627 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 2024-06-24 | Done | Done | 2024-06-25 | Done | 100% | 2024-06-24 | 2024-06-25 | 2024-06-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-05 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 2024-07-17 | 2024-07-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
596 | 2404-UPMod-4G#672-LBA022-0032 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Add BBU | LBA022 | DMT AMASING KALI |  |  | TERNATE | -0.599 | 127.4747 | YPTT | 2026-04-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 31-May-24 | Done | Done | 31-May-24 | Done | 100% | 31-May-24 | 31-May-24 | 31-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 02 June 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-11-07 | 2024-07-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 2024-07-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
597 | 2404-UPMod-4G#672-MAS036-0017 | CAPEX RAN 1 PART 2E 2024 | MODERNIZATION ONLY | Add BBU | MAS036 | DMT ISAT Rampoang |  |  | PARE PARE | -264641 | 120578 | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 15-May-24 | Done | Done | 15-May-24 | Done | 100% | 15-May-24 | 15-May-24 | 15-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 17-May-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 29-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
598 | 2404-UPMod-4G#672-MAS047-0033 | CAPEX RAN 1 PART 2E 2024 | MODERNIZATION ONLY | Add BBU | MAS047 | DMT Poreang |  |  | PARE PARE | -26373 | 120633 | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 16-May-24 | Done | Done | 16-May-24 | Done | 100% | 16-May-24 | 16-May-24 | 16-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 17-May-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 29-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
599 | 2404-UPMod-4G#672-PAL014-0040 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Swap RRU and BBU | PAL014 | BTN Tavanjuka |  |  | PALU | -0.92844 | 119.871 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 24-May-24 | Done | Done | 26-May-24 | Done | 100% | 24-May-24 | 26-May-24 | 26-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 06-Aug |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 28-Aug-24 | 2024-09-02 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
600 | 2404-UPMod-4G#672-PAL025-0038 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Add BBU and RRU | PAL025 | DMT Juanda |  |  | PALU | -0.89739 | 119.8811 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Azbar | Done Productivity 100 % |  |  |  |  | 11-Aug-24 | Done | Done | 13-Aug-24 | Done | 100% | 11-Aug-24 | 13-Aug-24 | 13-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 19-Aug |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-17 | 2024-09-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
601 | 2404-UPMod-4G#672-PAL064-0051 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Swap RRU and BBU | PAL064 | Kasuari-DMT |  |  | PALU | -0.91119 | 119.8948 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-06-06 | Done | Done | 2024-06-08 | Done | 100% | 2024-06-06 | 2024-06-09 | 2024-06-09 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-20 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 2024-09-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
602 | 2404-UPMod-4G#672-PAL070-0004 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Swap RRU and BBU | PAL070 | SKP BTN Lagarutu |  |  | PALU | -0.88353 | 119.8887 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 27-May-24 | Done | Done | 29-May-24 | Done | 100% | 27-May-24 | 29-May-24 | 29-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 18-Aug |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 25-Oct-24 | 25-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
603 | 2404-UPMod-4G#672-PAL119-0057 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Swap RRU and BBU | PAL119 | ZebraIndah-DMT |  |  | PALU | -0.92131 | 119.8889 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 29-May-24 | Done | Done | 31-May-24 | Done | 100% | 29-May-24 | 31-May-24 | 31-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 07-Aug |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 2024-09-30 | 5-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
604 | 2404-UPMod-4G#672-PLP023-0008 | CAPEX RAN 1 PART 2E 2024 | MODERNIZATION ONLY | Add BBU | PLP023 | Telkom Durian Kunyit |  |  | PARE PARE | -2.6423 | 120.2084 | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 18-May-24 | Done | Done | 18-May-24 | Done | 100% | 18-May-24 | 18-May-24 | 18-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 19-May-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 29-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-06-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
605 | 2404-UPMod-4G#672-PSO031-0029 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Swap BBU | PSO031 | Mayasari |  |  | PALU | -2.1396 | 120.7266 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 15-May-24 | Done | Done | 15-May-24 | Done | 100% | 15-May-24 | 15-May-24 | 15-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 17-May |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 25-Oct-24 | 25-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-06-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
606 | 2404-UPMod-4G#672-RHA048-0016 | CAPEX RAN 1 PART 2E 2024 | MODERNIZATION ONLY | Add BBU | RHA048 | TBG Towea |  | ALL CLOSE | KENDARI | -4.5452 | 122.7169 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 1 | 1 | 0 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),BPN2(3),PM5(2),FA0(1),CR0(2),CC1B(2),UBPG3(1) | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 10-May-24 | Done | Done | 10-May-24 | Done | 100% | 10-May-24 | 11-May-24 | 11-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 11-May-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-30 | 7-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
607 | 2404-UPMod-4G#672-SKG027-0014 | CAPEX RAN 1 PART 2E 2024 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | Add BBU | SKG027 | Limpuriliau |  |  | MAKASSAR | -401806 | 119944 | YPTT | 2026-04-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 14-May-24 | Done | Done | 14-May-24 | Done | 100% | 14-May-24 | 14-May-24 | 14-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 19-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 25-Oct-24 | 2024-11-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
608 | 2404-UPMod-4G#672-SNN019-0001 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Add BBU | SNN019 | TBG Sanana |  |  | TERNATE | -2.065 | 125.9804 | YPTT | 2026-04-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 25-May-24 | Done | Done | 26-May-24 | Done | 100% | 25-May-24 | 26-May-24 | 26-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 28 May 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 29-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
609 | 2404-UPMod-4G#672-TDO247-0023 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Add BBU and RRU | TDO247 | DMT Munte Likupang |  |  | MANADO | 1.6931 | 125.01 | YPTT | 2026-04-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 27-May-24 | Done | Done | 28-May-24 | Done | 100% | 27-May-24 | 28-May-24 | 28-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 19 June 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 29-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-12 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
610 | 2404-UPMod-4G#672-TER108-0020 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Swap BTS and BBU | TER108 | MCUNKHAIRTernate |  | MOS by CCSI but imp take over to YPTT due to CCSI no team to continue imp, PR to CCSI_PO No : S1ID2023070101WBF1-1365 | TERNATE | 0.76367 | 127.3356 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | [5 empty] | 2024-06-29 | Done | Done | 2024-06-30 | Done | 100% | 2024-06-29 | 2024-06-30 | 2024-06-30 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 02 July 2024 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 2024-11-07 | 2024-07-17 |  | PO NY Release |  |  | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload
611 | 2404-UPMod-4G#672-THN001-0053 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Add BBU and RRU | THN001 | Sangir Talaud |  |  | MANADO | 3.6322 | 125.514 | YPTT | 2026-04-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 30-May-24 | Done | Done | 30-May-24 | Done | 100% | 30-May-24 | 31-May-24 | 31-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 10 June 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 29-Aug-24 | 2024-09-02 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
612 | 2404-UPMod-4G#672-THN025-0039 | CAPEX RAN 1 PART 2E 2024 | EQP Modular Upgrade | Add BBU and RRU | THN025 | Tamako Raya |  |  | MANADO | 3.4525 | 125.5046 | YPTT | 2026-04-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 26-May-24 | Done | Done | 26-May-24 | Done | 100% | 26-May-24 | 27-May-24 | 27-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 14 June 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 26-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
613 | 2405-4GDCS-4G#RO-COI132-0163 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | COI132 | CombatARRKilong |  |  | TERNATE | -3.9761 | 119.6118 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-07-15 | Done | Done | 2024-07-21 | Done | 100% | 2024-07-15 | 2024-07-17 | 2024-07-21 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 22 July 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-30 | 4-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4332 | 2024-07-12 | 17-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
614 | 2405-4GDCS-4G#RO-LBA125-0177 | 0 | EQP New NE 4G LTE 1800 20 Mhz 4T4R + DCS | Add Antenna and RRU and Module BBU | LBA125 | KPS Smelter 1 |  |  | TERNATE | -1.515922 | 127446187 | YPTT | June-24 |  | 2024 | 2024 | LBA125-N-3M2P | [28 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-11-15 | Done | Done | 2024-11-19 | Done | 100% | 2024-11-15 | 2024-11-17 | 2024-11-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-11-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-11-21 | 2024-11-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4492 | 2024-07-30 | 28-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
615 | 2405-4GDCS-4G#RO-LBA126-0178 | 0 | EQP New NE 4G LTE 1800 20 Mhz 4T4R + DCS | Add Antenna and RRU and Module BBU (New Infra) | LBA126 | TBP Mess |  |  | TERNATE | -1.525183 | 127431221 | YPTT | June-24 |  | 2024 | 2024 | LBA126-N-3M2P | [28 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 08-Aug-24 | Done | Done | 13-Aug-24 | Done | 100% | 08-Aug-24 | 13-Aug-24 | 13-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 24-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-09 | 2024-09-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
616 | 2405-4GDCS-4G#RO-LBA127-0179 | 0 | EQP New NE 4G LTE 1800 20 Mhz 4T4R + DCS | Add Antenna and RRU and Module BBU (New Infra) | LBA127 | ONC Smelter 2 |  |  | TERNATE | -1.555459 | 127444232 | YPTT | June-24 |  | 2024 | 2024 | LBA127-N-3M2P | [28 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-07-30 | Done | Done | 04-Aug-24 | Done | 100% | 2024-07-30 | 01-Aug-24 | 03-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 5-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-20 | 2024-09-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 5-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
617 | 2405-4GDCS-4G#RO-PIN079-0160 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 1800 20 Mhz | Swap Module BBU | PIN079 | TBG Mattiro Sompo |  |  | PARE PARE | -3.8454 | 119.6142 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 24-May-24 | Done | Done | 24-May-24 | Done | 100% | 24-May-24 | 24-May-24 | 24-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-04 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-07-17 | 2024-07-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
618 | 2405-4GDCS-4G#RO-SKG099-0174 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Swap Module BBU | SKG099 | TBG Ujunge |  |  | MAKASSAR | 12002303 | -407882 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-06-12 | Done | Done | 2024-06-12 | Done | 100% | 2024-06-12 | 2024-06-12 | 2024-06-12 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-12 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3968 | 2024-06-14 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
619 | 2405-4GDCS-4G#RO-SKG205-0154 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | SKG205 | Tengnga |  |  | MAKASSAR | -4.0613 | 120.1823 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 29-May-24 | Done | Done | 30-May-24 | Done | 100% | 29-May-24 | 30-May-24 | 30-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-24 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-07-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
620 | 2405-4GDCS-4G#RO-TDO153-0175 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Swap RRU and Module BBU | TDO153 | Protelindo Lumpias |  |  | MANADO | 1.5823 | 125.007 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Aditia | Done Productivity 100 % |  |  |  |  | 2024-06-26 | Done | Done | 2024-07-01 | Done | 100% | 2024-06-26 | 2024-07-01 | 2024-07-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 23 July 2024 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-13 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 2024-09-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
621 | 2405-4GGSM-4G#RO-BAU217-0586 | 0 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | BAU217 | TBG Waha |  | ALL CLOSE | KENDARI | -5.7447 | 123.8985 | YPTT | June-24 |  | 2024 | 2024 |  |  | MOBI 12 Port | 1 | 1 | R9224E M1821 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | MOBI 10 Port | 1 | 1 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2024-06-20 | Done | Done | 2024-06-21 | Done | 100% | 2024-06-20 | 2024-06-21 | 2024-06-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-26 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 17-Aug-24 | 19-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4217 | 2024-06-30 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
622 | 2405-4GGSM-4G#RO-MRW923-0585 | 0 | EQP New NE 4G LTE 900 10 MHz | Add RRU and Module BBU | MRW923 | EMA Split Wosu |  |  | PALU | -2.3596 | 121.8492 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-07-01 | Done | Done | 2024-07-01 | Done | 100% | 2024-07-01 | 2024-07-01 | 2024-07-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2026-07-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-24 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
623 | 2405-4GGSM-4G#RO-PAL106-0594 | 0 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Module BBU and Add RRU | PAL106 | TBG Lambara |  |  | PALU | -0.73251 | 119.8778 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-06-26 | Done | Done | 2024-06-27 | Done | 100% | 2024-06-26 | 2024-06-27 | 2024-06-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-03 |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 2024-09-17 | 2024-09-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
624 | 2405-4GGSM-4G#RO-SKG204-0583 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Swap Antenna and Add RRU and Module BBU | SKG204 | Wiring Palenae |  |  | MAKASSAR | -4.1626 | 120.035 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 2024-06-15 | Done | Done | 2024-06-20 | Done | 100% | 2024-06-15 | 2024-06-19 | 2024-06-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-21 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-07 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4217 | 2024-06-30 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
625 | 2405-4GGSM-4G#RO-SSU002-0568 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 900 10 Mhz | Swap Antenna and Add RRU and Module BBU | SSU002 | TBG Puskesmas Sagea |  |  | TERNATE | 0.46479 | 128.0969 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-06-15 | Done | Done | 2024-06-19 | Done | 100% | 2024-06-15 | 2024-06-19 | 2024-06-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 20 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-Aug-24 | 2024-07-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 29-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
626 | 2405-4GGSM-4G#RO-WTG084-0584 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Swap Antenna and Add RRU and Module BBU | WTG084 | PTI Baringeng Sembada |  |  | MAKASSAR | -4.2157 | 123.1157 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 23-Aug-24 | Done | Done | 24-Aug-24 | Done | 100% | 23-Aug-24 | 24-Aug-24 | 24-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-20 | 2024-09-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4916 | 2024-09-06 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
627 | 2405-4T4R-4G#RO-DGL012-0009 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap Antenna and RRU and Cabinet+BBU | DGL012 | Agoamas |  |  | PALU | 0.73803 | 120.1317 | YPTT | July-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-07-27 | Done | Done | 2024-07-29 | Done | 100% | 2024-07-27 | 2024-07-28 | 2024-07-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-31 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 2024-09-27 | 5-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
628 | 2405-4T4R-4G#RO-RHA060-0010 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2100 20 - 20Mhz 4T4R | Swap RRU | RHA060 | Protelindo Talaga Kecil |  | ALL CLOSE | KENDARI | -5.4744 | 122.0753 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8852E S2100 | 2 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2024-06-03 | Done | Done | 2024-06-02 | Done | 100% | 2024-06-03 | 2024-06-03 | 2024-06-03 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-03 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
629 | 2405-4T4R-4G#RO-TDE047-0013 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap Antenna and RRU and Add Module BBU | TDE047 | DMT Sofifi |  |  | TERNATE | 0.70365 | 127.5577 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-06-17 | Done | Done | 2024-06-18 | Done | 100% | 2024-06-17 | 2024-06-17 | 2024-06-17 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 22 June 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 15-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
630 | 2405-ADSTR-4G#RO-KKA059-0047 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Module BBU | KKA059 | PTI Tiwu |  | ALL CLOSE | KENDARI | -3.3137 | 120.9799 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBPd0p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),BFAN(1),DCPD7(1),Cabinet(1),FA0(1),PM5(2),BPN2(4),CR0(2),CCE1B(1),CCF0(1) | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 28-May-24 | Done | Done | 29-May-24 | Done | 100% | 28-May-24 | 29-May-24 | 29-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 30-May-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
631 | 2405-ADSTR-4G#RO-LBA034-0053 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Add Sector LTE 2100 4T4R | Add Antenna and RRU and Swap Module BBU | LBA034 | Gebe |  |  | TERNATE | -0.067153 | 129.4225 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-09-02 | Done | Done | 2024-09-05 | Done | 100% | 2024-09-02 | 2024-09-03 | 2024-09-03 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-09-05 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 15-Oct-24 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
632 | 2405-ADSTR-4G#RO-LBA119-0033 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Add Sector LTE 2300 Massive MIMO 64T64R | Add RRU | LBA119 | Mess DCM |  |  | TERNATE | -1.553 | 127.4293 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-06-24 | Done | Done | 2024-06-25 | Done | 100% | 2024-06-24 | 2024-06-25 | 2024-06-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-17 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 27-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
633 | 2405-ADSTR-4G#RO-MRW028-0043 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Add Sector LTE 1800 4T4R | Swap RRU and Module BBU | MRW028 | DMT Atananga |  |  | PALU | -2.2175 | 121.7008 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 31-May-24 | Done | Done | 2024-06-01 | Done | 100% | 31-May-24 | 2024-06-02 | 2024-06-02 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 11-Aug-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-01-10 | 5-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 2024-11-08 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
634 | 2405-ADSTR-4G#RO-MRW077-0008 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Add Sector LTE 2300 4T4R | Add RRU | MRW077 | TBG Arthabumi Morowali |  |  | PALU | -3.0521 | 122.273 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 25-May-24 | Done | Done | 27-May-24 | Done | 100% | 25-May-24 | 27-May-24 | 27-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2026-06-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-24 | 2024-07-01 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
635 | 2405-ADSTR-4G#RO-PLP073-0021 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Add Sector LTE 1800 4T4R | Add Antenna and RRU and Swap Module BBU | PLP073 | TBG Belopa Utara |  |  | PARE PARE | -3.3665 | 120.3627 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 2024-06-13 | Done | Done | 2024-06-15 | Done | 100% | 2024-06-13 | 2024-06-14 | 2024-06-15 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 16-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
636 | 2405-ADSTR-4G#RO-PLP077-0057 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Add Sector LTE 2100 4T4R | Swap RRU and module BBU | PLP077 | Protelindo Lanipa |  |  | PARE PARE | -3.2638 | 120.3444 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 29-May-24 | Done | Done | 29-May-24 | Done | 100% | 29-May-24 | 29-May-24 | 29-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-03 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 16-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 18-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
637 | 2405-ADSTR-4G#RO-PLP080-0022 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Add Sector LTE 1800 4T4R | Add Antenna and RRU and Swap Module BBU | PLP080 | Protelindo Battang Kaleakan |  |  | PARE PARE | -2.962 | 120.1484 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yusuf | Done Productivity 100 % |  |  |  |  | 2024-07-04 | Done | Done | 2024-07-05 | Done | 100% | 2024-07-04 | 2024-07-05 | 2024-07-05 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-11 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-17 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4348 | 2024-07-15 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
638 | 2405-ADSTR-4G#RO-RHA049-0041 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Module BBU | RHA049 | DMT Labunti |  | ALL CLOSE | KENDARI | -4.7543 | 122.7217 | YPTT | May-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBpd0p(3) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),BFAN5(1),LPU(1),DCPD7(1),PM5(2),SA(1),FA0(1),CCE1B(2),CR0(1),FS5(1),UBPG(1),BPN(3) | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-06-12 | Done | Done | 2024-06-12 | Done | 100% | 2024-06-12 | 2024-06-13 | 2024-06-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-19 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 17-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
639 | 2405-ADSTR-4G#RO-RHA054-0028 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Add Sector LTE 2100 4T4R | Swap RRU and Module BBU | RHA054 | TBG Bonegunu |  | ALL CLOSE | KENDARI | -4.9484 | 122.9748 | YPTT | May-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9264E M1821 | 1 | 1 | 1 | 0 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800 | 1 | Cabinet(1),BBU(1),BFAN5(1),DCPD7(1),LPU(1),BPN2(2),BPQ(1),CCE1B(2),CR0(2),PM5(2),SA(1) | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 28-May-24 | Done | Done | 29-May-24 | Done | 100% | 28-May-24 | 29-May-24 | 29-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 30-May-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 17-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
640 | 2405-ADSTR-4G#RO-SSU043-0023 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Add Sector LTE 1800 4T4R | Add Antenna and RRU | SSU043 | DMT Sagea |  |  | TERNATE | 0.4622 | 128.1005 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-06-16 | Done | Done | 2024-06-16 | Done | 100% | 2024-06-16 | 2024-06-16 | 2024-06-16 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 20 June 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 07-Oct-24 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 2-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
641 | 2405-ADSTR-4G#RO-SSU047-0035 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Add Sector LTE 2300 4T4R | Add RRU | SSU047 | TBG Pasar Lelilef |  |  | TERNATE | 0.4665 | 127.9344 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Rahmanto | Done Productivity 100 % |  |  |  |  | 22-May-24 | Done | Done | 22-May-24 | Done | 100% | 22-May-24 | 22-May-24 | 22-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 24 May 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-07 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
642 | 2405-ADSTR-4G#RO-THN008-0061 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Add Sector LTE 1800 4T4R | Add Antenna and RRU and Swap Module BBU | THN008 | Tagulandang |  |  | MANADO | 2.3565 | 125.397 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-06-29 | Done | Done | 2024-06-29 | Done | 100% | 2024-06-29 | 2024-06-30 | 2024-06-30 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 03 July 2024 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 2024-09-13 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
643 | 2405-NNE4G-4G#RO-ADL032-0768 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | ADL032 | TBG Buapinang 2 |  | ALL CLOSE | KENDARI | -4.7916 | 121.6164 | YPTT | June-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | Vbpdop(1),VBPd2p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),BFAN5(1),LPU(1),FA0(1),PM5(2),BPN2(3),BPQ(1),CR0(2),CCF0(1),CCE1B(1),SA(1) | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 20-Oct-24 | Done | Done | 21-Oct-24 | Done | 100% | 20-Oct-24 | 21-Oct-24 | 21-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 23-Oct-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-11-11 | 2024-11-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5299 | 24-Oct-24 | 9-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
644 | 2405-NNE4G-4G#RO-ADL083-0769 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | ADL083 | Protelindo Pancalogam |  | ALL CLOSE | KENDARI | -4.6588 | 121.9117 | YPTT | June-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | Vbpdop(1),VBPd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(10,BFAN5(1),DCPD7(1),LPU(1),BBU(1),FA0(1),PM5(2),BPN2(3),UBPG3(1),CR0(2),CCF0(1),SA(1) | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2024-06-25 | Done | Done | 2024-06-25 | Done | 100% | 2024-06-25 | 2024-06-25 | 2024-06-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-27 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 16-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
645 | 2405-NNE4G-4G#RO-ADL143-0770 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | ADL143 | Anugerah Kampung Bali |  | ALL CLOSE | KENDARI | -4.0726 | 122.3869 | YPTT | June-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | Vbpdop(1),VBPd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),BFAN5(1),DCPD7(1),LPU(1),FA0(1),PM5(2),BPN2(2),CR0(2),CCF0(1),SA(1) | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2024-06-28 | Done | Done | 2024-06-28 | Done | 100% | 2024-06-28 | 2024-06-28 | 2024-06-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-29 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-30 | 5-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 16-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
646 | 2405-NNE4G-4G#RO-ADL251-0487 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | ADL251 | DMT Sanggi-Sanggi |  | ALL CLOSE | KENDARI | -4.3441 | 122.3063 | YPTT | May-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBPd2p(1),VBPd0p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),PM5(2),SA(1),FA0(1),CCE1B(1),CR0(2),BPN(2),BPQ(1),DCPD7(1) | [6 empty] | PT. Djaya Sukses Pratama | Herdianto | Done Productivity 100 % |  |  |  |  | 28-May-24 | Done | Done | 28-May-24 | Done | 100% | 28-May-24 | 28-May-24 | 28-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 31-May-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 17-Aug-24 | 19-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
647 | 2405-NNE4G-4G#RO-ADL300-0771 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | ADL300 | PTI Poros Lameroro |  | ALL CLOSE | KENDARI | -4.7577 | 122.0242 | YPTT | June-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | Vbpdop(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2024-06-23 | Done | Done | 2024-06-23 | Done | 100% | 2024-06-23 | 2024-06-23 | 2024-06-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-27 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-07 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
648 | 2405-NNE4G-4G#RO-BAU060-0449 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Swap Antenna and RRU and Module BBU | BAU060 | Protelindo Tomia Timur |  | NR EHS & Dismantle | KENDARI | -5.7562 | 123.9899 | YPTT | May-24 |  | 2024 | 2024 |  |  | MOBI 12 Port | 3 | 0 | R9264E M1821 | 3 | 1 | 1 | 0 | VBpd2p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | TDQ 4 Port(1),Kathrein 4 Port(2) | 3 | 0 | No Need | 0 | R8872A S1800 | 3 | BBU(1),CC16B(1),UBPG(1),FS5(1),BPN2(1),PM3(2),SA(1),LPU(1),BFAN5(1),DCPD71),Cabinet(1) | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2024-07-03 | Done | Done | 2024-07-04 | Done | 100% | 2024-07-03 | 2024-07-04 | 2024-07-04 | Connected | Connected |  | 01-Passed | 01-Passed | NR | 2024-07-17 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4348 | 2024-07-15 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
649 | 2405-NNE4G-4G#RO-BAU206-0498 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | BAU206 | DMT MCP Bandara Matohara Wanci |  | ALL CLOSE | KENDARI | -5.287 | 123.6396 | YPTT | May-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | Vbpdop(1),VBPd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),CCF0(1),CR0(1),BPQ(1),BPN2(2),PM5(2),SA(1),DCPD7(1)LPU(1),BFAN5(1) | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 31-May-24 | Done | Done | 2024-06-01 | Done | 100% | 31-May-24 | 2024-06-01 | 2024-06-01 | Connected | Connected |  | 01-Passed | 01-Passed | NR | 19-Aug-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 17-Aug-24 | 19-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
650 | 2405-NNE4G-4G#RO-BAU259-0689 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Swap Antenna and RRU and Module BBU | BAU259 | Wakatobi Dive Resort |  | NR ATP | KENDARI | -5.7749 | 123.8953 | YPTT | June-24 |  | 2024 | 2024 |  | Upgrade CSU | MOBI 12 Port | 1 | 0 | R9264E M1821 | 3 | 1 | 1 | 0 | VBpd2p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | Kathrein 2 port(3),TDQ 4 Port(1) | 4 | 0 | No Need | 0 | R8872A S1800 | 1 | Cabinet(1),BBU(1),CCE1B(1),CR0(1),BPN2(2),PM5(1),SA(1),LPU(1),BFAN5(1)FA0(1),DCPD7(1) | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2024-06-27 | Done | Done | 2024-06-28 | Done | 100% | 2024-06-27 | 2024-06-28 | 2024-06-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-11-05 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
651 | 2405-NNE4G-4G#RO-BAU287-0453 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | BAU287 | DMT Non 3T Kahiyanga |  | ALL CLOSE | KENDARI | -5.7543 | 123.9499 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 3 | 0 | 0 | 0 | VBpd0p(1), | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800 | 3 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2024-06-03 | Done | Done | 2024-06-04 | Done | 100% | 2024-06-03 | 2024-06-04 | 2024-06-04 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-26 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-26 | 4-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | NEW PO
652 | 2405-NNE4G-4G#RO-BGA002-0454 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU and Module BBU | BGA002 | DMT Non3T Laanoipi |  | ALL CLOSE | KENDARI | -4.893 | 122.9945 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 2 | 0 | 0 | 0 | VBPd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 30-May-24 | Done | Done | 31-May-24 | Done | 100% | 30-May-24 | 31-May-24 | 31-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 31-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-25 | 2024-07-01 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
653 | 2405-NNE4G-4G#RO-BIT006-0474 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 2300 50 MHz | Swap Antenna and Module BBU and Add RRU | BIT006 | DMT Kungkungan |  |  | MANADO | 1.469 | 125.2269 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-06-13 | Done | Done | 2024-06-13 | Done | 100% | 2024-06-13 | 2024-06-13 | 2024-06-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-10 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-23 | 2024-09-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
654 | 2405-NNE4G-4G#RO-BIT008-0780 | 0 | EQP New NE 4G LTE 2300 50 MHz | Swap Antenna and Add RRU and Module BBU | BIT008 | DMT Danowudu |  |  | MANADO | 1.4757 | 125.13 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-06-21 | Done | Done | 2024-06-22 | Done | 100% | 2024-06-21 | 2024-06-22 | 2024-06-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 02 July 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 16-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4217 | 2024-06-30 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
655 | 2405-NNE4G-4G#RO-BIT025-0529 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | BIT025 | Protelindo Mawali |  |  | MANADO | 1.4403 | 125.2362 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-06-08 | Done | Done | 2024-06-08 | Done | 100% | 2024-06-08 | 2024-06-08 | 2024-06-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 11 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-May-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3969 | 2024-06-14 | 13-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
656 | 2405-NNE4G-4G#RO-BIT027-0500 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | BIT027 | DMT Kolombo |  |  | MANADO | 1.4523 | 125.1839 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-06-04 | Done | Done | 2024-06-04 | Done | 100% | 2024-06-04 | 2024-06-04 | 2024-06-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 13 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-May-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 13-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
657 | 2405-NNE4G-4G#RO-BIT031-0501 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Add RRU and Module BBU | BIT031 | DMT Kadoodan |  |  | MANADO | 1.4377 | 125.1362 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Aditia | Done Productivity 100 % |  |  |  |  | 2024-06-07 | Done | Done | 2024-06-07 | Done | 100% | 2024-06-07 | 2024-06-07 | 2024-06-07 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 15 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-19 | 2024-07-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3969 | 2024-06-14 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
658 | 2405-NNE4G-4G#RO-BIT063-0540 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | BIT063 | TBG Pateten Maramis |  |  | MANADO | 1.4498 | 125.1747 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Aditia | Done Productivity 100 % |  |  |  |  | 28-May-24 | Done | Done | 28-May-24 | Done | 100% | 28-May-24 | 28-May-24 | 28-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 03 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-May-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 13-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
659 | 2405-NNE4G-4G#RO-BIT064-0781 | 0 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Swap Module BBU | BIT064 | DMT Kolombo Btg |  |  | MANADO | 1.4569 | 125.1865 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-06-28 | Done | Done | 2024-06-28 | Done | 100% | 2024-06-28 | 2024-06-28 | 2024-06-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 30-Aug-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-13 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
660 | 2405-NNE4G-4G#RO-BIT108-0782 | 0 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Swap Module BBU | BIT108 | DMT MCP Pussung Girian |  |  | MANADO | 1.444 | 125.1217 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-06-26 | Done | Done | 2024-06-27 | Done | 100% | 2024-06-26 | 2024-06-27 | 2024-06-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 05 July 2024 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 09-Dec-24 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 2024-09-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
661 | 2405-NNE4G-4G#RO-COI129-0685 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Swap Antenna and RRU and Module BBU | COI767 | Combat Kabaena |  | NY Tag Dismantle | KENDARI | -5.2747 | 121.8377 | YPTT | December-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 3 | 3 | R9264E M1821 | 3 | 1 | 1 | 0 | VBPd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | DBXLHA 4Port | 3 | 3 | No Need | 0 | R8872A S1800 | 3 | Cabinet(1),BBU(1),SA(1),PM5(1),CCE1B(1),CR0(1),BPN2(3),DCPD7(1),BFAN5(1)LPU(1) | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 14-Dec-24 | Done | Done | 15-Dec-24 | Done | 100% | 14-Dec-24 | 15-Dec-24 | 15-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 16-Dec-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-02-18 | 2025-02-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5722 | 24-Dec-24 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
662 | 2405-NNE4G-4G#RO-COI562-0700 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Swap Antenna and RRU and Module BBU | COI562 | COMBAT MNR KALUKU |  |  | MAKASSAR | -3.7566 | 120.3611 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 2024-06-12 | Done | Done | 2024-06-13 | Done | 100% | 2024-06-12 | 2024-06-13 | 2024-06-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-26 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 20-Aug-24 | 21-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3968 | 2024-06-14 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
663 | 2405-NNE4G-4G#RO-COI609-1017 | 0 | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Module BBU and Add RRU | COI609 | Combat Pasar Malam Bahodopi |  |  | PALU | -2.7899 | 122.1335 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-06-15 | Done | Done | 2024-06-16 | Done | 100% | 2024-06-15 | 2024-06-16 | 2024-06-16 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2026-06-21 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 17-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 29-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
664 | 2405-NNE4G-4G#RO-COI615-0793 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | COI615 | Combat Sassa Gambesi |  |  | TERNATE | 3.5633 | 125.5831 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-06-27 | Done | Done | 2024-06-28 | Done | 100% | 2024-06-27 | 2024-06-28 | 2024-06-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | ############### |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 09-Dec-24 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
665 | 2405-NNE4G-4G#RO-COI769-0440 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Swap Module BBU | COI769 | Combat MOP Sampuabalo Ambuau Indah |  | ALL CLOSE | KENDARI | -5.4339 | 123.0122 | YPTT | May-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | 0 | 0 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),Cabinet(1),CCE1B(1),CR0(1),PM5(2),SA(1),BPN2(2),FA0(1),DCPD7(1),LPU(1),BFAN5(1) | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 31-May-24 | Done | Done | 2024-06-01 | Done | 100% | 31-May-24 | 2024-06-01 | 2024-06-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-01 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-30 | 4-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
666 | 2405-NNE4G-4G#RO-DGL038-0795 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Add RRU and Module BBU | DGL038 | DMT Boya |  |  | PALU | -0.66581 | 119.7393 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 2024-06-28 | Done | Done | 2024-06-28 | Done | 100% | 2024-06-28 | 2024-06-28 | 2024-06-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-17 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 2024-09-17 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
667 | 2405-NNE4G-4G#RO-DGL118-0827 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | DGL118 | PST MCP Mpanau |  |  | PALU | -0.95061 | 119.918 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | hendro | Done Productivity 100 % |  |  |  |  | 2024-06-21 | Done | Done | 2024-06-21 | Done | 100% | 2024-06-21 | 2024-06-21 | 2024-06-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-10 |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 20-Aug-24 | 21-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 29-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
668 | 2405-NNE4G-4G#RO-DGL132-0710 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Module BBU | DGL132 | EBT Ganti |  |  | PALU | -0.70493 | 119.7296 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 2024-06-28 | Done | Done | 2024-06-29 | Done | 100% | 2024-06-28 | 2024-06-29 | 2024-06-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-18 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 20-Aug-24 | 21-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
669 | 2405-NNE4G-4G#RO-DGL150-0704 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | DGL150 | DMT Dombu |  |  | PALU | -0.96691 | 119.7806 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-06-22 | Done | Done | 2024-06-22 | Done | 100% | 2024-06-22 | 2024-06-22 | 2024-06-22 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-22 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-07 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 28-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
670 | 2405-NNE4G-4G#RO-DGL157-0830 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | DGL157 | DMT Tosale |  |  | PALU | -0.7558 | 119.6821 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-06-28 | Done | Done | 2024-06-28 | Done | 100% | 2024-06-28 | 2024-06-28 | 2024-06-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-17 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 2024-09-27 | 4-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
671 | 2405-NNE4G-4G#RO-KKA020-0522 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | KKA020 | Rate-Rate |  | ALL CLOSE | KENDARI | -4.0611 | 121.8817 | YPTT | May-24 |  | 2024 | 2024 |  | Upgrade CSU | Mobi 10 Port | 1 | 1 | R9614 S2300 | 1 | 1 | 1 | 0 | VBPd2p(1),VBPd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | DBXRHA 4 Port,Kathrein 2 Port | 2 | 2 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),PM5(2),SA(1),CR0(1),FS5(1),CCE1B(1),BPN2(3),FA0(1),DCPD7(1),BFAN5(1),LPU(1) | [6 empty] | PT. Djaya Sukses Pratama | Maman Putrawan | Done Productivity 100 % |  |  |  |  | 29-May-24 | Done | Done | 30-May-24 | Done | 100% | 29-May-24 | 30-May-24 | 30-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-19 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
672 | 2405-NNE4G-4G#RO-KKA075-0799 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | KKA075 | DMT Lasusua Kota Baru |  | ALL CLOSE | KENDARI | -3.4942 | 120.88 | YPTT | June-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBPd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(10,BBU(1),BPN2(3),FS5(1),CR0(1),CCE1B(1),PM5(2),SA(1),FA0(1),DCPD7(1),LPU(1),BFAN5(1) | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-06-24 | Done | Done | 2024-06-24 | Done | 100% | 2024-06-24 | 2024-06-25 | 2024-06-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-26 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 17-Aug-24 | 19-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
673 | 2405-NNE4G-4G#RO-KKA101-0800 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | KKA101 | PTI Tanggaruru |  | ALL CLOSE | KENDARI | -3.0025 | 121.1116 | YPTT | June-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBpd0p(3) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),DCPD10(1),BPN2(3),UBPG(1),CR0(2),CCE1B(1),PM5(2),SA(1),FA0(1),BFAN5(10,LPU(1) | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-06-26 | Done | Done | 2024-06-27 | Done | 100% | 2024-06-26 | 2024-07-27 | 2024-06-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-27 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 5-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
674 | 2405-NNE4G-4G#RO-KKA132-0523 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | KKA132 | LSP Pohu Ranteangin |  | ALL CLOSE | KENDARI | -3.6482 | 121.0039 | YPTT | May-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),PM5(1),PM3(1),SA(1),CR0(2),CCE1B(1),BPN2(2),UBPG3(1),FA0(1),BFAN5(1)DCPD7(1),Cabinet(1) | [6 empty] | PT. Djaya Sukses Pratama | Maman Putrawan | Done Productivity 100 % |  |  |  |  | 2024-06-13 | Done | Done | 2024-06-14 | Done | 100% | 2024-06-13 | 2024-06-14 | 2024-06-14 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-14 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 21-Aug-24 | 22-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
675 | 2405-NNE4G-4G#RO-KKA145-0524 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | KKA145 | DMT Lorong Mistik |  | ALL CLOSE | KENDARI | -4.0696 | 121.6181 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBPd0p(1) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | PT. Djaya Sukses Pratama | Maman Putrawan | Done Productivity 100 % |  |  |  |  | 29-May-24 | Done | Done | 29-May-24 | Done | 100% | 29-May-24 | 29-May-24 | 29-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 29-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-25 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
676 | 2405-NNE4G-4G#RO-KKA156-0502 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU | KKA156 | CMI Wowoli |  | ALL CLOSE | KENDARI | -4.5307 | 121.508 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | PT. Djaya Sukses Pratama | Maman Putrawan | Done Productivity 100 % |  |  |  |  | 2024-06-01 | Done | Done | 2024-06-01 | Done | 100% | 2024-06-01 | 2024-06-01 | 2024-06-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-01 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-25 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
677 | 2405-NNE4G-4G#RO-KKA162-0831 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | KKA162 | DMT Collo Uluwawo |  | ALL CLOSE | KENDARI | -3.6799 | 121.0316 | YPTT | June-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-06-23 | Done | Done | 2024-06-23 | Done | 100% | 2024-06-23 | 2024-06-23 | 2024-06-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-07 | 2024-07-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
678 | 2405-NNE4G-4G#RO-MAJ021-0854 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | MAJ021 | DMT ISAT Malundak |  |  | PARE PARE | -301323 | 11885811 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 13-Aug-24 | Done | Done | 15-Aug-24 | Done | 100% | 13-Aug-24 | 14-Aug-24 | 14-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 26-Aug-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-04-10 | 5-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4913 | 2024-09-05 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
679 | 2405-NNE4G-4G#RO-MAJ045-0855 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | MAJ045 | DMT Lembang |  |  | PARE PARE | -355291 | 11898455 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-25 | Done | Done | 2024-06-25 | Done | 100% | 2024-06-25 | 2024-06-25 | 2024-06-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-04 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 17-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
680 | 2405-NNE4G-4G#RO-MAJ069-0719 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | MAJ069 | Protelindo Salutambung |  |  | PARE PARE | -308768 | 11883487 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-15 | Done | Done | 2024-06-15 | Done | 100% | 2024-06-15 | 2024-06-15 | 2024-06-15 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-16 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-25 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 2-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
681 | 2405-NNE4G-4G#RO-MAM026-0856 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | MAM026 | Telkom STO Mamuju |  |  | PARE PARE | -2.68 | 11888889 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-07-24 | Done | Done | 2024-07-24 | Done | 100% | 2024-07-24 | 2024-07-24 | 2024-07-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-10 | 4-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
682 | 2405-NNE4G-4G#RO-MAM045-0683 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | MAM045 | C_MAM045M41_BelangBelang-DMT |  |  | PARE PARE | 0 | 0 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-29 | Done | Done | 2024-06-29 | Done | 100% | 2024-06-29 | 2024-06-29 | 2024-06-29 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-Dec-24 | 7-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 29-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
683 | 2405-NNE4G-4G#RO-MAM064-0857 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | MAM064 | DMT Bonda Pappalang |  |  | PARE PARE | -241875 | 11913759 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-21 | Done | Done | 2024-06-22 | Done | 100% | 2024-06-21 | 2024-06-22 | 2024-06-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-30 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
684 | 2405-NNE4G-4G#RO-MAM104-0858 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | MAM104 | Protelindo Desa Toabo |  |  | PARE PARE | -238935 | 11917254 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-14 | Done | Done | 2024-06-14 | Done | 100% | 2024-06-14 | 2024-06-14 | 2024-06-14 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-May-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
685 | 2405-NNE4G-4G#RO-MAM111-0859 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | MAM111 | TBG ISAT Kaluku |  |  | PARE PARE | -262926 | 11898863 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-27 | Done | Done | 2024-06-27 | Done | 100% | 2024-06-27 | 2024-06-28 | 2024-06-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-01 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
686 | 2405-NNE4G-4G#RO-MAM193-0720 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | MAM193 | DMT Saletto |  |  | PARE PARE | -273269 | 118849 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-09 | Done | Done | 2024-06-09 | Done | 100% | 2024-06-09 | 2024-06-09 | 2024-06-09 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-13 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-06-25 | 2024-07-01 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3969 | 2024-06-14 | 2024-07-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
687 | 2405-NNE4G-4G#RO-MDO320-0553 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | MDO320 | MC Galilea |  |  | MANADO | 1.4518 | 124.8305 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Aditia | Done Productivity 100 % |  |  |  |  | 2024-06-22 | Done | Done | 2024-06-23 | Done | 100% | 2024-06-22 | 2024-06-23 | 2024-06-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 16-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
688 | 2405-NNE4G-4G#RO-MDO541-0556 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | MDO541 | PST MCP Liwas Kairagi |  |  | MANADO | 1.4954 | 124.8765 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Aditia | Done Productivity 100 % |  |  |  |  | 2024-06-21 | Done | Done | 2024-06-21 | Done | 100% | 2024-06-21 | 2024-06-21 | 2024-06-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 19 July 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 21-Aug-24 | 22-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 29-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
689 | 2405-NNE4G-4G#RO-MGN005-0869 | 0 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Swap Module BBU | MGN005 | DMT Essang |  |  | MANADO | 4.4906 | 126.7268 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Noris | Done Productivity 100 % |  |  |  |  | 2024-07-02 | Done | Done | 2024-07-04 | Done | 100% | 2024-07-02 | 2024-07-03 | 2024-07-03 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 17 July 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
690 | 2405-NNE4G-4G#RO-MGN046-0455 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | MGN046 | DMT Non3T Kuma Talaud |  |  | MANADO | 4.4235 | 126.7091 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Noris | Done Productivity 100 % |  |  |  |  | 31-May-24 | Done | Done | 2024-06-05 | Done | 100% | 31-May-24 | 2024-06-05 | 2024-06-05 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 25 June 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 15-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
691 | 2405-NNE4G-4G#RO-MGN047-0468 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | MGN047 | DMT Non3T Awit |  |  | MANADO | 4.3343 | 126.692 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Noris | Done Productivity 100 % |  |  |  |  | 31-May-24 | Done | Done | 2024-06-07 | Done | 100% | 31-May-24 | 2024-06-07 | 2024-06-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 18 June 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 15-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
692 | 2405-NNE4G-4G#RO-MGN052-0484 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | MGN052 | DMT Pangeran |  |  | MANADO | 3.7641 | 126.7689 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Noris | Done Productivity 100 % |  |  |  |  | 30-May-24 | Done | Done | 30-May-24 | Done | 100% | 30-May-24 | 30-May-24 | 30-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 12 July 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-25 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
693 | 2405-NNE4G-4G#RO-MRW012-0885 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | MRW012 | Permanenisasi COI396 - Onepute |  |  | PALU | -2.7374 | 122.0124 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 2024-07-14 | Done | Done | 2024-07-15 | Done | 100% | 2024-07-14 | 2024-07-15 | 2024-07-15 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2026-07-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-24 | 7-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4492 | 2024-07-30 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
694 | 2405-NNE4G-4G#RO-MRW050-0569 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | MRW050 | TBG Lemoborama |  |  | PALU | -2.1197 | 121.3239 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-06-17 | Done | Done | 2024-06-18 | Done | 100% | 2024-06-17 | 2024-06-18 | 2024-06-18 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2026-06-20 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 2024-09-27 | 4-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
695 | 2405-NNE4G-4G#RO-MRW929-0687 | 0 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | Add RRU | MRW929 | Perumahan Topogaro-Umpanga |  |  | PALU | -2.29 | 121.7947 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 2024-06-28 | Done | Done | 2024-06-28 | Done | 100% | 2024-06-28 | 2024-06-28 | 2024-06-28 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2026-07-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 08-May-24 | 7-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
696 | 2405-NNE4G-4G#RO-NTI076-0425 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | NTI076 | DMT N3T BULU BONGGU |  |  | PALU | -1.7043 | 119.4347 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 17-May-24 | Done | Done | 17-May-24 | Done | 100% | 17-May-24 | 17-May-24 | 17-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 17-May |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-07 | 2024-07-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-07-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
697 | 2405-NNE4G-4G#RO-NTI285-0653 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | NTI285 | DMT Non 3T Adolang Dhua |  |  | PARE PARE | -343304 | 11889239 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-24 | Done | Done | 2024-06-24 | Done | 100% | 2024-06-24 | 2024-06-24 | 2024-06-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-Dec-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
698 | 2405-NNE4G-4G#RO-NTI286-0654 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | NTI286 | DMT Non 3T Betteng |  |  | PARE PARE | -347141 | 1189202 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Roy | Done Productivity 100 % |  |  |  |  | 2024-06-26 | Done | Done | 2024-06-26 | Done | 100% | 2024-06-26 | 2024-06-26 | 2024-06-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-04 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-Aug-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
699 | 2405-NNE4G-4G#RO-NTI287-0655 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | NTI287 | DMT Non 3T Adolang |  |  | PARE PARE | -344832 | 11890972 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Roy | Done Productivity 100 % |  |  |  |  | 2024-06-29 | Done | Done | 2024-06-29 | Done | 100% | 2024-06-29 | 2024-06-29 | 2024-06-29 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-30 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-May-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
700 | 2405-NNE4G-4G#RO-NTI288-0724 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | NTI288 | DMT Non 3T Tabone |  |  | PARE PARE | -31822 | 119332 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-11 | Done | Done | 2024-06-11 | Done | 100% | 2024-06-11 | 2024-06-11 | 2024-06-11 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-25 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3968 | 2024-06-14 | 2-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
701 | 2405-NNE4G-4G#RO-NTI294-0725 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU and Module BBU | NTI294 | DMT Non 3T Sambali Wali |  |  | PARE PARE | -339919 | 11908469 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Roy | Done Productivity 100 % |  |  |  |  | 2024-07-01 | Done | Done | 2024-07-01 | Done | 100% | 2024-07-01 | 2024-07-01 | 2024-07-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-Dec-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
702 | 2405-NNE4G-4G#RO-NTI295-0726 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU and Module BBU | NTI295 | DMT Non 3T Bussu Tapango |  |  | PARE PARE | -331869 | 1192033 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yusuf | Done Productivity 100 % |  |  |  |  | 2024-06-25 | Done | Done | 2024-06-25 | Done | 100% | 2024-06-25 | 2024-06-25 | 2024-06-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-May-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
703 | 2405-NNE4G-4G#RO-NTI297-0727 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | NTI297 | DMT Non 3T Padang Campalagian |  |  | PARE PARE | -3474 | 119.1 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-10 | Done | Done | 2024-06-10 | Done | 100% | 2024-06-10 | 2024-06-10 | 2024-06-10 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-06-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-25 | 2024-07-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3968 | 2024-06-14 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
704 | 2405-NNE4G-4G#RO-NTI299-0728 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU and Module BBU | NTI299 | DMT Non 3T Todang Todang |  |  | PARE PARE | -343407 | 119032 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yusuf | Done Productivity 100 % |  |  |  |  | 2024-06-27 | Done | Done | 2024-06-27 | Done | 100% | 2024-06-27 | 2024-06-27 | 2024-06-27 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-28 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-May-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
705 | 2405-NNE4G-4G#RO-NTI341-0731 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | NTI341 | DMT Non 3T SEPANG |  |  | PARE PARE | -330135 | 11941734 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-11 | Done | Done | 2024-06-11 | Done | 100% | 2024-06-11 | 2024-06-11 | 2024-06-11 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-25 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3968 | 2024-06-14 | 2-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
706 | 2405-NNE4G-4G#RO-NTI343-0656 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | NTI343 | DMT Non 3T Simbang |  |  | PARE PARE | -349257 | 11893179 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Suardi | Done Productivity 100 % |  |  |  |  | 2024-06-26 | Done | Done | 2024-06-26 | Done | 100% | 2024-06-26 | 2024-06-26 | 2024-06-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-27 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-Aug-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
707 | 2405-NNE4G-4G#RO-NTI344-0732 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | NTI344 | DMT Non 3T Puttada |  |  | PARE PARE | -335783 | 118864 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-10 | Done | Done | 2024-06-10 | Done | 100% | 2024-06-10 | 2024-06-10 | 2024-06-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-25 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3968 | 2024-06-14 | 2024-07-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
708 | 2405-NNE4G-4G#RO-NTI345-0733 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | NTI345 | DMT Non 3T Binanga |  |  | PARE PARE | -33298 | 118.86 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-06-10 | Done | Done | 2024-06-10 | Done | 100% | 2024-06-10 | 2024-06-10 | 2024-06-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-25 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3968 | 2024-06-14 | 2024-07-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
709 | 2405-NNE4G-4G#RO-PAL201-0888 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PAL201 | Toko Galaxy Palu |  |  | PALU | -0.91211 | 119.8759 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-06-13 | Done | Done | 2024-06-18 | Done | 100% | 2024-06-13 | 2024-06-18 | 2024-06-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-25 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-03-10 | 5-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
710 | 2405-NNE4G-4G#RO-PAL308-0479 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PAL308 | TBG Bulu Masomba |  |  | PALU | -0.90328 | 119.9165 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 21-May-24 | Done | Done | 23-May-24 | Done | 100% | 21-May-24 | 23-May-24 | 23-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 18-Aug |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 2024-09-17 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
711 | 2405-NNE4G-4G#RO-PAL388-0890 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PAL388 | MCR Mako Lanal |  |  | PALU | -0.82079 | 119.8101 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 2024-06-19 | Done | Done | 2024-06-20 | Done | 100% | 2024-06-19 | 2024-06-20 | 2024-06-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-08 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-17 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
712 | 2405-NNE4G-4G#RO-PAL395-0891 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PAL395 | TBG Bale |  |  | PALU | -0.77522 | 119.9083 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Adriyanto | Done Productivity 100 % |  |  |  |  | 2024-06-20 | Done | Done | 2024-06-21 | Done | 100% | 2024-06-20 | 2024-06-21 | 2024-06-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 21-Aug |  | Done Tagging |  | Done Tagging | [12 empty] | 2024-09-17 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
713 | 2405-NNE4G-4G#RO-PIN010-0578 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PIN010 | DMT Benteng |  |  | PARE PARE | -3.7035 | 119.6703 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yusuf | Done Productivity 100 % |  |  |  |  | 30-May-24 | Done | Done | 31-May-24 | Done | 100% | 30-May-24 | 31-May-24 | 31-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-07 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-02-09 | 2024-09-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 2024-09-12 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
714 | 2405-NNE4G-4G#RO-PIN016-0471 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and module BBU | PIN016 | DMT Batulappa |  |  | PARE PARE | -3.6591 | 119.7164 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 30-May-24 | Done | Done | 30-May-24 | Done | 100% | 30-May-24 | 30-May-24 | 30-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-01 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 17-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
715 | 2405-NNE4G-4G#RO-PIN027-0579 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PIN027 | DMT Maccorowalie |  |  | PARE PARE | -3.812 | 119.6567 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 30-May-24 | Done | Done | 31-May-24 | Done | 100% | 30-May-24 | 30-May-24 | 30-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-03 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 17-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
716 | 2405-NNE4G-4G#RO-PIN075-0580 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PIN075 | TBG Carawali |  |  | PARE PARE | -3.8104 | 119.666 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 26-May-24 | Done | Done | 27-May-24 | Done | 100% | 26-May-24 | 27-May-24 | 27-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-07 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 17-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
717 | 2405-NNE4G-4G#RO-PIN091-0581 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PIN091 | MCR Macorawalie |  |  | PARE PARE | -3.8105 | 119.6533 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yusuf | Done Productivity 100 % |  |  |  |  | 25-May-24 | Done | Done | 27-May-24 | Done | 100% | 25-May-24 | 27-May-24 | 27-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-20 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 17-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
718 | 2405-NNE4G-4G#RO-PIN151-0582 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PIN151 | TBG Benteng Patampanua |  |  | PARE PARE | -3.699 | 119.6924 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 24-May-24 | Done | Done | 25-May-24 | Done | 100% | 24-May-24 | 25-May-24 | 25-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-06 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 18-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
719 | 2405-NNE4G-4G#RO-PLP005-0585 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PLP005 | Sampodo |  |  | PARE PARE | -3.0491 | 120.2255 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Suardi | Done Productivity 100 % |  |  |  |  | 2024-06-10 | Done | Done | 2024-06-29 | Done | 100% | 2024-06-10 | 2024-06-20 | 2024-06-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-10 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 16-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
720 | 2405-NNE4G-4G#RO-PLP016-0586 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PLP016 | Simoma |  |  | PARE PARE | -3.6302 | 120.4071 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Suardi | Done Productivity 100 % |  |  |  |  | 23-May-24 | Done | Done | 2024-06-07 | Done | 100% | 23-May-24 | 2024-06-01 | 2024-06-10 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-11 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 16-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
721 | 2405-NNE4G-4G#RO-PLP046-0587 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PLP046 | Tolemo |  |  | PARE PARE | -2.8482 | 120.2336 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Suardi | Done Productivity 100 % |  |  |  |  | 16-Aug-24 | Done | Done | 17-Aug-24 | Done | 100% | 16-Aug-24 | 17-Aug-24 | 17-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 19-Aug-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-17 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
722 | 2405-NNE4G-4G#RO-PLP054-0588 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PLP054 | DMT Larompong Selatan |  |  | PARE PARE | -3.4927 | 120.3714 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Suardi | Done Productivity 100 % |  |  |  |  | 2024-06-10 | Done | Done | 2024-06-22 | Done | 100% | 2024-06-10 | 2024-06-20 | 2024-06-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-10 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 18-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
723 | 2405-NNE4G-4G#RO-PLP066-0589 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PLP066 | DMT ISAT Cimpu |  |  | PARE PARE | -3.4249 | 120.3812 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yusuf | Done Productivity 100 % |  |  |  |  | 2024-06-14 | Done | Done | 2024-06-21 | Done | 100% | 2024-06-14 | 2024-06-14 | 2024-06-21 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2024-07-09 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 29-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
724 | 2405-NNE4G-4G#RO-PLP078-0590 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PLP078 | Protelindo Bupon |  |  | PARE PARE | -3.2647 | 120.2831 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yusuf | Done Productivity 100 % |  |  |  |  | 2024-06-10 | Done | Done | 2024-06-12 | Done | 100% | 2024-06-10 | 2024-06-11 | 2024-06-12 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-01 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 16-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3968 | 2024-06-14 | 29-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
725 | 2405-NNE4G-4G#RO-PLP113-0591 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PLP113 | Labombo |  |  | PARE PARE | -3.0047 | 120.2063 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Suardi | Done Productivity 100 % |  |  |  |  | 30-May-24 | Done | Done | 2024-06-05 | Done | 100% | 30-May-24 | 30-May-24 | 2024-06-06 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-10 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 17-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
726 | 2405-NNE4G-4G#RO-PLP117-0592 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PLP117 | DMT Wara Selatan |  |  | PARE PARE | -3.0248 | 120.2114 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Suardi | Done Productivity 100 % |  |  |  |  | 29-May-24 | Done | Done | 30-May-24 | Done | 100% | 29-May-24 | 30-May-24 | 30-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-20 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
727 | 2405-NNE4G-4G#RO-PLP119-0593 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PLP119 | LMA Dangerakko |  |  | PARE PARE | -3.0264 | 120.2006 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Suardi | Done Productivity 100 % |  |  |  |  | 26-May-24 | Done | Done | 28-May-24 | Done | 100% | 26-May-24 | 26-May-24 | 30-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-07 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
728 | 2405-NNE4G-4G#RO-PLP131-0638 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | PLP131 | TBG Temmalebba |  |  | PARE PARE | -3.0118 | 120.194 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Roy | Done Productivity 100 % |  |  |  |  | 2024-06-09 | Done | Done | 2024-06-19 | Done | 100% | 2024-06-09 | 2024-06-18 | 2024-06-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-10 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
729 | 2405-NNE4G-4G#RO-PLP197-0594 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | PLP197 | TBG Jend Sudirman Palopo |  |  | PARE PARE | -3.0308 | 120.2155 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Suardi | Done Productivity 100 % |  |  |  |  | 2024-06-12 | Done | Done | 2024-06-14 | Done | 100% | 2024-06-12 | 2024-06-14 | 2024-06-14 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-10 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
730 | 2405-NNE4G-4G#RO-PLP228-0595 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PLP228 | DMT Cakke Awo |  |  | PARE PARE | -3.4196 | 120.3531 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yusuf | Done Productivity 100 % |  |  |  |  | 2024-06-10 | Done | Done | 2024-06-15 | Done | 100% | 2024-06-10 | 2024-06-15 | 2024-06-16 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 16-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 29-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
731 | 2405-NNE4G-4G#RO-PSO062-0923 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PSO062 | DMT Tokilo |  |  | PALU | -2.0235 | 120.7124 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-06-21 | Done | Done | 2024-06-22 | Done | 100% | 2024-06-21 | 2024-06-22 | 2024-06-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-25 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 2024-01-10 | 4-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
732 | 2405-NNE4G-4G#RO-PSO063-0924 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | PSO063 | DMT Maengko Lama |  |  | PALU | -1.3979 | 120.7141 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-06-25 | Done | Done | 2024-06-26 | Done | 100% | 2024-06-25 | 2024-06-26 | 2024-06-26 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-11 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 17-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
733 | 2405-NNE4G-4G#RO-PSO134-0925 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | PSO134 | MCR Poso City Mall |  |  | PALU | -1.3868 | 120.7433 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 2024-06-14 | Done | Done | 2024-06-14 | Done | 100% | 2024-06-14 | 2024-06-14 | 2024-06-14 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2026-07-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-24 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
734 | 2405-NNE4G-4G#RO-PSO144-0743 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | PSO144 | DMT BNPT TAMANJEKA |  |  | PALU | -1.3575 | 120.6059 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-06-24 | Done | Done | 2024-06-24 | Done | 100% | 2024-06-24 | 2024-06-24 | 2024-06-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2026-07-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-24 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 18-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
735 | 2405-NNE4G-4G#RO-PSO191-0744 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU | PSO191 | Protelindo Pandiri |  |  | PALU | -1.5149 | 120.749 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-06-23 | Done | Done | 2024-06-23 | Done | 100% | 2024-06-23 | 2024-06-23 | 2024-06-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-17 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 17-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
736 | 2405-NNE4G-4G#RO-RHA082-0604 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | RHA082 | TBG Bangun Sari |  | ALL CLOSE | KENDARI | -4.7694 | 122.6885 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBPd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 27-May-24 | Done | Done | 28-May-24 | Done | 100% | 27-May-24 | 28-May-24 | 28-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 29-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-25 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
737 | 2405-NNE4G-4G#RO-RHA103-0926 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | RHA103 | DMT Langkumapo |  | ALL CLOSE | KENDARI | -4.6584 | 122.6616 | YPTT | June-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),BFAN5(1),LPU(1),DCPD10(1),PM5(2),SA(10,FA0(1),CC16B(1)CR0(2),BPN2(2) | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-06-23 | Done | Done | 2024-06-24 | Done | 100% | 2024-06-23 | 2024-06-24 | 2024-06-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-26 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-04-09 | 2024-09-09 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 5-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
738 | 2405-NNE4G-4G#RO-RHA122-0927 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | RHA122 | TBG Masalili Muna |  | ALL CLOSE | KENDARI | -4.8696 | 122.6864 | YPTT | June-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),BFAN5(1),LPU(1),DCPD7(1),PM5(2),SA(1),FA0(1),CCE1B(1),CR0(2),BPN2(2) | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-06-13 | Done | Done | 2024-06-14 | Done | 100% | 2024-06-13 | 2024-06-14 | 2024-06-14 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-15 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 17-Aug-24 | 19-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 16-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
739 | 2405-NNE4G-4G#RO-RHA143-0514 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU | RHA143 | DMT Labone |  | ALL CLOSE | KENDARI | -4.7327 | 122.7275 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 27-May-24 | Done | Done | 28-May-24 | Done | 100% | 27-May-24 | 28-May-24 | 28-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 29-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-25 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
740 | 2405-NNE4G-4G#RO-RHA147-0928 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | RHA147 | TBG Danagoa Muna |  | ALL CLOSE | KENDARI | -5.1637 | 122.5199 | YPTT | June-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-06-10 | Done | Done | 2024-06-18 | Done | 100% | 2024-06-10 | 2024-06-10 | 2024-06-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-07 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 29-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
741 | 2405-NNE4G-4G#RO-SKG046-0936 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | SKG046 | DMT ISAT_Lembu_Tempe |  |  | MAKASSAR | 12002792 | -411544 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 2024-07-06 | Done | Done | 2024-07-06 | Done | 100% | 2024-07-06 | 2024-07-06 | 2024-07-06 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-07 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4348 | 2024-07-15 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
742 | 2405-NNE4G-4G#RO-SKG047-0937 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | SKG047 | Protelindo Sabbangparu |  |  | MAKASSAR | 11995805 | -424245 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 2024-06-16 | Done | Done | 2024-06-16 | Done | 100% | 2024-06-16 | 2024-06-16 | 2024-06-16 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 21-Aug-24 | 22-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 29-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
743 | 2405-NNE4G-4G#RO-SKG058-0938 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | SKG058 | DMT Salobulo |  |  | MAKASSAR | 12025657 | -395679 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-06-23 | Done | Done | 2024-06-23 | Done | 100% | 2024-06-23 | 2024-06-23 | 2024-06-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-26 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 16-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
744 | 2405-NNE4G-4G#RO-SKG072-0609 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | SKG072 | TBG Sitarda Paneki |  |  | MAKASSAR | -4.1472 | 120.2703 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 28-May-24 | Done | Done | 28-May-24 | Done | 100% | 28-May-24 | 28-May-24 | 28-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 30-May-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
745 | 2405-NNE4G-4G#RO-SKG146-0610 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | SKG146 | Quattro Gilireng |  |  | MAKASSAR | -3.933 | 120.1746 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 2024-11-21 | Done | Done | 2024-11-22 | Done | 100% | 2024-11-21 | 2024-11-22 | 2024-11-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-11-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 16-Dec-24 | 16-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5512 | 2024-11-28 | 27-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
746 | 2405-NNE4G-4G#RO-SKG195-0748 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Swap RRU | SKG195 | CMI Salotengnga |  |  | MAKASSAR | 11998245 | -4228869 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 2024-06-21 | Done | Done | 2024-06-23 | Done | 100% | 2024-06-21 | 2024-06-22 | 2024-06-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
747 | 2405-NNE4G-4G#RO-SKG200-0486 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 1800 20 Mhz | Swap RRU | SKG200 | DMT Wage |  |  | MAKASSAR | -4.1835 | 120.0166 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 31-May-24 | Done | Done | 31-May-24 | Done | 100% | 31-May-24 | 31-May-24 | 31-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-01 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
748 | 2405-NNE4G-4G#RO-SKG202-0612 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | SKG202 | TBG Wele Belawa |  |  | MAKASSAR | -3.9581 | 119.9903 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 19-May-24 | Done | Done | 19-May-24 | Done | 100% | 19-May-24 | 19-May-24 | 19-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 20-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 13-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
749 | 2405-NNE4G-4G#RO-TDE029-0614 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | TDE029 | DMT Dowara |  |  | TERNATE | 0.70855 | 127.4546 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-06-22 | Done | Done | 2024-06-23 | Done | 100% | 2024-06-22 | 2024-06-23 | 2024-06-23 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 25 June 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 21-Aug-24 | 22-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4217 | 2024-06-30 | 29-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
750 | 2405-NNE4G-4G#RO-TDO023-0947 | 0 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | TDO023 | DMT Sawangan |  |  | MANADO | 1.3865 | 124.9523 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Aditia | Done Productivity 100 % |  |  |  |  | 2024-06-28 | Done | Done | 2024-06-28 | Done | 100% | 2024-06-28 | 2024-06-28 | 2024-06-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 25 July 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 23-Aug-24 | 30-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 2024-09-12 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
751 | 2405-NNE4G-4G#RO-TDO084-0951 | 0 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Swap Module BBU | TDO084 | DMT Kuala Batu |  |  | MANADO | 1.6632 | 125.0246 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Aditia | Done Productivity 100 % |  |  |  |  | 2024-06-29 | Done | Done | 2024-07-05 | Done | 100% | 2024-06-29 | 2024-07-05 | 2024-07-05 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 02 August 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-23 | 2024-09-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
752 | 2405-NNE4G-4G#RO-TDO433-0955 | 0 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | TDO433 | TBG Paslaten Kema |  |  | MANADO | 1402601 | 124998709 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-06-20 | Done | Done | 2024-06-20 | Done | 100% | 2024-06-20 | 2024-06-20 | 2024-06-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 23 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-Aug-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4217 | 2024-06-30 | 18-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
753 | 2405-NNE4G-4G#RO-TER033-0957 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | TER033 | DMT Loto |  |  | TERNATE | 0.82822 | 127.3 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-06-25 | Done | Done | 2024-06-26 | Done | 100% | 2024-06-25 | 2024-06-26 | 2024-06-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 30 July 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
754 | 2405-NNE4G-4G#RO-TER061-0619 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | TER061 | Hotel Ayu Lestari |  |  | TERNATE | 0.76611 | 127.3739 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-06-20 | Done | Done | 2024-06-20 | Done | 100% | 2024-06-20 | 2024-06-20 | 2024-06-20 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 19-Aug-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 09-Dec-24 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4217 | 2024-06-30 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
755 | 2405-NNE4G-4G#RO-THN014-0620 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | THN014 | DMT Lamanggo |  |  | MANADO | 2.1251 | 125.3568 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-06-15 | Done | Done | 2024-06-15 | Done | 100% | 2024-06-15 | 2024-06-16 | 2024-06-16 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 25 June 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 16-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
756 | 2405-NNE4G-4G#RO-THN051-0621 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | THN051 | TBG Kampung Buwang |  |  | MANADO | 2.082 | 125.3385 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-06-19 | Done | Done | 2024-06-19 | Done | 100% | 2024-06-19 | 2024-06-20 | 2024-06-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 27 June 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 16-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
757 | 2405-NNE4G-4G#RO-THN068-0629 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 MHz | Add RRU | THN068 | TBG Bebali Siau Timur |  |  | MANADO | 2.7391 | 125.3969 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-07-11 | Done | Done | 2024-07-11 | Done | 100% | 2024-07-11 | 2024-07-11 | 2024-07-11 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 12 July 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-24 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4380 | 2024-07-20 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
758 | 2405-NNE4G-4G#RO-THN070-0536 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | THN070 | MC Raramenusa |  |  | MANADO | 3.6088 | 125.4883 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-06-15 | Done | Done | 2024-06-21 | Done | 100% | 2024-06-15 | 2024-06-21 | 2024-06-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 03 July 2024 |  | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 16-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
759 | 2405-NNE4G-4G#RO-THN076-0958 | 0 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Swap Module BBU | THN076 | DMT MCP KANTOR BUPATI SITARO |  |  | MANADO | 2.7437 | 125.3623 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-07-08 | Done | Done | 2024-07-09 | Done | 100% | 2024-07-08 | 2024-07-09 | 2024-07-09 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 15 July 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4380 | 2024-07-20 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
760 | 2405-NNE4G-4G#RO-THN097-0637 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 MHz | Add RRU | THN097 | Sesiwwung-TBG |  |  | MANADO | 3.5026 | 125.4893 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 28-May-24 | Done | Done | 28-May-24 | Done | 100% | 28-May-24 | 28-May-24 | 28-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 14 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-07 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
761 | 2405-NNE4G-4G#RO-THN101-0959 | 0 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | THN101 | TBG Lesah Wijaya |  |  | MANADO | 2.3615 | 125.3783 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-07-03 | Done | Done | 2024-07-04 | Done | 100% | 2024-07-03 | 2024-07-04 | 2024-07-04 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 07 July 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-07-25 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4492 | 2024-07-30 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
762 | 2405-NNE4G-4G#RO-THN116-0960 | 0 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | THN116 | Permanenisasi COI934 - Combat CRU Talawit |  |  | MANADO | 3.714 | 125.407 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-06-22 | Done | Done | 2024-06-22 | Done | 100% | 2024-06-22 | 2024-06-23 | 2024-06-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 24 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-Aug-24 | 2024-07-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
763 | 2405-NNE4G-4G#RO-TWA002-0968 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | TWA002 | TBG Papawu Rate-rate |  | ALL CLOSE | KENDARI | -4.0464 | 121.892 | YPTT | June-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 2 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | PT. Djaya Sukses Pratama | Maman Putrawan | Done Productivity 100 % |  |  |  |  | 2024-06-08 | Done | Done | 2024-06-08 | Done | 100% | 2024-06-08 | 2024-06-08 | 2024-06-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-15 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-07 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3969 | 2024-06-14 | 18-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
764 | 2405-NNE4G-4G#RO-UNH050-0969 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | UNH050 | DMT Inolobu |  | ALL CLOSE | KENDARI | -3.8646 | 122.1147 | YPTT | June-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBpd0p(3) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),BFAN5(1),LPU(1),PM5(2),CCE1B(1),CR0(2),BPN2(3),SA(1),FA0(1),DCPD10(1) | [6 empty] | PT. Djaya Sukses Pratama | Herdianto | Done Productivity 100 % |  |  |  |  | 2024-06-21 | Done | Done | 2024-06-21 | Done | 100% | 2024-06-21 | 2024-06-22 | 2024-06-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 17-Aug-24 | 19-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
765 | 2405-NNE4G-4G#RO-UNH057-0970 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU | UNH057 | TBG Puuwonua |  | ALL CLOSE | KENDARI | -3.8812 | 122.0922 | YPTT | June-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | PT. Djaya Sukses Pratama | Herdianto | Done Productivity 100 % |  |  |  |  | 2024-06-08 | Done | Done | 2024-06-08 | Done | 100% | 2024-06-08 | 2024-06-08 | 2024-06-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-07 | 2024-07-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3969 | 2024-06-14 | 2024-07-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
766 | 2405-NNE4G-4G#RO-UNH060-0971 | 0 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | UNH060 | PTI Wonua Hoa |  | ALL CLOSE | KENDARI | -3.9416 | 122.0661 | YPTT | June-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 0 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | PT. Djaya Sukses Pratama | Maman Putrawan | Done Productivity 100 % |  |  |  |  | 2024-06-22 | Done | Done | 2024-06-22 | Done | 100% | 2024-06-22 | 2024-06-22 | 2024-06-22 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-22 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-07 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 17-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
767 | 2405-NNE4G-4G#RO-UNH062-0515 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU | UNH062 | TBG Walay |  | ALL CLOSE | KENDARI | -3.7832 | 121.9634 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | PT. Djaya Sukses Pratama | Herdianto | Done Productivity 100 % |  |  |  |  | 27-May-24 | Done | Done | 26-May-24 | Done | 100% | 27-May-24 | 28-May-24 | 28-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 29-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-25 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3901 | 2024-06-13 | 2024-07-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
768 | 2405-NNE4G-4G#RO-UNH077-0630 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | UNH077 | PTI Meluhu |  | ALL CLOSE | KENDARI | -3.815 | 122.1922 | YPTT | May-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBpd0p(1),VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),BfAN5(1),LPU(1),PM5(1),CCF0(1),CR0(1),BPN2(3),SA(1),FA0(1),DCPD7(1) | [6 empty] | PT. Djaya Sukses Pratama | Herdianto | Done Productivity 100 % |  |  |  |  | 2024-06-14 | Done | Done | 2024-06-11 | Done | 100% | 2024-06-14 | 2024-06-14 | 2024-06-14 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-14 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 17-Aug-24 | 19-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3968 | 2024-06-14 | 5-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
769 | 2405-NNE4G-4G#RO-UNH087-0631 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | UNH087 | PTI Amesiu |  | ALL CLOSE | KENDARI | -3.9669 | 122.2511 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | PT. Djaya Sukses Pratama | Herdianto | Done Productivity 100 % |  |  |  |  | 2024-06-04 | Done | Done | 2024-06-04 | Done | 100% | 2024-06-04 | 2024-06-04 | 2024-06-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-04 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-07 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3969 | 2024-06-14 | 13-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
770 | 2405-NNE4G-4G#RO-WGU003-0764 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | WGU003 | DMT N3T Landawe Utama |  | ALL CLOSE | KENDARI | -3.234 | 122.1756 | YPTT | June-24 |  | 2024 | 2024 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | PT. Djaya Sukses Pratama | Herdianto | Done Productivity 100 % |  |  |  |  | 2024-06-13 | Done | Done | 2024-06-13 | Done | 100% | 2024-06-13 | 2024-06-13 | 2024-06-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-Aug-24 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3968 | 2024-06-14 | 2-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
771 | 2405-NNE4G-4G#RO-WGU005-0765 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | WGU005 | DMT N3T Tambakua |  | ALL CLOSE | KENDARI | -3.2667 | 122.1936 | YPTT | June-24 |  | 2024 | 2024 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | PT. Djaya Sukses Pratama | Herdianto | Done Productivity 100 % |  |  |  |  | 2024-06-13 | Done | Done | 2024-06-13 | Done | 100% | 2024-06-13 | 2024-06-13 | 2024-06-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-Aug-24 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3968 | 2024-06-14 | 2-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
772 | 2405-NNE4G-4G#RO-WGU015-0464 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU and Module BBU | WGU015 | DMT N3T Kuratao |  | ALL CLOSE | KENDARI | -3.2775 | 122.1412 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-06-04 | Done | Done | 2024-06-04 | Done | 100% | 2024-06-04 | 2024-06-05 | 2024-06-05 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-06-24 | 2024-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 17-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
773 | 2405-NNE4G-4G#RO-WGU016-0434 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU | LBA023 | Permanenisasi MXW047 - Nain |  |  | TERNATE | -0.74515 | 127.645 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-29 | Done | Done | 2025-01-29 | Done | 100% | 2025-01-29 | 2025-01-29 | 2025-01-29 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-02-14 | 2025-02-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5910 | 2025-02-05 | 2025-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
774 | 2405-NNE4G-4G#RO-WTG042-0997 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | WTG042 | Protelindo Mario Riwawo |  |  | MAKASSAR | 11983315 | -450703 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-06-25 | Done | Done | 2024-06-25 | Done | 100% | 2024-06-25 | 2024-06-25 | 2024-06-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-30 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4286 | 2024-07-04 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
775 | 2405-NNE4G-4G#RO-WTG049-0998 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | WTG049 | DMT ISAT Batu-Batu |  |  | MAKASSAR | 11989301 | -414665 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-06-22 | Done | Done | 2024-06-22 | Done | 100% | 2024-06-22 | 2024-06-22 | 2024-06-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-27 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4238 | 2024-07-02 | 29-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
776 | 2405-NNE4G-4G#RO-WTG058-0999 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | WTG058 | DMT XL Liliriaja |  |  | MAKASSAR | 11995596 | -43383 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 2024-06-12 | Done | Done | 2024-09-12 | Done | 100% | 2024-06-12 | 2024-09-12 | 2024-09-12 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-17 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 23-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
777 | 2405-NNE4G-4G#RO-WTG063-0766 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add Module BBU | WTG063 | DMT Maddumpa |  |  | MAKASSAR | -4.2272 | 119.8927 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-06-07 | Done | Done | 2024-06-07 | Done | 100% | 2024-06-07 | 2024-06-07 | 2024-06-07 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-07 | 2024-07-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3969 | 2024-06-14 | 2024-07-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
778 | 2405-REENG-4G#RO-BIT129-0082 | CAPEX RAN 2 2024 Acceleration Support Part 2 for Area 4 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Add RRU | BIT129 | DMT Woka Lembeh |  |  | MANADO | 1.4664 | 125.2572 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-09-24 | Done | Done | 2024-09-24 | Done | 100% | 2024-09-24 | 2024-09-24 | 2024-09-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-10 | 4-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 17-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
779 | 2405-REENG-4G#RO-COI991-0103 | 0 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Swap Antenna | COI991 | Combat Lapaopao |  | ALL CLOSE | KENDARI | -3.8996 | 121.3413 | YPTT | July-24 |  | 2024 | 2024 |  |  | Mobi 10 Port | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DBXLHA 4Port | 3 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-07-17 | Done | Done | 2024-07-17 | Done | 100% | 2024-07-17 | 2024-07-18 | 2024-07-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-18 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-17 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
780 | 2405-REENG-4G#RO-LBA113-0112 | 0 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Add Module BBU | LBA113 | Bandara Soligi 1 |  |  | TERNATE | -1.6447 | 127.4041 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-09-20 | Done | Done | 2024-09-20 | Done | 100% | 2024-09-20 | 2024-09-20 | 2024-09-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 31-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4492 | 2024-07-30 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
781 | 2405-REENG-4G#RO-MAJ039-0113 | 0 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Swap Antenna and Add RRU and Module BBU | MAJ039 | Protelindo Mosso Sendana |  |  | PARE PARE | -345738 | 11887892 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Suardi | Done Productivity 100 % |  |  |  |  | 2024-07-26 | Done | Done | 2024-07-29 | Done | 100% | 2024-07-26 | 2024-07-29 | 2024-07-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-31 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-17 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
782 | 2405-REENG-4G#RO-MRW169-0119 | 0 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Add RRU | COI185 | Combat Fun UNSULBAR |  |  | PARE PARE | -3.5313 | 118.9843 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-03-17 | Done | Done | 2025-03-18 | Done | 100% | 2025-03-17 | 2025-03-18 | 2025-03-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-16 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 9-May-25 | 8-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6241 | 2025-04-17 | 2025-06-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
783 | 2405-REENG-4G#RO-TDO111-0140 | 0 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Swap Antenna and Add RRU and Module BBU | TDO111 | Protelindo Kulu |  |  | MANADO | 1.6769 | 124.9524 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 07-Aug-24 | Done | Done | 08-Aug-24 | Done | 100% | 07-Aug-24 | 08-Aug-24 | 08-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 29-Aug-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
784 | 2405-REENG-4G#RO-TER152-0076 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Add RRU | TER152 | TBG Todowongi |  |  | TERNATE | 1.0633 | 127.4994 | YPTT | May-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | ahmad | Done Productivity 100 % |  |  |  |  | 23-May-25 | Done | Done | 23-May-25 | Done | 100% | 23-May-25 | 23-May-25 | 23-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 13-May-25 |  | Done Tagging |  | Done Tagging | Work Not Start | Work Not Start | Work Not Start | Work Not Start | [8 empty] | 2025-06-25 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6770 | 2025-06-21 | 2025-07-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
785 | 2405-REENG-4G#RO-THN069-0072 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP eNode B Modular Relocation Service New NE LTE 2100 | Add RRU and Module BBU | THN069 | TBG Humbia |  |  | MANADO | 2.3183 | 125.4223 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-07-18 | Done | Done | 2024-07-18 | Done | 100% | 2024-07-18 | 2024-07-18 | 2024-07-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-18 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 28-Aug-24 | 2024-09-02 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4491 | 2024-07-30 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
786 | 2405-REENG-4G#RO-WTG038-0147 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Swap Module BBU | WTG038 | TBG Lompoe Tempe |  |  | MAKASSAR | 11988812 | -417769 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-06-12 | Done | Done | 2024-06-13 | Done | 100% | 2024-06-12 | 2024-06-13 | 2024-06-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-13 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 19-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4205 | 2024-06-28 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
787 | 2405-UMIMO-4G#RO-BAU140-0025 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | BAU140 | TBG Mandati |  | ALL CLOSE | KENDARI | -5.3352 | 123.5418 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | A9631 S2300 | 1 | 0 | 0 | 0 | VBPd2(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8978 S2300 | 1 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 24-May-24 | Done | Done | 25-May-24 | Done | 100% | 24-May-24 | 25-May-24 | 25-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-06-15 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-07-26 | 2024-07-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 13-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
788 | 2405-UMIMO-4G#RO-BAU140-0026 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | BAU140 | TBG Mandati |  | ALL CLOSE | KENDARI | -5.3352 | 123.5418 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | A9631 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8978 S2300 | 1 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 24-May-24 | Done | Done | 25-May-24 | Done | 100% | 24-May-24 | 25-May-24 | 25-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-07-11 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 21-Aug-24 | 22-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
789 | 2405-UMIMO-4G#RO-BAU140-0027 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | BAU140 | TBG Mandati |  | ALL CLOSE | KENDARI | -5.3352 | 123.5418 | YPTT | May-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | A9631 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 24-May-24 | Done | Done | 25-May-24 | Done | 100% | 24-May-24 | 25-May-24 | 25-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-24 | 2024-07-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3543 | 31-May-24 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
790 | 2405-UMIMO-4G#RO-COI168-0045 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU | COI168 | CombatARRKawasi |  |  | TERNATE | -1.5346 | 127.4225 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-06-29 | Done | Done | 2024-07-11 | Done | 100% | 2024-06-29 | 2024-07-11 | 2024-07-11 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 06-Aug-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-23 | 2024-09-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
791 | 2405-UMIMO-4G#RO-COI168-0046 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU and Swap Module BBU | COI168 | CombatARRKawasi |  |  | TERNATE | -1.5346 | 127.4225 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-06-29 | Done | Done | 2024-07-11 | Done | 100% | 2024-06-29 | 2024-07-11 | 2024-07-11 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 07-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-23 | 2024-09-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3545 | 31-May-24 | 5-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
792 | 2405-UMIMO-4G#RO-LBA021-0036 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | LBA021 | Jikotamo |  |  | TERNATE | -1.345 | 127.6566 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 05-Aug-24 | Done | Done | 05-Aug-24 | Done | 100% | 05-Aug-24 | 05-Aug-24 | 05-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 07-Aug-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-11-09 | 2024-09-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
793 | 2405-UMIMO-4G#RO-MRW052-0040 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU and Swap Module BBU | MRW052 | TBG Leulea |  |  | PALU | -2.7945 | 122.0989 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 26-May-24 | Done | Done | 28-May-24 | Done | 100% | 26-May-24 | 28-May-24 | 28-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-13 |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 2024-09-17 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3900 | 2024-06-13 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
794 | 2405-UMIMO-4G#RO-MRW059-0038 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU and Swap Module BBU | MRW059 | TBG Tofogaro |  |  | PALU | -2.2743 | 121.7781 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 29-May-24 | Done | Done | 30-May-24 | Done | 100% | 29-May-24 | 29-May-24 | 30-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-09 |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 2024-03-10 | 5-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3900 | 2024-06-13 | 12-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
795 | 2405-UMIMO-4G#RO-MRW077-0015 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | MRW077 | TBG Arthabumi Morowali |  |  | PALU | -3.0521 | 122.273 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 25-May-24 | Done | Done | 27-May-24 | Done | 100% | 25-May-24 | 27-May-24 | 27-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-06-06 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 20-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3900 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
796 | 2405-UMIMO-4G#RO-MRW123-0018 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | MRW123 | DMT Tugu Bahomakmur |  |  | PALU | -2.8133 | 122.1298 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 29-May-24 | Done | Done | 29-May-24 | Done | 100% | 29-May-24 | 29-May-24 | 29-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-06-13 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 17-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3900 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
797 | 2405-UMIMO-4G#RO-MRW123-0023 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU | MRW123 | DMT Tugu Bahomakmur |  |  | PALU | -2.8133 | 122.1298 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 29-May-24 | Done | Done | 29-May-24 | Done | 100% | 29-May-24 | 29-May-24 | 29-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-06-13 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 20-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3900 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
798 | 2405-UMIMO-4G#RO-MRW123-0024 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU | MRW123 | DMT Tugu Bahomakmur |  |  | PALU | -2.8133 | 122.1298 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 29-May-24 | Done | Done | 29-May-24 | Done | 100% | 29-May-24 | 29-May-24 | 29-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-06-13 |  | Done Tagging |  | Done Tagging | Done tagging | [11 empty] | 20-Aug-24 | 20-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3900 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
799 | 2405-UMIMO-4G#RO-MRW227-0042 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP add sector LTE 2300 50 Mhz Massive mimo 32T32R | Add RRU | PRE024 | PRE024 CR fr IMIP PLTU Terminal |  |  | PARE PARE | -4.0343 | 119.642 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Narfin | Done Productivity 100 % |  |  |  |  | 27-May-25 | Done | Done | 28-May-25 | Done | 100% | 27-May-25 | 28-May-25 | 28-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 28-May-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 18-Aug-25 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6868 | 2025-06-30 | 19-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
800 | 2405-UMIMO-4G#RO-MRW369-0017 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | MRW369 | Protelindo Jl. Pendidikan Keurea |  |  | PALU | -2.7986 | 122.1141 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 19-May-24 | Done | Done | 19-May-24 | Done | 100% | 19-May-24 | 19-May-24 | 19-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 20-May-24 |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 20-Aug-24 | 21-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3544 | 31-May-24 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
801 | 2405-UMIMO-4G#RO-MRW369-0021 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU | MRW369 | Protelindo Jl. Pendidikan Keurea |  |  | PALU | -2.7986 | 122.1141 | YPTT | May-24 |  | 2024 | 2024 | [34 empty] | YPTT | Hendro | Done Productivity 100 % |  |  |  |  | 19-May-24 | Done | Done | 19-May-24 | Done | 100% | 19-May-24 | 19-May-24 | 19-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 20-May-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-07 | 2024-07-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3544 | 31-May-24 | 2-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
802 | 2405-UMIMO-4G#RO-SSU004-0028 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | SSU004 | TBG Wahyu Lelilef |  |  | TERNATE | 0.4684 | 127.9324 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-06-01 | Done | Done | 2024-06-02 | Done | 100% | 2024-06-01 | 2024-06-02 | 2024-06-02 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 9-Aug-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 15-Aug-24 | 16-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 18-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
803 | 2405-UMIMO-4G#RO-SSU004-0029 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU | SSU004 | TBG Wahyu Lelilef |  |  | TERNATE | 0.4684 | 127.9324 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-06-01 | Done | Done | 2024-06-02 | Done | 100% | 2024-06-01 | 2024-06-02 | 2024-06-02 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 9-Aug-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
804 | 2405-UMIMO-4G#RO-SSU004-0030 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU | SSU004 | TBG Wahyu Lelilef |  |  | TERNATE | 0.4684 | 127.9324 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-06-01 | Done | Done | 2024-06-02 | Done | 100% | 2024-06-01 | 2024-06-02 | 2024-06-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 9-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-29 | 2024-07-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 13-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
805 | 2405-UMIMO-4G#RO-SSU075-0054 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU | TER071 | TBG Jambu Ternate |  |  | TERNATE | 0.79781 | 127.3862 | YPTT | December-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 11-Dec-24 | Done | Done | 11-Dec-24 | Done | 100% | 11-Dec-24 | 11-Dec-24 | 11-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 16-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 23-Dec-24 | 24-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5723 | 24-Dec-24 | 2025-03-10 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
806 | 2405-UMIMO-4G#RO-THN054-0032 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Swap RRU and Add Module BBU | THN054 | DMT Tlk Tahuna |  |  | MANADO | 3.6129 | 125.504 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 29-May-24 | Done | Done | 29-May-24 | Done | 100% | 29-May-24 | 29-May-24 | 29-May-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 03 June 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 16-Aug-24 | 18-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3900 | 2024-06-13 | 27-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
807 | 2405-UMIMO-4G#RO-THN054-0033 | CAPEX RAN 2 2024 Acceleration Part 1 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 64T64R | Add RRU | THN054 | DMT Tlk Tahuna |  |  | MANADO | 3.6129 | 125.504 | YPTT | May-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-06-01 | Done | Done | 2024-06-01 | Done | 100% | 2024-06-01 | 2024-06-01 | 2024-06-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 03 June 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-07 | 2024-07-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-3899 | 2024-06-13 | 2-Aug-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
808 | 2406-4GDCS-4G#315-BAU005-0279 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add Antenna and RRU and Module BBU (New Infra) | BAU005 | DMT Karya Baru |  | ALL CLOSE | KENDARI | -5.4836 | 122.6945 | YPTT | August-24 |  | 2024 | 2024 | BAU005-N-3M2P |  | MOBI 12 Port | 3 | 3 | R9264E M1821 | 3 | 1 | 1 | 0 | VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 24-Aug-24 | Done | Done | 25-Aug-24 | Done | 100% | 24-Aug-24 | 25-Aug-24 | 26-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-20 | 2024-09-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4916 | 2024-09-06 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
809 | 2406-4GDCS-4G#315-KDI030-0286 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add Antenna and RRU and Module BBU (New Infra) | KDI030 | TBG Kampung Bakau-Permanenisasi COI459 |  | ALL CLOSE | KENDARI | -3.9844 | 122.5353 | YPTT | August-24 |  | 2024 | 2024 | KDI030-N-3M2B |  | MOBI 12 Port | 3 | 3 | R9264E M1821 | 3 | 1 | 1 | 0 | VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 30-Aug-24 | Done | Done | 31-Aug-24 | Done | 100% | 30-Aug-24 | 31-Aug-24 | 2024-09-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 31-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-18 | 2024-09-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
810 | 2406-4GDCS-4G#315-LBA002-0290 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | New Infra | LBA002 | DMT OBI BARU |  |  | TERNATE | -1.3443 | 127.6315 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-11-05 | Done | Done | 2024-11-07 | Done | 100% | 2024-11-05 | 2024-11-06 | 2024-11-30 | Connected | Connected |  | 03-NY SM | 01-Passed | Passed | 24-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-12 | 16-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5419 | 2024-11-08 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
811 | 2406-4GDCS-4G#315-LGI002-0291 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add Antenna and RRU and Module BBU (New Infra) | LGI002 | TBG Talaga Raya-PERMANENISASICOI182 |  | NY Ineom | KENDARI | -5.4785 | 122.0789 | YPTT | October-24 |  | 2024 | 2024 |  |  | MOBI 12 Port | 3 | 3 | R9264E M1821 | 3 | 1 | 1 | 0 | VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 08-Oct-24 | Done | Done | 09-Oct-24 | Done | 100% | 08-Oct-24 | 08-Oct-24 | 08-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 09-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-11-18 | 2024-11-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5241 | 19-Oct-24 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
812 | 2406-4GDCS-4G#315-MRW036-0301 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | New Infra | MRW036 | BKKBN_015 |  |  | PALU | -2.217 | 121.6014 | YPTT | August-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-09-13 | Done | Done | 2024-09-14 | Done | 100% | 2024-09-13 | 2024-09-14 | 03-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 19-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 31-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
813 | 2406-4GDCS-4G#315-PSW002-0310 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add Antenna and RRU and Module BBU(New Infra) | PSW002 | DMT Kamelanta |  | ALL CLOSE | KENDARI | -5.2833 | 122.7071 | YPTT | 2026-09-24 |  | 2024 | 2024 | PSW002-N-3M2B |  | MOBI 12 Port | 3 | 3 | R9264E M1821 | 3 | 1 | 1 | 0 | VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-09-12 | Done | Done | 2024-09-17 | Done | 100% | 2024-09-12 | 2024-09-13 | 14-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 21-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 28-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2024-11-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
814 | 2406-4GDCS-4G#315-SKG076-0315 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | New Infra | SKG076 | PTISANRESANGADE |  |  | MAKASSAR | -4.2263 | 120.2828 | YPTT | July-24 |  | 2024 | 2024 | SKG076-N-3M2B | [28 empty] | Done Req ZTE |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-07-13 | Done | Done | 2024-07-15 | Done | 100% | 2024-07-13 | 2024-07-01 | 31-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-24 | 4-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4492 | 2024-07-30 | 16-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
815 | 2406-4GDCS-4G#315-SKG077-0316 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | New Infra | SKG077 | PERMANENISASICOI561 |  |  | MAKASSAR | -4.8613 | 119.5739 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-09-26 | Done | Done | 2024-09-27 | Done | 100% | 2024-09-26 | 2024-09-28 | 2024-09-28 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 1-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 28-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 24-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
816 | 2406-4GDCS-4G#315-SNN001-0317 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | New Infra | SNN001 | DMT Orifola Mangoli |  |  | TERNATE | -1.9263 | 125.8977 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 26-Oct-24 | Done | Done | 27-Oct-24 | Done | 100% | 26-Oct-24 | 27-Oct-24 | 29-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 29-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-11 | 2024-11-13 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5385 | 2024-11-01 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
817 | 2406-4GDCS-4G#315-SRI004-0324 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add Antenna and RRU and Module BBU (New Infra) | SRI004 | TBG Pajala Maginti |  | ALL CLOSE | KENDARI | -4.8443 | 122.3519 | YPTT | August-24 |  | 2024 | 2024 | SRI004-N-3M2P |  | Mobi 12 Port | 3 | 3 | R9264E M1821 | 3 | 1 | 1 | 0 | VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 19-Aug-24 | Done | Done | 19-Aug-24 | Done | 100% | 19-Aug-24 | 21-Aug-24 | 28-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 28-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-09 | 2024-09-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4913 | 2024-09-05 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
818 | 2406-4GDCS-4G#315-SSU006-0325 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | New Infra | SSU006 | HSMCENDANA |  |  | TERNATE | 0.46845 | 127.9223 | YPTT | October-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 05-Dec-24 | Done | Done | 10-Dec-24 | Done | 100% | 05-Dec-24 | 07-Dec-24 | 11-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 16-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 23-Dec-24 | 24-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5721 | 24-Dec-24 | 2025-01-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
819 | 2406-4GDCS-4G#315-TDK006-0326 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | New Infra | TDK006 | BKKBN_002 |  |  | PARE PARE | -1.9557 | 119.3167 | YPTT | August-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Andika | Done Productivity 100 % |  |  |  |  | 2024-09-21 | Done | Done | 2024-09-25 | Done | 100% | 2024-09-21 | 2024-09-22 | 04-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 5-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-11 | 2024-11-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2024-11-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
820 | 2406-4GDCS-4G#315-TDK010-0327 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | New Infra | TDK010 | TABOLANGTBG |  |  | PARE PARE | -2.02 | 119.3277 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Aswin | Done Productivity 100 % |  |  |  |  | 2024-09-10 | Done | Done | 2024-09-12 | Done | 100% | 2024-09-10 | 2024-09-11 | 2024-11-05 | Connected | Connected |  | 01-Passed | 01-Passed | NO NEED | 2024-09-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 11-Dec-24 | 2024-11-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
821 | 2406-4GDCS-4G#315-THN013-0328 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | New Infra | THN013 | TBGBEHA |  |  | MANADO | 3.6337 | 125.4313 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-09-27 | Done | Done | 2024-09-27 | Done | 100% | 2024-09-27 | 2024-09-28 | 13-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 14-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 29-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
822 | 2406-4GDCS-4G#RO-COI588-0264 | 0 | EQP New Site 4G LTE 1800 20 Mhz + DCS | Add Antenna, RRU and module BBU | COI588 | Leling Barat |  |  | PARE PARE | -2.23426 | 11939061 | YPTT | July-24 |  | 2024 | 2024 | [28 empty] | PTI | [5 empty] | PT. Djaya Sukses Pratama | Very | Done Productivity 100 % |  |  |  |  | 2024-09-02 | Done | Done | 2024-09-04 | Done | 100% | 2024-09-02 | 2024-09-04 | 2024-09-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-07-04 | 2025-07-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 31-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
823 | 2406-4GDCS-4G#RO-COI667-0271 | 0 | EQP New Site 4G LTE 1800 20 Mhz + DCS | Add Antenna, RRU and module BBU | COI667 | Combat MV Barakkang |  |  | PARE PARE | -2.20903 | 11920235 | YPTT | July-24 |  | 2024 | 2024 | [28 empty] | PTI | [5 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 30-Oct-24 | Done | Done | 31-Oct-24 | Done | 100% | 30-Oct-24 | 31-Oct-24 | 31-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | NO NEED | 2024-11-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-07-04 | 2025-07-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5385 | 2024-11-01 | 6-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
824 | 2406-4GDCS-4G#RO-DGL020-0211 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add RRU and Module BBU | DGL020 | KolaKolaDonggala-TBG |  |  | PALU | -0.73177 | 119.7114 | YPTT | July-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Azbar | Done Productivity 100 % |  |  |  |  | 2024-07-30 | Done | Done | 2024-07-30 | Done | 100% | 2024-07-30 | 2024-07-30 | 2024-07-30 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 5-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 9-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4554 | 7-Aug-24 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
825 | 2406-4GDCS-4G#RO-LBA107-0207 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add RRU and Module BBU | LBA107 | Sambiki |  |  | TERNATE | -1.3425 | 127.7174 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 02-Aug-24 | Done | Done | 02-Aug-24 | Done | 100% | 02-Aug-24 | 02-Aug-24 | 02-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 3-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 17-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
826 | 2406-4GDCS-4G#RO-LGI003-0250 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add Antenna and RRU and Module BBU(New Infra) | LGI003 | TBG Tanailandu |  | ALL CLOSE | KENDARI | -5.2372 | 122.3241 | YPTT | 2026-09-24 |  | 2024 | 2024 | LGI003-N-4M2P |  | MOBI 12 Port | 3 | 3 | R9264E M1821 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-09-13 | Done | Done | 2024-09-17 | Done | 100% | 2024-09-13 | 2024-09-14 | 2024-09-21 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 06-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | Waiting Permit | [10 empty] | 24-Oct-24 | 25-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 2024-11-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
827 | 2406-4GDCS-4G#RO-NTI110-0221 | 0 | EQP New NE 4G LTE 1800 20 Mhz 4T4R + DCS | Add RRU | NTI110 | N3T KAPALEO |  |  | TERNATE | -0.07608 | 129.4339 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-09-06 | Done | Done | 2024-09-05 | Done | 100% | 2024-09-06 | 2024-09-06 | 2024-09-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-24 | 5-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 9-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
828 | 2406-4GDCS-4G#RO-PKJ063-0222 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add RRU | BGA006 | TBG Laeya |  | ALL CLOSE | KENDARI | -4.5251 | 122.8705 | YPTT | December-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 15-Dec-24 | Done | Done | 16-Dec-24 | Done | 100% | 15-Dec-24 | 16-Dec-24 | 16-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 17-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-02-01 | 2025-01-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5722 | 24-Dec-24 | 2025-02-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
829 | 2406-4GDCS-4G#RO-PSK028-0210 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add RRU and Module BBU | PSK028 | DMT Doda Sarudu |  |  | PALU | -1.6366 | 119.3089 | YPTT | August-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Adri | Done Productivity 100 % |  |  |  |  | 24-Aug-24 | Done | Done | 24-Aug-24 | Done | 100% | 24-Aug-24 | 24-Aug-24 | 24-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 24-Aug |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4916 | 2024-09-06 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
830 | 2406-4GDCS-4G#RO-PSW001-0223 | 0 | EQP New NE 4G LTE 1800 20 Mhz 4T4R + DCS | Add RRU | PSW001 | DMT MH Pasar Ambuau |  | ALL CLOSE | KENDARI | -5.3177 | 123.1687 | YPTT | June-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-07-10 | Done | Done | 2024-07-09 | Done | 100% | 2024-07-10 | 2024-07-11 | 2024-07-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-08 | 13-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4380 | 2024-07-20 | 2024-09-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
831 | 2406-4GDCS-4G#RO-RHA152-0206 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add RRU and Module BBU | RHA152 | DMT Oensuli Kabangka |  | ALL CLOSE | KENDARI | -4.9507 | 122.3883 | YPTT | June-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 3 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-07-06 | Done | Done | 2024-07-09 | Done | 100% | 2024-07-06 | 2024-07-07 | 2024-07-07 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Aug-24 | 9-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4380 | 2024-07-20 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
832 | 2406-4GDCS-4G#RO-SKG010-0226 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | SKG010 | PENRANG |  |  | MAKASSAR | -4.1131 | 120.1742 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-07-26 | Done | Done | 2024-07-26 | Done | 100% | 2024-07-26 | 2024-07-26 | 2024-07-26 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-07-27 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-01-08 | 22-Aug-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 2024-09-17 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
833 | 2406-4GDCS-4G#RO-SRI003-0239 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add Antenna and RRU and Module BBU (New Infra) | SRI003 | TBG Parura Jaya |  | ALL CLOSE | KENDARI | -4.8522 | 122.4086 | YPTT | August-24 |  | 2024 | 2024 | SRI003-N-4M2P |  | MOBI 12 Port | 3 | 3 | R9224E M1821 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-09-01 | Done | Done | 2024-09-03 | Done | 100% | 2024-09-01 | 2024-09-02 | 2024-09-30 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 07-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 24-Oct-24 | 2024-11-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
834 | 2406-4GDCS-4G#RO-TDE012-0195 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add RRU | TDE012 | Paru Bengkok |  |  | TERNATE | 0.41176 | 127.7221 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-07-02 | Done | Done | 2024-07-03 | Done | 100% | 2024-07-02 | 2024-07-03 | 2024-07-03 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 16 August 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 23-Oct-24 | 25-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4332 | 2024-07-12 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
835 | 2406-4GDCS-4G#RO-TDE023-0240 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | New Infra | TDE023 | TBG Kusu Sofifi |  |  | TERNATE | 0.69266 | 127.5553 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-25 | Done | Done | 10-Oct-24 | Done | 100% | 2024-09-25 | 2024-09-25 | 13-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 15-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 28-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5241 | 19-Oct-24 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
836 | 2406-4GDCS-4G#RO-TDE073-0197 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add RRU | TDE073 | Pasigau |  |  | TERNATE | 0.63604 | 127.5406 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-06-29 | Done | Done | 2024-06-30 | Done | 100% | 2024-06-29 | 2024-06-30 | 2024-06-30 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 02 August 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
837 | 2406-4GDCS-4G#RO-TDE075-0229 | 0 | EQP New NE 4G LTE 1800 20 Mhz 4T4R + DCS | Add RRU | TDE075 | Change 3 |  |  | TERNATE | 0.71558 | 127.5542 | YPTT | June-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-06-28 | Done | Done | 2024-06-28 | Done | 100% | 2024-06-28 | 2024-06-28 | 2024-06-28 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 18 July 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-29 | 2024-07-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
838 | 2406-4GDCS-4G#RO-TDK003-0214 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | TDK003 | TDK003 |  |  | PARE PARE | 0 | 0 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Suardi | Done Productivity 100 % |  |  |  |  | 2024-06-29 | Done | Done | 2024-06-29 | Done | 100% | 2024-06-29 | 2024-06-29 | 2024-06-29 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
839 | 2406-4GDCS-4G#RO-TDK004-0198 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | TDK004 | TDK004 |  |  | PARE PARE | 0 | 0 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Suardi | Done Productivity 100 % |  |  |  |  | 2024-07-01 | Done | Done | 2024-07-01 | Done | 100% | 2024-07-01 | 2024-07-01 | 2024-07-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-06-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
840 | 2406-4GDCS-4G#RO-WGU012-0237 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | Add Antenna and RRU and Module BBU (New Infra) | WGU012 | TBG Bende Motui |  | ALL CLOSE | KENDARI | -3.8072 | 122.435 | YPTT | August-24 |  | 2024 | 2024 | WGU012-N-4M2P |  | MOBI 12 Port | 3 | 3 | R9264E M1821 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 23-Aug-24 | Done | Done | 25-Aug-24 | Done | 100% | 23-Aug-24 | 24-Aug-24 | 2024-09-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-18 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
841 | 2406-4GDCS-4G#RO-WTG057-0219 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | WTG057 | Desa Abbanuange, Kec. Lilirilau |  |  | MAKASSAR | -4.3672 | 120.0662 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-07-24 | Done | Done | 2024-07-24 | Done | 100% | 2024-07-24 | 2024-07-24 | 2024-07-24 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-07-28 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-10 | 9-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
842 | 2406-4GDCS-4G#RO-WTG065-0201 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | WTG065 | DONRI DONRI |  |  | MAKASSAR | -4.2406 | 119.9235 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-07-17 | Done | Done | 2024-07-17 | Done | 100% | 2024-07-17 | 2024-07-17 | 2024-07-17 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-07-18 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4492 | 2024-07-30 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
843 | 2406-4GDCS-4G#RO-WTG066-0205 | 0 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | WTG066 | BC_SOPPENG_MASING |  |  | MAKASSAR | -4.297 | 120.041 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-07-25 | Done | Done | 2024-07-26 | Done | 100% | 2024-07-25 | 2024-07-25 | 2024-07-25 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2024-07-28 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
844 | 2406-4GGSM-4G#RO-BAU028-0635 | 0 | EQP New NE 4G LTE 900 10 Mhz | Add Antenna and RRU and Module BBU (New Infra) | ADL122 | Permanenisasi COI272 |  | NY OA | KENDARI | -4.3947 | 122.0524 | YPTT | December-24 |  | 2024 | 2024 |  |  | MOBI 12 Port | 3 | 0 | R9224E M7290 | 3 | 1 | 1 | 0 | VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 6 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Cancel |  |  |  |  | 12-Dec-24 | Done |  | 11-Oct-24 | Done |  | 12-Dec-24 | 13-Dec-24 |  | NY | Installation Done |  | 03-NY SM | 01-Passed | No Need | 06-May-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-18 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5721 | 24-Dec-24 | 2025-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
845 | 2406-4GGSM-4G#RO-BGA005-0616 | 0 | EQP New NE 4G LTE 900 10 MHz + GSM | Add Antenna and RRU and Module BBU (New Infra) | BGA005 | TBG Pelabuhan Labuan |  | ALL CLOSE | KENDARI | -4.4798 | 122.9027 | YPTT | August-24 |  | 2024 | 2024 | BGA005-N-4M2P |  | MOBI 12 Port | 3 | 3 | R9224E M1821 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 6 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 31-Aug-24 | Done | Done | 2024-09-03 | Done | 100% | 31-Aug-24 | 2024-09-01 | 16-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 17-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 24-Oct-24 | 2024-11-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 9-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
846 | 2406-4GGSM-4G#RO-BGA006-0617 | 0 | EQP New NE 4G LTE 900 10 MHz + GSM | Add Antenna and RRU and Module BBU (New Infra) | BGA006 | TBG Laeya |  | ALL CLOSE | KENDARI | -4.5251 | 122.8705 | YPTT | August-24 |  | 2024 | 2024 | BGA006-N-4M2P |  | MOBI 12 Port | 3 | 3 | R9224E M1821 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 6 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 28-Aug-24 | Done | Done | 31-Aug-24 | Done | 100% | 28-Aug-24 | 30-Aug-24 | 10-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 16-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 28-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
847 | 2406-4GGSM-4G#RO-BUA003-0638 | 0 | EQP New NE 4G LTE 900 10 MHz + GSM | Add Antenna and RRU and Module BBU (New Infra) | BUA003 | TBG Bola-Permanenisasi COI014 |  | ALL CLOSE | KENDARI | -5.694 | 122.6514 | YPTT | August-24 |  | 2024 | 2024 |  |  | MOBI 12 Port | 3 | 3 | R9224E M1821 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-09-08 | Done | Done | 2024-09-05 | Done | 100% | 2024-09-08 | 2024-09-09 | 2024-09-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 20-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 21-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
848 | 2406-4GGSM-4G#RO-COI588-0620 | 0 | EQP New Site 4G LTE 900 10 Mhz + GSM | Add RRU | COI588 | Leling Barat |  |  | PARE PARE | -2.23426 | 11939061 | YPTT | July-24 |  | 2024 | 2024 | [28 empty] | PTI | [5 empty] | PT. Djaya Sukses Pratama | Very | Done Productivity 100 % |  |  |  |  | 2024-09-02 | Done | Done | 2024-09-04 | Done | 100% | 2024-09-02 | 2024-09-05 | 2024-09-05 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-22 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-07-04 | 2025-07-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 2026-01-07 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
849 | 2406-4GGSM-4G#RO-COI662-0631 | 0 | EQP New Site 4G LTE 900 10 Mhz + GSM | Add RRU | COI662 | TBG Kayangan Soppeng |  |  | MAKASSAR | -4.3606 | 11988732 | YPTT | July-24 |  | 2024 | 2024 | [28 empty] | TBG | Done Req ZTE |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 27-Aug-24 | Done | Done | 29-Aug-24 | Done | 100% | 27-Aug-24 | 28-Aug-24 | 2024-09-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-02-27 | 2025-03-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4916 | 2024-09-06 | 2025-03-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
850 | 2406-4GGSM-4G#RO-COI667-0627 | 0 | EQP New Site 4G LTE 900 10 Mhz + GSM | Add RRU | COI667 | Combat MV Barakkang |  |  | PARE PARE | -2.20903 | 11920235 | YPTT | July-24 |  | 2024 | 2024 | [28 empty] | PTI | [5 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 30-Oct-24 | Done | Done | 2024-11-02 | Done | 100% | 30-Oct-24 | 2024-11-01 | 2024-11-01 | Connected | Connected |  | 01-Passed | 01-Passed | NO NEED | 2024-11-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-07-04 | 30-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5385 | 2024-11-01 | 22-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
851 | 2406-4GGSM-4G#RO-KKA035-0643 | 0 | EQP New NE 4G LTE 900 10 MHz + GSM | Add Antenna and RRU and Module BBU | KKA035 | DMT Sopura - Permanenisasi COI581 |  |  | KENDARI | -4.2673 | 121.5672 | YPTT | July-24 |  | 2024 | 2024 |  |  | MOBI 12 Port | 3 | 3 | R9224E M7290 | 3 | 1 | 1 | 0 | VBPd2p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 6 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Aladin | Done Productivity 100 % |  |  |  |  | 2025-02-09 | Done | Done | 2025-02-09 | Done | 100% | 2025-02-09 | 2025-02-09 | 2025-03-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-24 | 2025-03-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6155 | 2025-03-17 | 2025-04-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
852 | 2406-4GGSM-4G#RO-MMS012-0646 | 0 | EQP New NE 4G LTE 900 10 MHz + GSM | New Infra | MMS012 | BKKBN_009 |  |  | PARE PARE | -2.9138 | 119.4216 | YPTT | August-24 |  | 2024 | 2024 | MMS012-N-3M2B | [33 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-09-02 | Done | Done | 2024-09-05 | Done | 100% | 2024-09-02 | 2024-09-04 | 2024-09-11 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-09-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-23 | 5-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
853 | 2406-4GGSM-4G#RO-MRW055-0649 | 0 | EQP New Site 4G LTE 900 10 Mhz | New Infra | MRW055 | PERMANENISASICOI389 |  |  | PALU | -2.1711 | 121.5164 | YPTT | August-24 |  | 2024 | 2024 | MRW055-N-3M2P | [33 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 22-Aug-24 | Done | Done | 23-Aug-24 | Done | 100% | 22-Aug-24 | 25-Aug-24 | 23-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 31-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 11-Aug-24 | 2024-11-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4913 | 2024-09-05 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
854 | 2406-4GGSM-4G#RO-OSU012-0610 | 0 | EQP New NE 4G LTE 900 10 MHz | Add Antenna and RRU and Module BBU | OSU012 | Permanenisasi COI605 - Combat Winangun Siau |  |  | MANADO | 2.7803 | 125.3772 | YPTT | October-24 |  | 2024 | 2024 | [28 empty] | DMT | Release |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 20-Dec-24 | Done | Done | 30-Dec-24 | Done | 100% | 20-Dec-24 | 29-Dec-24 | 2025-01-07 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 02-Dec-25 | 2025-02-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5760 | 2025-01-01 | 2025-02-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
855 | 2406-4GGSM-4G#RO-RHA068-0653 | 0 | EQP New NE 4G LTE 900 10 MHz + GSM | Add Antenna and RRU and Module BBU(New Infra) | RHA068 | TBG Laiba Muna |  | ALL CLOSE | KENDARI | -5.0461 | 122.4933 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | MOBI 12 Port | 3 | 3 | R9224E M1821 | 3 | 1 | 1 | 0 | VBpd2p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 6 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2024-09-12 | Done | Done | 2024-09-19 | Done | 100% | 2024-09-12 | 2024-09-13 | 03-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 15-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 28-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
856 | 2406-4GGSM-4G#RO-SKG078-0608 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | New Infra | SKG078 | CAND_CP#1-24__01689 |  |  | MAKASSAR | -4.1626 | 120.1941 | YPTT | July-24 |  | 2024 | 2024 | SKG078-N-4M2P | [28 empty] | Done Req ZTE |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 25-Aug-24 | Done | Done | 30-Aug-24 | Done | 100% | 25-Aug-24 | 29-Aug-24 | 2024-09-27 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-30 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4916 | 2024-09-06 | 2024-11-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
857 | 2406-4GGSM-4G#RO-SNN003-0605 | 0 | EQP New NE 4G LTE 900 10 MHz | New Infra | SNN003 | DMT Wailau Sanana |  |  | TERNATE | -2.132 | 125.9573 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-09-30 | Done | Done | 2024-09-30 | Done | 100% | 2024-09-30 | 01-Oct-24 | 01-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 10-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 24-Oct-24 | 2024-11-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
858 | 2406-4GGSM-4G#RO-SRI002-0607 | 0 | EQP New NE 4G LTE 900 10 MHz | Add Antenna and RRU and Module BBU (New Infra) | SRI002 | TBG Guali |  | ALL CLOSE | KENDARI | -4.7493 | 12254046 | YPTT | August-24 |  | 2024 | 2024 | SRI002-N-4M2P |  | MOBI 12 Port | 3 | 3 | R9224E M1821 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 29-Aug-24 | Done | Done | 2024-09-07 | Done | 100% | 29-Aug-24 | 30-Aug-24 | 2024-09-30 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 08-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 24-Oct-24 | 25-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 2024-11-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
859 | 2406-4GGSM-4G#RO-SSU008-0606 | 0 | EQP New NE 4G LTE 900 10 MHz | New Infra | SSU008 | PERMANENISASI SSU062 |  |  | TERNATE | 13661 | 12787386 | YPTT | October-24 |  | 2024 | 2024 | [28 empty] | DMT | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-11-02 | Done | Done | 2024-11-03 | Done | 100% | 28-Oct-24 | 30-Oct-24 | 2025-06-28 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-07-03 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-04 | 2025-07-14 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5385 | 2024-11-01 | 4-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
860 | 2406-4GGSM-4G#RO-SSU009-0663 | 0 | EQP New NE 4G LTE 900 10 MHz + GSM | New Infra | TDE024 | DMT Oba Akelamo |  |  | TERNATE | 0.53433 | 127.5425 | YPTT | October-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-11-01 | Done | Done | 2024-11-05 | Done | 100% | 2024-11-01 | 2024-11-03 | 2024-11-03 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-11-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-11-25 | 2024-11-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5419 | 2024-11-08 | 2025-01-07 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
861 | 2406-4GGSM-4G#RO-TDK007-0657 | 0 | L900 | New Infra | TDK007 | PERMANENISASICOI580 |  |  | PARE PARE | -2.0603 | 119.4366 | YPTT | July-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Aswin | Done Productivity 100 % |  |  |  |  | 12-Oct-23 | Done | Done | 12-Oct-23 | Done | 100% | 12-Oct-23 | 14-Oct-24 | 2025-01-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 31-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-02 | 2025-02-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5277 | 24-Oct-24 | 2025-02-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
862 | 2406-4GGSM-4G#RO-TDK008-0664 | 0 | EQP New NE 4G LTE 900 10 MHz + GSM | New Infra | TDK008 | PERMANENISASICOI135 |  |  | PARE PARE | -2.0354 | 119.2931 | YPTT | August-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Very | Done Productivity 100 % |  |  |  |  | 2024-09-02 | Done | Done | 2024-09-07 | Done | 100% | 2024-09-02 | 2024-09-05 | 2024-09-17 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-09-17 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-23 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
863 | 2406-4GGSM-4G#RO-TDK009-0603 | 0 | EQP New NE 4G LTE 900 10 Mhz | New Infra | TDK009 | TDK009 |  |  | PARE PARE | -2.1341 | 119.1928 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Aswin | Done Productivity 100 % |  |  |  |  | 15-Oct-24 | Done | Done | 16-Oct-24 | Done | 100% | 15-Oct-24 | 17-Oct-24 | 2024-11-26 | Connected | Connected |  | 01-Passed | 01-Passed | NO NEED | 23-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-12 | 11-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5285 | 24-Oct-24 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
864 | 2406-4GGSM-4G#RO-TOB002-0600 | 0 | EQP New NE 4G LTE 900 10 MHz | Add Antenna and RRU and Module BBU (New Infra) | TOB002 | GAMSUNGI |  |  | TERNATE | 1.0025 | 127.6424 | YPTT | 2026-09-24 |  | 2024 | 2024 | TOB002-N-4M2P | [28 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-20 | Done | Done | 2024-09-20 | Done | 100% | 2024-09-20 | 2024-09-21 | 04-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 15-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 24-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
865 | 2406-4GGSM-4G#RO-WGI003-0618 | 0 | EQP New NE 4G LTE 900 10 MHz | Add Antenna and RRU and Module BBU(New Infra) | WGI003 | TBG Marina Togo-PERMANENISASICOI382 |  | ALL CLOSE | KENDARI | -5.3216 | 123.5329 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | MOBI 12 Port | 3 | 3 | R9224E M1821 | 3 | 1 | 1 | 0 | VBpd0p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 6 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 10-Oct-24 | Done | Done | 11-Oct-24 | Done | 100% | 10-Oct-24 | 11-Oct-24 | 11-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 15-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 24-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5241 | 19-Oct-24 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
866 | 2406-4GGSM-4G#RO-WGI004-0659 | 0 | EQP New NE 4G LTE 900 10 MHz + GSM | Add Antenna and RRU and Module BBU (New Infra) | WGI004 | TBG Puncak Toliamba-Permanenisasi COI474 |  | NY OA | KENDARI | -5.2939 | 123.5455 | YPTT | August-24 |  | 2024 | 2024 | WGI004-N-3M2P | [33 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 21-Aug-24 | Done | Done | 23-Aug-24 | Done | 100% | 21-Aug-24 | 22-Aug-24 | 30-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 31-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-11-15 | 2024-11-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4913 | 2024-09-05 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
867 | 2406-4GGSM-4G#RO-WGU011-0660 | 0 | EQP New NE 4G LTE 900 10 MHz | Add Antenna and RRU and Module BBU (New Infra) | WGU011 | DMT Molore Pantai |  | ALL CLOSE | KENDARI | -3.3069 | 122.2762 | YPTT | October-24 |  | 2024 | 2024 |  |  | MOBI 12 Port | 3 | 3 | R9224E M1821 | 3 | 1 | 1 | 0 | VBpd2p(1) | VSWD1(1) | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 6 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 16-Oct-24 | Done | Done | 2024-07-20 | Done | 100% | 16-Oct-24 | 17-Oct-24 | 2024-11-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-11-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-11-11 | 2024-11-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
868 | 2406-4GGSM-4G#RO-WTG067-0661 | 0 | EQP New NE 4G LTE 900 10 MHz + GSM | New Infra | WTG067 | PERMANENISASICOI536 |  |  | MAKASSAR | -5.195 | 119.4999 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 2024-09-25 | Done | Done | 2024-09-27 | Done | 100% | 2024-09-25 | 2024-09-26 | 06-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 6-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 28-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 24-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
869 | 2406-4GGSM-4G#RO-WTG068-0602 | 0 | EQP New NE 4G LTE 1800 20 Mhz + DCS | New Infra | WT068 | DMT KEBO LILIRILAU |  |  | MAKASSAR | -4.2976 | 119.9853 | YPTT | July-24 |  | 2024 | 2024 | WTG068-N-4M2P | [28 empty] | Done Req ZTE |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 28-Aug-24 | Done | Done | 2024-09-02 | Done | 100% | 28-Aug-24 | 2024-09-01 | 2024-09-22 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-30 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
870 | 2406-ADSTR-4G#316-EPS005-0080 | 0 | EQP Add Sector LTE 1800 2T2R | Add RRU and Module BBU | EPS005 | DMT EP Mozaik Kalumata |  |  | TERNATE | 0.79823 | 127.2933 | YPTT | October-24 |  | 2024 | 2024 | [28 empty] | DMT | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 16-Oct-24 | Done | Done | 23-Oct-24 | Done | 100% | 16-Oct-24 | 25-Oct-24 | 2025-02-17 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-07-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5371 | 31-Oct-24 | 2025-03-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
871 | 2406-ADSTR-4G#RO-EPS002-0065 | 0 | EQP Add Sector LTE L1800 + L2100 | Add RRU | EPS002 | DMT EP Taduma |  |  | TERNATE | 798373 | 12729335 | YPTT | October-24 |  | 2024 | 2024 | [28 empty] | DMT | Release |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 16-Oct-24 | Done | Done | 23-Oct-24 | Done | 100% | 16-Oct-24 | 22-Oct-24 | 2025-02-27 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2025-03-04 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-08 | 2025-04-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5372 | 31-Oct-24 | 2025-06-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
872 | 2406-ADSTR-4G#RO-EPS006-0067 | 0 | EQP Add Sector LTE L1800 + L2100 | Add RRU and Module BBU | EPS006 | RUSUNAWAUNKHAIR |  |  | TERNATE | 0.76235 | 127.3409 | YPTT | October-24 |  | 2024 | 2024 | [28 empty] | DMT | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 24-Oct-24 | Done | Done | 2024-11-07 | Done | 100% | 24-Oct-24 | 2024-11-04 | 2025-02-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-19 | 2025-03-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5406 | 2024-11-06 | 2025-06-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
873 | 2406-ADSTR-4G#RO-EPS007-0072 | 0 | EQP Add Sector LTE L1800 + L2100 | Add RRU | EPS007 | RSUDTERNATE |  |  | TERNATE | -0.087769 | 127.3748 | YPTT | October-24 |  | 2024 | 2024 | [28 empty] | DMT | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-31 | Done | Done | 2025-02-01 | Done | 100% | 2025-01-31 | 2025-01-31 | 2025-02-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-07-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5910 | 2025-02-05 | 2025-03-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
874 | 2406-ADSTR-4G#RO-EPS011-0069 | 0 | EQP Add Sector LTE L1800 + L2100 | Add RRU and Swap Module BBU | EPS011 | JENNAELAJOA |  |  | MAKASSAR | -4.4038 | 119.9478 | YPTT | July-24 |  | 2024 | 2024 | [28 empty] | TBG | Done Req ZTE |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2024-11-03 | Done | Done | 2024-11-04 | Done | 100% | 2024-11-03 | 2024-11-03 | 2025-01-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-29 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-02-19 | 2025-02-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5406 | 2024-11-06 | 2025-03-04 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
875 | 2406-NNE4G-4G#RO-COI590-1080 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Swap Module BBU | COI590 | CombatMVPintuMasukPerusahaanGNIBunta |  |  | PALU | -2.0611 | 121.3747 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-06-29 | Done | Done | 2024-06-30 | Done | 100% | 2024-06-29 | 2024-06-30 | 2024-06-30 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-17 |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 2024-11-25 | 2024-11-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
876 | 2406-NNE4G-4G#RO-COI591-1081 | 0 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Swap Module BBU | COI591 | CombatMVDesaBahururu |  |  | PALU | -2.5179 | 121.9496 | YPTT | June-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Musdar | Done Productivity 100 % |  |  |  |  | 2024-06-29 | Done | Done | 2024-06-30 | Done | 100% | 2024-06-29 | 2024-06-30 | 2024-06-30 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2026-07-09 |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 21-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4297 | 2024-07-06 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
877 | 2406-NNE4G-4G#RO-COI662-1089 | 0 | EQP New Site 4G LTE 2100 5 Mhz | Add Antenna, RRU and module BBU | COI662 | TBG Kayangan Soppeng |  |  | MAKASSAR | -4.3606 | 11988732 | YPTT | July-24 |  | 2024 | 2024 | [28 empty] | TBG | Done Req ZTE |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 27-Aug-24 | Done | Done | 29-Aug-24 | Done | 100% | 27-Aug-24 | 28-Aug-24 | 2024-09-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-03 | 2025-03-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4916 | 2024-09-06 | 2025-03-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
878 | 2406-UPMod-4G#316-DGL051-0073 | 0 | EQP Modular Upgrade | Swap Module BBU and RRU | DGL051 | DMT BANAWA SELATAN |  |  | PALU | -0.80086 | 119.6303 | YPTT | July-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Azbar | Done Productivity 100 % |  |  |  |  | 2024-07-29 | Done | Done | 2024-07-29 | Done | 100% | 2024-07-29 | 2024-07-29 | 2024-07-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-05 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4558 | 7-Aug-24 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
879 | 2406-UPMod-4G#316-MDO016-0077 | 0 | EQP Modular Upgrade | Swap Module BBU and RRU | MDO016 | KAYUWATU |  |  | MANADO | 1.5034 | 124.8928 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-07-16 | Done | Done | 2024-07-18 | Done | 100% | 2024-07-16 | 2024-07-18 | 2024-07-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 29 July 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-13 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4380 | 2024-07-20 | 2024-09-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
880 | 2406-UPMod-4G#316-MDO017-0078 | 0 | EQP Modular Upgrade | Swap Module BBU and RRU | MDO017 | Pineleng |  |  | MANADO | 1.4344 | 124.8439 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-07-12 | Done | Done | 2024-07-16 | Done | 100% | 2024-07-12 | 2024-07-16 | 2024-07-16 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 23 July 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 09-Dec-24 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4380 | 2024-07-20 | 2024-09-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
881 | 2406-UPMod-4G#316-MDO019-0079 | 0 | EQP Modular Upgrade | Swap Module BBU and RRU | MDO019 | Kanaka |  |  | MANADO | 1.4894 | 124.8473 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-07-30 | Done | Done | 14-Aug-24 | Done | 100% | 2024-07-30 | 13-Aug-24 | 14-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 20-Aug-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 2024-09-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
882 | 2406-UPMod-4G#316-MDO048-0080 | 0 | EQP Modular Upgrade | Swap Module BBU and RRU | MDO048 | DMT Kampus Unsrat |  |  | MANADO | 1.4588 | 124.8288 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 01-Aug-24 | Done | Done | 02-Aug-24 | Done | 100% | 01-Aug-24 | 02-Aug-24 | 02-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 21-Aug-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-13 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 2024-09-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
883 | 2406-UPMod-4G#316-MDO079-0081 | 0 | EQP Modular Upgrade | Swap Module BBU and RRU | MDO079 | MDO079M41_CAMAR |  |  | MANADO | 1.4708 | 124.8819 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Aditia | Done Productivity 100 % |  |  |  |  | 01-Aug-24 | Done | Done | 2024-07-31 | Done | 100% | 01-Aug-24 | 02-Aug-24 | 02-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 28-Aug-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-13 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 2024-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
884 | 2406-UPMod-4G#316-MDO103-0082 | 0 | EQP Modular Upgrade | Swap RRU | MDO103 | MDO103M41_BAHU2-PTI |  |  | MANADO | 1.4627 | 124.826 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-07-30 | Done | Done | 13-Aug-24 | Done | 100% | 2024-07-30 | 2024-07-30 | 13-Aug-24 | Connected | Connected | Need Komfirm Tim Planning | 01-Passed | 01-Passed | SM Passed | 26-Aug-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-09-15 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 2024-09-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
885 | 2406-UPMod-4G#316-MDO119-0083 | 0 | EQP Modular Upgrade | Swap Module BBU and RRU | MDO119 | Protelindo Hotel Grand Puri |  |  | MANADO | 1.4592 | 124.8373 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Aditia | Done Productivity 100 % |  |  |  |  | 13-Aug-24 | Done | Done | 16-Aug-24 | Done | 100% | 13-Aug-24 | 16-Aug-24 | 16-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-03 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 09-Dec-24 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 2024-09-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
886 | 2406-UPMod-4G#316-MDO132-0084 | 0 | EQP Modular Upgrade | Swap Module BBU and RRU | MDO132 | MDO132M41_ALANDREW-PTI |  |  | MANADO | 1.4468 | 124.8146 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-07-31 | Done | Done | 01-Aug-24 | Done | 100% | 2024-07-31 | 01-Aug-24 | 01-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 22-Aug-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 09-Dec-24 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 2024-09-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
887 | 2406-UPMod-4G#316-MDO150-0085 | 0 | EQP Modular Upgrade | Swap Module BBU and RRU | MDO150 | DMT Paal IV |  |  | MANADO | 1.4735 | 124.8652 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 2024-07-29 | Done | Done | 2024-07-30 | Done | 100% | 2024-07-29 | 2024-07-30 | 2024-07-31 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 16 August 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-11-09 | 2024-09-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 2024-09-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
888 | 2406-UPMod-4G#316-MDO214-0087 | 0 | EQP Modular Upgrade | Swap Module BBU and RRU | MDO214 | MDO214M41_KOMBOS-IBS |  |  | MANADO | 1.5002 | 124.871 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-07-13 | Done | Done | 2024-07-14 | Done | 100% | 2024-07-13 | 2024-07-14 | 2024-07-14 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 04-Dec-24 |  | Done Tagging |  | Done Tagging | Work Not Start | Need Reloc OTB | [10 empty] | 09-Dec-24 | 2024-09-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4380 | 2024-07-20 | 2024-09-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
889 | 2406-UPMod-4G#316-MDO217-0088 | 0 | EQP Modular Upgrade | Swap Module BBU and RRU | MDO217 | MDO217M41_HOTELDIVACHK |  |  | MANADO | 1.4606 | 124.8237 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Hendra | Done Productivity 100 % |  |  |  |  | 02-Aug-24 | Done | Done | 02-Aug-24 | Done | 100% | 02-Aug-24 | 02-Aug-24 | 02-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 09 August 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-09-23 | 2024-09-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4559 | 7-Aug-24 | 2024-09-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
890 | 2406-UPMod-4G#RO-MDO156-0107 | 0 | BBU Modernization | Swap BBU | MDO156 | Prot Megamasstreetlayer 1 |  |  | MANADO | 1.4782 | 124.8343 | YPTT | July-24 |  | 2024 | 2024 | [28 empty] | PTI | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 03-Aug-24 | Done | Done | 05-Aug-24 | Done | 100% | 03-Aug-24 | 05-Aug-24 | 05-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-06 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-18 | 2025-06-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
891 | 2406-UPMod-4G#RO-MDO157-0108 | 0 | BBU Modernization | Swap BBU | MDO157 | Prot Megamasstreetlayer 2 |  |  | MANADO | 1.476 | 124.8338 | YPTT | July-24 |  | 2024 | 2024 | [28 empty] | PTI | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 03-Aug-24 | Done | Done | 03-Aug-24 | Done | 100% | 03-Aug-24 | 03-Aug-24 | 03-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-04 |  | Done Tagging |  | Done Tagging | [12 empty] | 2025-06-18 | 2025-06-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 2025-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
892 | 2406-UPMod-4G#RO-MDO519-0137 | 0 | BBU Modernization | Swap BBU | MDO519 | MCR Titiwungan Sario |  |  | MANADO | 1.4769 | 124.8351 | YPTT | July-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Done Req ZTE |  |  |  |  | YPTT | hendra | Done Productivity 100 % |  |  |  |  | 01-Aug-24 | Done | Done | 01-Aug-24 | Done | 100% | 01-Aug-24 | 01-Aug-24 | 01-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 10 August 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-15 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 2025-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
893 | 2406-UPMod-4G#RO-MDO573-0142 | 0 | BBU Modernization | Swap BBU | MDO573 | Anugerah MM Samratulangi |  |  | MANADO | 1.4817 | 124.8365 | YPTT | July-24 |  | 2024 | 2024 | [28 empty] | CMI | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Aditia | Done Productivity 100 % |  |  |  |  | 04-Aug-24 | Done | Done | 04-Aug-24 | Done | 100% | 04-Aug-24 | 04-Aug-24 | 04-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 12 August 2024 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-15 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 2025-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
894 | 2407-4GDCS-4G#RO-BOB001-0338 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | BOB001 | Desa Todoli |  |  | TERNATE | -1.6667 | 124.4641 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 10-Oct-24 | Done | Done | 14-Oct-24 | Done | 100% | 10-Oct-24 | 15-Oct-24 | 14-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 15-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 25-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5277 | 24-Oct-24 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
895 | 2407-4GDCS-4G#RO-COI287-0339 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | COI287 | Kantor Penyuluh Pertanian Sagea |  |  | TERNATE | 0.46204 | 128.0891 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 24-Aug-24 | Done | Done | 27-Aug-24 | Done | 100% | 24-Aug-24 | 24-Aug-24 | 24-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 25-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
896 | 2407-4GDCS-4G#RO-KKA008-0340 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | KKA008 | DMT Tolowe Ponrewaru |  | ALL CLOSE | KENDARI | -3.8356 | 121.307 | YPTT | August-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 3 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 17-Aug-24 | Done | Done | 17-Aug-24 | Done | 100% | 17-Aug-24 | 17-Aug-24 | 17-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 18-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-10 | 9-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4913 | 2024-09-05 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
897 | 2407-4GDCS-4G#RO-LBA014-0342 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | LBA014 | Pertambangan Obi Anggai |  |  | TERNATE | -1.3622 | 127.7287 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-09-01 | Done | Done | 2024-09-01 | Done | 100% | 2024-09-01 | 2024-09-01 | 2024-09-01 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-07-01 | 2025-01-14 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 90%
898 | 2407-4GDCS-4G#RO-LBA023-0343 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | LBA023 | Permanenisasi MXW047 - Nain |  |  | TERNATE | -0.74515 | 127.645 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 28-Aug-24 | Done | Done | 29-Aug-24 | Done | 100% | 28-Aug-24 | 29-Aug-24 | 29-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 31-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 9-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
899 | 2407-4GDCS-4G#RO-LBA077-0344 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | LBA077 | DMT Moti Surya |  |  | TERNATE | 0.45439 | 127.3841 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 24-Aug-24 | Done | Done | 26-Aug-24 | Done | 100% | 24-Aug-24 | 25-Aug-24 | 25-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 27-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 9-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 2024-11-08 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
900 | 2407-4GDCS-4G#RO-PIN022-0347 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | PIN022 | LETTA |  |  | PARE PARE | -301323 | 11885811 | YPTT | August-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 20-Aug-24 | Done | Done | 22-Aug-24 | Done | 100% | 20-Aug-24 | 21-Aug-24 | 21-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 22-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4916 | 2024-09-06 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
901 | 2407-4GDCS-4G#RO-RHA059-0350 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | RHA059 | DMT Wulanga Jaya |  | ALL CLOSE | KENDARI | -4.8291 | 12243420 | YPTT | August-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 3 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 26-Aug-24 | Done | Done | 26-Aug-24 | Done | 100% | 26-Aug-24 | 27-Aug-24 | 27-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 27-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4916 | 2024-09-06 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
902 | 2407-4GDCS-4G#RO-SSU133-0351 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | SSU133 | Trans Lelilef |  |  | TERNATE | 0.47054 | 127.9109 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 21-Aug-24 | Done | Done | 21-Aug-24 | Done | 100% | 21-Aug-24 | 21-Aug-24 | 21-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 28-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4916 | 2024-09-06 | 9-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
903 | 2407-4GDCS-4G#RO-TDE074-0352 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | TDE074 | Togeme |  |  | TERNATE | 0.455 | 127.5704 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 27-Aug-24 | Done | Done | 28-Aug-24 | Done | 100% | 27-Aug-24 | 28-Aug-24 | 28-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 05-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 9-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 2024-11-08 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
904 | 2407-4GDCS-4G#RO-TOB016-0356 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | TOB016 | Desa MKCM, Kec. Tobelo |  |  | TERNATE | 1.7313 | 127.9909 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 30-Aug-24 | Done | Done | 30-Aug-24 | Done | 100% | 30-Aug-24 | 30-Aug-24 | 30-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-01 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Aug-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 17-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
905 | 2407-4GDCS-4G#RO-TOB126-0357 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | TOB126 | TBG Kakara Pulau |  |  | TERNATE | 1.7479 | 128.0484 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-02 | Done | Done | 2024-09-02 | Done | 100% | 2024-09-02 | 2024-09-02 | 2024-09-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 17-Oct-24 | 2024-11-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
906 | 2407-4GGSM-4G#RO-RHA067-0668 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 900 10 MHz | Add RRU and Module BBU | RHA067 | DMT Wadolao |  | ALL CLOSE | KENDARI | -5.1009 | 122.3614 | YPTT | August-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 3 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 20-Aug-24 | Done | Done | 20-Aug-24 | Done | 100% | 20-Aug-24 | 20-Aug-24 | 20-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 20-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4913 | 2024-09-05 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
907 | 2407-4GGSM-4G#RO-SSU138-0670 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 900 10 MHz | Add RRU and Module BBU | SSU138 | Perumahan Fidi Jaya |  |  | TERNATE | 0.33879 | 127.871 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 11-Aug-24 | Done | Done | 13-Aug-24 | Done | 100% | 11-Aug-24 | 11-Aug-24 | 11-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 12-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
908 | 2407-BARNC-4G#RO-BAU007-0010 | #N/A | Dismantle Donor | Dismantle BSC | BAU007 | RNCZ_BAUBAU1 |  | Done | KENDARI | -5.4599 | 122.6176 | YPTT | July-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Ruslan | [5 empty] | 16-Aug-24 | Done | Done | 16-Aug-24 | Done | 100% | 16-Aug-24 | 16-Aug-24 | 16-Aug-24 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | No Need |  | No Need |  | Done Tagging | Done Tagging | Done Tagging | [10 empty] | 00-Jan-00 | 0-Jan-00 | 17-Work NY Done | PO NY Release |  |  |  | #N/A |  | Done Upload
909 | 2407-BARNC-4G#RO-KKA002-0009 | CAPEX RAN 2 PART 3 2024 | Dismantle Donor | Dismantle BSC | KKA002 | RNCZ_POMALA1 |  | Done | KENDARI | -4.1947 | 121.6032 | YPTT | July-24 |  | 2024 | 2024 | [34 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 13-Aug-24 | Done | Done |  | Done | 100% | 13-Aug-24 | 13-Aug-24 | 13-Aug-24 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | No Need |  | No Need |  | Done Tagging | Done Tagging | Done Tagging | [10 empty] | 13-Dec-24 | 16-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5285 | 24-Oct-24 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
910 | 2407-MiRNC-4G#RO-KDI082-0025 | CAPEX RAN 2 PART 3 2024 | RNC Migration | Relocation BSC | KDI082 | BSCZ_KENDARI4 |  | OA | KENDARI | -3.9973 | 122.5 | YPTT | July-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 20-Aug-24 | Done | Done | 2024-07-31 | Done | 100% | 20-Aug-24 | 21-Aug-24 | 2024-11-30 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 15-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | Work Not Start | [10 empty] | 2025-03-25 | 2025-03-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5221 | 17-Oct-24 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
911 | 2407-MiRNC-4G#RO-KDI082-0026 | CAPEX RAN 2 PART 3 2024 | RNC Migration | Relocation BSC | KDI082 | BSCZ_KENDARI5 |  | OA | KENDARI | -3.9973 | 122.5 | YPTT | July-24 |  | 2024 | 2024 | [34 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 20-Aug-24 | Done | Done | 2024-07-31 | Done | 100% | 20-Aug-24 | 21-Aug-24 | 2024-11-30 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 15-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | Work Not Start | [10 empty] | 2025-03-17 | 2025-03-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5221 | 17-Oct-24 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
912 | 2407-NNE4G-4G#RO-LBA076-1096 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | LBA076 | CombatFUNAirportBacan |  |  | TERNATE | -0.63976 | 127.5025 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 08-Aug-24 | Done | Done | 09-Aug-24 | Done | 100% | 08-Aug-24 | 09-Aug-24 | 09-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 10-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 9-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
913 | 2407-NNE4G-4G#RO-SSU131-1101 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | SSU131 | Split Lokolamo |  |  | TERNATE | 0.47697 | 127.8961 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 04-Aug-24 | Done | Done | 05-Aug-24 | Done | 100% | 04-Aug-24 | 05-Aug-24 | 05-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 07 August 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-10 | 9-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
914 | 2407-NNE4G-4G#RO-SSU132-1102 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | SSU132 | Lelilef Utara |  |  | TERNATE | 0.47067 | 127.926 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 04-Aug-24 | Done | Done | 04-Aug-24 | Done | 100% | 04-Aug-24 | 04-Aug-24 | 04-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 10-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
915 | 2407-NNE4G-4G#RO-SSU136-1103 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | SSU136 | Weda City |  |  | TERNATE | 0.33054 | 127.8768 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 08-Aug-24 | Done | Done | 08-Aug-24 | Done | 100% | 08-Aug-24 | 08-Aug-24 | 08-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 11-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
916 | 2407-NNE4G-4G#RO-TDE071-1104 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | TDE071 | Alun Alun Sofifi |  |  | TERNATE | 0.7408 | 127.5696 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 13-Aug-24 | Done | Done | 13-Aug-24 | Done | 100% | 13-Aug-24 | 13-Aug-24 | 13-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 14 August 2024 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 9-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4912 | 2024-09-05 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
917 | 2407-NNE4G-4G#RO-TER214-1105 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Module BBU | TER214 | Maliaoro |  |  | TERNATE | 0.78416 | 127.3597 | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 13-Aug-24 | Done | Done | 14-Aug-24 | Done | 100% | 13-Aug-24 | 14-Aug-24 | 14-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 16-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-4913 | 2024-09-05 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
918 | 2407-NNE4G-4G#RO-TOB127-1106 | Activity Non MPSL_R09 Sulawesi_2024_KKST Non MPSL Presales #2 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | TOB127 | TBG Kupa Kupa |  |  | TERNATE | 1.6284 | 127.9801 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 30-Aug-24 | Done | Done | 31-Aug-24 | Done | 100% | 30-Aug-24 | 31-Aug-24 | 31-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-01 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
919 | 2407-TRIAL-4G#RO-MDO024-0007 | #N/A | 4G TDD 2300 50MHz Massive Mimo +4G TDD 2300 20MHz + 5G TNR2.3 30MHz NSA | Add RRU and Module BBU | MDO024 | Mega Mas(Limbunan II) |  |  | MANADO | #N/A | #N/A | YPTT | July-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-07-10 | Done | Done |  | Done | 100% | 2024-07-10 | 2024-07-10 | 2024-07-11 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 28-Aug-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-6212 | 2025-04-09 |  | #N/A |  | Done Upload | Invoiced 100%
920 | 2407-UPBSC-4G#RO-TER036-0007 | CAPEX RAN 2 PART 3 2024 | Dismantle Controller BSC | Dismantle Controller BSC | SNN019 | TBG Sanana |  | Dismantle cable and power off after Rehoming BSC Sanana | TERNATE | 7878 | 1273828 | YPTT | 2026-11-24 |  | 2024 | 2024 | [29 empty] | No Need |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | [5 empty] | 03-Dec-24 | Done | Done | 2024-07-31 | Done | 100% | 03-Dec-24 | 03-Dec-24 | 03-Dec-24 | Connected | Connected |  | 03-NY SM | 03-NY SM | Passed | No Need |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 24-Dec-24 |  | PO NY Release |  |  | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload
921 | 2408-ADSTR-4G#RO-MLE033-0082 | CAPEX RAN 2 2024 Acceleration Support Part 5 for RGB Improvement | EQP Add Sector LTE 2300 4T4R | Add RRU | MLE033 | DMT Hotel Novotel Rantepao |  |  | PARE PARE | -2.9811 | 119.8961 | YPTT | August-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-09-06 | Done | Done | 2024-09-07 | Done | 100% | 2024-09-06 | 2024-09-07 | 2024-09-13 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-09-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-10 | 5-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
922 | 2408-BABSC-4G#RO-KKA022-0037 | CAPEX RAN 2 PART 3 2024 | EQP 2G Site Dismantle | Dismantle Module/Rack Controller | KKA022 | BSCZ_LASUSUA1 |  |  | KENDARI | -3.4755 | 120.8747 | YPTT | December-24 |  | 2024 | 2024 | [34 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 28-Dec-24 | Done | Done | 29-Dec-24 | Done | 100% | 28-Dec-24 | 29-Dec-24 | 29-Dec-24 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | No Need |  | No Need |  | Done Tagging | Done Tagging | [11 empty] | 2025-01-30 | 2025-01-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5797 | 2025-01-08 | 2025-02-06 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
923 | 2408-BABSC-4G#RO-MAM001-0050 | CAPEX RAN 2 PART 3 2024 | EQP 2G Site Dismantle | Dismantle Module/Rack Controller | MAM001 | BSCZ_MAMUJU1 |  |  | PARE PARE | -2.6821 | 118.8838 | YPTT | December-24 |  | 2024 | 2024 | [29 empty] | Og Request |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 19-Dec-24 | Done | Done | 19-Dec-24 | Done | 100% | 19-Dec-24 | 19-Dec-24 | 19-Dec-24 | Connected | Connected | Only Dismantle Rack | 03-NY SM | 01-Passed | SM Passed | 20-Dec-24 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-01-20 | 2025-01-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5774 | 2025-01-03 | 2025-01-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
924 | 2408-BABSC-4G#RO-RHA001-0039 | CAPEX RAN 2 PART 3 2024 | EQP 2G Site Dismantle | Dismantle Module/Rack Controller | RHA001 | BSCZ_MUNA1 |  | PR/PO release to YPTT (PO No : S1ID2023070102WBF1-5860) | KENDARI | -4.8428 | 122.7194 | YPTT | December-24 |  | 2024 | 2024 | [34 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 30-Dec-24 | Done | Done | 30-Dec-24 | Done | 100% | 30-Dec-24 | 31-Dec-24 | 31-Dec-24 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | No Need |  | No Need |  | Done Tagging | Done Tagging | [11 empty] | 2025-02-20 | 2025-02-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9523 | 2026-04-09 | 2025-02-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
925 | 2408-BARNC-4G#RO-MAM001-0069 | CAPEX RAN 2 PART 3 2024 | Dismantle Cabinet | Add RRU and Swap Module BBU | MAM001 | RNCZ_MAMUJU1 |  |  | PARE PARE | -301323 | 11885811 | YPTT | August-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 25-Aug-24 | Done | Done |  | Done | 100% | 25-Aug-24 | 25-Aug-24 | 25-Aug-24 | Connected | Connected | Dismantle Only Cabinet | 03-NY SM | 01-Passed | SM Passed | No Need |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-03-12 | 4-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5221 | 17-Oct-24 | 6-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
926 | 2408-TRIAL-4G#RO-TER028-0011 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add Antenna RRU (AAU) | TER028 | DMT Gambesi |  |  | TERNATE | 0.76005 | 127.3321 | YPTT | August-24 |  | 2024 | 2024 | [28 empty] | DMT | Done Req ZTE |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 22-Aug-24 | Done | Done | 23-Aug-24 | Done | 100% | 22-Aug-24 | 23-Aug-24 | 23-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-07 | 2025-07-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6242 | 2025-04-17 | 2025-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
927 | 2408-UMIMO-4G#RO-MLE033-0167 | CAPEX RAN 2 2024 Acceleration Support Part 5 for RGB Improvement | EQP Upgrade LTE 2300 Massive MIMO 64T64R | Swap RRU and Add Module BBU | MLE033 | DMT Hotel Novotel Rantepao |  |  | PARE PARE | -2.9811 | 119.8961 | YPTT | August-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-09-06 | Done | Done | 2024-09-07 | Done | 100% | 2024-09-06 | 2024-09-07 | 2024-09-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-14 |  | Done Tagging |  | Done Tagging | [12 empty] | 18-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
928 | 2408-UMIMO-4G#RO-MLE071-0169 | CAPEX RAN 2 2024 Acceleration Support Part 5 for RGB Improvement | EQP Upgrade LTE 1800 MIMO 4T4R | Swap RRU and Module BBU | MLE071 | TBG Swaya |  |  | PARE PARE | -3.0943 | 119.907 | YPTT | August-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 28-Aug-24 | Done | Done | 29-Aug-24 | Done | 100% | 28-Aug-24 | 29-Aug-24 | 29-Aug-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-01 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 18-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5088 | 2024-09-23 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
929 | 2408-UMIMO-4G#RO-MRW052-0172 | CAPEX RAN 2 2024 Acceleration Support Part 5 for RGB Improvement | EQP Upgrade LTE 2300 Massive MIMO 64T64R | Swap RRU | MRW052 | TBG Leulea |  |  | PALU | -2.7945 | 122.0989 | YPTT | August-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-09-02 | Done | Done | 2024-09-04 | Done | 100% | 2024-09-02 | 2024-09-04 | 2024-09-04 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-07 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 18-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 2024-11-08 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
930 | 2408-UMIMO-4G#RO-TDE015-0174 | CAPEX RAN 2 2024 Acceleration Support Part 5 for RGB Improvement | EQP Upgrade LTE 2300 Massive MIMO 64T64R | Add RRU and Module BBU | TDE015 | Protelindo Oba Utara |  |  | TERNATE | 0.72854 | 127.573 | YPTT | August-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-26 | Done | Done | 2024-09-26 | Done | 100% | 2024-09-26 | 2024-09-26 | 2024-09-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 5-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Oct-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
931 | 2409-4GGSM-4G#RO-TDE070-0674 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 900 10 MHz | Add RRU and Module BBU | TDE070 | TBG Ampera Sofifi |  |  | TERNATE | 0.71344 | 127.5679 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-15 | Done | Done | 2024-09-16 | Done | 100% | 2024-09-15 | 2024-09-16 | 2024-09-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 18-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
932 | 2409-ADSTR-4G#RO-BAU013-0084 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Add Sector LTE 2300 4T4R | Reconfigure RRU with add jumper for add sector | BAU013 | Lakudo-DMT |  | ALL CLOSE | KENDARI | -5.3127 | 122.53 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-09-11 | Done | Done | 2024-09-10 | Done | 100% | 2024-09-11 | 2024-09-11 | 2024-09-11 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-10 | 5-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 16-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
933 | 2409-ADSTR-4G#RO-BAU056-0085 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Add Sector LTE 2300 4T4R | Reconfigure RRU with add jumper for add sector | BAU056 | Matanauwe-DMT |  | ALL CLOSE | KENDARI | -5.4123 | 123.0122 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-09-09 | Done | Done | 2024-09-08 | Done | 100% | 2024-09-09 | 2024-09-09 | 2024-09-09 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Aug-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
934 | 2409-ADSTR-4G#RO-MAM157-0093 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Add Sector LTE 2300 4T4R | Reconfigure RRU with add jumper for add sector | MAM157 | GRAHA NUSA |  |  | PARE PARE | -2.6785 | 118.8661 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Edar | Done Productivity 100 % |  |  |  |  | 2024-09-07 | Done | Done | 2024-09-09 | Done | 100% | 2024-09-07 | 2024-09-08 | 2024-09-09 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-09-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
935 | 2409-ADSTR-4G#RO-MRW088-0103 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Module BBU | MRW088 | DMT Bahomohoni |  |  | PALU | -2.4671 | 121.9274 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-09-18 | Done | Done | 2024-09-18 | Done | 100% | 2024-09-18 | 2024-09-19 | 2024-09-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 19-Oct-24 |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 21-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 2024-11-08 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
936 | 2409-ADSTR-4G#RO-RHA085-0108 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Add Sector LTE 2300 4T4R | Reconfigure RRU with add jumper for add sector | RHA085 | MCP Bata Laiworu-PST |  | ALL CLOSE | KENDARI | -4.8236 | 122.7285 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-09-08 | Done | Done | 2024-09-08 | Done | 100% | 2024-09-08 | 2024-09-08 | 2024-09-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-17 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Aug-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
937 | 2409-ADSTR-4G#RO-SNN005-0110 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Add Sector LTE 2300 4T4R | Reconfigure RRU with add jumper for add sector and Add Module BBU | SNN005 | TBG Waihama |  |  | TERNATE | -2.0745 | 125.9744 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-09-25 | Done | Done | 2024-09-26 | Done | 100% | 2024-09-25 | 2024-09-25 | 2024-09-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 6-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Oct-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5221 | 17-Oct-24 | 2024-11-08 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
938 | 2409-ADSTR-4G#RO-SSU083-0112 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Add Sector LTE 2300 4T4R | Add RRU | SSU083 | DMT Rusunawa Weda |  |  | TERNATE | 0.32965 | 127.8597 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-09-22 | Done | Done | 2024-09-22 | Done | 100% | 2024-09-22 | 2024-09-22 | 2024-09-22 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 7-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Oct-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
939 | 2409-ADSTR-4G#RO-TDE045-0114 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Add Sector LTE 2300 4T4R | Add RRU | TDE045 | DMT MM Oba Utara Sofifi |  |  | TERNATE | 0.73769 | 127.5583 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-14 | Done | Done | 2024-09-14 | Done | 100% | 2024-09-14 | 2024-09-14 | 2024-09-14 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-16 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Aug-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 17-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
940 | 2409-ADSTR-4G#RO-THN045-0116 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Add Sector LTE 900 2T2R | Add RRU and Swap Module BBU | THN045 | DMT Lia |  |  | MANADO | 2.7708 | 125.456 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-09-14 | Done | Done | 2024-09-15 | Done | 100% | 2024-09-14 | 2024-09-15 | 2024-09-15 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-17 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 17-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 27-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
941 | 2409-NNE4G-4G#RO-ADL004-1121 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU and Module BBU | ADL004 | Lapulu Tinanggea-TBG |  | ALL CLOSE | KENDARI | -4.4787 | 122.2578 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2024-09-08 | Done | Done | 2024-09-08 | Done | 100% | 2024-09-08 | 2024-09-08 | 2024-09-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 04-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
942 | 2409-NNE4G-4G#RO-BAU011-1158 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | BAU011 | Kadolo Katapi-TBG |  | ALL CLOSE | KENDARI | -5.4662 | 122.6418 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2024-09-09 | Done | Done | 2024-09-08 | Done | 100% | 2024-09-09 | 2024-09-09 | 2024-09-09 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-10 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-02-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
943 | 2409-NNE4G-4G#RO-BAU218-1112 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | BAU218 | Desa Haka-TBG |  | ALL CLOSE | KENDARI | -6.0081 | 124.0471 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800 | 1 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2024-09-12 | Done | Done | 2024-09-13 | Done | 100% | 2024-09-12 | 2024-09-13 | 2024-09-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-14 |  | Done Tagging |  | Done Tagging | Done Tagging | Waiting Tag Asset Store | [10 empty] | 2024-11-21 | 2024-11-21 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
944 | 2409-NNE4G-4G#RO-BAU268-1143 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | BAU268 | Taipabu Binongko-TBG |  | NY ATP & NY Ineom | KENDARI | -5.9159 | 123.9793 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R8998 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 22-Oct-24 | Done | Done | 23-Oct-24 | Done | 100% | 22-Oct-24 | 23-Oct-24 | 23-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-11-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-04-11 | 2024-11-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5372 | 31-Oct-24 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
945 | 2409-NNE4G-4G#RO-COI015-1229 | CAPEX RAN 3 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | COI015 | IAAS Combat ONC Limonite |  |  | TERNATE | -1.5683 | 127.4259 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-09-27 | Done | Done | 2024-09-27 | Done | 100% | 2024-09-27 | 2024-09-27 | 2024-09-27 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 1-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 18-Oct-24 | 2024-11-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
946 | 2409-NNE4G-4G#RO-COI016-1161 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | COI016 | HARITASULAWESI3 |  |  | TERNATE | -1.5555 | 127.4443 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2024-09-11 | Done | Done | 2024-09-11 | Done | 100% | 2024-09-11 | 2024-09-11 | 2024-09-11 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 17-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
947 | 2409-NNE4G-4G#RO-COI036-1162 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | COI036 | SJU |  |  | TERNATE | -1.7326 | 124.4564 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 13-Oct-24 | Done | Done | 13-Oct-24 | Done | 100% | 13-Oct-24 | 13-Oct-24 | 13-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 13-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 25-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
948 | 2409-NNE4G-4G#RO-COI211-1116 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Module BBU | COI211 | Combat Arrow Lelilef Walibuan |  |  | TERNATE | 0.47918 | 127.985 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-09-12 | Done | Done | 2024-09-26 | Done | 100% | 2024-09-12 | 2024-09-25 | 2024-09-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 9-Dec-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-11-12 | 16-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
949 | 2409-NNE4G-4G#RO-COI213-1146 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | COI211 | Combat Bacan |  |  | TERNATE | -0.64239 | 127.4908 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-09-30 | Done | Done | 04-Oct-24 | Done | 100% | 2024-09-30 | 04-Oct-24 | 04-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 9-Oct-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-11-28 | 2024-11-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5221 | 17-Oct-24 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
950 | 2409-NNE4G-4G#RO-COI246-1145 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | COI246 | Combat MOP Burangasi Kontu |  | ALL CLOSE | KENDARI | -5.6733 | 122.7871 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R8978 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 18-Oct-24 | Done | Done | 19-Oct-24 | Done | 100% | 18-Oct-24 | 20-Oct-24 | 20-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 20-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 28-Oct-24 | 2024-11-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5285 | 24-Oct-24 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
951 | 2409-NNE4G-4G#RO-COI583-1199 | CAPEX RAN 3 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2300 50 Mhz | Swap RRU and Module BBU | COI583 | CombatMVSalumanurung |  |  | PARE PARE | -2.183546 | 119194677 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Andika | Done Productivity 100 % |  |  |  |  | 2024-09-13 | Done | Done | 2024-09-14 | Done | 100% | 2024-09-13 | 2024-09-14 | 2024-09-14 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-21 |  | Done Tagging |  | Done Tagging | [12 empty] | 22-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
952 | 2409-NNE4G-4G#RO-COI591-1164 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Swap RRU and Add Module BBU | COI591 | CombatMVDesaBahururu |  |  | PALU | -2.5179 | 121.9496 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-09-10 | Done | Done | 2024-09-10 | Done | 100% | 2024-09-10 | 2024-09-10 | 2024-09-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-09-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
953 | 2409-NNE4G-4G#RO-COI608-1204 | CAPEX RAN 3 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU and Swap Module BBU | COI608 | Combat Wahyu Fatufia |  |  | PALU | -2.7913 | 122.1225 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-09-15 | Done | Done | 03-Oct-24 | Done | 100% | 2024-09-15 | 2024-09-17 | 2024-09-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 16-Oct-24 |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 11-May-24 | 2024-11-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
954 | 2409-NNE4G-4G#RO-COI939-1114 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU and Swap Module BBU | COI939 | Combat CRU Langke Ereke |  | ALL CLOSE | KENDARI | -4.7662 | 123.1785 | YPTT | 2026-09-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | R9264E M1821 | 1 | 1 | 1 | 0 | VBpd2p(1) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),BFAN5(1),DCPD7(1),LPU(1),FA0(1),PM5(2),BPN2(2),CR0(2),CCE1B(1),SA(1) | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2024-09-09 | Done | Done | 2024-09-10 | Done | 100% | 2024-09-09 | 2024-09-10 | 2024-09-10 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-13 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 11-May-24 | 2024-11-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
955 | 2409-NNE4G-4G#RO-KDI027-1225 | CAPEX RAN 3 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | KDI027 | Tomia Permanent |  | ALL CLOSE | KENDARI | -5.7261 | 123.8992 | YPTT | 2026-09-24 |  | 2024 | 2024 |  | Upgrade CSU | MOBI 12 Port | 3 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBpd0p(1),VBpd2p(1) | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | TBXLHA 6 Port | 2 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),Cabinet(1),CCE1B(1),CR0(2),BPN2(3),PM5(2),SA(1),LPU(1),BFAN5(1),FA0(1),DCPD7(1),GPS(1) | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2024-09-20 | Done | Done | 2024-09-23 | Done | 100% | 2024-09-20 | 2024-09-21 | 2024-09-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 15-Oct-24 |  | Done Tagging |  | Done Tagging | Done Tagging | Waiting Permit | [10 empty] | 11-May-24 | 2024-11-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 12-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
956 | 2409-NNE4G-4G#RO-MAJ056-1208 | CAPEX RAN 3 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2100 20 Mhz | Swap Antenna and RRU and Module BBU | MAJ056 | ISATBababulo-DMT |  |  | PARE PARE | -3.5042 | 118.9096 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 09-Oct-24 | Done | Done | 11-Oct-24 | Done | 100% | 09-Oct-24 | 10-Oct-24 | 12-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 12-Oct-24 |  | Done Tagging |  | Done Tagging | [12 empty] | 2024-11-11 | 2024-11-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5241 | 19-Oct-24 | 2024-11-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
957 | 2409-NNE4G-4G#RO-MAM041-1124 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU | MAM041 | MAM041 |  |  | PARE PARE | -2.4698 | 119.1481 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Very | Done Productivity 100 % |  |  |  |  | 2024-09-12 | Done | Done | 2024-09-12 | Done | 100% | 2024-09-12 | 2024-09-12 | 2024-09-12 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-22 |  | Done Tagging |  | Done Tagging | [12 empty] | 15-Oct-24 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 2024-11-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
958 | 2409-NNE4G-4G#RO-MAM063-1148 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | MAM063 | MAM063 |  |  | PARE PARE | -2.6712 | 118.8925 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Andika | Done Productivity 100 % |  |  |  |  | 2024-09-15 | Done | Done | 2024-09-16 | Done | 100% | 2024-09-15 | 2024-09-16 | 2024-09-16 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-19 |  | Done Tagging |  | Done Tagging | [12 empty] | 23-Oct-24 | 25-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
959 | 2409-NNE4G-4G#RO-MAM087-1149 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Module BBU and Add RRU | MAM087 | MCR PANTAI MANAKARA |  |  | PARE PARE | -2.6711 | 118.8905 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Edar | Done Productivity 100 % |  |  |  |  | 2024-09-07 | Done | Done | 2024-09-07 | Done | 100% | 2024-09-07 | 2024-09-08 | 2024-09-08 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-11 |  | Done Tagging |  | Done Tagging | [12 empty] | 23-Oct-24 | 25-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
960 | 2409-NNE4G-4G#RO-MGN014-1210 | CAPEX RAN 3 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Module BBU | MGN014 | DMT Kiama |  |  | MANADO | 3.9999 | 126.7239 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Noris | Done Productivity 100 % |  |  |  |  | 2024-09-26 | Done | Done | 2024-09-29 | Done | 100% | 2024-09-26 | 2024-09-29 | 2024-09-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 8-Oct-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 15-Oct-24 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
961 | 2409-NNE4G-4G#RO-PSW001-1238 | CAPEX RAN 3 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | PSW001 | DMT MH Pasar Ambuau |  | ALL CLOSE | KENDARI | -5.3176 | 123.1687 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-09-19 | Done | Done | 2024-09-20 | Done | 100% | 2024-09-19 | 2024-09-20 | 2024-09-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-22 |  | Done Tagging |  | Done Tagging | No Need | Waiting Permit | [10 empty] | 28-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
962 | 2409-NNE4G-4G#RO-RHA062-1176 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | RHA062 | Wanseriwu-DMT |  | ALL CLOSE | KENDARI | -4.7936 | 122.3769 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-09-09 | Done | Done | 2024-09-08 | Done | 100% | 2024-09-09 | 2024-09-09 | 2024-09-09 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-15 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Aug-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
963 | 2409-NNE4G-4G#RO-RHA067-1239 | CAPEX RAN 3 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | RHA067 | DMT Wadolao Marobo |  | ALL CLOSE | KENDARI | -5.1009 | 122.3614 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2024-09-18 | Done | Done | 2024-09-18 | Done | 100% | 2024-09-18 | 2024-09-18 | 2024-09-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-19 |  | Done Tagging |  | Done Tagging | No Need | Waiting Permit | [10 empty] | 28-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 6-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
964 | 2409-NNE4G-4G#RO-SSU137-1177 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | SSU137 | TBG DPRD Halteng |  |  | TERNATE | 0.33208 | 127.8738 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-09-12 | Done | Done | 2024-09-12 | Done | 100% | 2024-09-12 | 2024-09-12 | 2024-09-12 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Oct-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
965 | 2409-NNE4G-4G#RO-TDE070-1178 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | TDE070 | TBG Ampera Sofifi |  |  | TERNATE | 0.71344 | 127.5679 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-15 | Done | Done | 2024-09-16 | Done | 100% | 2024-09-15 | 2024-09-20 | 2024-09-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
966 | 2409-NNE4G-4G#RO-TDE072-1133 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | TDE072 | TBG Akesai |  |  | TERNATE | 0.51538 | 127.5631 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-13 | Done | Done | 2024-09-13 | Done | 100% | 2024-09-13 | 2024-09-13 | 2024-09-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
967 | 2409-NNE4G-4G#RO-TDE073-1134 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | TDE073 | TBG Pasigau |  |  | TERNATE | 0.63604 | 127.5406 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-13 | Done | Done | 2024-09-13 | Done | 100% | 2024-09-13 | 2024-09-13 | 2024-09-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
968 | 2409-NNE4G-4G#RO-TDE075-1135 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | TDE075 | TBG Oba Utara |  |  | TERNATE | 0.71558 | 127.5542 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-13 | Done | Done | 2024-09-13 | Done | 100% | 2024-09-13 | 2024-09-13 | 2024-09-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Oct-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
969 | 2409-NNE4G-4G#RO-TDK002-1136 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2100 20 Mhz | Add Module BBU | TDK002 | DMT Sukamaju Karossa |  |  | PARE PARE | -1.8257 | 119.396 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Very | Done Productivity 100 % |  |  |  |  | 2024-09-07 | Done | Done | 2024-09-07 | Done | 100% | 2024-09-07 | 2024-09-07 | 2024-09-07 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-09-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-07-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
970 | 2409-NNE4G-4G#RO-TDK004-1221 | CAPEX RAN 3 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2300 50 Mhz | Add Module BBU | TDK004 | BojoBudong-TBG |  |  | PARE PARE | -2.1903 | 119.3056 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Very | Done Productivity 100 % |  |  |  |  | 2024-09-13 | Done | Done | 2024-09-13 | Done | 100% | 2024-09-13 | 2024-09-13 | 2024-09-13 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-09-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Aug-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5126 | 2024-09-27 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
971 | 2409-NNE4G-4G#RO-TDK007-1244 | CAPEX RAN 3 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | TDK007 | BatuParigi-DMT |  |  | PARE PARE | -2.0603 | 119.4366 | YPTT | 2026-09-24 |  | 2024 | 2024 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Very | Done Productivity 100 % |  |  |  |  | 2024-11-05 | Done | Done | 2024-11-10 | Done | 100% | 2024-11-05 | 2024-11-06 | 2025-01-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-11-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-02 | 2025-02-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5428 | 2024-11-14 | 2025-02-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
972 | 2409-NNE4G-4G#RO-TER125-1247 | CAPEX RAN 3 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2300 50 MHz | Swap Antenna and Module BBU and Add RRU | TER125 | DMT MCP Jambula |  |  | TERNATE | 0.75542 | 127.3221 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-27 | Done | Done | 2024-11-10 | Done | 100% | 2024-09-27 | 2024-11-10 | 2024-11-10 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-11-16 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-11-28 | 2024-11-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
973 | 2409-NNE4G-4G#RO-THN012-1155 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | THN012 | Mahuneni |  |  | MANADO | 2.6551 | 125.3771 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-09-08 | Done | Done | 2024-09-08 | Done | 100% | 2024-09-08 | 2024-09-09 | 2024-09-09 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-11 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 15-Oct-24 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
974 | 2409-NNE4G-4G#RO-THN020-1181 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | THN020 | TBG Perkantoran Tahuna |  |  | MANADO | 3.6048 | 125.5108 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-09-24 | Done | Done | 2024-09-24 | Done | 100% | 2024-09-24 | 2024-09-24 | 2024-09-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-09-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Oct-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2024-11-08 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
975 | 2409-NNE4G-4G#RO-THN080-1156 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | THN080 | Anugerah Mulengen |  |  | MANADO | 2.368 | 125.4123 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-09-20 | Done | Done | 2024-09-20 | Done | 100% | 2024-09-20 | 2024-09-20 | 2024-09-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-21 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-11-22 | 17-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
976 | 2409-NNE4G-4G#RO-TTY003-1248 | CAPEX RAN 3 2024 Acceleration Support Part 2 | EQP New NE 4G LTE 2300 50 MhzMacro-2_3 | Add Module BBU | WTG057 | AbbanuangeLilirilau-DMT |  |  | MAKASSAR | -4.3672 | 120.0662 | YPTT | December-24 |  | 2024 | 2024 | [34 empty] | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 09-Dec-24 | Done | Done | 09-Dec-24 | Done | 100% | 09-Dec-24 | 09-Dec-24 | 09-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | NO NEED | 11-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 18-Dec-24 | 24-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5761 | 2025-01-01 | 2025-02-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
977 | 2409-NNE4G-4G#RO-WGI002-1182 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | WGI002 | TBG Numana |  | NY Ineom | KENDARI | -535628 | 1235562 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2024-09-10 | Done | Done | 2024-09-10 | Done | 100% | 2024-09-10 | 2024-09-10 | 2024-09-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 16-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 23-Oct-24 | 25-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 2024-11-08 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
978 | 2409-UMIMO-4G#RO-BAU066-0176 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU and Module BBU | BAU066 | Gu-PTI |  | ALL CLOSE | KENDARI | -5.2552 | 122.5767 | YPTT | 2026-09-24 |  | 2024 | 2024 |  | Upgrade CSU | No Need Antena | 0 | 0 | A9631A S23 | 1 | 1 | 1 | 0 | VBpd0p(1),VBpd2p(1),VBpd2(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8978 S2300 | 1 | BBU(1),Cabinet(1),PM5(2),SA(1),BPN(3),UBPG(1),CR0(2),CCE1B(2),FA0(1),BFAN5(1),LPU(1),DCPD7(1) | [6 empty] | CV. Puri Tepule Abadi | Laode Salni | Done Productivity 100 % |  |  |  |  | 2024-09-29 | Done | Done | 2024-09-30 | Done | 100% | 2024-09-29 | 2024-09-30 | 2024-09-30 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 08-Oct-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 22-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
979 | 2409-UMIMO-4G#RO-LBA021-0179 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU | LBA021 | Jikotamo |  |  | TERNATE | -1.345 | 127.6566 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 13-Oct-24 | Done | Done | 14-Oct-24 | Done | 100% | 13-Oct-24 | 14-Oct-24 | 14-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 15-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 28-Oct-24 | 31-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5277 | 24-Oct-24 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
980 | 2409-UMIMO-4G#RO-LBA032-0180 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU and Module BBU | LBA032 | DMT Sayoang Bacan |  |  | TERNATE | -2.6445 | 121.3629 | YPTT | 2026-09-24 |  | 2024 | 2024 | [28 empty] | DMT | Release |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2025-04-18 | Done | Done | 2025-04-20 | Done | 100% | 2025-04-20 | 2025-04-20 | 2025-04-20 | Connected | Connected |  | 01-Passed | 01-Passed | No need | 2024-09-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 18-Oct-24 | 2024-11-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2025-06-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
981 | 2409-UMIMO-4G#RO-LBA046-0181 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU and Swap Module BBU | LBA046 | TBG Labuha |  |  | TERNATE | -0.63222 | 127.4814 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-09-28 | Done | Done | 2024-09-29 | Done | 100% | 2024-09-28 | 2024-09-29 | 2024-09-29 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 11-Oct-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 15-Oct-24 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
982 | 2409-UMIMO-4G#RO-MAM157-0183 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU and Swap Module BBU | MAM157 | GRAHA NUSA |  |  | PARE PARE | -2.6785 | 118.8661 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Edar | Done Productivity 100 % |  |  |  |  | 2024-09-07 | Done | Done | 2024-09-07 | Done | 100% | 2024-09-07 | 2024-09-07 | 2024-09-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-11 |  | Done Tagging |  | Done Tagging | [12 empty] | 17-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 25-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
983 | 2409-UMIMO-4G#RO-MAM191-0184 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU and Add Module BBU | MAM191 | MAM191 |  |  | PARE PARE | -2.0773 | 119.2915 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Iswanto | Done Productivity 100 % |  |  |  |  | 2024-09-20 | Done | Done | 2024-09-20 | Done | 100% | 2024-09-20 | 2024-09-20 | 2024-09-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-21 |  | Done Tagging |  | Done Tagging | Pending Tagg Dismentel | [11 empty] | 18-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5194 | 10-Oct-24 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
984 | 2409-UMIMO-4G#RO-MLI002-0196 | CAPEX RAN 3 2024 Acceleration Support Part 1 | Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU and Module BBU | SSU133 | Trans Lelilef |  | Take over dismantle & closing ATP to YPTT d/t CCSI no team | TERNATE | 0.47054 | 127.9109 | YPTT | July-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  | 3098411 | 2026-01-17 | Done | 2026-01-18 | 2026-01-20 | Done | 100% | 2026-01-18 | 2026-01-20 | 2026-01-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 2025-06-18 | 18 June 2025 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9550 | 2026-04-13 | 2025-09-15 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Workoad 100%
985 | 2409-UMIMO-4G#RO-MRW002-0201 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap Antenna and Add RRU and Module BBU | MRW002 | Bungku |  |  | PALU | -2.5461 | 121.97 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Yafril | Done Productivity 100 % |  |  |  |  | 2024-09-29 | Done | Done | 01-Oct-24 | Done | 100% | 2024-09-29 | 2024-09-30 | 2024-09-30 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 14-Oct-24 |  | Done Tagging |  | Done Tagging | Pending tagg dismantle | [11 empty] | 2024-04-11 | 2024-11-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5196 | 10-Oct-24 | 2024-11-08 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
986 | 2409-UMIMO-4G#RO-PAL165-0209 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU and Swap Module BBU | PAL165 | DMT Palu Timur |  |  | PALU | -0.89495 | 119.876 | YPTT | 2026-09-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Andika | Done Productivity 100 % |  |  |  |  | 2024-09-29 | Done | Done | 2024-09-26 | Done | 100% | 2024-09-29 | 2024-09-30 | 2024-09-30 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-27 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 18-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5196 | 10-Oct-24 | 2024-11-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
987 | 2409-UMIMO-4G#RO-RHA060-0211 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU | RHA060 | Talaga Kecil-PTI |  | ALL CLOSE | KENDARI | -5.4744 | 122.0753 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 1 | A9631A S23 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8978 S2300 | 1 | No Need Board | [6 empty] | YPTT | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 06-Oct-24 | Done | Done | 06-Oct-24 | Done | 100% | 06-Oct-24 | 06-Oct-24 | 06-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 10-Oct-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-11-28 | 2024-11-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5221 | 17-Oct-24 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
988 | 2409-UMIMO-4G#RO-RHA060-0212 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU and Add Module BBU | RHA060 | Talaga Kecil-PTI |  | ALL CLOSE | KENDARI | -5.4744 | 122.0753 | YPTT | 2026-09-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 1 | A9631A S23 | 1 | 0 | 0 | 0 | VBpd0p(1_ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8978 S2300 | 1 | No Need Board | [6 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 06-Oct-24 | Done | Done | 06-Oct-24 | Done | 100% | 06-Oct-24 | 06-Oct-24 | 06-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 10-Oct-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2024-11-28 | 2024-11-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5221 | 17-Oct-24 | 13-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
989 | 2409-UMIMO-4G#RO-SNN004-0213 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU and Module BBU | SNN004 | Bobong |  |  | TERNATE | -1.9495 | 124.3918 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 18-Oct-24 | Done | Done | 19-Oct-24 | Done | 100% | 18-Oct-24 | 19-Oct-24 | 19-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 21-Oct-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 11-May-24 | 2024-11-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5285 | 24-Oct-24 | 27-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
990 | 2409-UMIMO-4G#RO-SNN005-0214 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU | SNN005 | TBG Waihama |  |  | TERNATE | -2.0745 | 125.9744 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-09-26 | Done | Done | 2024-09-25 | Done | 100% | 2024-09-26 | 2024-09-26 | 2024-09-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 6-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Oct-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5196 | 10-Oct-24 | 2024-11-08 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
991 | 2409-UMIMO-4G#RO-SNN008-0215 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU and Add Module BBU | SNN008 | Sanana 2 |  |  | TERNATE | -2.0561 | 125.9764 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-09-24 | Done | Done | 2024-09-24 | Done | 100% | 2024-09-24 | 2024-09-24 | 2024-09-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-09-30 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 17-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5196 | 10-Oct-24 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
992 | 2409-UMIMO-4G#RO-SNN020-0216 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU and Module BBU | SNN020 | DMT Sanana |  |  | TERNATE | -2.0702 | 125.9779 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-09-27 | Done | Done | 2024-09-28 | Done | 100% | 2024-09-27 | 2024-09-28 | 2024-09-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 5-Oct-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 17-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5196 | 10-Oct-24 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
993 | 2409-UMIMO-4G#RO-SNN020-0217 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU | SNN020 | DMT Sanana |  |  | TERNATE | -2.0702 | 125.9779 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-09-27 | Done | Done | 2024-09-28 | Done | 100% | 2024-09-27 | 2024-09-28 | 2024-09-28 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 5-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Oct-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5196 | 10-Oct-24 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
994 | 2409-UMIMO-4G#RO-SSU082-0224 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU | SSU082 | TBG Lelilef |  |  | TERNATE | 0.46647 | 127.9296 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-09-21 | Done | Done | 2024-09-21 | Done | 100% | 2024-09-21 | 2024-09-21 | 2024-09-21 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 6-Oct-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-11-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5196 | 10-Oct-24 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
995 | 2409-UMIMO-4G#RO-SSU089-0225 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU and Module BBU | SSU089 | TBG NEW SPLIT RELIEF |  |  | TERNATE | 0.47023 | 127.9354 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-09-21 | Done | Done | 2024-09-21 | Done | 100% | 2024-09-21 | 2024-09-21 | 2024-09-21 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 7-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-Oct-24 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5196 | 10-Oct-24 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
996 | 2409-UMIMO-4G#RO-SSU109-0226 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU | SSU109 | TBG Lelilef Lokulamo |  |  | TERNATE | 0.47317 | 127.8898 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Agus | Done Productivity 100 % |  |  |  |  | 2024-09-20 | Done | Done | 2024-09-24 | Done | 100% | 2024-09-20 | 2024-09-20 | 2024-09-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 7-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-11-10 | 11-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5196 | 10-Oct-24 | 2024-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
997 | 2409-UMIMO-4G#RO-TDE003-0227 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU and Swap Module BBU | TDE003 | Gurabati |  |  | TERNATE | 0.62706 | 127.4205 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-09 | Done | Done | 2024-09-09 | Done | 100% | 2024-09-09 | 2024-09-09 | 2024-09-09 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2024-09-12 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 15-Oct-24 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5127 | 2024-09-27 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
998 | 2409-UMIMO-4G#RO-TDE041-0230 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU and Add Module BBU | TDE041 | STP Gosalaha |  |  | TERNATE | 0.68375 | 127.4533 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-30 | Done | Done | 2024-09-30 | Done | 100% | 2024-09-30 | 2024-09-30 | 2024-09-30 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 1-Oct-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 15-Oct-24 | 16-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5196 | 10-Oct-24 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
999 | 2409-UMIMO-4G#RO-TDE043-0231 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU and Swap Module BBU | TDE043 | STP Tomalau |  |  | TERNATE | 0.62355 | 127.4012 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 01-Oct-24 | Done | Done | 02-Oct-24 | Done | 100% | 01-Oct-24 | 01-Oct-24 | 01-Oct-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2-Oct-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-11-28 | 2024-11-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5221 | 17-Oct-24 | 6-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1000 | 2409-UMIMO-4G#RO-TER077-0232 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU and Swap Module BBU | TER077 | TBG RSUD Ternate |  |  | TERNATE | 0.78307 | 127.3717 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Sulaiman | Done Productivity 100 % |  |  |  |  | 2024-09-20 | Done | Done | 2024-09-27 | Done | 100% | 2024-09-20 | 2024-09-27 | 2024-09-27 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 24-Oct-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 21-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5196 | 10-Oct-24 | 27-Oct-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1001 | 2409-UMIMO-4G#RO-TER083-0233 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU | TER083 | Protelindo Gambesi Kota |  |  | TERNATE | 0.75791 | 127.3406 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2024-09-28 | Done | Done | 2024-09-28 | Done | 100% | 2024-09-28 | 2024-09-28 | 2024-09-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 03-Oct-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 17-Oct-24 | 23-Oct-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5196 | 10-Oct-24 | 2024-11-05 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1002 | 2409-UMIMO-4G#RO-THN056-0234 | CAPEX RAN 3 2024 Acceleration Support Part 1 | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU and Add Module BBU | THN056 | TBG Pelabuhan Sangir |  |  | MANADO | 3.6048 | 125.5071 | YPTT | 2026-09-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-09-22 | Done | Done | 2024-09-22 | Done | 100% | 2024-09-22 | 2024-09-22 | 2024-09-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-09-26 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-04-11 | 2024-11-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5221 | 17-Oct-24 | 2024-11-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1003 | 2410-4GDCS-4G#RO-NTI105-0372 | CAPEX RAN 4 2024 Acceleration Support Part 1 | L1800 New 4G | Add RRU | NTI105 | N3T RAE SELATAN |  |  | MANADO | 4.2836 | 126.7198 | YPTT | October-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-11-11 | Done | Done | 2024-11-12 | Done | 100% | 2024-11-11 | 2024-11-12 | 2024-11-12 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-11-16 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-11-12 | 15-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5465 | 2024-11-21 | 2025-02-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1004 | 2410-4GGSM-4G#RO-KDI030-0686 | CAPEX RAN 4 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 900 10 Mhz | Add RRU | KDI030 | TBG Kampung Bakau-Permanenisasi COI459 |  | ALL CLOSE | KENDARI | -3.9844 | 122.5353 | YPTT | 2026-11-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-11-06 | Done | Done | 2024-11-06 | Done | 100% | 2024-11-06 | 2024-11-06 | 2024-11-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-11-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 12-Oct-24 | 11-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5419 | 2024-11-08 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1005 | 2410-4T4R-4G#RO-MDO367-0033 | CAPEX RAN 4 2024 Acceleration Support Part 1 | L1800 Capacity Upgrade 4G | Swap RRU | MDO367 | MC FEKON UNSRAT |  |  | MANADO | 1.4596 | 124.8263 | YPTT | October-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Nopik | Done Productivity 100 % |  |  |  |  | 2024-11-06 | Done | Done | 2024-11-06 | Done | 100% | 2024-11-06 | 2024-11-06 | 2024-11-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-11-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 17-May-25 | 17-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5420 | 2024-11-11 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1006 | 2410-ADSTR-4G#RO-SSU035-0121 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP Add Sector LTE 2100 2T2R | Swap RRU | SSU035 | IWIP Apartemen |  |  | TERNATE | 0.4816 | 128.0118 | YPTT | 2026-11-24 |  | 2024 | 2024 | [28 empty] | IWIP | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-24 | Done | Done | 2025-01-31 | Done | 100% | 2025-01-24 | 2025-02-01 | 2025-02-01 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-22 | 2025-04-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5908 | 2025-02-05 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1007 | 2410-NNE4G-4G#913-MLE051-1258 | CAPEX RAN 3 PART 1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | SRI003 | TBG Parura Jaya |  | ALL CLOSE | KENDARI | -4.8522 | 122.4086 | YPTT | December-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 12-Dec-24 | Done | Done | 12-Dec-24 | Done | 100% | 12-Dec-24 | 12-Dec-24 | 12-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 13-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 23-Dec-24 | 2025-01-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5721 | 24-Dec-24 | 2025-02-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1008 | 2410-NNE4G-4G#913-SNN019-1253 | CAPEX RAN 3 PART 1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | SNN019 | TBG Sanana |  |  | TERNATE | -2.065 | 125.9804 | YPTT | October-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 01-Dec-24 | Done | Done | 01-Dec-24 | Done | 100% | 01-Dec-24 | 01-Dec-24 | 01-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 3-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-03-12 | 15-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5406 | 2024-11-06 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1009 | 2410-NNE4G-4G#913-SSU027-1254 | CAPEX RAN 3 PART 1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | BAU219 | Todanga-DMT |  | ALL CLOSE | KENDARI | -5108815 | 122791581 | YPTT | December-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBPd0p(1) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-02-09 | Done | Done | 2025-02-10 | Done | 100% | 2025-02-09 | 2025-02-10 | 2025-02-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-02-27 | 2025-03-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6047 | 2025-02-25 | 2025-03-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1010 | 2410-NNE4G-4G#913-SSU045-1255 | CAPEX RAN 3 PART 1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | LBA067 | DMT Laluin |  |  | TERNATE | -0.040446 | 127.4263 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-03-15 | Done | Done | 2025-03-17 | Done | 100% | 2025-03-15 | 2025-03-15 | 2025-03-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-16 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-09 | 2025-04-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6241 | 2025-04-17 | 2025-06-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1011 | 2410-NNE4G-4G#913-SSU108-1256 | CAPEX RAN 3 PART 1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU | JLO011 | Desa Cempaka |  |  | TERNATE | 1.167 | 127.4959 | YPTT | December-24 |  | 2024 | 2024 | [29 empty] | Done Req ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 12-Dec-24 | Done | Done | 12-Dec-24 | Done | 100% | 12-Dec-24 | 12-Dec-24 | 12-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 13-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 18-Dec-24 | 2025-01-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5721 | 24-Dec-24 | 2025-02-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1012 | 2410-NNE4G-4G#913-THN049-1257 | CAPEX RAN 3 PART 1 2024 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | THN049 | PROTELINDO TANAKI |  |  | MANADO | 2.6362 | 125.4049 | YPTT | October-24 |  | 2024 | 2024 | [29 empty] | Release |  |  |  |  | YPTT | Vendi | Done Productivity 100 % |  |  |  |  | 2024-11-23 | Done | Done | 2024-11-24 | Done | 100% | 2024-11-23 | 2024-11-24 | 2024-11-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 3-Dec-24 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 12-Oct-24 | 11-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5497 | 2024-11-27 | 27-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1013 | 2410-NNE4G-4G#RO-COI769-1261 | CAPEX RAN 4 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | COI769 | Combat MOP Sampuabalo Ambuau Indah |  | ALL CLOSE | KENDARI | -5.434 | 123.0121 | YPTT | 2026-11-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-11-13 | Done | Done | 2024-11-13 | Done | 100% | 2024-11-13 | 2024-11-13 | 2024-11-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-11-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-11-12 | 11-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5465 | 2024-11-21 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1014 | 2410-NNE4G-4G#RO-KDI350-1264 | CAPEX RAN 4 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | KDI350 | BTN Dewi Bunga |  | ALL CLOSE | KENDARI | -4.0317 | 122.5566 | YPTT | 2026-11-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-11-21 | Done | Done | 2024-11-21 | Done | 100% | 2024-11-21 | 2024-11-21 | 2024-11-21 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-11-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 12-Dec-24 | 16-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5514 | 2024-11-29 | 18-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1015 | 2410-NNE4G-4G#RO-SNN055-1270 | CAPEX RAN 4 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 MHz | Add RRU and Swap Module BBU | SNN055 | MERANTIJAYA_TBG |  |  | TERNATE | -1.9037 | 124.3441 | YPTT | October-24 |  | 2024 | 2024 | [28 empty] | TBG | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-02-22 | Done | Done | 2025-02-23 | Done | 100% | 2025-02-22 | 2025-02-23 | 2025-02-23 | Connected | Connected |  | 03-NY SM | 01-Passed | Passed | 2025-02-19 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-15 | 2025-04-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6094 | 2025-03-06 | 16-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1016 | 2410-NNE4G-4G#RO-SRI001-1273 | CAPEX RAN 4 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | SRI001 | Bakaremba Muna |  | ALL CLOSE | KENDARI | -4.7279 | 122.5292 | YPTT | 2026-11-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | [6 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2024-11-12 | Done | Done | 2024-11-12 | Done | 100% | 2024-11-12 | 2024-11-12 | 2024-11-12 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2024-11-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 12-Oct-24 | 11-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5465 | 2024-11-21 | 2025-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1017 | 2410-NNE4G-4G#RO-TDK004-1275 | CAPEX RAN 4 2024 Acceleration Support Part 1 | EQP New NE 4G LTE 2300 50 MhzMacro-2_3 | Add RRU and Module BBU | TDK004 | N_TDK004M41_BojoBudong-TBG |  |  | PARE PARE | -2.1903 | 119.3056 | YPTT | October-24 |  | 2024 | 2024 | [34 empty] | PT. Djaya Sukses Pratama | Aswin | Done Productivity 100 % |  |  |  |  | 2024-11-02 | Done | Done | 2024-11-04 | Done | 100% | 2024-11-02 | 2024-11-03 | 2024-11-04 | Connected | Connected |  | 01-Passed | 01-Passed | NO NEED | 2024-11-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2024-11-12 | 11-Dec-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5406 | 2024-11-06 | 26-Dec-24 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1018 | 2411-4GGSM-4G#320-SSU101-0699 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port+Mounting Antenna | SSU101 | IAAS Hauling Road IWIP BL North | L900 |  | TERNATE | 127976037 | 0.54336 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Candra A Putra | Need change paper application to paperless |  |  |  | 13277883.28 | 08-May-26 | Done | 08-May-26 | 16-May-26 | Done | 100% | 08-May-26 | 16-May-26 | 16-May-26 | Connected | Connected |  | Progress | 01-Passed | No need | passed | May-26 | Done Tagging | May-26 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [8 empty] | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9744 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1019 | 2411-NNE4G-4G#RO-KDI008-1315 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | KDI008 | Wanci |  | NY ATP & Ineom | KENDARI | -5.3267 | 123.5414 | YPTT | December-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 1 | A9631A S23 | 1 | 0 | 0 | 0 | VBpd2(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 13-Dec-24 | Done | Done | 14-Dec-24 | Done | 100% | 13-Dec-24 | 14-Dec-24 | 14-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 17-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-02-27 | 2025-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5722 | 24-Dec-24 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1020 | 2411-NNE4G-4G#RO-SSU035-1282 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Swap RRU and Antenna Add Module BBU and Modernize RRU | SSU035 | IWIP Apartemen |  |  | TERNATE | 0.4816 | 128.0118 | YPTT | 2026-11-24 |  | 2024 | 2024 | [28 empty] | IWIP | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-24 | Done | Done | 2025-01-28 | Done | 100% | 2025-01-24 | 2024-01-28 | 2025-01-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-22 | 2025-04-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5908 | 2025-02-05 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1021 | 2411-NNE4G-4G#RO-SSU036-1283 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Swap RRU and Antenna and Modernize RRU | SSU036 | IWIP Triangle Smelter |  |  | TERNATE | 0.4818 | 127.9953 | YPTT | 2026-11-24 |  | 2024 | 2024 | [28 empty] | IWIP | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-10 | Done | Done | 2025-01-12 | Done | 100% | 2025-01-10 | 2025-01-13 | 2025-01-13 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-18 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-22 | 2025-04-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5857 | 2025-01-19 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1022 | 2411-NNE4G-4G#RO-SSU036-1284 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Swap RRU | SSU036 | IWIP Triangle Smelter |  |  | TERNATE | 0.4818 | 127.9953 | YPTT | 2026-11-24 |  | 2024 | 2024 | [28 empty] | IWIP | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-10 | Done | Done | 2025-01-13 | Done | 100% | 2025-01-10 | 2025-01-13 | 2025-01-13 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-18 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-02-19 | 2025-02-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5857 | 2025-01-19 | 2025-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1023 | 2411-NNE4G-4G#RO-SSU070-1288 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Swap RRU | SSU070 | New Office 4 IWIP |  |  | TERNATE | 0.48196 | 128.0007 | YPTT | 2026-11-24 |  | 2024 | 2024 | [28 empty] | IWIP | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-17 | Done | Done | 2025-01-19 | Done | 100% | 2025-01-17 | 2025-01-20 | 2025-01-20 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-01-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-23 | 2025-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5869 | 2025-01-23 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1024 | 2411-NNE4G-4G#RO-SSU070-1289 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU | SSU070 | New Office 4 IWIP |  |  | TERNATE | 0.48196 | 128.0007 | YPTT | 2026-11-24 |  | 2024 | 2024 | [28 empty] | IWIP | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-17 | Done | Done | 2025-01-19 | Done | 100% | 2025-01-17 | 2025-01-19 | 2025-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-01-31 | 2025-02-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5869 | 2025-01-23 | 2025-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1025 | 2411-NNE4G-4G#RO-SSU070-1290 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU | SSU070 | New Office 4 IWIP |  |  | TERNATE | 0.48196 | 128.0007 | YPTT | 2026-11-24 |  | 2024 | 2024 | [28 empty] | IWIP | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-17 | Done | Done | 2025-01-19 | Done | 100% | 2025-01-17 | 2025-01-19 | 2025-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-01-31 | 2025-02-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5869 | 2025-01-23 | 2025-02-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1026 | 2411-NNE4G-4G#RO-SSU073-1291 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Swap RRU and Antenna and Modernize RRU | SSU073 | Tambang Baru IWIP |  |  | TERNATE | 0.47635 | 127.9436 | YPTT | 2026-11-24 |  | 2024 | 2024 | [29 empty] | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 12-Dec-24 | Done | Done | 19-Dec-24 | Done | 100% | 12-Dec-24 | 17-Dec-24 | 17-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-02-13 | 2025-02-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5722 | 24-Dec-24 | 2025-02-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1027 | 2411-NNE4G-4G#RO-SSU113-1296 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU | SSU113 | Klinik IWIP |  |  | TERNATE | 0.48362 | 127.9754 | YPTT | 2026-11-24 |  | 2024 | 2024 | [28 empty] | CORPORATE (IMIP) | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-08 | Done | Done | 2025-01-08 | Done | 100% | 2025-01-08 | 2025-01-08 | 2025-01-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-01-14 | 2025-01-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5841 | 2025-01-17 | 28-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1028 | 2411-NNE4G-4G#RO-SSU116-1297 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU | SSU116 | Airport IWIP |  |  | TERNATE | 0.47026 | 127.9561 | YPTT | December-24 |  | 2024 | 2024 | [29 empty] | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 26-Dec-24 | Done | Done | 26-Dec-24 | Done | 100% | 26-Dec-24 | 27-Dec-24 | 27-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 28-Dec-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-02-17 | 2025-02-19 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5774 | 2025-01-03 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1029 | 2411-NNE4G-4G#RO-SSU116-1298 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Swap RRU | SSU116 | Airport IWIP |  |  | TERNATE | 0.47026 | 127.9561 | YPTT | December-24 |  | 2024 | 2024 | [29 empty] | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 26-Dec-24 | Done | Done | 26-Dec-24 | Done | 100% | 26-Dec-24 | 27-Dec-24 | 27-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 28-Dec-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 03-Oct-25 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5774 | 2025-01-03 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1030 | 2411-NNE4G-4G#RO-SSU121-1303 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | SSU121 | IWIP Blok P |  |  | TERNATE | 0.478 | 127.9892 | YPTT | 2026-11-24 |  | 2024 | 2024 | [28 empty] | IWIP | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-02 | Done | Done | 2025-01-02 | Done | 100% | 2025-01-02 | 2025-01-02 | 2025-01-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-01-14 | 2025-01-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5797 | 2025-01-08 | 28-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1031 | 2411-NNE4G-4G#RO-SSU128-1305 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU | SSU128 | IWIP HF3 |  |  | TERNATE | 0.47091 | 127.9518 | YPTT | 2026-11-24 |  | 2024 | 2024 | [29 empty] | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 21-Dec-24 | Done | Done | 21-Dec-24 | Done | 100% | 21-Dec-24 | 21-Dec-24 | 21-Dec-24 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2025-02-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 02-Oct-25 | 2025-02-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5722 | 24-Dec-24 | 2025-02-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1032 | 2411-NNE4G-4G#RO-SSU144-1308 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | SSU144 | IWIP Industri 2 |  |  | TERNATE | 0.48565 | 127.9878 | YPTT | 2026-11-24 |  | 2024 | 2024 | [28 empty] | CORPORATE | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-02-05 | Done | Done | 2025-02-05 | Done | 100% | 2025-02-05 | 2025-02-05 | 2025-02-05 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need | [11 empty] | 2025-03-19 | 2025-03-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5908 | 2025-02-05 | 16-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1033 | 2411-NNE4G-4G#RO-SSU146-1312 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU and Module BBU | SSU146 | IWIP Industri 4 |  |  | TERNATE | 0.48978 | 127.9731 | YPTT | 2026-11-24 |  | 2024 | 2024 | [28 empty] | CORPORATE | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 29-Dec-24 | Done | Done | 2025-01-02 | Done | 100% | 2025-01-02 | 2025-01-02 | 2025-01-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 29-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-19 | 2025-03-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5796 | 2025-01-08 | 2025-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1034 | 2411-NNE4G-4G#RO-SSU146-1313 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU | SSU146 | IWIP Industri 4 |  |  | TERNATE | 0.48978 | 127.9731 | YPTT | 2026-11-24 |  | 2024 | 2024 | [28 empty] | CORPORATE | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 29-Dec-24 | Done | Done | 2025-01-02 | Done | 100% | 2025-01-02 | 2025-01-02 | 2025-01-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 29-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-02-26 | 2025-03-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5796 | 2025-01-08 | 2025-03-08 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1035 | 2411-NNE4G-4G#RO-SSU146-1314 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU | SSU146 | IWIP Industri 4 |  |  | TERNATE | 0.48978 | 127.9731 | YPTT | 2026-11-24 |  | 2024 | 2024 | [28 empty] | CORPORATE | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 29-Dec-24 | Done | Done | 2025-01-02 | Done | 100% | 2025-01-02 | 2025-01-02 | 2025-01-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 29-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-02-26 | 2025-02-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5796 | 2025-01-08 | 2025-03-09 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1036 | 2411-NNE4G-4G#RO-TER064-1317 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Swap RRU and Module BBU | TER064 | TernateTengah-DMT |  |  | TERNATE | 0.79466 | 127.3886 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 21-Dec-24 | Done | Done | 22-Dec-24 | Done | 100% | 21-Dec-24 | 22-Dec-24 | 22-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-01-03 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-03 | 2025-03-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5774 | 2025-01-03 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1037 | 2411-NNE4G-4G#RO-TER064-1318 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 64T64R | Add RRU | TER064 | TernateTengah-DMT |  |  | TERNATE | 0.79466 | 127.3886 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 21-Dec-24 | Done | Done | 22-Dec-24 | Done | 100% | 21-Dec-24 | 22-Dec-24 | 22-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5774 | 2025-01-03 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1038 | 2411-ReANT-4G#RO-SSU073-0004 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP Antenna Refinement | Add Insmat | SSU073 | Tambang Baru IWIP |  |  | TERNATE | 0.47635 | 127.9436 | YPTT | 2026-11-24 |  | 2024 | 2024 | [29 empty] | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 12-Dec-24 | Done | Done | 19-Dec-24 | Done | 100% | 12-Dec-24 | 19-Dec-24 | 19-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-11 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 02-Dec-25 | 2025-02-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5722 | 24-Dec-24 | 2025-02-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1039 | 2411-ReANT-4G#RO-SSU103-0005 | CAPEX RAN SUPPORT IWIP EXPANSION 2024 | EQP Antenna Refinement | Add Insmat | SSU103 | HF1 |  |  | TERNATE | 0.4711 | 127.9444 | YPTT | 2026-11-24 |  | 2024 | 2024 | [29 empty] | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 23-Dec-24 | Done | Done | 24-Dec-24 | Done | 100% | 23-Dec-24 | 24-Dec-24 | 24-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 23-Dec-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-02-01 | 2025-01-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5722 | 24-Dec-24 | 2025-02-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1040 | 2412-4GDCS-4G#RO-BGA005-0377 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | BGA005 | TBG Pelabuhan Labuan |  | NR ATP & NY Ineom | KENDARI | -4.4798 | 122.9027 | YPTT | December-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 2 | 0 | 0 | 0 | VBpd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | TBG | [5 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 14-Dec-24 | Done | Done | 14-Dec-24 | Done | 100% | 14-Dec-24 | 14-Dec-24 | 14-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 17-Dec-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-03 | 2025-03-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5722 | 24-Dec-24 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1041 | 2412-4GDCS-4G#RO-LGI001-0382 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | NTI122 | DMT N3T PANTURA JAYA |  | Take over closing ATP to YPTT d/t CCSI no team | TERNATE | 128.7249 | 128.7249 | YPTT | July-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 29-May-25 | Done | Done | 30-May-25 | Done | 100% | 30-May-25 | 30-May-25 | 30-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-07-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 13-Aug-25 | 2025-06-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8095 | 14-Oct-25 | 19-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1042 | 2412-4GDCS-4G#RO-MRW909-0383 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | MMS039 | DMT Non3T Tanete Tomba |  |  | PARE PARE | -2.96 | 119.2185 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-03-25 | Done | Done | 2025-03-25 | Done | 100% | 2025-03-25 | 2025-03-25 | 2025-03-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-15 | 2025-04-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6244 | 2025-04-18 | 7-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1043 | 2412-4GDCS-4G#RO-NTI118-0379 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | COI445 | Combat VIP Villa Gubernur Sulsel CR fr DMT MCP Anggrek Raya |  |  | MAKASSAR | -4.7929 | 122.4825 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-03-02 | Done | Done | 2025-03-04 | Done | 100% | 2025-03-02 | 2025-03-02 | 2025-03-04 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-04 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 9-May-25 | 21-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6156 | 2025-03-17 | 28-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1044 | 2412-4GDCS-4G#RO-TDE024-0390 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | TDE024 | DMT Oba Akelamo |  |  | TERNATE | 0.53433 | 127.5425 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-10 | Done | Done | 2025-01-10 | Done | 100% | 2025-01-10 | 2025-01-10 | 2025-01-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-10 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1045 | 2412-4T4R-4G#RO-ADL004-0136 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap antenna and RRU | ADL004 | TBG Lapulu |  | NY Tag Dismantle & NR FI | KENDARI | -4.4787 | 122.2578 | YPTT | January-25 |  | 2025 | 2025 |  |  | MOBI 12 Port | 1 | 1 | R9224E M7290 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | Prose 10 Port | 1 | 1 | Commscope | 1 | R8852E S9000 | 1 | No Need Board | TBG | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-01-13 | Done | Done | 2025-01-13 | Done | 100% | 2025-01-13 | 2025-01-13 | 2025-01-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-14 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-26 | 2025-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1046 | 2412-4T4R-4G#RO-ADL024-0152 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap Antenna and RRU | ADL024 | Tampabulu |  | NY ATP & Ineom | KENDARI | -4.7518 | 121.7177 | YPTT | January-25 |  | 2025 | 2025 |  |  | MOBI 12 Port | 1 | 1 | R9224E M7290 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | MOBI 10 Port | 1 | 1 | No Need | 0 | R8852E S9000 | 1 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2025-01-19 | Done | Done | 2025-01-19 | Done | 100% | 2025-01-19 | 2025-01-19 | 2025-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-09 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Permit | [10 empty] | 2025-06-25 | 2025-07-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1047 | 2412-4T4R-4G#RO-ADL065-0163 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap Antenna and RRU | ADL065 | DMT Baito |  | NY ATP & Ineom | KENDARI | -4.2546 | 122.3175 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9224E M7290 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | No Need Antena | 0 | 0 | No Need | 0 | R8862 S9000 | 2 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2025-01-17 | Done | Done | 2025-01-17 | Done | 100% | 2025-01-17 | 2025-01-17 | 2025-01-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-11 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Permit | [10 empty] | 2025-06-25 | 2025-07-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-04-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1048 | 2412-4T4R-4G#RO-ADL153-0051 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU and Module BBU | ADL153 | BMT Tedubara |  |  | KENDARI | -5.1214 | 121.8755 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 1 | 1 | 1 | 0 | VBPe3p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872S S1800(2),R8863 S2100(1) | 3 | Cabinet(1),BBU(1),PM5(2),SA(1),FS(1),CCE1(1),BPN(3),FA0(1),LPU(1),BFAN5(1),CR0(1),DCPD7(1) | TBG | [5 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2025-01-28 | Done | Done | 2025-01-29 | Done | 100% | 2025-01-28 | 2025-01-29 | 2025-01-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-03 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-21 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1049 | 2412-4T4R-4G#RO-BAU015-0077 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU and Module BBU | BAU015 | Lasalimu |  | NY ATP & Ineom | KENDARI | -5.1624 | 123.0601 | YPTT | January-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-01-14 | Done | Done | 2025-01-16 | Done | 100% | 2025-01-14 | 2025-01-15 | 2025-01-15 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-11 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 21-May-25 | 22-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1050 | 2412-4T4R-4G#RO-BAU272-0085 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap Antenna and RRU | BAU272 | DMT Non3T Benteng |  | NY Ineom | KENDARI | -5.2285 | 122.9478 | YPTT | January-25 |  | 2025 | 2025 |  |  | MOBI 12 Port | 1 | 1 | R9224E M7290 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | MOBI 10 Port | 1 | 1 | No Need | 0 | R8852E S9000 | 1 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-01-17 | Done | Done | 2025-01-17 | Done | 100% | 2025-01-17 | 2025-01-17 | 2025-01-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-18 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-04-24 | 2025-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1051 | 2412-4T4R-4G#RO-BIT007-0086 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap Antenna and RRU | BIT007 | Permanenisasi COI360 - Combat Manembo-nemboTangkoko |  |  | MANADO | 1.425 | 125.1168 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TBG | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Vendi | Done Productivity 100 % |  |  |  |  | 2025-01-06 | Done | Done | 2025-01-05 | Done | 100% | 2025-01-06 | 2025-01-07 | 2025-01-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-12 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-24 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1052 | 2412-4T4R-4G#RO-KKA027-0140 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap antenna and RRU | KKA027 | Repeater Lambiku |  |  | KENDARI | -4.7064 | 122.7016 | YPTT | January-25 |  | 2025 | 2025 |  |  | MOBI 12 Port | 1 | 1 | R9224E M7290 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Rosenberger 10 Port | 1 | 1 | 1 | 1 | R8852E S9000 | 1 | No Need Board | TELKOMSEL | [5 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2025-01-09 | Done | Done | 2025-01-09 | Done | 100% | 2025-01-09 | 2025-01-09 | 2025-01-09 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-10 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-28 | 2025-04-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1053 | 2412-4T4R-4G#RO-KKA254-0129 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap Antenna and RRU | KKA254 | DMT Popalia |  | NY Tag Dismantle | KENDARI | -4.3797 | 121.5554 | YPTT | January-25 |  | 2025 | 2025 |  |  | MOBI 12 Port | 1 | 1 | R9224E M7290 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | MOBI 10 Port | 1 | 1 | No Need | 0 | R8852E S9000 | 1 | No Need Board | DMT | [5 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2025-01-24 | Done | Done | 2025-01-24 | Done | 100% | 2025-01-24 | 2025-01-24 | 2025-01-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-26 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-24 | 2025-06-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1054 | 2412-4T4R-4G#RO-MAM024-0064 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap Antenna and RRU | MAM024 | Benggaulu |  |  | PARE PARE | -1.7581 | 119.3996 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Og Request |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 23-Dec-24 | Done | Done | 24-Dec-24 | Done | 100% | 23-Dec-24 | 24-Dec-24 | 24-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 30-Dec-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 22-May-25 | 2025-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1055 | 2412-4T4R-4G#RO-RHA034-0156 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU and Module BBU | RHA034 | DMT Wakadia |  |  | KENDARI | -4.7922 | 122.6305 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 1 | 1 | 1 | 0 | VBPe1p(1),VBPe2p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8894 M1821 | 1 | Cabinet(1),BBU(1),BFAn5(1),LPU(1),FA0(1),PM5(2),SA(1),CR0(2),CCE1B(2),BPQ(1),BPN(2),UBPG(1) | DMT | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-16 | Done | Done | 2025-01-17 | Done | 100% | 2025-01-16 | 2025-01-17 | 2025-01-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-08 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-25 | 2025-07-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1056 | 2412-4T4R-4G#RO-RHA058-0165 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap antenna and RRU | RHA058 | TBG Moolu |  | Ny Ineom | KENDARI | -4.8041 | 122.861 | YPTT | January-25 |  | 2025 | 2025 |  |  | MOBI 12 Port | 1 | 1 | R9224E M7290 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | MOBI 10 Port | 1 | 1 | No Need | 0 | R8852E S9000 | 1 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-01-16 | Done | Done | 2025-01-16 | Done | 100% | 2025-01-16 | 2025-01-16 | 2025-01-16 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-17 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-28 | 2025-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1057 | 2412-4T4R-4G#RO-RHA131-0115 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap antenna and RRU | RHA131 | TBG Wakorumba Utara |  |  | KENDARI | -4.433 | 122.9583 | YPTT | January-25 |  | 2025 | 2025 |  |  | MOBI 12 Port | 1 | 1 | R9224E M7290 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | MOBI 10 Port | 1 | 1 | No Need | 0 | R8852E S9000 | 1 | No Need Board | TBG | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-01-15 | Done | Done | 2025-01-15 | Done | 100% | 2025-01-15 | 2025-01-15 | 2025-01-15 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-16 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-25 | 2025-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1058 | 2412-4T4R-4G#RO-SKG014-0164 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU and Module BBU | SKG014 | Keera |  |  | MAKASSAR | -3.7958 | 120.3319 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Romy | Done Productivity 100 % |  |  |  |  | 2025-01-19 | Done | Done | 2025-01-23 | Done | 100% | 2025-01-19 | 2025-01-23 | 2025-01-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-20 | 2025-03-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1059 | 2412-4T4R-4G#RO-SKG016-0133 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap Antenna and RRU and Module BBU | SKG016 | Gilireng-DMT |  |  | MAKASSAR | -3.9591 | 120.1638 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Rezky | Done Productivity 100 % |  |  |  |  | 2025-01-19 | Done | Done | 2025-01-22 | Done | 100% | 2025-01-19 | 2025-01-22 | 2025-01-22 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-20 | 2025-03-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1060 | 2412-4T4R-4G#RO-SKG017-0117 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade BW LTE 1800 20 - 20 Mhz 4T4R | Swap RRU and Module BBU | SKG017 | Bola |  |  | MAKASSAR | -4.2201 | 120.311 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Romy | Done Productivity 100 % |  |  |  |  | 2025-01-04 | Done | Done | 2025-01-08 | Done | 100% | 2025-01-04 | 2025-01-04 | 2025-01-08 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-08 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-25 | 2025-03-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1061 | 2412-4T4R-4G#RO-SNN018-0118 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap Antenna and RRU | SNN018 | DMT Mangoli |  |  | TERNATE | -1.9298 | 125.9283 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-02-17 | Done | Done | 2025-02-18 | Done | 100% | 2025-02-17 | 2025-02-18 | 2025-02-18 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-18 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-04-23 | 2025-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6098 | 2025-03-06 | 7-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1062 | 2412-4T4R-4G#RO-SNN020-0066 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU | SNN020 | DMT Sanana |  |  | TERNATE | -2.0702 | 125.9779 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-02-15 | Done | Done | 2025-02-15 | Done | 100% | 2025-02-15 | 2025-02-15 | 2025-02-15 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-16 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-04-14 | 2025-04-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6048 | 2025-02-25 | 2025-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1063 | 2412-4T4R-4G#RO-TDE009-0080 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap Antenna and RRU and Add Module BBU | TDE009 | Faulery |  |  | TERNATE | 0.37885 | 127.6244 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-03-10 | Done | Done | 2025-03-10 | Done | 100% | 2025-03-10 | 2025-03-10 | 2025-03-10 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-03-17 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 08-May-25 | 21-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 28-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1064 | 2412-4T4R-4G#RO-TDE018-0134 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Add RRU and Swap Module BBU | TDE018 | DMT Bale Oba |  |  | TERNATE | 0.39552 | 127.6965 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-22 | Done | Done | 2025-01-22 | Done | 100% | 2025-01-22 | 2025-01-22 | 2025-01-22 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 20-May-25 | 21-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1065 | 2412-4T4R-4G#RO-TDE068-0119 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap Antenna and RRU | TDE068 | Aketobololo |  |  | TERNATE | 0.56259 | 127.5382 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-04 | Done | Done | 2025-01-04 | Done | 100% | 2025-01-04 | 2025-01-04 | 2025-01-04 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-01-06 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-23 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1066 | 2412-4T4R-4G#RO-TDK003-0148 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap antenna and RRU | TDK003 | SALOGATTA |  |  | PARE PARE | -2.1365 | 119.2514 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TBG | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Romy | Done Productivity 100 % |  |  |  |  | 2025-01-04 | Done | Done | 2025-01-04 | Done | 100% | 2025-01-04 | 2025-01-04 | 2025-01-04 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2025-01-05 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-24 | 2025-07-03 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1067 | 2412-4T4R-4G#RO-TDO357-0149 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Swap antenna and RRU | TDO357 | DMT Lansa |  |  | MANADO | 1.6435 | 124.9298 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Release |  |  |  |  | CV. Puri Tepule Abadi | Sulaiman | Done Productivity 100 % |  |  |  |  | 2025-01-18 | Done | Done | 2025-01-18 | Done | 100% | 2025-01-18 | 2025-01-18 | 2025-01-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-31 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-23 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1068 | 2412-4T4R-4G#RO-TER089-0081 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade BW LTE 900 10 - 10Mhz 4T4R | Add Antenna and RRU | TER089 | Protelindo Sindangoli Beach |  |  | TERNATE | 0.90581 | 127.5167 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | PTI | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-02-19 | Done | Done | 2025-01-20 | Done | 100% | 2025-02-19 | 2025-01-20 | 2025-01-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-16 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-27 | 2025-04-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1069 | 2412-4T4R-4G#RO-TOB054-0127 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | TOB054 | DMT Wari Tobelo |  |  | TERNATE | 1.7473 | 127.9952 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-29 | Done | Done | 2025-01-29 | Done | 100% | 2025-01-29 | 2025-01-29 | 2025-01-29 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-01-31 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 29-May-25 | 2025-06-02 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1070 | 2412-ADSTR-4G#RO-ADL049-0215 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Module BBU | ADL049 | DMT Rumbia |  | NY ATP & Ineom | KENDARI | -4.7749 | 122.0517 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBPe3q(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | TBD | DMT | [5 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2025-01-18 | Done | Done | 2025-01-18 | Done | 100% | 2025-01-18 | 2025-01-18 | 2025-01-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-06 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Permit | [10 empty] | 2025-06-25 | 2025-07-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1071 | 2412-ADSTR-4G#RO-ADL081-0212 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Add Sector LTE 1800 2T2R | Add RRU | ADL081 | TBG Amondo |  | NY Ineom | KENDARI | -4.4327 | 122.3896 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | TBG | [5 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2025-01-14 | Done | Done | 2025-01-14 | Done | 100% | 2025-01-14 | 2025-01-14 | 2025-01-14 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-15 |  | Done Tagging |  | Done Tagging | No Need | Waiting Permit | [10 empty] | 2025-04-03 | 2025-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5857 | 2025-01-19 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1072 | 2412-ADSTR-4G#RO-ADL274-0127 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | ADL274 | PT. PAG 1 |  | NY Tag Dismantle | KENDARI | -4.5845 | 121.8798 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 0 | 0 | 0 | VBPe2q(1) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | DCPD7(1) | PT. PAG | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-01-09 | Done | Done | 2025-01-09 | Done | 100% | 2025-01-09 | 2025-01-09 | 2025-01-09 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-10 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Tag Asset Store | [10 empty] | 2025-03-26 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1073 | 2412-ADSTR-4G#RO-BAU039-0130 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP eNode B Modular Relocation Service New NE LTE 2300 | Add RRU | BAU039 | Lapandewa |  |  | KENDARI | -5.6479 | 122.787 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-29 | Done | Done | 2025-01-30 | Done | 100% | 2025-01-29 | 2025-01-29 | 2025-01-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-31 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 03-Oct-25 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1074 | 2412-ADSTR-4G#RO-BAU044-0131 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP eNode B Modular Relocation Service New NE LTE 2300 | Add RRU and Swap Module BBU | BAU044 | DMT Sampolawa Baru |  | NY ATP & Ineom | KENDARI | -5.6301 | 122.7012 | YPTT | January-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-01-17 | Done | Done | 2025-01-18 | Done | 100% | 2025-01-17 | 2025-01-18 | 2025-01-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-05 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2026-01-22 | 2025-03-15 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1075 | 2412-ADSTR-4G#RO-BAU109-0202 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Module BBU | BAU109 | PTI Kamaru Sribarata |  | NY ATP & Ineom | KENDARI | -5.0868 | 122.9687 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBPe1p(1),VBPe3p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),CR)(2),CCE1B(1),BPN(2),UBPG(1),PM5(2),SA(1),FA0(1),BFAN5(1),LPU(1),DCPD7(1),MCB 63A(2) | PTI | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-01-18 | Done | Done | 2025-01-18 | Done | 100% | 2025-01-18 | 2025-01-18 | 2025-01-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-26 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-26 | 2025-07-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1076 | 2412-ADSTR-4G#RO-BAU263-0133 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP eNode B Modular Relocation Service New NE LTE 2300 | Add RRU | BAU263 | TBG Kapota |  | NY Ineom | KENDARI | -5.3401 | 123.4959 | YPTT | January-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-01-28 | Done | Done | 2025-01-29 | Done | 100% | 2025-01-28 | 2025-01-29 | 2025-01-29 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-29 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 14-May-25 | 2025-04-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-23 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1077 | 2412-ADSTR-4G#RO-BIT004-0136 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Add Sector LTE 2300 4T4R | Swap RRU and Module BBU | BIT004 | DMT Madidir Weru |  |  | MANADO | 1.4417 | 125.152 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Vendi | Done Productivity 100 % |  |  |  |  | 2025-01-20 | Done | Done | 2025-01-20 | Done | 100% | 2025-01-20 | 2025-01-21 | 2025-01-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-27 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-28 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1078 | 2412-ADSTR-4G#RO-COI551-0192 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Add Sector LTE 2100 2T2R | Swap RRU and Module BBU | COI551 | COMBAT FUN TUBO |  |  | TERNATE | 0.82569 | 127.3736 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-05 | Done | Done | 2025-01-05 | Done | 100% | 2025-01-05 | 2025-01-05 | 2025-01-05 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-01-10 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 15-May-25 | 16-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6097 | 2025-03-06 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1079 | 2412-ADSTR-4G#RO-LBA035-0148 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP eNode B Modular Relocation Service New NE LTE 2300 | Swap RRU and Add Module BBU | LBA035 | DMT RSUD Bacan |  |  | TERNATE | -0.63242 | 127.5252 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-30 | Done | Done | 2025-01-30 | Done | 100% | 2025-01-30 | 2025-01-31 | 2025-01-30 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-01-31 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-03-27 | 2025-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-04-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1080 | 2412-ADSTR-4G#RO-MAM191-0150 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Add Sector LTE 2300 4T4R | Add RRU | MAM191 | TBG Kantor Bupati Mamuju Tengah |  |  | PARE PARE | -2.0773 | 119.2915 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TBG | Og Request |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-01-06 | Done | Done | 2025-01-07 | Done | 100% | 2025-01-06 | 2025-01-07 | 2025-01-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-07 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1081 | 2412-ADSTR-4G#RO-PIN156-0208 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Add Sector LTE 1800 2T2R | Add antenna and RRU and Module BBU | PIN156 | DMT Ulu Saddang |  |  | PARE PARE | -3.433 | 119.5631 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Rezky | Done Productivity 100 % |  |  |  |  | 2025-01-16 | Done | Done | 2025-01-16 | Done | 100% | 2025-01-16 | 2025-01-16 | 2025-01-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-18 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1082 | 2412-ADSTR-4G#RO-PSO076-0169 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Add Sector LTE 2300 4T4R | Add RRU | KKA257 | TBG Anaiwoi Kolaka |  | ALL CLOSE | KENDARI | -4.3727 | 121.5213 | YPTT | March-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | TBG | [5 empty] | CV. Puri Tepule Abadi | Aladin | Done Productivity 100 % |  |  |  |  | 2025-03-09 | Done | Done | 2025-03-09 | Done | 100% | 2025-03-09 | 2025-03-09 | 2025-03-09 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-25 | 2025-03-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6211 | 2025-04-09 | 7-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1083 | 2412-ADSTR-4G#RO-RHA008-0195 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Add Sector LTE 2100 2T2R | Swap RRU and Module BBU | RHA008 | Kabawo |  | NY Tag Dismantle | KENDARI | -5.0008 | 122.5008 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 1 | 1 | 1 | 0 | VBPe1p(1),VBPe3p | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800 | 1 | Cabinet(1),BBU(1),CR0(2),CCE1B(2),BPN(4),LPU(1),BFAN5(1),SA(1),PM5(2),FA0(1) | TELKOMSEL | [5 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2025-01-12 | Done | Done | 2025-01-12 | Done | 100% | 2025-01-12 | 2025-01-12 | 2025-01-12 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-13 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-26 | 2025-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1084 | 2412-ADSTR-4G#RO-RHA014-0213 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Module BBU | RHA014 | TBG Tampo 2 |  |  | KENDARI | -4.6341 | 122.7111 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBPe1p(1),VBPe3p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),BFAN5(1),DCPD7(1),LPU(1),FA0(1),SA(1),PM5(2),CR0(2),CCE1B(2),BPN(3),UBPG(1) | TBG | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-12 | Done | Done | 2025-01-14 | Done | 100% | 2025-01-12 | 2025-01-13 | 2025-01-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-16 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-28 | 2025-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1085 | 2412-ADSTR-4G#RO-RHA047-0170 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP eNode B Modular Relocation Service New NE LTE 2300 | Add RRU | RHA047 | TBG Pelabuhan Dongkala |  | NY Tag Dismantle | KENDARI | -5.3148 | 122.0444 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R8998G S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | TBG | [5 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2025-01-31 | Done | Done | 2025-01-31 | Done | 100% | 2025-01-31 | 2025-01-31 | 2025-01-31 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-01 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-25 | 2025-03-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1086 | 2412-ADSTR-4G#RO-RHA112-0171 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP eNode B Modular Relocation Service New NE LTE 2300 | Add RRU and Swap Module BBU | RHA112 | DMT Tondasi |  | NY Tag Dismantle | KENDARI | -4.7573 | 122.3721 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBPd0p(1),VBPd2p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),PM5(2),SA(1),Fa0(1),LPU(1),BFAN5(1),BPN(4),CR0(2),CCE1B(2) | DMT | [5 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2025-01-16 | Done | Done | 2025-01-17 | Done | 100% | 2025-01-16 | 2025-01-17 | 2025-01-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-18 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-25 | 2025-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1087 | 2412-ADSTR-4G#RO-SKG090-0199 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Module BBU | SKG090 | TaneteSimpellu-PTI |  |  | MAKASSAR | -3.7791 | 120.2881 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | PTI | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Romy | Done Productivity 100 % |  |  |  |  | 2025-01-05 | Done | Done | 2025-01-07 | Done | 100% | 2025-01-07 | 2025-01-07 | 2025-01-07 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-07 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-25 | 2025-03-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1088 | 2412-ADSTR-4G#RO-SNN019-0174 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Add Sector LTE 2300 4T4R | Add RRU | SNN019 | TBG Sanana |  |  | TERNATE | -2.065 | 125.9804 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TBG | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | ahmad | Done Productivity 100 % |  |  |  |  | 22-May-25 | Done | Done | 22-May-25 | Done | 100% | 22-May-25 | 22-May-25 | 22-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 22-May-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 29-May-25 | 2025-06-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6759 | 2025-06-20 | 2025-07-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1089 | 2412-ADSTR-4G#RO-SNN055-0175 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Add Sector LTE 2300 4T4R | Add RRU | SNN055 | TBG Meranti Jaya |  |  | TERNATE | -1.9037 | 124.3441 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TBG | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-02-22 | Done | Done | 2025-02-23 | Done | 100% | 2025-02-22 | 2025-02-23 | 2025-02-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-02-26 | 2025-02-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6098 | 2025-03-06 | 16-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1090 | 2412-ADSTR-4G#RO-SRI003-0177 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Add Sector LTE 2300 4T4R | Add RRU and Module BBU | SRI003 | TBG Parura Jaya |  | ALL CLOSE | KENDARI | -4.8522 | 122.4086 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBPd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | TBG | [5 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2025-01-13 | Done | Done | 2025-01-15 | Done | 100% | 2025-01-13 | 2025-01-14 | 2025-01-14 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-03 | 2025-03-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1091 | 2412-ADSTR-4G#RO-TER155-0186 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Add Sector LTE 2100 2T2R | Swap RRU | TER155 | Tataleka |  |  | TERNATE | 0.9566 | 127.5159 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | KiSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-05 | Done | Done | 2025-01-06 | Done | 100% | 2025-01-05 | 2025-01-06 | 2025-01-06 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-01-12 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-23 | 2025-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1092 | 2412-ADSTR-4G#RO-THN081-0184 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Module BBU | THN081 | TagulandangUtara-ACO |  |  | MANADO | 2.3606 | 125.4307 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | CMI | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Vendi | Done Productivity 100 % |  |  |  |  | 2025-01-30 | Done | Done | 2025-01-31 | Done | 100% | 2025-01-30 | 2025-01-31 | 2025-02-01 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-05 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-02-19 | 2025-02-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1093 | 2412-MSCTR-4G#RO-BAU044-0006 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade Multisector LTE | Add Antenna and Swap RRU | BAU044 | DMT Sampolawa Baru |  | NY Tag Dismantle | KENDARI | -5.6301 | 122.7012 | YPTT | January-25 |  | 2025 | 2025 |  |  | Mobi 4 Port | 1 | 1 | R9224E M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | No Need Antena | 0 | 0 | No Need | 0 | R8862 S9000 | 0 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Aladin | Done Productivity 100 % |  |  |  |  | 2025-03-11 | Done | Done | 2025-03-12 | Done | 100% | 2025-03-11 | 2025-03-12 | 2025-03-12 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-12 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 05-May-25 | 8-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6211 | 2025-04-09 | 16-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1094 | 2412-MSCTR-4G#RO-KKA055-0008 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade Multisector LTE | Add Antenna and Swap RRU | KKA055 | TBG Lalembuu |  | NY Tag Asset Reutilise | KENDARI | -4.3654 | 122.0093 | YPTT | January-25 |  | 2025 | 2025 |  |  | HBXX | 1 | 1 | R9254 M1821 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | TBG | [5 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2025-02-03 | Done | Done | 2025-02-03 | Done | 100% | 2025-02-03 | 2025-02-03 | 2025-02-03 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-04 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 03-Oct-25 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6015 | 2025-02-17 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1095 | 2412-MSCTR-4G#RO-LBA059-0009 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade Multisector LTE 1800 | Add RRU and Swap Module BBU | LBA059 | TBG HIDAYAT BACAN |  |  | TERNATE | -0.64399 | 127.4951 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TBG | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-27 | Done | Done | 2025-01-28 | Done | 100% | 2025-01-27 | 2025-01-28 | 2025-01-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-01 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-27 | 2025-04-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1096 | 2412-MSCTR-4G#RO-RHA010-0016 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade Multisector LTE | Add Antenna and RRU and Swap Module BBU | RHA010 | Wasolangka |  | NY Ineom & NR EHS | KENDARI | -5.0833 | 122.4417 | YPTT | January-25 |  | 2025 | 2025 |  |  | HBXX | 1 | 1 | R9264E M1821 | 1 | 1 | 1 | 0 | VBPd0p(1)VBPd2p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),LPU(1),BFAN5(1),PM5(2),SA(1),BPQ(2),BPN(2),CR0(2),CCF0(2),FA0(1) | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2025-02-03 | Done | Done | 2025-02-06 | Done | 100% | 2025-02-03 | 2025-02-05 | 2025-02-05 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-05 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-25 | 2025-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6015 | 2025-02-17 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1097 | 2412-MSCTR-4G#RO-SKG067-0019 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade Multisector LTE 1800 | Add Antenna and RRU | SKG067 | CenaeBola-STP |  |  | MAKASSAR | -4.1924 | 120.2231 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | STP | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Rezky | Done Productivity 100 % |  |  |  |  | 2025-01-19 | Done | Done | 2025-01-28 | Done | 100% | 2025-01-19 | 2025-01-28 | 2025-01-28 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-28 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-03 | 2025-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 16-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1098 | 2412-MSCTR-4G#RO-TDE008-0020 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade Multisector LTE 2100 | Add Antenna and RRU | TDE008 | Sofifi |  |  | TERNATE | 0.75194 | 127.5761 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-19 | Done | Done | 2025-01-29 | Done | 100% | 2025-01-19 | 2025-01-29 | 2025-01-29 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-08 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-11-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1099 | 2412-MSCTR-4G#RO-TER083-0021 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade Multisector LTE 2100 | Swap RRU and Module BBU | TER083 | Protelindo Gambesi Kota |  |  | TERNATE | 0.75791 | 127.3406 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | PTI | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-27 | Done | Done | 2025-01-27 | Done | 100% | 2025-01-27 | 2025-01-28 | 2025-01-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-04 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1100 | 2412-NNE4G-4G#931-LBA077-1322 | CAPEX RAN 4 PART 1 2024 FOR CAPACITY & COVERAGE | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | LBA077 | DMT Moti Surya |  |  | TERNATE | 0.45439 | 127.3841 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-03-16 | Done | Done | 2025-03-18 | Done | 100% | 2025-03-18 | 2025-03-18 | 2025-03-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-09 | 2025-04-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6241 | 2025-04-17 | 16-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1101 | 2412-NNE4G-4G#931-RHA152-1323 | CAPEX RAN 4 PART 1 2024 FOR CAPACITY & COVERAGE | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | RHA152 | DMT Oensuli Kabangka |  | NY ATP & Ineom | KENDARI | -4.9493 | 122386651 | YPTT | December-24 |  | 2024 | 2024 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBPd0p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | DMT | [5 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2025-01-17 | Done | Done | 2025-01-18 | Done | 100% | 2025-01-17 | 2025-01-18 | 2025-01-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-13 | 2025-03-15 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5873 | 2025-01-31 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1102 | 2412-NNE4G-4G#RO-ADL083-1331 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU | ADL083 | PTI Pancalogam |  | NY ATP & Ineom | KENDARI | -4.6588 | 121.9117 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | n | No Need | 0 | R8872A (2),R8863 (2) | 4 | No Need Board | PTI | [5 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2025-01-22 | Done | Done | 2025-01-22 | Done | 100% | 2025-01-22 | 2025-01-22 | 2025-01-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-10 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-21 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1103 | 2412-NNE4G-4G#RO-BIT055-1370 | CAPEX RAN 1 PART 2D 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Add RRU and Module BBU | BIT055 | Protelindo Aer Tembaga Dua |  |  | MANADO | 1.4612 | 125.2019 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | PTI | Release |  |  |  |  | CV. Puri Tepule Abadi | Vendi | Done Productivity 100 % |  |  |  |  | 2025-01-16 | Done | Done | 2025-01-17 | Done | 100% | 2025-01-16 | 2025-01-18 | 2025-01-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-12 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-24 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5868 | 2025-01-23 | 16-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1104 | 2412-NNE4G-4G#RO-COI397-1339 | CAPEX RAN 1 PART 2D 2024 | EQP New NE 4G LTE 2300 50 Mhz | Swap Antenna and Swap Module BBU and Add RRU | BAU193 | TBG MCP Unismuh Buton |  | NY ATP & Ineom | KENDARI | -5.4631 | 122.5997 | YPTT | January-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 90 % |  |  |  |  | 2025-01-29 | Done | Done | 2025-01-29 | Done | 100% | 2025-01-29 | 2025-01-29 | 2025-01-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-09 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 21-Aug-25 | 21-Aug-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1105 | 2412-NNE4G-4G#RO-COI499-1359 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP New NE 4G LTE 1800 20 Mhz | Swap Antenna and Module BBU and Add RRU | SKG031 | DMT Wele |  |  | MAKASSAR | -4.7929 | 122.4825 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-03-28 | Done | Done | 2025-03-28 | Done | 100% | 2025-03-28 | 2025-03-28 | 2025-03-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-04-13 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 6-May-25 | 8-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6244 | 2025-04-18 | 2025-06-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1106 | 2412-NNE4G-4G#RO-COI672-1353 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP New NE 4G LTE 2100 20 Mhz | Swap Antenna and RRU and Module BBU | BAU054 | Pertigaan Bandara Matahora |  | NY ATP | KENDARI | -5.3354 | 123.6314 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-03-27 | Done | Done | 2025-03-28 | Done | 100% | 2025-03-27 | 2025-03-28 | 2025-03-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-30 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 08-May-25 | 20-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6244 | 2025-04-18 | 2025-06-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1107 | 2412-NNE4G-4G#RO-MAJ008-1361 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | MAJ008 | DMT Tammaroddo |  |  | PARE PARE | -3.2392 | 118.8355 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Rezky | Done Productivity 90 % |  |  |  |  | 2025-01-17 | Done | Done | 2025-01-18 | Done | 100% | 2025-01-17 | 2025-01-17 | 2025-01-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2024-01-18 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-27 | 2025-04-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1108 | 2412-NNE4G-4G#RO-NTI119-1346 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | NTI119 | DMT N3T Masara |  | NY Ineom | KENDARI | -4.6941 | 122.5809 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 3 | 0 | 0 | 0 | VBPe1p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800 | 3 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-14 | Done | Done | 2025-01-14 | Done | 100% | 2025-01-14 | 2025-01-15 | 2025-01-15 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-15 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-28 | 2025-04-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1109 | 2412-NNE4G-4G#RO-NTI120-1347 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | NTI120 | DMT N3T Kasakamu |  |  | KENDARI | -4.7458 | 122.5101 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 1 | 0 | 0 | 0 | VBP31p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800 | 1 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-17 | Done | Done | 2025-01-17 | Done | 100% | 2025-01-17 | 2025-01-17 | 2025-01-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-17 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-28 | 2025-04-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1110 | 2412-NNE4G-4G#RO-NTI300-1356 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP New NE 4G LTE 2100 20 Mhz | Add module BBU | NTI300 | N3TPENDULANGANLIMBORO |  |  | PARE PARE | -3.3964 | 119.049 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Og Request |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-01-09 | Done | Done | 2025-01-09 | Done | 100% | 2025-01-09 | 2025-01-09 | 2025-01-09 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1111 | 2412-NNE4G-4G#RO-PIN144-1350 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Module BBU | PIN144 | TBG Maccobu |  |  | PARE PARE | -3.7418 | 119.6526 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TBG | Og Request |  |  |  |  | YPTT | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-01-11 | Done | Done | 2025-01-11 | Done | 100% | 2025-01-11 | 2025-01-11 | 2025-01-11 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-11 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-06 | 2-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1112 | 2412-NNE4G-4G#RO-RHA059-1368 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | RHA059 | DMT Wulanga Jaya |  | NR ATP & NY Ineom | KENDARI | -4.8291 | 12243420 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBPe1p(1) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 90 % |  |  |  |  | 2025-01-19 | Done | Done | 2025-01-19 | Done | 100% | 2025-01-19 | 2025-01-19 | 2025-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-03 | 2025-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1113 | 2412-NNE4G-4G#RO-SRI002-1348 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP New NE 4G LTE 2100 20 Mhz | Swap RRU and Add Module BBU | SRI002 | TBG Guali |  | ALL CLOSE | KENDARI | -4.7493 | 12254046 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | 0 | VBPe1p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800 | 1 | No Need Board | TBG | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-20 | Done | Done | 2025-01-21 | Done | 100% | 2025-01-20 | 2025-01-20 | 2025-01-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-20 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-24 | 2025-06-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1114 | 2412-NNE4G-4G#RO-TER064-1329 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU | TER064 | TernateTengah-DMT |  |  | TERNATE | 0.79466 | 127.3886 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 21-Dec-24 | Done | Done | 22-Dec-24 | Done | 100% | 21-Dec-24 | 22-Dec-24 | 22-Dec-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-5774 | 2025-01-03 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1115 | 2412-NNE4G-4G#RO-THN040-1344 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | THN040 | DMT Peling Sawah |  |  | MANADO | 2.6991 | 125.3677 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Sulaiman | Done Productivity 100 % |  |  |  |  | 2025-01-24 | Done | Done | 2025-01-24 | Done | 100% | 2025-01-24 | 2025-01-24 | 2025-01-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-26 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 17-May-25 | 19-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1116 | 2412-UMIMO-4G#RO-ADL111-0392 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap BBU and Add RRU | ADL111 | CMI MCP Tapuahi |  | NY ATP & Ineom | KENDARI | -5.1016 | 121.8555 | YPTT | January-25 |  | 2025 | 2025 | [28 empty] | CMI | [5 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2025-01-21 | Done | Done | 2025-01-21 | Done | 100% | 2025-01-21 | 2025-01-21 | 2025-01-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-09 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-26 | 2025-07-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1117 | 2412-UMIMO-4G#RO-ADL261-0270 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | ADL261 | TBG Lantari Jaya |  | NY ATP & Ineom | KENDARI | -4.6155 | 122.0015 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 1 | 1 | 0 | VBPd2p(1),VBPe2q(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),CR0(1),CCE1b(2),BPN(3),PM3(1),PM5(1),SA(1),FA0(1),BFAN5(1),LPU(1),DCPD7(1) | TBG | [5 empty] | CV. Puri Tepule Abadi | Nusmin samil | Done Productivity 100 % |  |  |  |  | 2025-01-20 | Done | Done | 2025-01-20 | Done | 100% | 2025-01-20 | 2025-01-20 | 2025-01-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-10 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-21 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1118 | 2412-UMIMO-4G#RO-BAU001-0383 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU | BAU001 | Bau-Bau |  |  | KENDARI | -5.459 | 122.6133 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-04-27 | Done | Done | 2025-04-28 | Done | 100% | 2025-04-27 | 2025-04-28 | 2025-04-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 06-May-25 |  | Done Tagging |  | Done Tagging | Pending | [11 empty] | 22-Aug-25 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6048 | 2025-02-25 | 2025-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1119 | 2412-UMIMO-4G#RO-BAU008-0271 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | BAU008 | Lombe |  | NY ATP & Ineom | KENDARI | -5.2469 | 122.5767 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 0 | 0 | 0 | VBPe1p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8998G S2300 | 1 | No Need Board | TELKOMSEL | [5 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2025-01-19 | Done | Done | 2025-01-19 | Done | 100% | 2025-01-19 | 2025-01-19 | 2025-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-20 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 08-May-25 | 20-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 28-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1120 | 2412-UMIMO-4G#RO-BAU025-0272 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | BAU025 | Wanci 2 |  | NY ATP & Ineom | KENDARI | -5.3451 | 123.5443 | YPTT | January-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-01-22 | Done | Done | 2025-01-22 | Done | 100% | 2025-01-22 | 2025-01-23 | 2025-01-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-30 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-03 | 2025-03-05 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1121 | 2412-UMIMO-4G#RO-BAU056-0273 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | BAU056 | DMT Matanauwe |  |  | KENDARI | -5.4123 | 123.0122 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 1 | 1 | 0 | VBPd2p(1),VBPe1p(1),VBPe2q(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),FA0(1),LPU(1),PM5(1),CR0(2),CCF0(2),BPN(4),DCPD7(1),BFAN5(1) | DMT | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-27 | Done | Done | 2025-01-26 | Done | 100% | 2025-01-27 | 2025-01-28 | 2025-01-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-28 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-04-22 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1122 | 2412-UMIMO-4G#RO-BAU078-0274 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | BAU078 | DMT Kadolomoku |  | NY Tag Dismantle | KENDARI | -5.462 | 122.6255 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 1 | 1 | 0 | VBPd2p(1),VBPe1p(1),VBPe2q(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | BBU(1),Cabinet(1),LPU(1),BFAN5(1),DCPD7(1),PM5(2),SA(1),BPN(4),CCE1B(2),CR0(1),FS(1),FA0(1) | DMT | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-21 | Done | Done | 2025-01-22 | Done | 100% | 2025-01-21 | 2025-01-22 | 2025-01-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-22 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1123 | 2412-UMIMO-4G#RO-BAU082-0275 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | BAU082 | DMT Wasilomata |  | NY Tag Dismantle | KENDARI | -5.3191 | 122.3137 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 0 | 0 | 0 | VBPe1p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8978 S2300 | 1 | SFP 10G(2) | DMT | [5 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2025-01-20 | Done | Done | 2025-01-21 | Done | 100% | 2025-01-20 | 2025-01-21 | 2025-01-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-26 | 2025-07-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1124 | 2412-UMIMO-4G#RO-BAU086-0393 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU | BAU086 | TBG Bahari |  | NY Tag Dismantle | KENDARI | -5.6771 | 122.7112 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 1 | 1 | 0 | VBPe2q(1),VBPe3p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8978 S2300 | 1 | Cabinet(1),BBU(1),BFAN5(1),CCE1B(2),CR0(2),BPN(3),BPQ(1),PM5(2),SA(1),FA0(1),DCPD7(1),LPU(1) | TBG | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 90 % |  |  |  |  | 2025-01-19 | Done | Done | 2025-01-20 | Done | 100% | 2025-01-19 | 2025-01-20 | 2025-01-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-21 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-26 | 2025-07-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1125 | 2412-UMIMO-4G#RO-BAU200-0276 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | BAU200 | TBG MCP Lipu |  | ALL CLOSE | KENDARI | -5.4765 | 122.5818 | YPTT | January-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-01-18 | Done | Done | 2025-01-19 | Done | 100% | 2025-01-18 | 2025-01-19 | 2025-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-07 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-22 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1126 | 2412-UMIMO-4G#RO-BAU261-0277 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | BAU261 | DMT Lapandewa Makmur |  |  | KENDARI | -5.6381 | 122.7519 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 0 | 0 | 0 | VBPe1p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-25 | Done | Done | 2025-01-25 | Done | 100% | 2025-01-25 | 2025-01-25 | 2025-01-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-03 | 2025-03-06 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1127 | 2412-UMIMO-4G#RO-BIT003-0278 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add module BBU | BIT003 | Bitung III (Aertembaga) |  |  | MANADO | 1.4488 | 125.2038 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Vendi | Done Productivity 100 % |  |  |  |  | 2025-01-22 | Done | Done | 2025-01-23 | Done | 100% | 2025-01-22 | 2025-01-23 | 2025-01-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-14 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-28 | 2025-07-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1128 | 2412-UMIMO-4G#RO-COI211-0281 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU | COI211 | Combat IWIP |  | 2x PO | TERNATE | 0.47918 | 127.985 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-01 | Done | Done | 2025-01-02 | Done | 100% | 2025-01-01 | 2025-01-02 | 2025-01-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 03-May-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-23 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1129 | 2412-UMIMO-4G#RO-COI211-0282 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | COI211 | Combat IWIP |  | 2x PO | TERNATE | 0.47918 | 127.985 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-01 | Done | Done | 2025-01-02 | Done | 100% | 2025-01-01 | 2025-01-02 | 2025-01-02 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 03-May-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-25 | 2025-07-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1130 | 2412-UMIMO-4G#RO-COI769-0283 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | COI769 | Combat MOP Sampuabalo Ambuau Indah |  | NY ATP & Ineom | KENDARI | -5.434 | 123.0121 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 0 | 0 | 0 | VBPe2q(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R9614 S23 | 1 | No Need Board | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-01-21 | Done | Done | 2025-01-21 | Done | 100% | 2025-01-21 | 2025-01-21 | 2025-01-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-11 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1131 | 2412-UMIMO-4G#RO-KDI028-0285 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | KDI028 | Kaledupa |  | NY Ineom | KENDARI | -5.5031 | 123.7525 | YPTT | January-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-01-24 | Done | Done | 2025-01-24 | Done | 100% | 2025-01-24 | 2025-01-25 | 2025-01-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-08 |  | Done Tagging |  | Done Tagging | Work Not Start | Waiting Permit | [10 empty] | 27-May-25 | 28-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1132 | 2412-UMIMO-4G#RO-KKA074-0290 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | KKA074 | DMT Balandete |  |  | KENDARI | -4.077 | 121.63 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT Bifur PTI | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 27-May-25 | Done | Done | 28-May-25 | Done | 100% | 27-May-25 | 28-May-25 | 28-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 29-May-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 22-Aug-25 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6870 | 2025-06-30 | 27-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1133 | 2412-UMIMO-4G#RO-KKA078-0377 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU | KKA078 | PTI Lappai |  | NY Tag Dismantle | KENDARI | -3.2983 | 121.0076 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 2 | 1 | 1 | 0 | VBPe3q(1),VBPe1p(1),VBPe2q(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Mobi 8 port | 1 | 1 | No Need | 0 | R8978 S2300 | 2 | Cabinet(1),BBU(2),BPN(4),BPQ(1),CCE1B(2),CR0(3),PM5(4),FA0(2),SA(2),DCPD7(1),LPU(1) | PTI | [5 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2025-01-26 | Done | Done | 2025-01-26 | Done | 100% | 2025-01-26 | 2025-01-26 | 2025-01-26 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-27 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 23-Dec-25 | 2025-03-15 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1134 | 2412-UMIMO-4G#RO-KKA098-0291 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | KKA098 | PTI Oko Oko |  | NY Ineom | KENDARI | -4.2883 | 121.5591 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 0 | 0 | 0 | VBPe2q(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8978 S2300 | 1 | No Need Board | PTI | [5 empty] | CV. Puri Tepule Abadi | Maman | Done Productivity 100 % |  |  |  |  | 2025-01-24 | Done | Done | 2025-01-24 | Done | 100% | 2025-01-24 | 2025-01-24 | 2025-01-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1135 | 2412-UMIMO-4G#RO-KKA254-0385 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | KKA254 | DMT Popalia |  | NY Ineom | KENDARI | -4.3797 | 121.5554 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 1 | 1 | 0 | VBPe3p(1),VBPe1p(1)VBPe2q(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),BFAN5(1),LPU(1),DCPD7(1),FA0(1),CR0(2),BPN(4),CCE1B(1),CCF0(1),SA(1),PM5(2) | DMT | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-02-10 | Done | Done | 2025-02-11 | Done | 100% | 2025-02-10 | 2025-02-11 | 2025-02-11 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-11 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-09-22 | 2025-09-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6053 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1136 | 2412-UMIMO-4G#RO-LBA020-0295 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Antenna and Modernize RRU | LBA020 | Protelindo Bacan Towokona |  |  | TERNATE | -0.68011 | 127.4734 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | PTI | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-22 | Done | Done | 2025-01-22 | Done | 100% | 2025-01-22 | 2025-01-22 | 2025-01-22 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-01 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 05-May-25 | 8-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 28-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1137 | 2412-UMIMO-4G#RO-LBA033-0406 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap BBU and RRU | LBA033 | Protelindo Bacan Kupal |  |  | TERNATE | -0.6666 | 127.4798 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | PTI | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-25 | Done | Done | 2025-01-26 | Done | 100% | 2025-01-25 | 2025-01-26 | 2025-01-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1138 | 2412-UMIMO-4G#RO-LBA051-0296 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU and Swap Module BBU | LBA051 | DMT MM Mandaung Bacan |  |  | TERNATE | -0.64359 | 127.4826 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-24 | Done | Done | 2025-01-24 | Done | 100% | 2025-01-24 | 2025-01-24 | 2025-01-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-02 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 21-Aug-25 | 22-Aug-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1139 | 2412-UMIMO-4G#RO-MAM038-0396 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add BBU and RRU | MAM038 | TBG Binanga |  |  | PARE PARE | -2.6888 | 118.8816 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TBG | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Romy | Done Productivity 100 % |  |  |  |  | 2025-01-18 | Done | Done | 2025-01-19 | Done | 100% | 2025-01-19 | 2025-01-19 | 2025-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-13 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1140 | 2412-UMIMO-4G#RO-MAM039-0299 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | MAM039 | TBG Pontanakayang |  |  | PARE PARE | -2.1616 | 119.2598 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TBG | Og Request |  |  |  |  | CV. Puri Tepule Abadi | Rezky | Done Productivity 100 % |  |  |  |  | 2025-01-19 | Done | Done | 2025-01-22 | Done | 100% | 2025-01-19 | 2025-01-22 | 2025-01-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1141 | 2412-UMIMO-4G#RO-PSW001-0335 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | PSW001 | DMT MH Pasar Ambuau |  |  | KENDARI | -5.3176 | 123.1687 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 0 | 0 | 0 | VBPd2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R9614 S23 | 1 |  | DMT | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2025-01-27 | Done | Done | 2025-01-27 | Done | 100% | 2025-01-27 | 2025-01-27 | 2025-01-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-28 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-04-24 | 2025-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1142 | 2412-UMIMO-4G#RO-RBI001-0336 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | RBI001 | PTI Sikeli Kabaena |  |  | KENDARI | -5262857 | 121.8022 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 0 | 0 | 0 | VBPd2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8978 S2300 | 1 | No Need Board | PTI | [5 empty] | CV. Puri Tepule Abadi | Nusmin Samil | Done Productivity 100 % |  |  |  |  | 2025-01-27 | Done | Done | 2025-01-27 | Done | 100% | 2025-01-27 | 2025-01-27 | 2025-01-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-02 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2024-06-24 | 2025-06-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1143 | 2412-UMIMO-4G#RO-RHA002-0390 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | RHA002 | DMT Tampo |  | NY Tag Dismantle | KENDARI | -4.6247 | 122.7031 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 2 | 0 | 0 | 0 | VBpe2q(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8978 S2300 | 1 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-01-28 | Done | Done | 2025-01-29 | Done | 100% | 2025-01-28 | 2025-01-29 | 2025-01-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-31 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 03-Oct-25 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1144 | 2412-UMIMO-4G#RO-RHA022-0337 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | RHA022 | Telkom Muna |  | NY Tag Dismantle | KENDARI | -4.8413 | 122.7219 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 1 | 1 | 0 | VBpd0p(1),VBpd2p(1),VBpd2(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),DCPD7(1),BFAN5(1),LPU(1),SA(1),FA0(1),BPN(2),BPQ(2),CCE1B(2),CR)(2),PM5(2) | DMT Sarpen PAK | [5 empty] | CV. Puri Tepule Abadi | Karimuddin | Done Productivity 100 % |  |  |  |  | 2025-02-27 | Done | Done | 2025-02-28 | Done | 100% | 2025-02-27 | 2025-02-28 | 2025-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-02 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 05-May-25 | 8-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6124 | 2025-03-10 | 16-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1145 | 2412-UMIMO-4G#RO-RHA024-0338 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | RHA024 | DMT Katobu |  | NY ATP & Ineom | KENDARI | -4.8277 | 122.7177 | YPTT | January-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 1 | 1 | 0 | VBPd2p(1),VBPd2(1),VBPd0p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),BFAN5(1),CC16B(1),CCE1B(1),CR0(2),BPN(4),PM5(2),SA(1),LPU(1),DCPD7(1) | DMT | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-01-30 | Done | Done | 2025-01-30 | Done | 100% | 2025-01-30 | 2025-01-30 | 2025-01-30 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-31 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-24 | 2025-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1146 | 2412-UMIMO-4G#RO-SAK052-0341 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | LBA106 | Split Mess HJF |  |  | TERNATE | -1.5651 | 127.4334 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | HARITA OBI | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-03-09 | Done | Done | 2025-03-09 | Done | 100% | 2025-03-09 | 2025-03-09 | 2025-03-09 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-09 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-20 | 2025-03-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6124 | 2025-03-10 | 2025-07-01 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1147 | 2412-UMIMO-4G#RO-SNN004-0346 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | SNN004 | Bobong |  |  | TERNATE | -1.9495 | 124.3918 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-02-24 | Done | Done | 2025-02-24 | Done | 100% | 2025-02-24 | 2025-02-24 | 2025-02-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-30 | 2025-03-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6098 | 2025-03-06 | 7-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1148 | 2412-UMIMO-4G#RO-SSU089-0350 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | SSU089 | New Split Lelilef |  | 2x PO | TERNATE | 0.47023 | 127.9354 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TBG | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-01 | Done | Done | 2025-01-01 | Done | 100% | 2025-01-01 | 2025-01-01 | 2025-01-01 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-01-04 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-25 | 2025-07-03 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1149 | 2412-UMIMO-4G#RO-TDE001-0415 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add BBU and RRU | TDE001 | Tidore |  |  | TERNATE | 0.67547 | 127.4517 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-21 | Done | Done | 2025-01-21 | Done | 100% | 2025-01-21 | 2025-01-21 | 2025-01-21 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-01-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-11-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1150 | 2412-UMIMO-4G#RO-TDE004-0391 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap Antenna and RRU | TDE004 | Soadara |  |  | TERNATE | 0.66521 | 127.4482 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | PTI | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-22 | Done | Done | 2025-01-23 | Done | 100% | 2025-01-22 | 2025-01-22 | 2025-01-22 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-23 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1151 | 2412-UMIMO-4G#RO-TDE015-0357 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | TDE015 | Protelindo Oba Utara |  |  | TERNATE | 0.72854 | 127.573 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | PTI | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-19 | Done | Done | 2025-01-19 | Done | 100% | 2025-01-19 | 2025-01-19 | 2025-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-19 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 03-Oct-25 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1152 | 2412-UMIMO-4G#RO-TDE055-0398 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU and Module BBU | TDE055 | TBG Guraping Sofifi |  |  | TERNATE | 0.75515 | 127.5883 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TBG | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-20 | Done | Done | 2025-01-20 | Done | 100% | 2025-01-20 | 2025-01-20 | 2025-01-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 22-May-25 | 23-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1153 | 2412-UMIMO-4G#RO-TER001-0359 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add Antenna and Swap RRU | TER001 | DMT Ternate |  |  | TERNATE | 0.79015 | 127.3796 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-28 | Done | Done | 2025-01-28 | Done | 100% | 2025-01-28 | 2025-01-28 | 2025-01-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-12 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 03-Oct-25 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1154 | 2412-UMIMO-4G#RO-TER002-0360 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | TER002 | Airport Ternate |  |  | TERNATE | 0.81712 | 127.3799 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-14 | Done | Done | 2025-01-14 | Done | 100% | 2025-01-14 | 2025-01-14 | 2025-01-14 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-01-14 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-25 | 2025-07-03 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1155 | 2412-UMIMO-4G#RO-TER008-0361 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU | TER008 | DMT Gerai Halo |  |  | TERNATE | 0.79779 | 127.3809 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-24 | Done | Done | 2025-01-25 | Done | 100% | 2025-01-24 | 2025-01-25 | 2025-01-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-04 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 28-Aug-25 | 2025-07-03 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1156 | 2412-UMIMO-4G#RO-TER009-0362 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU and Add Module BBU | TER009 | Jambula Pertamina |  |  | TERNATE | 0.76069 | 127.3174 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-18 | Done | Done | 2025-01-18 | Done | 100% | 2025-01-18 | 2025-01-18 | 2025-01-18 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-13 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 03-Oct-25 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1157 | 2412-UMIMO-4G#RO-TER075-0363 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | TER075 | TBG Tanah Tinggi |  |  | TERNATE | 0.78132 | 127.3788 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TBG | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-14 | Done | Done | 2025-01-14 | Done | 100% | 2025-01-14 | 2025-01-14 | 2025-01-14 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-01-16 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-23 | 2025-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6051 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1158 | 2412-UMIMO-4G#RO-TER128-0364 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU | TER128 | MCR Ngade |  |  | TERNATE | 0.76413 | 127.3538 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-17 | Done | Done | 2025-01-17 | Done | 100% | 2025-01-17 | 2025-01-17 | 2025-01-17 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-12 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 28-Aug-25 | 2025-07-03 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1159 | 2412-UMIMO-4G#RO-TER158-0380 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | TER158 | Jati |  |  | TERNATE | 0.77823 | 127.3761 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-16 | Done | Done | 2025-01-16 | Done | 100% | 2025-01-16 | 2025-01-16 | 2025-01-16 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-13 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 20-May-25 | 21-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6050 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1160 | 2412-UMIMO-4G#RO-THN062-0416 | CAPEX RAN 1B 2025 Acceleration Support Part 3 for Additional RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | THN062 | TBG Dame Siau Timur |  |  | MANADO | 2.7428 | 125.4184 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | TBG | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Sulaiman | Done Productivity 100 % |  |  |  |  | 2025-01-23 | Done | Done | 2025-01-23 | Done | 100% | 2025-01-23 | 2025-01-23 | 2025-01-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-13 | 2025-03-15 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6049 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1161 | 2412-UMIMO-4G#RO-THN080-0367 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Add RRU and Module BBU | THN080 | Mulengen-ACO |  |  | MANADO | 2.368 | 125.4123 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | CMI | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Vendi | Done Productivity 100 % |  |  |  |  | 2025-01-29 | Done | Done | 2025-01-30 | Done | 100% | 2025-01-29 | 2025-01-29 | 2025-01-29 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-03 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-28 | 9-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1162 | 2412-UMIMO-4G#RO-TOB119-0373 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | TOB119 | GURA |  |  | TERNATE | 1.7375 | 128.0031 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-29 | Done | Done | 2025-01-29 | Done | 100% | 2025-01-29 | 2025-01-29 | 2025-01-29 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-01-31 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-11-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1163 | 2412-UMIMO-4G#RO-TOB122-0374 | CAPEX RAN 1B 2025 Acceleration Support Part 2 for RCI Solution | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | TOB122 | Ex Permanenisasi COI212 - Combat Moto Tobelo |  |  | TERNATE | 1.7116 | 128.0105 | YPTT | December-24 |  | 2024 | 2024 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-01-29 | Done | Done | 2025-01-29 | Done | 100% | 2025-01-29 | 2025-01-29 | 2025-01-29 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-01-31 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6052 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1164 | 2501-4GDCS-4G#RO-NTI124-0006 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | NTI124 | TAWALIAN TIMUR |  |  | PARE PARE | -2954 | 119.4182 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-02-15 | Done | Done | 2025-02-15 | Done | 100% | 2025-02-15 | 2025-02-15 | 2025-02-15 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-16 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-13 | 2025-03-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6048 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1165 | 2501-4GDCS-4G#RO-TDK009-0007 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | TDK009 | Desa Kire |  |  | PARE PARE | -2.1341 | 119.1928 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | PTI | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-02-11 | Done | Done | 2025-02-11 | Done | 100% | 2025-02-11 | 2025-02-12 | 2025-02-12 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6053 | 2025-02-25 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1166 | 2501-4GGSM-4G#RO-SRI004-0005 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP New NE 4G LTE 900 10 MHz | Add RRU and Module BBU | SRI004 | TBG Pajala Maginti |  | ALL CLOSE | KENDARI | -4.8443 | 122.3519 | YPTT | February-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9224E M1821 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | TBG | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-02-17 | Done | Done | 2025-02-17 | Done | 100% | 2025-02-17 | 2025-02-17 | 2025-02-17 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-18 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-17 | 2025-03-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6048 | 2025-02-25 | 28-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1167 | 2501-4GGSM-4G#RO-WTG052-0004 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP New NE 4G LTE 900 10 MHz | Swap Antenna and Add RRU and Module BBU | WTG052 | MC Pasar Cabenge |  |  | MAKASSAR | -4.3394 | 119.9623 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | DMT | Release |  |  |  |  | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-02-21 | Done | Done | 2025-02-22 | Done | 100% | 2025-02-21 | 2025-02-22 | 2025-02-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-24 | 2025-07-03 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6098 | 2025-03-06 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1168 | 2501-ADSTR-4G#RO-LBA110-0001 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Add Sector LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU | LBA110 | Smelter Area |  |  | TERNATE | -1.5556 | 127.425 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-02-22 | Done | Done | 2025-02-23 | Done | 100% | 2025-02-22 | 2025-02-23 | 2025-02-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-20 | 2025-03-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6098 | 2025-03-06 | 28-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1169 | 2501-ADSTR-4G#RO-RHA045-0009 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Add Sector LTE 2300 4T4R | Add RRU | RHA045 | TBG Lakandito |  | NY Tag Dismantle | KENDARI | -4.965 | 122.4787 | YPTT | February-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | VEMC4(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | VEMC1(1) | TBG | [5 empty] | YPTT | Aladin | Done Productivity 100 % |  |  |  |  | 2025-02-18 | Done | Done | 2025-02-17 | Done | 100% | 2025-02-18 | 2025-02-19 | 2025-02-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-21 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-24 | 8-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6048 | 2025-02-25 | 16-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1170 | 2501-ADSTR-4G#RO-RHA051-0010 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Module BBU | RHA051 | DMT Raha |  | NY ATP & Ineom | KENDARI | -4.8315 | 122.7209 | YPTT | February-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 1 | 1 | 0 | VBPe1p(1),VBPe3p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | Cabinet(1),BBU(1),CR0(2),CCE1B(2),BPN(4),LPU(1),BFAN5(1),SA(1),PM5(2),FA0(1),DCPD7(1) | DMT | [5 empty] | CV. Puri Tepule Abadi | Aladin | Done Productivity 90 % |  |  |  |  | 2025-02-26 | Done | Done | 2025-02-23 | Done | 100% | 2025-02-26 | 2025-02-26 | 2025-02-26 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-26 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 21-May-25 | 22-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6098 | 2025-03-06 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1171 | 2501-ADSTR-4G#RO-WGI004-0011 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Add Sector LTE 2100 2T2R | Swap RRU and Add Module BBU | WGI004 | TBG Puncak Toliamba |  | NY Tag Dismantle | KENDARI | -5.2939 | 123.5455 | YPTT | February-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8872A S1800(1),R8852E S1800(1) | 2 | No Need Board | TBG | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-02-24 | Done | Done | 2025-02-24 | Done | 100% | 2025-02-24 | 2025-02-24 | 2025-02-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-26 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-26 | 2025-07-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6097 | 2025-03-06 | 2025-03-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1172 | 2501-NNE4G-4G#RO-BAU005-0001 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | BAU005 | DMT Karya Baru |  | ALL CLOSE | KENDARI | -5.4836 | 122.6946 | YPTT | February-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 2 | 0 | 0 | 0 | VBPe1p(1) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Aladin | Done Productivity 100 % |  |  |  |  | 2025-02-27 | Done | Done | 2025-02-25 | Done | 100% | 2025-02-27 | 2025-02-27 | 2025-02-27 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-27 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-03-13 | 2025-03-15 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6124 | 2025-03-10 | 2025-04-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1173 | 2501-UMIMO-4G#RO-BAU025-0005 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | BAU025 | Wanci 2 |  | NY Ineom | KENDARI | -5.3451 | 123.5443 | YPTT | February-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8978 S2300 | 1 | No Need Board | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-02-16 | Done | Done | 2025-02-17 | Done | 100% | 2025-02-16 | 2025-02-17 | 2025-02-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-19 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-03-25 | 2025-03-26 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6048 | 2025-02-25 | 2025-03-18 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1174 | 2501-UMIMO-4G#RO-BAU261-0006 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | BAU261 | DMT Lapandewa Makmur |  | NY Tag Dismantle | KENDARI | -5.6381 | 122.7519 | YPTT | February-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 0 | 0 | VEMC4(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8978 S2300 | 1 | VEMC1(1) | DMT | [5 empty] | CV. Puri Tepule Abadi | Aladin | Done Productivity 100 % |  |  |  |  | 2025-02-28 | Done | Done | 2025-02-26 | Done | 100% | 2025-02-28 | 2025-02-28 | 2025-02-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-02-28 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-10 | 2025-04-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6097 | 2025-03-06 | 2025-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1175 | 2501-UMIMO-4G#RO-COI610-0007 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | COI610 | COMBAT PERUM KOKA ADP |  |  | MANADO | 1.4345 | 124.8543 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | Release |  |  |  |  | CV. Puri Tepule Abadi | Vendi | Done Productivity 100 % |  |  |  |  | 2025-02-15 | Done | Done | 2025-02-15 | Done | 100% | 2025-02-15 | 2025-02-15 | 2025-02-15 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-01-04 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-03 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6048 | 2025-02-25 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1176 | 2501-UMIMO-4G#RO-KDI008-0008 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and module BBU | KDI008 | Wanci |  | ALL CLOSE | KENDARI | -5.3265 | 123.5419 | YPTT | February-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9732 M1821 | 1 | 0 | 0 | 0 | VBPe2q(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-02-14 | Done | Done | 2025-02-14 | Done | 100% | 2025-02-14 | 2025-02-15 | 2025-02-15 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-16 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-08 | 2025-04-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6048 | 2025-02-25 | 7-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1177 | 2501-UMIMO-4G#RO-LBA103-0011 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | LBA103 | MESS HJF - P2 |  |  | TERNATE | -1.5576 | 127.4296 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | HARITA OBI | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-02-23 | Done | Done | 2025-02-24 | Done | 100% | 2025-02-23 | 2025-02-24 | 2025-02-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-26 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-17 | 2025-04-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6098 | 2025-03-06 | 2025-07-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1178 | 2501-UMIMO-4G#RO-LBA108-0012 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | LBA108 | Desa Kawasi 1 |  |  | TERNATE | -1.5409 | 127.4087 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-03-06 | Done | Done | 2025-03-07 | Done | 100% | 2025-03-06 | 2025-03-07 | 2025-03-07 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-03-07 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-17 | 2025-04-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6098 | 2025-03-06 | 28-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1179 | 2501-UMIMO-4G#RO-LBA109-0013 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | LBA109 | Desa Kawasi 2 |  |  | TERNATE | -1.5635 | 127.4151 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-02-26 | Done | Done | 2025-02-27 | Done | 100% | 2025-02-26 | 2025-02-27 | 2025-02-27 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-28 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-04-17 | 2025-04-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6098 | 2025-03-06 | 2025-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1180 | 2501-UMIMO-4G#RO-LBA110-0014 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | LBA110 | Smelter Area |  |  | TERNATE | -1.5556 | 127.425 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-02-22 | Done | Done | 2025-02-23 | Done | 100% | 2025-02-22 | 2025-02-23 | 2025-02-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-17 | 2025-04-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6098 | 2025-03-06 | 28-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1181 | 2501-UMIMO-4G#RO-TDE071-0041 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | TDE071 | Alun Alun Sofifi |  |  | TERNATE | 0.7408 | 127.5696 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | TBG | Release |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-02-18 | Done | Done | 2025-02-18 | Done | 100% | 2025-02-18 | 2025-02-18 | 2025-02-18 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-02-19 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 03-Oct-25 | 2025-03-11 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6098 | 2025-03-06 | 2025-03-26 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1182 | 2501-UMIMO-4G#RO-TER002-0042 | CAPEX RAN 1B 2025 Acceleration Support Part 5 for Capacity Coverage | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | TER002 | AIRPORT TERNATE |  |  | TERNATE | 0.81712 | 127.3799 | YPTT | February-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-02-23 | Done | Done | 2025-02-24 | Done | 100% | 2025-02-23 | 2025-02-24 | 2025-02-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-02-22 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-04-10 | 2025-04-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6097 | 2025-03-06 | 2025-04-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1183 | 2503-4GDCS-4G#RO-COI133-0016 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP New NE 4G LTE 1800 20 Mhz | Add RRU And Swap Module BBU | COI133 | Combat ARR Pelabuhan Lasora Ereke |  | NY Ineom | KENDARI | -4.7836 | 123.1696 | YPTT | March-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9264E M1821 | 2 | 1 | 1 | 0 | VBPe1p(1) | VSWD1(1) | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R8852E S1800 | 2 | Cabinet(1),BBU(1),BFAN5(1),LPU(1),BPN(2),CR0(1),CC16B(1),PM5(2),FA0(1),SA(1),Dummy(4),DCPD7(1) | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Aladin | Done Productivity 100 % |  |  |  |  | 2025-03-26 | Done | Done | 2025-04-10 | Done | 100% | 2025-03-26 | 2025-03-26 | 2025-03-26 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-04-11 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 00-Jan-00 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6244 | 2025-04-18 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 70%
1184 | 2503-4GDCS-4G#RO-COI846-0020 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP New NE 4G LTE 1800 20 Mhz | Add RRU And Swap Module BBU | COI846 | Combat Belang Belang PLTU |  |  | PARE PARE | -2.4721 | 119.1457 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-03-22 | Done | Done | 2025-03-22 | Done | 100% | 2025-03-22 | 2025-03-22 | 2025-03-22 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2025-04-11 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-29 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6242 | 2025-04-17 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1185 | 2503-4GDCS-4G#RO-SSU151-0013 | IAAS JANUARI 2025 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | SSU151 | IAAS IWIP Plant Hydro 2 |  |  | TERNATE | 127.9598 | 127.9598 | YPTT | February-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | CORPORATE | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  | 8330418 | 2026-01-09 | Done | 2026-01-09 | 2026-01-11 | Done | 100% | 2026-01-09 | 2026-01-11 | 2026-01-11 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | passed | 2026-04-26 | Done Tagging | 2026-04-30 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 2025-07-24 | 18 June 2025 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6211 | 2025-04-09 | 2025-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1186 | 2503-4GDCS-4G#RO-SSU152-0014 | IAAS JANUARI 2025 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | SSU152 | IAAS IWIP HF4 |  |  | TERNATE | 127.9394 | 127.9394 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-03-06 | Done | Done | 2025-03-10 | Done | 100% | 2025-03-06 | 2025-03-10 | 2025-03-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-04-10 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 10-May-25 | 23-May-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6211 | 2025-04-09 | 28-May-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1187 | 2503-ADSTR-4G#RO-BAU022-0026 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Add Sector LTE 2300 4T4R | Add RRU | BAU022 | Kelapa Tiga |  | NY Tag Asset Reutilise | KENDARI | -5.2635 | 123.1959 | YPTT | March-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9878 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Aladin | Done Productivity 100 % |  |  |  |  | 2025-03-25 | Done | Done | 2025-03-26 | Done | 100% | 2025-03-25 | 2025-03-26 | 2025-03-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-14 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6242 | 2025-04-17 | 2025-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1188 | 2503-ADSTR-4G#RO-BAU185-0090 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Add Sector LTE 2300 4T4R | Add RRU and Module BBU | BAU185 | DMT MCP Sapatimanjawari |  |  | KENDARI | -5.4698 | 122.5845 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-04-24 | Done | Done | 2025-04-24 | Done | 100% | 2025-04-24 | 2025-04-24 | 2025-04-24 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 22-May-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 13-Aug-25 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6318 | 6-May-25 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1189 | 2503-ADSTR-4G#RO-BAU219-0027 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Add Sector LTE 2300 4T4R | Add RRU and Module BBU | BAU219 | Todanga-DMT |  | NY Ineom | KENDARI | -5.1088 | 122.7916 | YPTT | March-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R8978 S2300 | 1 | 0 | 0 | VEMC4(1) | VBPe1p(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | VEMC1(1) | DMT | [5 empty] | CV. Puri Tepule Abadi | Aladin | Done Productivity 100 % |  |  |  |  | 2025-03-21 | Done | Done | 2025-03-22 | Done | 100% | 2025-03-21 | 2025-03-22 | 2025-03-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 00-Jan-00 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6242 | 2025-04-17 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1190 | 2503-ADSTR-4G#RO-KKA032-0096 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Add Sector LTE 2300 4T4R | Add RRU | KKA032 | Watubangga |  | NY Tag Asset Reutilise | KENDARI | -4.4735 | 121.5079 | YPTT | March-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R8978 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-03-25 | Done | Done | 2025-03-25 | Done | 100% | 2025-03-25 | 2025-03-25 | 2025-03-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-26 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6242 | 2025-04-17 | 2025-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1191 | 2503-ADSTR-4G#RO-KKA257-0039 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Add Sector LTE 2300 4T4R | Add RRU and Module BBU | KKA257 | TBG Anaiwoi Kolaka |  | NY Ineom | KENDARI | -4.3727 | 121.5213 | YPTT | March-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R9614 S2300 | 1 | 0 | 0 | VEMC4(1) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | VEMC1(1) | TBG | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-03-22 | Done | Done | 2025-03-22 | Done | 100% | 2025-03-22 | 2025-03-22 | 2025-03-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-05 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6242 | 2025-04-17 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1192 | 2503-ADSTR-4G#RO-LBA112-0018 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Add Sector LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU | LBA112 | Harita Desa Eco Village |  |  | TERNATE | -1.5909 | 127.4174 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | CORPORATE (HARITA) | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-03-14 | Done | Done | 2025-03-16 | Done | 100% | 2025-03-14 | 2025-03-15 | 2025-03-15 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-15 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-15 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6211 | 2025-04-09 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1193 | 2503-ADSTR-4G#RO-MAM001-0042 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Add Sector LTE 2300 4T4R | Swap Antenna and Add RRU | MAM001 | RNC MAMUJU1 |  |  | PARE PARE | -2.6821 | 118.8838 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-03-19 | Done | Done | 2025-03-19 | Done | 100% | 2025-03-19 | 2025-03-19 | 2025-03-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-29 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6242 | 2025-04-17 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1194 | 2503-ADSTR-4G#RO-MAM006-0098 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Add Sector LTE 2300 4T4R | Add RRU and Module BBU | MAM006 | Tarailu |  |  | PARE PARE | -2.3182 | 119.1747 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-03-23 | Done | Done | 2025-03-23 | Done | 100% | 2025-03-23 | 2025-03-23 | 2025-03-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-24 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-25 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6242 | 2025-04-17 | 2025-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1195 | 2503-ADSTR-4G#RO-RHA016-0021 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Add Sector LTE 2300 4T4R | Add RRU | RHA016 | TBG Pasar Muna |  | NY Ineom | KENDARI | -4.8132 | 122.7311 | YPTT | March-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R8978 S2300 | 1 | 0 | 0 | VEMC4(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | VEMC1(1) | TBG | [5 empty] | CV. Puri Tepule Abadi | Aladin | Done Productivity 100 % |  |  |  |  | 2025-03-14 | Done | Done | 2025-03-13 | Done | 100% | 2025-03-14 | 2025-03-14 | 2025-03-14 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6211 | 2025-04-09 | 2025-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1196 | 2503-ADSTR-4G#RO-SNN006-0079 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Add Sector LTE 2300 4T4R | Add RRU | SNN006 | Waifara |  |  | TERNATE | -2.0445 | 125.9854 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-04-25 | Done | Done | 2025-04-24 | Done | 100% | 2025-04-25 | 2025-04-25 | 2025-04-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-04-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6318 | 6-May-25 | 4-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1197 | 2503-ADSTR-4G#RO-TDE020-0107 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Add Sector LTE 2300 4T4R | Add RRU and module BBU | TDE020 | DMT Kaiyasa |  |  | TERNATE | 0.78089 | 127.6183 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-04-18 | Done | Done | 2025-04-18 | Done | 100% | 2025-04-18 | 2025-04-18 | 2025-04-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-06-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-19 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6272 | 2025-04-26 | 2025-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1198 | 2503-ADSTR-4G#RO-TDE053-0081 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Add Sector LTE 2300 4T4R | Reconfigure RRU with add jumper for add sector | TDE053 | PST MM GOTO TIDORE |  |  | TERNATE | 0.67957 | 127.4521 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | PST | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-03-26 | Done | Done | 2025-03-26 | Done | 100% | 2025-03-26 | 2025-03-26 | 2025-03-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-28 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-06 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6244 | 2025-04-18 | 2025-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1199 | 2503-ADSTR-4G#RO-THN038-0084 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Add Sector LTE 2300 4T4R | Add RRU | THN038 | TBG Dagho Sangir |  |  | MANADO | 3.4414 | 125.5696 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | TBG | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | sulaiman | Done Productivity 100 % |  |  |  |  | 2025-03-26 | Done | Done | 2025-03-27 | Done | 100% | 2025-03-26 | 2025-03-26 | 2025-03-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-28 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-07 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6244 | 2025-04-18 | 2025-09-15 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1200 | 2503-BABSC-2G#RO-BAU003-0006 | RO BSC Merging 2025 | EQP 2G Site Dismantle | BSC Dismantle | BAU003 | BSCZ_PASARWAJO1 |  | Done Dismantle | KENDARI | -5.4949 | 122.8448 | YPTT | July-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-07-20 | Done | Done | 2025-07-20 | Done | 100% | 2025-07-20 | 2025-07-20 | 2025-07-20 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | No Need |  | No Need |  | No Need | Work Not Start | [11 empty] | 2026-01-05 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7409 | 2025-07-30 | 22-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | NEW PO
1201 | 2503-BABSC-2G#RO-BAU007-0005 | RO BSC Merging 2025 | EQP 2G Site Dismantle | BSC Dismantle | BAU007 | BSCZ_BAUBAU1 |  | Done Dismantle | KENDARI | -5.4599 | 122.6176 | YPTT | July-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-07-21 | Done | Done | 2025-07-21 | Done | 100% | 2025-07-21 | 2025-07-21 | 2025-07-21 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | No Need |  | No Need |  | No Need | Work Not Start | [11 empty] | 2026-01-05 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7409 | 2025-07-30 | 22-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | NEW PO
1202 | 2503-NNE4G-4G#RO-KKA008-0018 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | KKA008 | DMT Tolowe Ponrewaru |  | NY Ineom | KENDARI | -3.8399 | 121.3051 | YPTT | March-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R8978 S2300 | 1 | 0 | 0 | VEMC4(1) | VBPe1p(1) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | VEMC1(1) | DMT | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-03-23 | Done | Done | 2025-03-23 | Done | 100% | 2025-03-23 | 2025-03-23 | 2025-03-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 00-Jan-00 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6242 | 2025-04-17 | 2025-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1203 | 2503-NNE4G-4G#RO-KKA035-0008 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | KKA035 | DMT Sopura - Permanenisasi COI581 |  | NY Ineom | KENDARI | -4.2673 | 121.5672 | YPTT | March-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 0 | R8978 S2300 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | DMT | [5 empty] | CV. Puri Tepule Abadi | Herdianto | Done Productivity 100 % |  |  |  |  | 2025-03-12 | Done | Done | 2025-03-12 | Done | 100% | 2025-03-12 | 2025-03-12 | 2025-03-12 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-03-13 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6211 | 2025-04-09 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1204 | 2503-NNE4G-4G#RO-MAM047-0019 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | MAM047 | DMT Salubarana |  |  | PARE PARE | -1.8554 | 119.3821 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-04-09 | Done | Done | 2025-04-09 | Done | 100% | 2025-04-09 | 2025-04-10 | 2025-04-10 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2025-04-10 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-25 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6272 | 2025-04-26 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 90%
1205 | 2503-NNE4G-4G#RO-TDE073-0035 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | TDE073 | TBG Pasigau |  |  | TERNATE | 0.63604 | 127.5406 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | TBG | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-03-29 | Done | Done | 2025-03-29 | Done | 100% | 2025-03-29 | 2025-03-29 | 2025-03-29 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-04-18 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-06 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6244 | 2025-04-18 | 2025-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1206 | 2503-NNE5G-5G#RO-UPD009-0061 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR2300 Makassar Rev | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 64T64R | Add RRU | UPD009 | Hotel Singgasana |  |  | MAKASSAR | -5.1368 | 119.4099 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-04-16 | Done | Done | 2025-04-17 | Done | 100% | 2025-04-16 | 2025-04-17 | 2025-04-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-04-15 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-16 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6272 | 2025-04-26 | 2025-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1207 | 2503-NNE5G-5G#RO-UPD009-0062 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR2300 Makassar Rev | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and add Module BBU | UPD009 | Baji Minasa |  |  | MAKASSAR | -5.1368 | 119.4099 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-04-16 | Done | Done | 2025-04-17 | Done | 100% | 2025-04-16 | 2025-04-17 | 2025-04-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-04-15 |  | Done Tagging |  | Done Tagging | Pending | [11 empty] | 2025-07-25 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6272 | 2025-04-26 | 2025-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1208 | 2503-NNE5G-5G#RO-UPD074-0056 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR2300 Makassar Rev | EQP New 5G NR 2300 30MHz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD074 | Baji Minasa |  |  | MAKASSAR | -5.1672 | 119.4078 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Didik | Done Productivity 100 % |  |  |  |  | 2025-04-12 | Done | Done | 2025-04-13 | Done | 100% | 2025-04-13 | 2025-04-13 | 2025-04-13 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-04-15 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-25 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6272 | 2025-04-26 | 2025-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1209 | 2503-NNE5G-5G#RO-UPD076-0058 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR2300 Makassar Rev | EQP New 5G NR 2300 30MHz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD076 | Hotel Singgasana |  |  | MAKASSAR | -5.1461 | 119.4339 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-04-16 | Done | Done | 2025-04-17 | Done | 100% | 2025-04-16 | 2025-04-16 | 2025-04-16 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-04-15 |  | Done Tagging |  | Done Tagging | Pending | [11 empty] | 2025-07-25 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6272 | 2025-04-26 | 2025-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1210 | 2503-UMIMO-4G#RO-BAU066-0059 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Add module BBU | BAU066 | Protelindo Gu |  | ALL CLOSE | KENDARI | -5.2552 | 122.5767 | YPTT | March-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | No Need RRU | 0 | No Need Board | PTI | [5 empty] | CV. Puri Tepule Abadi | Aladin | Done Productivity 100 % |  |  |  |  | 2025-04-18 | Done | Done | 2025-04-18 | Done | 100% | 2025-04-18 | 2025-04-18 | 2025-04-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-04-19 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-05 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6272 | 2025-04-26 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1211 | 2503-UMIMO-4G#RO-LBA082-0076 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade BW LTE 2100 20 - 20Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | LBA082 | PT. HPAL OBI Harita Konstruksi |  |  | TERNATE | -1.5483 | 127.4195 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | HARITA OBI | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-04-25 | Done | Done | 2025-04-26 | Done | 100% | 2025-04-25 | 2025-04-26 | 2025-04-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | July-26 | Done Tagging | July-26 | Done Tagging | Pending | [11 empty] | 2025-07-25 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6318 | 6-May-25 | 2025-07-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1212 | 2503-UMIMO-4G#RO-LBA109-0077 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade BW LTE 2100 20 - 20Mhz Massive MIMO 32T32R | Add RRU and Module BBU | LBA109 | Desa Kawasi 2 |  |  | TERNATE | -1.5635 | 127.4151 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-04-30 | Done | Done | 2025-04-30 | Done | 100% | 2025-04-30 | 2025-04-30 | 2025-04-30 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 05-May-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-06 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6449 | 22-May-25 | 2025-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1213 | 2503-UMIMO-4G#RO-LBA110-0078 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade BW LTE 2100 20 - 20Mhz Massive MIMO 32T32R | Add RRU and Module BBU | LBA110 | Smelter Area |  |  | TERNATE | -1.5556 | 127.425 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-04-29 | Done | Done | 2025-04-29 | Done | 100% | 2025-04-29 | 2025-04-29 | 2025-04-29 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 02-May-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-06 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6449 | 22-May-25 | 2025-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1214 | 2503-UMIMO-4G#RO-LBA119-0079 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | LBA119 | Mess DCM |  |  | TERNATE | -1.553 | 127.4293 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | CORPORATE (HARITA) | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-04-28 | Done | Done | 2025-04-28 | Done | 100% | 2025-04-28 | 2025-04-28 | 2025-04-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-04-28 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 06-Aug-25 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6318 | 6-May-25 | 2025-07-14 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1215 | 2503-UMIMO-4G#RO-PSW001-0068 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | PSW001 | DMT MH Pasar Ambuau |  | NY Ineom | KENDARI | -5.3176 | 123.1687 | YPTT | March-25 |  | 2025 | 2025 |  |  | No Need Antena | 0 | 1 | A9652A | 1 | 0 | 0 | VEMC4(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | No Need Antena | 0 | 0 | No Need | 0 | R9614 S23 | 1 | VEMC1(1) | DMT | [5 empty] | CV. Puri Tepule Abadi | Aladin | Done Productivity 100 % |  |  |  |  | 2025-03-22 | Done | Done | 2025-03-23 | Done | 100% | 2025-03-22 | 2025-03-23 | 2025-03-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-03-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-24 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6242 | 2025-04-17 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1216 | 2503-UMIMO-4G#RO-SSU002-0095 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU002 | Permanenisasi COI264 - Combat Sagea |  |  | TERNATE | 0.46479 | 128.0969 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | ahmad | Done Productivity 100 % |  |  |  |  | 03-May-25 | Done | Done | 05-May-25 | Done | 100% | 04-May-25 | 04-May-25 | 05-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 06-May-25 |  | Done Tagging |  | Done Tagging | Pending | [11 empty] | 06-Aug-25 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6448 | 22-May-25 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1217 | 2503-UMIMO-4G#RO-SSU002-0096 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU | SSU002 | Permanenisasi COI264 - Combat Sagea |  |  | TERNATE | 0.46479 | 128.0969 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | ahmad | Done Productivity 100 % |  |  |  |  | 03-May-25 | Done | Done | 05-May-25 | Done | 100% | 04-May-25 | 04-May-25 | 05-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 06-May-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 06-Aug-25 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6448 | 22-May-25 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1218 | 2503-UMIMO-4G#RO-SSU004-0097 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU004 | Permanenisasi COI395 - Combat ARR Split Lelilef 1 |  |  | TERNATE | 0.4684 | 127.9324 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 11-May-25 | Done | Done | 14-May-25 | Done | 100% | 11-May-25 | 11-May-25 | 14-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 15-May-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-06-08 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6447 | 22-May-25 | 2025-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1219 | 2503-UMIMO-4G#RO-SSU020-0098 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU020 | DMT Lelilef Sawai |  |  | TERNATE | 0.47054 | 127.9342 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | ahmad | Done Productivity 100 % |  |  |  |  | 10-May-25 | Done | Done | 16-May-25 | Done | 100% | 10-May-25 | 10-May-25 | 16-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 10-May-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-06-14 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6513 | 29-May-25 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1220 | 2503-UMIMO-4G#RO-SSU020-0099 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU | SSU020 | DMT Lelilef Sawai |  |  | TERNATE | 0.47054 | 127.9342 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | ahmad | Done Productivity 100 % |  |  |  |  | 10-May-25 | Done | Done | 16-May-25 | Done | 100% | 10-May-25 | 10-May-25 | 16-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 10-May-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-06-14 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6513 | 29-May-25 | 2025-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1221 | 2503-UMIMO-4G#RO-SSU081-0100 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU081 | Camp 2 |  |  | TERNATE | 0.5044 | 127.8993 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | IWIP | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 11-May-25 | Done | Done | 14-May-25 | Done | 100% | 11-May-25 | 14-May-25 | 14-May-25 | Connected | Connected |  | 03-NY SM | 01-Passed | Passed | 2025-06-19 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 00-Jan-00 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6447 | 22-May-25 | 2025-07-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1222 | 2503-UMIMO-4G#RO-SSU081-0101 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU | SSU081 | Camp 2 |  |  | TERNATE | 0.5044 | 127.8993 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | IWIP | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 11-May-25 | Done | Done | 14-May-25 | Done | 100% | 11-May-25 | 14-May-25 | 14-May-25 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2025-06-19 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 00-Jan-00 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6447 | 22-May-25 | 2025-07-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1223 | 2503-UMIMO-4G#RO-SSU082-0102 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU082 | Permanenisasi COI166 - COMBAT LELILEF |  |  | TERNATE | 0.46647 | 127.9296 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | ahmad | Done Productivity 100 % |  |  |  |  | 11-May-25 | Done | Done | 14-May-25 | Done | 100% | 11-May-25 | 14-May-25 | 14-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 14-May-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-06-12 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6447 | 22-May-25 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1224 | 2503-UMIMO-4G#RO-SSU084-0103 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU084 | Iaas PPA_HSM Office |  |  | TERNATE | 0.61349 | 127.9462 | YPTT | July-25 |  | 2025 | 2025 | [28 empty] | PT. PPA | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-06-29 | Done | Done | 2025-06-30 | Done | 100% | 2025-06-29 | 2025-06-30 | 2025-06-30 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | 2026-07-21 | Done Tagging | 2026-07-21 | Done Tagging | Done Tagging | [11 empty] | 2025-07-16 | 2025-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7439 | 1-Aug-25 | 4-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1225 | 2503-UMIMO-4G#RO-SSU103-0104 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade BW LTE 2100 20 - 20Mhz Massive MIMO 32T32R | Add RRU and Module BBU | SSU103 | HF 1 |  |  | TERNATE | 0.4711 | 127.9444 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | IWIP | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 24-May-25 | Done | Done | 2025-06-01 | Done | 100% | 30-May-25 | 2025-06-01 | 2025-06-01 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | 2026-07-19 | Done Tagging | 2026-07-19 | Done Tagging | Work Not Start | [11 empty] | 2025-06-14 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6870 | 2025-06-30 | 7-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1226 | 2503-UMIMO-4G#RO-SSU103-0105 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade BW LTE 2100 20 - 20Mhz Massive MIMO 32T32R | Add RRU | SSU103 | HF 1 |  |  | TERNATE | 0.4711 | 127.9444 | YPTT | March-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | IWIP | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  | 8342895 | 2026-01-03 | Done | 2026-01-03 | 2026-01-05 | Done | 100% | 2026-01-03 | 2026-01-05 | 2026-01-05 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | passed | May-26 | Done Tagging | 23-May-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 2025-06-14 | 16 June 2025 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6870 | 2025-06-30 | 7-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1227 | 2503-UMIMO-4G#RO-SSU112-0106 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade BW LTE 2100 20 - 20Mhz Massive MIMO 32T32R | Add RRU and Module BBU | SSU112 | IWIP Mess KM15 |  |  | TERNATE | 0.51186 | 127.9028 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-07-02 | Done | Done | 2025-07-06 | Done | 100% | 2025-07-02 | 2025-07-04 | 2025-07-04 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-07-05 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-14 | 2025-07-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7439 | 1-Aug-25 | 27-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1228 | 2503-UMIMO-4G#RO-SSU112-0107 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade BW LTE 2100 20 - 20Mhz Massive MIMO 32T32R | Add RRU | SSU112 | IWIP Mess KM15 |  |  | TERNATE | 0.51186 | 127.9028 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-07-02 | Done | Done | 2025-07-06 | Done | 100% | 2025-07-02 | 2025-07-04 | 2025-07-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-07-05 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-07-14 | 2025-07-15 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7439 | 1-Aug-25 | 27-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1229 | 2503-UMIMO-4G#RO-SSU125-0109 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade BW LTE 2100 20 - 20Mhz Massive MIMO 32T32R | Add RRU and Module BBU | SSU125 | IWIP Plant Hydro |  |  | TERNATE | 0.4812 | 127.956 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | IWIP | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-06-04 | Done | Done | 2025-06-09 | Done | 100% | 2025-06-04 | 2025-06-04 | 2025-06-04 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2025-07-02 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 00-Jan-00 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6870 | 2025-06-30 | 4-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 70%
1230 | 2503-UMIMO-4G#RO-SSU136-0071 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | SSU136 | Weda City |  |  | TERNATE | 0.33054 | 127.8768 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | TBG | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-03-29 | Done | Done | 2025-03-29 | Done | 100% | 2025-03-29 | 2025-03-29 | 2025-03-29 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-04-20 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-25 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6244 | 2025-04-18 | 2025-06-27 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1231 | 2503-UMIMO-4G#RO-SSU138-0072 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | SSU138 | Perumahan Fidi Jaya |  |  | TERNATE | 0.33879 | 127.871 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | TBG | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-03-29 | Done | Done | 2025-03-29 | Done | 100% | 2025-03-29 | 2025-03-29 | 2025-03-29 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-04-20 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-17 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6244 | 2025-04-18 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1232 | 2503-UMIMO-4G#RO-TDE003-0073 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | TDE003 | Gurabati |  |  | TERNATE | 0.62706 | 127.4205 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-03-26 | Done | Done | 2025-03-27 | Done | 100% | 2025-03-26 | 2025-03-27 | 2025-03-27 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | 2025-03-27 | Done Tagging | 2025-03-27 | Done Tagging | Work Not Start | [11 empty] | 2025-07-25 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6244 | 2025-04-18 | 2025-06-28 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1233 | 2503-UMIMO-4G#RO-TER083-0112 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | TER083 | Protelindo Gambesi |  |  | TERNATE | 0.75791 | 127.3406 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | PTI | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-04-13 | Done | Done | 2025-04-13 | Done | 100% | 2025-04-13 | 2025-04-13 | 2025-04-13 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | 2025-04-13 | Done Tagging | 2025-04-13 | Done Tagging | Work Not Start | [11 empty] | 2025-07-26 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6272 | 2025-04-26 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1234 | 2503-UMIMO-4G#RO-THN025-0074 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | THN025 | Tamako Raya |  |  | MANADO | 3.4525 | 125.5046 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Sulaiman | Done Productivity 90 % |  |  |  |  | 2025-03-28 | Done | Done | 2025-03-29 | Done | 100% | 2025-03-28 | 2025-03-29 | 2025-03-29 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-04-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-07 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6244 | 2025-04-18 | 2025-06-19 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1235 | 2503-UMIMO-4G#RO-THN070-0113 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | THN070 | MC Raramenusa |  |  | MANADO | 3.6088 | 125.4883 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | DMT | Done request CAF ZTE |  |  |  |  | CV. Puri Tepule Abadi | Vendi | Done Productivity 100 % |  |  |  |  | 2025-04-04 | Done | Done | 2025-04-05 | Done | 100% | 2025-04-04 | 2025-04-04 | 2025-04-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-04-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-02-19 | 2025-02-20 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6244 | 2025-04-18 | 2025-06-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1236 | 2503-UPBWL-4G#RO-LBA103-0001 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade BW LTE 2100 20 - 20Mhz Massive MIMO 32T32R | Add RRU and Module BBU | LBA103 | Mess HJF - P2 |  |  | TERNATE | -1.5576 | 127.4296 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | HARITA OBI | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-03-13 | Done | Done | 2025-03-13 | Done | 100% | 2025-03-13 | 2025-03-13 | 2025-03-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | 2025-03-13 | Done Tagging | 2025-03-13 | Done Tagging | No Need | [11 empty] | 2025-06-12 | 2025-06-16 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6211 | 2025-04-09 | 2025-07-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1237 | 2503-UPBWL-4G#RO-SSU117-0002 | CAPEX RAN 2 2025 Acceleration Support Part 3 for Capacity | EQP Upgrade BW LTE 2100 20 - 20Mhz Massive MIMO 32T32R | Add RRU and Module BBU | SSU117 | Main office IWIP |  |  | TERNATE | 0.48171 | 127.9853 | YPTT | March-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-03-14 | Done | Done | 2025-03-14 | Done | 100% | 2025-03-14 | 2025-03-14 | 2025-03-14 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | 2025-03-14 | Done Tagging | 2025-03-14 | Done Tagging | No Need | [11 empty] | 2025-06-28 | 2025-06-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6211 | 2025-04-09 | 2025-07-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1238 | 2504-4GDCS-4G#RO-SSU153-0024 | RO New Infra IWIP 2025 | EQP New NE 4G LTE 1800 20 Mhz 4T4R | New Infra | SSU153 | Apartemen TJ Ulie |  |  | TERNATE | 0.47988 | 127.9805 | YPTT | May-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 08-May-25 | Done | Done | 17-May-25 | Done | 100% | 08-May-25 | 16-May-25 | 25-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | 2025-03-14 | Done Tagging | 2025-03-14 | Done Tagging | Work Not Start | Work Not Start | Work Not Start | Work Not Start | [8 empty] | 2025-11-18 | 2025-11-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6768 | 2025-06-21 | 2025-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1239 | 2504-4GGSM-4G#950-NTI074-0006 | CAPEX RAN OBLIGASI DESA BLANK SPOT 2025 | EQP New NE 4G LTE 900 10 Mhz | Add Antenna, RRU and Module BBU | NTI074 | DMT N3T Tanjung Pinang Kusambi- |  | HI DONE,NY OA | KENDARI | -4.7103 | 122537906 | YPTT | July-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 90 % |  |  |  |  | 2025-07-22 | Done | Done | 30-Aug-25 | Done | 100% | 2025-07-22 | 2025-07-23 | 2025-11-11 | Connected | Connected |  | 03-NY SM | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-07-07 | 2025-07-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | NEW PO
1240 | 2504-4GGSM-4G#RO-SSU153-0009 | RO New Infra IWIP 2025 | EQP New NE 4G LTE 900 10 Mhz 4T4R | Add RRU | SSU153 | Apartemen TJ Ulie |  |  | TERNATE | 0.47988 | 127.9805 | YPTT | May-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 08-May-25 | Done | Done | 17-May-25 | Done | 100% | 08-May-25 | 16-May-25 | 25-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | 2025-03-14 | Done Tagging | 2025-03-14 | Done Tagging | Work Not Start | Work Not Start | Work Not Start | Work Not Start | [8 empty] | 2025-11-18 | 2025-11-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6768 | 2025-06-21 | 2025-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1241 | 2504-ADSTR-4G#RO-THN079-0181 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR700 IWIP & Presales Acceleration Support RCI W8 Solving Opportunistic Sulawesi | EQP Add Sector LTE 2300 4T4R | Swap RRU, BTS and Add RRU | THN079 | MCR Tagulandang |  |  | MANADO | 2.344 | 125.3798 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Vendi | Done Productivity 100 % |  |  |  |  | 2025-04-26 | Done | Done | 2025-04-30 | Done | 100% | 2025-04-26 | 2025-04-29 | 2025-04-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 13-May-24 |  | Done Tagging |  | Done Tagging | Pending | [11 empty] | 25-Aug-25 | 27-Aug-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6318 | 6-May-25 | 2025-09-15 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1242 | 2504-NNE4G-4G#RO-COI112-0109 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR700 IWIP & Presales Acceleration Support RCI W8 Solving Opportunistic Sulawesi | EQP New 5G NR 2300 30MHz Massive MIMO 32T32R | Swap RRU and Swap Module BBU | COI112 | CombatARRKatubiri |  |  | MAKASSAR | -5.1461 | 119.4339 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Kurniadi | Done Productivity 100 % |  |  |  |  | 2025-04-28 | Done | Done | 2025-04-29 | Done | 100% | 2025-04-28 | 2025-04-29 | 2025-04-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | Passed | 2026-07-11 | Done Tagging | 2026-07-11 | Done Tagging | Pending | [11 empty] | 00-Jan-00 | 0-Jan-00 | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-6318 | 6-May-25 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 70%
1243 | 2504-NNE4G-4G#RO-SSU153-0111 | RO New Infra IWIP 2025 | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 32T32R | Add RRU | SSU153 | Apartemen TJ Ulie |  |  | TERNATE | 0.47988 | 127.9805 | YPTT | May-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 22-May-25 | Done | Done | 17-May-25 | Done | 100% | 24-May-25 | 25-May-25 | 25-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | 2026-07-13 | Done Tagging | 2026-07-13 | Done Tagging | Work Not Start | Work Not Start | Work Not Start | Work Not Start | [8 empty] | 2025-11-18 | 2025-11-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6768 | 2025-06-21 | 2025-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1244 | 2504-NNE5G-5G#RO-SSU081-0095 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR700 IWIP & Presales Acceleration Support RCI W8 Solving Opportunistic Sulawesi | EQP New NE 5G NR 700 20 Mhz | Swap Antenna and RRU | SSU081 | CAMP 2 |  |  | TERNATE | 0.5044 | 127.8993 | YPTT | 2026-04-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | IWIP | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  | 2267168 | 2026-01-21 | Done | 2026-01-21 | 2026-01-23 | Done | 100% | 2026-01-21 | 2026-01-23 | 2026-01-23 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  |  | 17 December 2025 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6449 | 22-May-25 | 22-Dec-25 | 01-BAUT Approved by Tsel | 13-Wait AS Doc Complete | Done Upload | Invoiced 70%
1245 | 2504-NNE5G-5G#RO-SSU106-0098 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR700 IWIP & Presales Acceleration Support RCI W8 Solving Opportunistic Sulawesi | EQP New NE 5G NR 700 20 Mhz | Swap Antenna and RRU and Add Module BBU | SSU106 | AKOMODASI H |  |  | TERNATE | 0.4915 | 127.9883 | YPTT | 2026-04-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | IWIP | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  | 5502814 | 2026-01-20 | Done | 2026-01-20 | 2026-01-22 | Done | 100% | 2026-01-20 | 2026-01-22 | 2026-01-22 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 2025-11-27 | 2025-11-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6449 | 22-May-25 | 2025-11-29 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 70%
1246 | 2504-NNE5G-5G#RO-SSU113-0100 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR700 IWIP & Presales Acceleration Support RCI W8 Solving Opportunistic Sulawesi | EQP New NE 5G NR 700 20 Mhz | Swap Antenna and RRU and Add Module BBU | SSU113 | KLINIK IWIP |  |  | TERNATE | 0.48362 | 127.9754 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | CORPORATE (IMIP) | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-04-27 | Done | Done | 2025-04-28 | Done | 100% | 2025-04-27 | 2025-04-28 | 2025-04-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-07-16 | Done Tagging | 2026-07-16 | Done Tagging | Pending | [11 empty] | 10-Oct-25 | 10-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6318 | 6-May-25 | 2025-11-29 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 70%
1247 | 2504-NNE5G-5G#RO-SSU117-0101 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR700 IWIP & Presales Acceleration Support RCI W8 Solving Opportunistic Sulawesi | EQP New NE 5G NR 700 20 Mhz | Swap Antenna and RRU | SSU117 | MAIN OFFICE IWIP |  |  | TERNATE | 0.48171 | 127.9853 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  |  | 2025-04-24 | Done | Done | 2025-04-24 | Done | 100% | 2025-04-24 | 2025-04-25 | 2025-04-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-07-18 | Done Tagging | 2026-07-18 | Done Tagging | Pending | [11 empty] | 2026-02-06 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6280 | 1-May-25 | 22-Dec-25 | 01-BAUT Approved by Tsel | 13-Wait AS Doc Complete | Done Upload | Invoiced 70%
1248 | 2504-NNE5G-5G#RO-SSU120-0102 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR700 IWIP & Presales Acceleration Support RCI W8 Solving Opportunistic Sulawesi | EQP New NE 5G NR 700 20 Mhz | Swap Antenna and Add RRU and Module BBU | SSU120 | IWIPAkomodasiP2 |  |  | TERNATE | 0.4794 | 128.0152 | YPTT | 2026-04-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | IWIP | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  | 5149440 | 2026-01-13 | Done | 2026-01-13 | 2026-01-15 | Done | 100% | 2026-01-13 | 2026-01-15 | 2026-01-15 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 2025-11-27 | 2025-11-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6449 | 22-May-25 | 18-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 70%
1249 | 2504-NNE5G-5G#RO-SSU127-0108 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR700 IWIP & Presales Acceleration Support RCI W8 Solving Opportunistic Sulawesi | EQP New NE 5G NR 700 20 Mhz | Swap Antenna and Add RRU and Module BBU | SSU127 | IWIP PLTU-4 |  |  | TERNATE | 0.47893 | 128.0116 | YPTT | 2026-04-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | CORPORATE | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | Done Productivity 100 % |  |  |  | 5149440 | 2026-01-15 | Done | 2026-01-15 | 2026-01-17 | Done | 100% | 2026-01-15 | 2026-01-17 | 2026-01-17 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 2025-11-27 | 2025-11-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6449 | 22-May-25 | 2026-02-09 | 01-BAUT Approved by Tsel | 14-Wait Document Complete | Done Upload | Invoiced 70%
1250 | 2504-UMIMO-4G#RO-BAU221-0284 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR700 IWIP & Presales Acceleration Support RCI W8 Solving Opportunistic Sulawesi | EQP Upgrade LTE 2300 Massive MIMO 64T64R impact New NE | Swap RRU | BAU221 | BMT LASALIMU |  | Need Add Board | KENDARI | -5.2585 | 123.1527 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Invoiced 100% |  |  |  |  | 2025-04-27 | Done | Done | 02-May-25 | Done | 100% | 2025-04-27 | 2025-04-27 | 2025-04-27 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 23-May-25 |  | Done Tagging |  | Done Tagging | Pending | [11 empty] | 17-Dec-25 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6449 | 22-May-25 | 22-Dec-25 | 01-BAUT Approved by Tsel | 13-Wait AS Doc Complete | Done Upload | Invoiced 70%
1251 | 2504-UMIMO-4G#RO-COI397-0285 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR700 IWIP & Presales Acceleration Support RCI W8 Solving Opportunistic Sulawesi | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and swap RRU | COI397 | Combat ARR Split Lelilef2-Ex-COC164 |  |  | TERNATE | 0.46979 | 127.9379 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | ahmad | Invoiced 100% |  |  |  |  | 2025-04-29 | Done | Done | 05-May-25 | Done | 100% | 2025-04-29 | 02-May-25 | 05-May-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 02-May-25 |  | Done Tagging |  | Done Tagging | Pending | [11 empty] | 25-Aug-25 | 27-Aug-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6448 | 22-May-25 | 7-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1252 | 2504-UMIMO-4G#RO-TER077-0286 | Activity Non MPSL_R09 Sulawesi_2025_MKT 5G NR700 IWIP & Presales Acceleration Support RCI W8 Solving Opportunistic Sulawesi | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and swap RRU | TER077 | TBG RSUD Ternate |  |  | TERNATE | 0.78307 | 127.3717 | YPTT | 2026-04-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Invoiced 100% |  |  |  |  | 03-May-25 | Done | Done | 2025-04-30 | Done | 100% | 03-May-25 | 03-May-25 | 2025-04-30 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 08-May-25 |  | Done Tagging |  | Done Tagging | Pending | [11 empty] | 25-Aug-25 | 27-Aug-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6449 | 22-May-25 | 2025-09-15 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1253 | 2505-4GDCS-4G#RO-BAU031-0030 | Risk Order New Infra Batch #1 2025 | EQP New NE 4G LTE 1800 20 Mhz | Add Antenna and RRU and Module BBU (New Infra) | BAU031 | TBG RSUD Bau Bau |  | NY ATP & Ineom | KENDARI | -5.484 | 122.5944 | YPTT | July-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-07-27 | Done | Done | 2025-07-17 | Done | 100% | 2025-07-27 | 2025-07-29 | 2025-07-29 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start | 2025-11-12 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-11-07 | 2025-11-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 | 2025-11-19 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1254 | 2505-4GDCS-4G#RO-BAU033-0031 | Risk Order New Infra Batch #1 2025 | EQP New NE 4G LTE 1800 20 Mhz | Add Antenna, RRU and Module BBU | BAU033 | Permanenisasi_COI457 |  | NY ATP & Ineom | KENDARI | -5.4961 | 122.5718 | YPTT | July-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-07-24 | Done | Done | 2025-07-07 | Done | 100% | 2025-07-24 | 2025-07-31 | 2025-07-31 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start | 18-Aug-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-11-10 | 2025-11-10 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7409 | 2025-07-30 | 18-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1255 | 2505-4GDCS-4G#RO-KKA043-0028 | Risk Order New Infra Batch #1 2025 | EQP New NE 4G LTE 1800 20 Mhz | New Infra + Dismentel RRU Donor | KKA043 | Permanenisasi_COI245 |  |  | KENDARI | -4.08 | 121.611 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | TBD | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-30 | Done | Done | 2025-09-30 | Done | 100% | 2025-09-30 | 2025-09-30 | 01-Oct-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 10-Oct-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-11-14 | 2025-11-14 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 | 2025-11-29 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1256 | 2505-4GDCS-4G#RO-WGU016-0049 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | WGU016 | DMT NON 3T MOROMBO PANTAI |  |  | KENDARI | -3.368757° | 122.246019° | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-06-12 | Done | Done | 2025-06-12 | Done | 100% | 2025-06-12 | 2025-06-12 | 2025-06-12 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-06-13 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-24 | 0-Jan-00 | 06-eATP Wait eOA | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 90%
1257 | 2505-4GGSM-4G#RO-JLO007-0013 | Risk Order New Infra Batch #1 2025 | EQP New NE 4G LTE 900 10 Mhz | New Infra | JLO007 | Permanenisasi_TER032 |  |  | TERNATE | 1.6721 | 127.5868 | YPTT | July-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-07-07 | Done | Done | 2025-07-08 | Done | 100% | 2025-07-07 | 2025-07-08 | 05-Aug-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 05-Aug-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-09-21 | 2025-09-22 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7409 | 2025-07-30 | 21-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1258 | 2505-4GGSM-4G#RO-PSW002-0018 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP eNode B Modular Relocation Service New NE LTE 900 | Swap antenna and add module BBU | PSW002 | KAMELANTA-DMT |  |  | KENDARI | -5.283 | 122.7079 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-06-25 | Done | Done | 2025-06-26 | Done | 100% | 2025-06-25 | 2025-06-26 | 2025-06-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-07-16 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 07-Aug-25 | 8-Aug-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 15-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1259 | 2505-ADSTR-4G#RO-BAU015-0215 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP eNode B Modular Relocation Service | Swap Antenna and Add RRU | BAU015 | LASALIMU |  |  | KENDARI | -5.1624 | 123.0602 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-07-01 | Done | Done | 2025-07-02 | Done | 100% | 2025-07-01 | 2025-07-02 | 2025-07-02 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 05-Aug-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 12-Aug-25 | 12-Aug-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7439 | 1-Aug-25 | 19-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1260 | 2505-ADSTR-4G#RO-BAU023-0213 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP eNode B Modular Relocation Service New NE LTE 2300 | Swap Antenna and Add RRU | BAU023 | SIOTAPINA |  |  | KENDARI | -5.4178 | 123.0667 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-07-02 | Done | Done | 2025-07-03 | Done | 100% | 2025-07-02 | 2025-07-03 | 2025-07-03 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 04-Aug-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 11-Aug-25 | 11-Aug-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7439 | 1-Aug-25 | 15-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1261 | 2505-ADSTR-4G#RO-COI246-0200 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Add Sector LTE 2300 4T4R | Add RRU and module BBU | COI246 | COMBAT FUN BURANGASI KONTU |  |  | KENDARI | -5.7766 | 123.9341 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-06-18 | Done | Done | 2025-06-18 | Done | 100% | 2025-06-18 | 2025-06-19 | 2025-06-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-07-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-07-20 | 2025-07-21 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 2025-07-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1262 | 2505-ADSTR-4G#RO-COI395-0190 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Add Sector LTE 2100 2T2R | add RRU | COI395 | Combat ARR Split Lelilef 1 |  |  | TERNATE | 0.46816 | 127.9329 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-07-10 | Done | Done | 2025-07-13 | Done | 100% | 2025-07-12 | 2025-07-13 | 2025-07-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-07-14 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-07-27 | 2025-07-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7555 | 18-Aug-25 | 27-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1263 | 2505-ADSTR-4G#RO-MAM109-0212 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Add Sector LTE 2300 4T4R | Add RRU and Module BBU | MAM109 | Paraili-DMT |  |  | PARE PARE | -2.0495 | 119.2535 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Narfin | Done Productivity 100 % |  |  |  |  | 2025-06-22 | Done | Done | 2025-06-23 | Done | 100% | 2025-06-22 | 2025-06-22 | 2025-06-23 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-06-23 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-30 | 2025-07-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7439 | 1-Aug-25 | 2025-07-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1264 | 2505-ADSTR-4G#RO-MBA002-0187 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Add Sector LTE 1800 2T2R | Add RRU | MBA002 | Buli |  |  | TERNATE | 0.88251 | 128.2944 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-06-21 | Done | Done | 2025-06-21 | Done | 100% | 2025-06-21 | 2025-06-21 | 2025-06-21 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-07-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-27 | 2025-07-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7439 | 1-Aug-25 | 27-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1265 | 2505-ADSTR-4G#RO-MBA021-0201 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap module BBU | MBA021 | DMT ISAT Subaim |  |  | TERNATE | 1.0946 | 128.1837 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | DMT ISAT | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-07-10 | Done | Done | 2025-07-11 | Done | 100% | 2025-07-10 | 2025-07-11 | 2025-07-11 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-07-13 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 20-Aug-25 | 21-Aug-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7555 | 18-Aug-25 | 7-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1266 | 2505-ADSTR-4G#RO-SKG052-0193 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Add Sector LTE 2100 2T2R | Add RRU and Swap module BBU | SKG052 | DELTACOMSEL CEMPALAGI |  |  | MAKASSAR | -412532 | 12005252 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Narfin | Done Productivity 100 % |  |  |  |  | 2025-06-12 | Done | Done | 2025-06-13 | Done | 100% | 2025-06-12 | 2025-06-13 | 2025-06-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-06-16 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-31 | 2025-07-31 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 15-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1267 | 2505-ADSTR-4G#RO-WGU016-0194 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Add Sector LTE 2100 2T2R | Add RRU | WGU016 | DMT NON 3T MOROMBO PANTAI |  |  | KENDARI | -3.368757° | 122.246019° | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-06-12 | Done | Done | 2025-06-12 | Done | 100% | 2025-06-12 | 2025-06-12 | 2025-06-12 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-06-13 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-24 | 2025-07-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 70%
1268 | 2505-NNE4G-4G#RO-ADL026-0113 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP eNode B Modular Relocation Service New NE LTE 2300 | Add RRU and Swap Antenna | ADL026 | DMT BONDOALA |  |  | KENDARI | -3.8964 | 122.4633 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-06-27 | Done | Done | 2025-06-28 | Done | 100% | 2025-06-27 | 2025-06-28 | 2025-06-28 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-06-28 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 08-Aug-25 | 11-Aug-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7439 | 1-Aug-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 90%
1269 | 2505-NNE4G-4G#RO-SKG165-0134 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP New NE 4G LTE 2300 50 Mhz | Reconfigure RRU with add jumper for add sector | SKG165 | TBG TAWAROE MAKMUR |  |  | MAKASSAR | -402108 | 12028092 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Narfin | Done Productivity 100 % |  |  |  |  | 2025-06-09 | Done | Done | 2025-06-11 | Done | 100% | 2025-06-09 | 2025-06-09 | 2025-06-09 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 2025-06-12 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-30 | 2025-07-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 2025-07-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1270 | 2505-REENG-4G#RO-BAU031-0004 | Risk Order New Infra Batch #1 2025 | EQP eNode B Modular Relocation Service New NELTE 2100 | Add RRU | BAU031 | TBG RSUD Bau Bau |  | OG | KENDARI | -5.484 | 122.5944 | YPTT | July-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 20-Aug-25 | Done | Done | 2025-07-17 | Done | 100% | 20-Aug-25 | 22-Aug-25 | 22-Aug-25 | Connected | Connected |  | 03-NY SM | 01-Passed | Work Not Start |  |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-11-12 | 2025-11-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 | 2025-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | NEW PO
1271 | 2505-REENG-4G#RO-BAU031-0014 | Risk Order New Infra Batch #1 2025 | EQP eNode B Modular Relocation Service New NELTE 900 | Add RRU | BAU031 | TBG RSUD Bau Bau |  | OG | KENDARI | -5.484 | 122.5944 | YPTT | July-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 20-Aug-25 | Done | Done | 2025-07-17 | Done | 100% | 20-Aug-25 | 22-Aug-25 | 22-Aug-25 | Connected | Connected |  | 03-NY SM | 01-Passed | Work Not Start |  |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-11-14 | 2025-11-14 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 | 2025-11-29 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | NEW PO
1272 | 2505-REENG-4G#RO-KKA043-0007 | Risk Order New Infra Batch #1 2025 | EQP New NE 4G LTE 2100 20 Mhz | Add RRU | KKA043 | Permanenisasi_COI245 |  |  | KENDARI | -4.08 | 121.611 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | TBD | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-30 | Done | Done | 2025-09-30 | Done | 100% | 2025-09-30 | 2025-09-30 | 01-Oct-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 10-Oct-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-11-14 | 2025-11-14 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 | 2025-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1273 | 2505-REENG-4G#RO-KKA043-0016 | Risk Order New Infra Batch #1 2025 | EQP New NE 4G LTE 900 10 Mhz | Add RRU | KKA043 | Permanenisasi_COI245 |  |  | KENDARI | -4.08 | 121.611 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | TBD | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-30 | Done | Done | 2025-09-30 | Done | 100% | 2025-09-30 | 2025-09-30 | 01-Oct-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 10-Oct-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-11-13 | 2025-11-13 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 | 2025-11-29 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1274 | 2505-REENG-4G#RO-KKA043-0022 | Risk Order New Infra Batch #1 2025 | EQP New NE 4G LTE2300 50 Mhz 4T4R | Add RRU and Module BBU | KKA043 | Permanenisasi_COI245 |  |  | KENDARI | -4.08 | 121.611 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | TBD | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-30 | Done | Done | 2025-09-30 | Done | 100% | 2025-09-30 | 2025-09-30 | 01-Oct-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 10-Oct-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-11-13 | 2025-11-13 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 | 2025-11-27 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1275 | 2505-UMIMO-4G#RO-BAU008-0288 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU RRU and Add Module BBU | BAU008 | LOMBE |  |  | KENDARI | -5.247 | 122.5768 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-06-19 | Done | Done | 2025-06-20 | Done | 100% | 2025-06-19 | 2025-06-20 | 2025-06-20 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-06-21 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-23 | 2025-07-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 2025-07-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1276 | 2505-UMIMO-4G#RO-BAU035-0289 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU | BAU035 | MATUNGGA |  |  | KENDARI | -5.4004 | 122.4539 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-06-18 | Done | Done | 2025-06-18 | Done | 100% | 2025-06-18 | 2025-06-19 | 2025-06-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-07-10 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-26 | 2025-07-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 6-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1277 | 2505-UMIMO-4G#RO-BAU038-0290 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap module BBU | BAU038 | TBG KOKALUKUNA |  |  | KENDARI | -5.4242 | 122.6505 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-06-15 | Done | Done | 2025-06-16 | Done | 100% | 2025-06-15 | 2025-06-15 | 2025-06-16 | Connected | Connected |  | 03-NY SM | 01-Passed | SM Passed | 2025-07-17 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 06-Aug-25 | 7-Aug-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 2025-09-15 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1278 | 2505-UMIMO-4G#RO-BAU066-0291 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and add Module BBU | BAU066 | PROTELINDO GU |  |  | KENDARI | -5.2552 | 122.5767 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | PTI | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-06-21 | Done | Done | 2025-06-21 | Done | 100% | 2025-06-21 | 2025-06-21 | 2025-06-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-06-22 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-23 | 2025-07-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 2025-09-17 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1279 | 2505-UMIMO-4G#RO-BAU103-0292 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap module BBU | BAU103 | TBG BUKIT WOLIO |  |  | KENDARI | -5.4715 | 122.6224 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-06-16 | Done | Done | 2025-06-19 | Done | 100% | 2025-06-16 | 2025-06-16 | 2025-06-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-07-17 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 06-Aug-25 | 7-Aug-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 15-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1280 | 2505-UMIMO-4G#RO-BAU114-0293 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU | BAU114 | STP LAKUDO |  |  | KENDARI | -5.3178 | 122.529 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | STP | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-06-16 | Done | Done | 2025-06-18 | Done | 100% | 2025-06-16 | 2025-06-16 | 2025-06-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-07-11 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-23 | 2025-07-24 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 6-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1281 | 2505-UMIMO-4G#RO-LBA106-0295 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | LBA106 | SPLIT MESS HJF |  |  | TERNATE | -1.5651 | 127.4334 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | HARITA OBI | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-06-23 | Done | Done | 2025-06-25 | Done | 100% | 2025-06-23 | 2025-06-24 | 2025-06-24 | Connected | Connected |  | 03-NY SM | 01-Passed | Passed | 2025-06-26 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-27 | 2025-07-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 4-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1282 | 2505-UMIMO-4G#RO-LBA110-0296 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Add RRU | LBA110 | HARITA SMELTER AREA |  |  | TERNATE | -1.5555 | 127.4252 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-06-19 | Done | Done | 2025-06-18 | Done | 100% | 2025-06-19 | 2025-06-19 | 2025-06-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-06-20 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-28 | 2025-07-03 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 4-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1283 | 2505-UMIMO-4G#RO-LBA118-0298 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | LBA118 | APARTEMENT 14-15 |  |  | TERNATE | -1.5319 | 127.4091 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | CORPORATE (HARITA) | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-06-24 | Done | Done | 2025-06-25 | Done | 100% | 2025-06-24 | 2025-06-25 | 2025-06-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-06-28 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-27 | 2025-07-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7439 | 1-Aug-25 | 2025-07-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1284 | 2505-UMIMO-4G#RO-MBA002-0297 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | MBA002 | Buli |  |  | TERNATE | 0.88251 | 128.2944 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-06-21 | Done | Done | 2025-06-21 | Done | 100% | 2025-06-21 | 2025-06-21 | 2025-06-21 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-07-12 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-16 | 2025-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7439 | 1-Aug-25 | 27-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1285 | 2505-UMIMO-4G#RO-RHA002-0314 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU | RHA002 | DMT TAMPO |  |  | KENDARI | -4.6247 | 122.7029 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-06-16 | Done | Done | 2025-06-17 | Done | 100% | 2025-06-16 | 2025-06-16 | 2025-06-17 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-06-16 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-15 | 2025-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 2025-07-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1286 | 2505-UMIMO-4G#RO-RHA002-0315 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | RHA002 | DMT Tampo |  |  | KENDARI | -4.6247 | 122.7029 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-06-16 | Done | Done | 2025-06-18 | Done | 100% | 2025-06-16 | 2025-06-16 | 2025-06-17 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-06-16 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-15 | 2025-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 6-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1287 | 2505-UMIMO-4G#RO-SNN005-0323 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SNN005 | TBG Waihama |  |  | TERNATE | -2.0745 | 125.9744 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-07-10 | Done | Done | 2025-07-10 | Done | 100% | 2025-07-10 | 2025-07-10 | 2025-07-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-07-11 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-07-24 | 2025-07-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7555 | 18-Aug-25 | 2025-09-15 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1288 | 2505-UMIMO-4G#RO-SSU002-0324 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | SSU002 | TBG PUSKESMAS SAGEA |  |  | TERNATE | 0.46479 | 128.0969 | YPTT | July-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-06-24 | Done | Done | 2025-06-25 | Done | 100% | 2025-06-24 | 2025-06-24 | 2025-06-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-06-24 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-07-16 | 2025-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7439 | 1-Aug-25 | 4-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1289 | 2505-UMIMO-4G#RO-SSU004-0325 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU004 | TBG WAHYU LELILEF |  |  | TERNATE | 0.4684 | 127.9324 | YPTT | July-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-06-24 | Done | Done | 2025-06-25 | Done | 100% | 2025-06-24 | 2025-06-25 | 2025-06-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-06-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-27 | 2025-07-03 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7439 | 1-Aug-25 | 2025-09-15 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1290 | 2505-UMIMO-4G#RO-SSU022-0338 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | SSU022 | TepeleoBatuDua |  | Take over closing ATP to YPTT d/t CCSI no team | TERNATE | 0.32291 | 128.7406 | YPTT | July-25 |  | 2025 | 2025 | [28 empty] | PemKab Halteng | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-06-08 | Done | Done | 2025-06-09 | Done | 100% | 2025-06-09 | 2025-06-09 | 2025-06-09 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-07-18 |  | Done Tagging |  | Done Tagging | Done Tagging | [11 empty] | 2025-06-08 | 7-Aug-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8095 | 14-Oct-25 | 19-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1291 | 2505-UMIMO-4G#RO-SSU109-0326 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU109 | TBG LELILEF LOKULAMO |  |  | TERNATE | 0.47317 | 127.8898 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-06-15 | Done | Done | 2025-06-15 | Done | 100% | 2025-06-15 | 2025-06-15 | 2025-06-15 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-06-16 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-28 | 2025-07-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 4-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1292 | 2505-UMIMO-4G#RO-SSU132-0328 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU132 | TBG LELILEF UTARA |  |  | TERNATE | 0.47173 | 127.9279 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-06-14 | Done | Done | 2025-06-15 | Done | 100% | 2025-06-14 | 2025-06-14 | 2025-06-14 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-06-15 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-28 | 2025-07-03 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 2025-07-16 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1293 | 2505-UMIMO-4G#RO-TDE004-0331 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | TDE004 | PTI Tomagoba Dermawan |  |  | TERNATE | 0.66521 | 127.4482 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | PTI | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-07-03 | Done | Done | 2025-07-06 | Done | 100% | 2025-07-03 | 2025-07-04 | 2025-07-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-07-10 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-07-16 | 2025-07-17 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7409 | 2025-07-30 | 27-Aug-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1294 | 2505-UMIMO-4G#RO-TDE008-0329 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | TDE008 | SOFIFI |  |  | TERNATE | 0.75194 | 127.5761 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-06-11 | Done | Done | 2025-06-13 | Done | 100% | 2025-06-11 | 2025-06-11 | 2025-06-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-06-12 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-06-28 | 2025-07-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 2025-07-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1295 | 2505-UMIMO-4G#RO-TDK007-0332 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and module BBU | TDK007 | BATUPARIGI-DMT |  |  | PARE PARE | -2.0603 | 119.4366 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Narfin | Done Productivity 100 % |  |  |  |  | 2025-06-19 | Done | Done | 2025-06-21 | Done | 100% | 2025-06-19 | 2025-06-21 | 2025-06-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-06-20 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-06-30 | 2025-07-07 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 2025-07-25 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1296 | 2505-UMIMO-4G#RO-WGU011-0337 | CAPEX RAN 2 2025 Acceleration Support Part 4 for Capacity RCI | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and add Module BBU | WGU011 | MOLOREPANTAI-DMT |  |  | KENDARI | -3.3103 | 122.2764 | YPTT | June-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-06-13 | Done | Done | 2025-06-14 | Done | 100% | 2025-06-13 | 2025-06-14 | 2025-06-14 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-06-14 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-09-04 | 2025-09-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-6869 | 2025-06-30 | 2025-09-15 | 01-BAUT Approved by Tsel | 05-BAST Approved by Tsel | Done Upload | Invoiced 100%
1297 | 2506-4GDCS-4G#RO-LBA026-0070 | CAPEX RAN 2 PART 3 2025 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | LBA026 | PAPALOANG-DMT |  |  | TERNATE | -0.64403 | 127.4996 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-09-04 | Done | Done | 2025-09-08 | Done | 100% | 2025-09-04 | 2025-09-07 | 2025-09-09 | Connected | Connected |  | 03-NY SM | 03-NY SM | Work Not Start | 2025-09-09 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 07-Oct-25 | 7-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8095 | 14-Oct-25 | 31-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1298 | 2506-4GDCS-4G#RO-LBA028-0060 | CAPEX RAN 2 PART 3 2025 | EQP New Site 4G LTE 1800 20 Mhz | New Infra (Add Antenna and RRU and Module BBU) | SRI006 | SRI006 CR fr Permanenisasi Combat |  |  | KENDARI | 0.74294 | 124.6077 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Haerun | Done Productivity 100 % |  |  |  |  | 2025-09-03 | Done | Done | 2025-09-03 | Done | 100% | 2025-09-03 | 2025-09-03 | 2025-09-28 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start | 19-Oct-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2026-02-18 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 | 23-Dec-25 | 01-BAUT Approved by Tsel | 13-Wait AS Doc Complete | Done Upload | Invoiced 100%
1299 | 2506-4GDCS-4G#RO-PSO034-0074 | CAPEX RAN 2 PART 3 2025 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | JLO020 | TONGUTE_GOIN_DMT |  |  | TERNATE | -1.281123996 | 120580864 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Akbar | Done Productivity 100 % |  |  |  |  | 2025-09-04 | Done | Done | 2025-09-08 | Done | 100% | 2025-09-04 | 2025-09-06 | 2025-09-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 17-Oct-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 30-Oct-25 | 30-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8095 | 14-Oct-25 | 12-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1300 | 2506-4GDCS-4G#RO-PSO035-0076 | CAPEX RAN 2 PART 3 2025 | EQP New NE 4G LTE 1800 20 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | SKG080 | PAMONA |  |  | MAKASSAR | -3.7589 | 120.3609 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Asdi | Done Productivity 100 % |  |  |  |  | 25-Aug-25 | Done | Done | 28-Aug-25 | Done | 100% | 25-Aug-25 | 30-Aug-25 | 30-Aug-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need |  |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2026-01-19 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7556 | 18-Aug-25 | 23-Dec-25 | 01-BAUT Approved by Tsel | 09-BAST Under Reviewer | Done Upload | Invoiced 100%
1301 | 2506-4GDCS-4G#RO-RTN006-0068 | CAPEX RAN 2 PART 3 2025 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | JLO017 | BATAKA_DMT |  |  | TERNATE | 1.4207 | 127.5147 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Akbar | Done Productivity 100 % |  |  |  |  | 2025-09-02 | Done | Done | 2025-09-03 | Done | 100% | 2025-09-02 | 2025-09-04 | 2025-09-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 21-Oct-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 30-Oct-25 | 30-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8095 | 14-Oct-25 | 22-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1302 | 2506-4GDCS-4G#RO-TER011-0067 | CAPEX RAN 2 PART 3 2025 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | JLO008 | JLO008 CR fr Tubo |  |  | TERNATE | 1.4353 | 127.534 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | ahmad | Done Productivity 100 % |  |  |  |  | 2025-09-16 | Done | Done | 2025-09-18 | Done | 100% | 2025-09-19 | 2025-09-20 | 2025-09-30 | Connected | Connected |  | 01-Passed | 03-NY SM | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 29-Oct-25 | 29-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8095 | 14-Oct-25 | 12-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1303 | 2506-4GDCS-4G#RO-TTY004-0073 | CAPEX RAN 2 PART 3 2025 | EQP New NE 4G LTE 1800 20 Mhz | New Infra | LBA028 | LBA028 CR fr Cand_CP1 24__01446 |  |  | TERNATE | 742942989 | 1246076584 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | akbar | Done Productivity 90 % |  |  |  |  | 2025-09-16 | Done | Done | 2025-09-18 | Done | 100% | 2025-09-16 | 2025-09-18 | 2025-09-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-09-20 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-09-29 | 8-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8095 | 14-Oct-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 90%
1304 | 2506-4GGSM-4G#RO-RBI002-0034 | CAPEX RAN 2 PART 3 2025 | EQP New NE 4G LTE 900 10 Mhz | New Infra | JLO018 | JLO018 CR fr HUKAEA |  |  | TERNATE | 1.4618 | 127.5456 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | ahmad | Done Productivity 100 % |  |  |  |  | 2025-09-16 | Done | Done | 2025-09-18 | Done | 100% | 2025-09-16 | 2025-09-18 | 2025-09-30 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 22-Oct-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 28-Oct-25 | 30-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8095 | 14-Oct-25 | 12-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1305 | 2506-4GGSM-4G#RO-UPD081-0025 | CAPEX RAN 2 PART 3 2025 | EQP New NE 4G LTE 900 10 Mhz | New Infra (Add Antenna and RRU and Module BBU) | UNH029 | UNAASI_ANGGABERI_DMT |  |  | KENDARI | -5.1264 | 119.4343 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 28-Aug-25 | Done | Done | 29-Aug-25 | Done | 100% | 28-Aug-25 | 29-Aug-25 | 29-Aug-25 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | 24-Oct-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 27-Oct-25 | 27-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 | 2025-11-19 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1306 | 2506-iMACR-4G#RO-SSU035-0001 | Risk Order IWIP Improvement Batch#2 | EQP Add Sector LTE 1800+L2100 (iMacro) | Add RRU Imacro | SSU035 | IWIP Apartment |  |  | TERNATE | 0.4816 | 128.0118 | YPTT | June-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | IWIP | [5 empty] | CV. Puri Tepule Abadi | Alimuddin | In Progress for Productivity |  |  |  | 8342895 | 2026-01-05 | Done | 2026-01-05 | 2026-01-07 | Done | 100% | 2026-01-05 | 2026-01-07 | 2026-01-07 | Connected | Connected |  | 03-NY SM | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | [6 empty] | No Need |  |  |  | 17 December 2025 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8095 | 14-Oct-25 | 18-Dec-25 | 01-BAUT Approved by Tsel | 13-Wait AS Doc Complete | Done Upload | NEW PO
1307 | 2506-iMACR-4G#RO-SSU162-0006 | Risk Order IWIP Improvement Batch#2 | EQP Add Sector LTE 1800+L2100 (iMacro) | Add RRU Imacro and Module BBU | SSU162 | IWIP New Office 3-2 |  |  | TERNATE | 0.4787 | 127.9798 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | In Progress for Productivity |  |  |  | 8393900 | 2026-02-17 | Done | 2026-02-19 | 2026-02-24 | Done | 100% | 2026-02-19 | 2026-02-24 | 2026-02-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9525 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1308 | 2506-iMACR-4G#RO-SSU162-0007 | Risk Order IWIP Improvement Batch#2 | EQP Add Sector LTE 1800+L2100 (iMacro) | Add RRU Imacro | SSU162 | IWIP New Office 3-2 |  |  | TERNATE | 0.47916 | 127.9804 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | In Progress for Productivity |  |  |  | 1920499 | 2026-02-17 | Done | 2026-02-19 | 2026-02-24 | Done | 100% | 2026-02-19 | 2026-02-24 | 2026-02-24 | Connected | Connected |  | Progress | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9525 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1309 | 2506-iMACR-4G#RO-SSU162-0008 | Risk Order IWIP Improvement Batch#2 | EQP Add Sector LTE 1800+L2100 (iMacro) | Add RRU Imacro | SSU162 | IWIP New Office 3-2 |  |  | TERNATE | 0.4783 | 127.9801 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | In Progress for Productivity |  |  |  | 1920499 | 2026-02-17 | Done | 2026-02-19 | 2026-02-24 | Done | 100% | 2026-02-19 | 2026-02-24 | 2026-02-24 | Connected | Connected |  | Progress | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9525 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1310 | 2506-iMACR-4G#RO-SSU162-0009 | Risk Order IWIP Improvement Batch#2 | EQP Add Sector LTE 1800+L2100 (iMacro) | Add RRU Imacro | SSU162 | IWIP New Office 3-2 |  |  | TERNATE | 0.47871 | 127.9807 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | In Progress for Productivity |  |  |  | 1920499 | 2026-02-17 | Done | 2026-02-19 | 2026-02-24 | Done | 100% | 2026-02-19 | 2026-02-24 | 2026-02-24 | Connected | Connected |  | Progress | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9525 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1311 | 2506-iMACR-4G#RO-SSU162-0010 | Risk Order IWIP Improvement Batch#2 | EQP Add Sector LTE 1800+L2100 (iMacro) | Add RRU Imacro | SSU162 | IWIP New Office 3-2 |  |  | TERNATE | 0.47922 | 127.9813 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | In Progress for Productivity |  |  |  | 1920499 | 2026-02-17 | Done | 2026-02-19 | 2026-02-24 | Done | 100% | 2026-02-19 | 2026-02-24 | 2026-02-24 | Connected | Connected |  | Progress | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9525 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1312 | 2507-ADSTR-4G#RO-COI769-0239 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Add Sector LTE 2100 2T2R | Add RRU | COI769 | Combat Pasar Muna |  |  | KENDARI | -4.8158 | 122.7348 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 15-Aug-25 | Done | Done | 16-Aug-25 | Done | 100% | 15-Aug-25 | 16-Aug-25 | 16-Aug-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 17-Aug-25 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-09-02 | 2025-09-08 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 | 2025-09-26 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1313 | 2507-ADSTR-4G#RO-RHA131-0252 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Add Sector LTE 2300 4T4R | Add RRU | RHA131 | TBG Wakorumba Utara |  |  | KENDARI | -443098 | 12295932 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-04 | Done | Done | 2025-09-05 | Done | 100% | 2025-09-04 | 2025-09-05 | 2025-09-05 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-09-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-09-11 | 2025-09-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 | 31-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1314 | 2507-ADSTR-4G#RO-TDE009-0255 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Module BBU | TDE009 | Faulery |  |  | TERNATE | 0.37885 | 127.6244 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [28 empty] | Waiitting Req | Release | Release |  |  | YPTT |  | Done Productivity 90 % |  |  |  | 9261574 | 2026-01-28 | Done | 2026-01-29 | 2026-01-30 | Done | 100% | 2026-01-29 | 2026-01-30 | 2026-01-30 | Connected | Connected |  | 03-NY SM | 01-Passed | Passed | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound | 30-Dec-25 | DRID07520251230002TSEL |  | Inbound |  |  | 24 February 2026 | 21 October 2025 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 90% | BOQ_Capex Ran 3 2025_Tech.xlsx
1315 | 2507-REENG-4G#RO-MAM192-0037 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP eNode B Modular Relocation Service New NE LTE 2300 Macro | Add RRU | MAM192 | LelingUtara-DMT |  |  | PARE PARE | -2.1828 | 119.4653 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Asdi | Invoiced 100% |  |  |  |  | 2025-09-01 | Done | Done | 2025-09-01 | Done | 100% | 2025-09-01 | 2025-09-01 | 2025-09-01 | Connected | Connected |  | 03-NY SM | 03-NY SM | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-11-04 | 2025-11-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7892 | 2025-09-22 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 70%
1316 | 2507-REENG-4G#RO-SRI004-0047 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP eNode B Modular Relocation Service | Add antenna and RRU | SRI004 | N_SRI004M41_PajalaMaginti-TBG |  |  | KENDARI | -4.8443 | 122.3519 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Haerun | Invoiced 100% |  |  |  |  | 2025-09-27 | Done | Done | 2025-09-27 | Done | 100% | 2025-09-27 | 2025-09-27 | 2025-09-27 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start | 16-Oct-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 23-Dec-25 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 | 22-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1317 | 2507-UMIMO-4G#RO-BAU025-0346 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | BAU025 | Wanci 2 |  |  | KENDARI | -5.3451 | 123.5443 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Invoiced 100% |  |  |  |  | 27-Aug-25 | Done | Done | 27-Aug-25 | Done | 100% | 27-Aug-25 | 28-Aug-25 | 28-Aug-25 | Connected | Connected |  | 03-NY SM | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2026-02-02 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 | 22-Dec-25 | 01-BAUT Approved by Tsel | 13-Wait AS Doc Complete | Done Upload | Invoiced 100%
1318 | 2507-UMIMO-4G#RO-MBA002-0357 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Module+Mounting Antenna | MBA002 | Buli |  |  | TERNATE | 0.88251 | 128.2944 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Akbar | Done Productivity 100 % |  |  |  |  | 2025-09-07 | Done | Done | 2025-09-08 | Done | 100% | 2025-09-07 | 2025-09-08 | 2025-09-08 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start | 2025-09-10 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 20-Oct-25 | 20-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7907 | 2025-09-24 | 31-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1319 | 2507-UMIMO-4G#RO-MBA011-0359 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | AAU+Module+Mounting Antenna | MBA011 | E_MBA011M41_Mabapura-DMT |  |  | TERNATE | 0.82333 | 128.2403 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Akbar | Done Productivity 100 % |  |  |  |  | 2025-09-10 | Done | Done | 2025-09-12 | Done | 100% | 2025-09-12 | 2025-09-12 | 2025-09-12 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-09-12 |  | Done Tagging |  | Work Not Start | Work Not Start | [11 empty] | 20-Oct-25 | 20-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8299 | 2025-11-01 | 2025-11-29 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1320 | 2507-UMIMO-4G#RO-MBA019-0360 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Swap Module+Mounting Antenna | MBA019 | N_MBA019M41_BuliTimur-PTI |  |  | TERNATE | 0.89018 | 128.2958 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | PTI | [5 empty] | CV. Puri Tepule Abadi | Akbar | Done Productivity 100 % |  |  |  |  | 2025-09-10 | Done | Done | 2025-09-11 | Done | 100% | 2025-09-10 | 2025-09-11 | 2025-09-11 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-09-14 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 20-Oct-25 | 20-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8095 | 14-Oct-25 | 2025-11-29 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1321 | 2507-UMIMO-4G#RO-RHA002-0396 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU | RHA002 | E_RHA002M41_Tampo-DMT |  |  | KENDARI | -4.6247 | 122.7029 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-09-15 | Done | Done | 2025-09-15 | Done | 100% | 2025-09-15 | 2025-09-15 | 2025-09-15 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-11-17 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2026-01-28 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 | 22-Dec-25 | 01-BAUT Approved by Tsel | 13-Wait AS Doc Complete | Done Upload | Invoiced 100%
1322 | 2507-UMIMO-4G#RO-SNN008-0408 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | SNN008 | Sanana 2 |  |  | TERNATE | -2.0561 | 125.9764 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [28 empty] | Waiitting Req |  |  |  |  | YPTT |  | Done Productivity 100 % | Done Invoice | 6500000 | additional cost special transportation from Ternate to Sanana & Sanana to Ternate | 9520808 | 2026-02-18 | Done | 2026-02-18 | 2026-02-19 | Done | 100% | 2026-02-18 | 2026-02-19 | 2026-02-19 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound |  |  |  | Inbound |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 100% | BOQ_Capex Ran 3 2025_Tech.xlsx
1323 | 2507-UMIMO-4G#RO-SNN020-0409 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SNN020 | DMT Sanana |  |  | TERNATE | -2.0702 | 125.9779 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [28 empty] | Waiitting Req |  |  |  |  | YPTT |  | Done Productivity 100 % |  |  |  | 8342895 | 2026-02-18 | Done | 2026-02-18 | 2026-02-19 | Done | 100% | 2026-02-18 | 2026-02-19 | 2026-02-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 12 February 2026 | 13 February 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 100% | BOQ_Capex Ran 3 2025_Tech.xlsx
1324 | 2507-UMIMO-4G#RO-SSU029-0411 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | SSU029 | PEMKABHALMAHERATENGAH |  |  | TERNATE | 0.39003 | 128.5607 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [28 empty] | Done Req | 45999 | 45999 |  |  | YPTT | Junaedi | Done Productivity 100 % |  |  |  | 10281396 | 2026-02-13 | Done | 2026-02-13 | 2026-02-15 | Done | 100% | 2026-02-13 | 2026-02-15 | 2026-02-15 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound | 20-Dec-25 | DRID07520251217001TSEL |  | Inbound |  |  | 20 February 2026 | 01 December 2025 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 | 2026-02-27 | 01-BAUT Approved by Tsel | 14-Wait Document Complete | Done Upload | Invoiced 100% | BOQ_Capex Ran 3 2025_Tech.xlsx
1325 | 2507-UMIMO-4G#RO-TDK007-0439 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE Macro | Add RRU | TDK007 | BatuParigi-DMT |  |  | PARE PARE | -2.0603 | 119.4366 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Asdi | Invoiced 100% |  |  |  |  | 2025-09-03 | Done | Done | 2025-09-02 | Done | 100% | 2025-09-03 | 2025-09-03 | 2025-09-03 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 27-Oct-25 | 28-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7892 | 2025-09-22 | 2025-11-29 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 70%
1326 | 2507-UMIMO-4G#RO-TER009-0440 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Module+Mounting Antenna | TER009 | JambulaPertamina |  |  | TERNATE | 0.76069 | 127.3174 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Akbar | Invoiced 100% |  |  |  |  | 15-Aug-25 | Done | Done | 17-Aug-25 | Done | 100% | 15-Aug-25 | 16-Aug-25 | 16-Aug-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 19-Aug-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-09-18 | 2025-09-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7907 | 2025-09-24 | 7-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1327 | 2507-UMIMO-4G#RO-TER009-0441 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Module+Mounting Antenna | TER009 | JambulaPertamina |  |  | TERNATE | 0.76069 | 127.3174 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Akbar | Invoiced 100% |  |  |  |  | 05-Aug-25 | Done | Done | 08-Aug-25 | Done | 100% | 05-Aug-25 | 08-Aug-25 | 08-Aug-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 13-Aug-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 20-Oct-25 | 20-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7907 | 2025-09-24 | 29-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1328 | 2507-UMIMO-4G#RO-TER091-0442 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | AAU+Swap Cabinet+Swap BBU+Swap Module+Mounting Antenna | TER091 | N_TER091M41_ManggaDuaUtara-PTI |  |  | TERNATE | 0.77464 | 127.3826 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | PTI | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-09-16 | Done | Done | 2025-09-16 | Done | 100% | 2025-09-16 | 2025-09-16 | 2025-09-16 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 2025-09-24 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 20-Oct-25 | 20-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8095 | 14-Oct-25 | 29-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1329 | 2507-UMIMO-4G#RO-UNH101-0447 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | UNH101 | TBG KAMPUNG JAWA MOROSI |  |  | KENDARI | -3.8976 | 122.4247 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-01 | Done | Done | 2025-09-02 | Done | 100% | 2025-09-01 | 2025-09-02 | 2025-09-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-09-06 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-09-11 | 2025-09-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 | 31-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1330 | 2507-UMIMO-4G#RO-WGU011-0450 | CAPEX RAN 3 2025 Acceleration Support Part 1 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | WGU011 | DMT Molore Pantai |  |  | KENDARI | -3.3103 | 122.2764 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-03 | Done | Done | 2025-09-03 | Done | 100% | 2025-09-03 | 2025-09-03 | 2025-09-03 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-09-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2025-09-11 | 2025-09-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 | 31-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1331 | 2508-4GDCS-4G#RO-COI707-0090 | Activity Non MPSL_R09 Sulawesi_2025_MKT IAAS Petrosea & PT. QMB New Energy Mineral | EQP New Site 4G LTE 1800 20 Mhz | Add Antenna, RRU and module BBU | COI707 | IAAS Combat Petrosea Antam Pakal |  |  | TERNATE | 0.77824 | 128.3318 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | [5 empty] | CV. Puri Tepule Abadi | Akbar | Done Productivity 100 % |  |  |  |  | 24-Aug-25 | Done | Done | 29-Aug-25 | Done | 100% | 25-Aug-25 | 29-Aug-25 | 29-Aug-25 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start | 2025-09-01 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-11-04 | 2025-11-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7907 | 2025-09-24 | 2025-11-29 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1332 | 2508-4GDCS-4G#RO-NTI066-0089 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Swap Module BBU | NTI075 | N3TPELITA |  |  | TERNATE | 2.1076 | 128.016 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 9261574 | 2026-02-17 | Done | 2026-02-20 | 2026-02-20 | Done | 100% | 2026-02-20 | 2026-02-20 | 2026-02-20 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  | No Need | Inbound |  |  |  | Inbound |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1333 | 2508-4GGSM-4G#RO-COI707-0049 | Activity Non MPSL_R09 Sulawesi_2025_MKT IAAS Petrosea & PT. QMB New Energy Mineral | EQP New Site 4G LTE L900 10 Mhz | Add RRU | COI707 | IAAS Combat Petrosea Antam Pakal |  |  | TERNATE | 0.77824 | 128.3318 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | CORPORATE | [5 empty] | CV. Puri Tepule Abadi | Akbar | Done Productivity 90 % |  |  |  |  | 24-Aug-25 | Done | Done | 29-Aug-25 | Done | 100% | 25-Aug-25 | 29-Aug-25 | 29-Aug-25 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start | passed | 05-Aug-26 | Done Tagging |  | Done Tagging | waiting tiket | [11 empty] | 00-Jan-00 | 0-Jan-00 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7907 | 2025-09-24 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 70%
1334 | 2508-ADSTR-4G#RO-COI551-0263 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Add Sector LTE 2300 4T4R | RRU+Module+Swap Antenna Multi Port+Mounting Antenna | COI551 | COMBAT FUN TUBO |  |  | TERNATE | 0.82569 | 127.3736 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Akbar | Done Productivity 100 % |  |  |  |  | 18-Aug-25 | Done | Done | 19-Aug-25 | Done | 100% | 18-Aug-25 | 19-Aug-25 | 19-Aug-25 | Connected | Connected |  | 03-NY SM | 01-Passed | Passed | 19-Aug-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 2025-09-18 | 2025-09-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7907 | 2025-09-24 | 7-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1335 | 2508-ADSTR-4G#RO-MAM040-0279 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Add Sector LTE 2300 4T4R | RRU+Swap Cabinet+Swap BBU+Swap Module | MAM040 | TBG Transmigran Tobadak |  |  | PARE PARE | -2.1439 | 119.3711 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Asdi | Done Productivity 100 % |  |  |  |  | 2025-09-05 | Done | Done | 2025-09-06 | Done | 100% | 2025-09-05 | 2025-09-06 | 2025-09-06 | Connected | Connected |  | 03-NY SM | 03-NY SM | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-11-27 | 28-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7891 | 2025-09-22 | 2025-11-29 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | PO Cancel
1336 | 2508-ADSTR-4G#RO-RHA005-0275 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Module BBU | RHA005 | Kalisusu |  |  | KENDARI | -4.7893 | 123.1799 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 70 % |  |  |  |  | 2025-09-05 | Done | Done | 2025-09-06 | Done | 100% | 2025-09-05 | 2025-09-06 | 2025-09-06 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | passed | 03-Aug-26 | Done Tagging | 03-Aug-26 | Done Tagging | waiting tiket | [11 empty] | 00-Jan-00 | 23-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 70%
1337 | 2508-NNE4G-4G#RO-SKG034-0181 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP New NE 4G LTE 2300 50 Mhz | RRU+Module | SKG034 | Permanenisasi COI565 |  |  | MAKASSAR | -3.3979 | 119.9363 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Asdi | Done Productivity 100 % |  |  |  |  | 23-Aug-25 | Done | Done | 23-Aug-25 | Done | 100% | 23-Aug-25 | 23-Aug-25 | 23-Aug-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need |  |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2026-01-23 | 2026-01-23 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7893 | 2025-09-22 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 90%
1338 | 2508-NNE4G-4G#RO-TER104-0184 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP New NE 4G LTE 2300 50 Mhz | RRU+Module | TER104 | MC Tobeleu |  |  | TERNATE | 0.80789 | 127.3817 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-09-14 | Done | Done | 2025-09-14 | Done | 100% | 2025-09-14 | 2025-09-14 | 2025-09-14 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start | 2025-09-14 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-09-25 | 2025-09-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7907 | 2025-09-24 | 31-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1339 | 2508-QCELL-4G#RO-SSU156-0001 | Risk Order Qcell IWIP | New Qcell | Add RRU and Module BBU | SSU156 | New Office IWIP |  |  | TERNATE | 0.47974 | 127.9775 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [28 empty] | Done Req | 45907 | Expierd |  |  | YPTT | External | Done Productivity 70 % |  |  |  | 110219967.06 | 2026-01-22 | Done | 2026-01-22 | 2026-01-24 | Done | 100% | 2026-01-22 | 2026-01-24 | 2026-01-24 | Connected | Connected | Waiting update from team external for closing ATP | 03-NY SM | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 15-Tagging New Asset NY, SM ATP NY | PO Confirmed | S1ID2023071503WBF1-439 | 2025-09-22 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 100% | 20250820_BOQ lWIP Proposal_scenario 1_20250619_1018_tech.xlsx
1340 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 0.47974 | 127.9775 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [28 empty] | Done Req | 45907 | Expierd |  |  | YPTT | External | In Progress for Productivity |  |  |  | 43497271 | 2026-06-01 | Done | 2026-06-05 | 2026-06-07 | Done | 100% | 2026-06-05 | 2026-06-07 | 2026-06-07 | Connected | Connected |  | Progress | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 |  | 08-BAUT NY Submit |  | NY Upload | NEW PO | 20250820_BOQ lWIP Proposal_scenario 1_20250619_1018_tech.xlsx
1341 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 3 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done | 2026-06-10 | 2026-06-12 | Done | 100% | 2026-06-10 | 2026-06-12 | 2026-06-12 | Connected | Connected |  | Progress | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1342 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 4 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done | 2026-06-10 | 2026-06-13 | Done | 100% | 2026-06-10 | 2026-06-13 | 2026-06-13 | Connected | Connected |  | Progress | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1343 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 5 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done | 2026-06-12 | 2026-06-15 | Done | 100% | 2026-06-12 | 2026-06-15 | 2026-06-15 | Connected | Connected |  | Progress | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1344 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 6 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done | 2026-06-15 | 2026-06-16 | Done | 100% | 2026-06-15 | 2026-06-16 | 2026-06-16 | Connected | Connected |  | Progress | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1345 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 7 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done | 2026-06-16 | 2026-06-17 | Done | 100% | 2026-06-16 | 2026-06-17 | 2026-06-17 | Connected | Connected |  | Progress | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1346 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 8 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done | 2026-06-16 | 2026-06-17 | Done | 100% | 2026-06-16 | 2026-06-17 | 2026-06-17 | Connected | Connected |  | Progress | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1347 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 9 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done | 2026-06-29 | 2026-07-01 | Done | 100% | 2026-06-29 | 2026-06-29 | 2026-07-01 | Connected | Connected |  | Progress | Progress | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1348 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 10 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done | 2026-06-30 | 2026-07-01 | Done | 100% | 2026-06-30 | 2026-06-30 | 2026-07-01 | Connected | Connected |  | Progress | Progress | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1349 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 11 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done | 2026-07-02 | 2026-07-03 | Done | 100% | 2026-07-02 | 2026-07-03 | 2026-07-03 | Connected | Connected |  | Progress | Progress | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1350 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 12 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done | 2026-07-04 | 2026-07-06 | Done | 100% | 2026-07-04 | 2026-07-06 | 2026-07-06 | Connected | Connected |  | Progress | Progress | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1351 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 13 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done | 2026-07-07 | 2026-07-09 | Done | 100% | 2026-07-07 | 2026-07-09 | 2026-07-09 | Connected | Connected |  | Progress | Progress | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1352 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 14 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done | 2026-07-21 | 2026-07-25 | Done | 100% | 2026-07-21 | 2026-07-25 | 2026-07-25 | Connected | Connected |  | Progress | Progress | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1353 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 15 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done |  |  | Done |  |  |  |  | NY | Progress |  | Progress | Progress | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1354 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 16 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done |  |  | Done |  |  |  |  | NY | Progress |  | Progress | Progress | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1355 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 17 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done |  |  | Done |  |  |  |  | NY | Progress |  | Progress | Progress | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1356 | 2508-QCELL-4G#RO-SSU156-0002 | Risk Order Qcell IWIP | New Qcell | Add RRU Qcel lantai 18 | SSU156 | New Office IWIP | L1800+L2100+L2300+NR2300 |  | TERNATE | 127977546 | 0.47974 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Edy Kurniawan | In Progress for Productivity |  |  |  | 9628545 | 2026-06-01 | Done |  |  | Done |  | 2026-06-05 |  |  | NY | Progress |  | Progress | Progress | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed | S1ID2023070102WBF1-8716
1357 | 2508-QCELL-4G#RO-SSU156-0002 | New-Indoor QCELL IWIP | EQP Add Sector LTE 1800 2T2R | Qcell AAU | SSU156 | New Office IWIP | L1800 |  | TERNATE | 127.9775 | 0.47974 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Waitting MOS |  |  |  | 7756340 | [12 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need
1358 | 2508-REENG-4G#RO-DRB003-0055 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP eNode B Modular Relocation Service | Add RRU | DRB003 | Permanenisasi COI620 - Combat FUN Gotalamo Morotai |  |  | TERNATE | 2.0546 | 128.2952 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [28 empty] | Waiitting Req | Release | NY Release |  |  | YPTT | Carlos | Done Productivity 100 % |  |  |  | 5741754 | 2026-01-02 | Done | 2026-01-02 | 2026-01-05 | Done | 100% | 2026-01-02 | 2026-01-05 | 2026-01-05 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 03 February 2026 | 03 February 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 100% | BOQ_Capex Ran 3 2025_Tech.xlsx
1359 | 2508-REENG-4G#RO-MAM150-0057 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP eNode B Modular Relocation Service | RRU+Module | MAM150 | Protelindo Stikes Andini |  |  | PARE PARE | -2.6551 | 118.9333 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | PTI | [5 empty] | CV. Puri Tepule Abadi | Asdi | Done Productivity 100 % |  |  |  |  | 30-Aug-25 | Done | Done | 30-Aug-25 | Done | 100% | 30-Aug-25 | 30-Aug-25 | 30-Aug-25 | Connected | Connected |  | 03-NY SM | 03-NY SM | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-11-04 | 28-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7891 | 2025-09-22 | 31-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1360 | 2508-REENG-4G#RO-RHA039-0071 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP eNode B Modular Relocation Service | Add RRU and Module BBU | RHA039 | N_RHA039M41_Kontomolepe-DMT |  |  | KENDARI | -5.1138 | 122.5116 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 2025-09-16 | Done | Done | 2025-09-16 | Done | 100% | 2025-09-16 | 2025-09-16 | 2025-09-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-11-16 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 2026-04-28 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 | 22-Dec-25 | 01-BAUT Approved by Tsel | 13-Wait AS Doc Complete | Done Upload | Invoiced 100%
1361 | 2508-REENG-4G#RO-TER018-0074 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP eNode B Modular Relocation Service | RRU+Module | TER018 | Mangga Dua |  |  | TERNATE | 0.77021 | 127.3757 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-09-13 | Done | Done | 2025-09-13 | Done | 100% | 2025-09-13 | 2025-09-13 | 2025-09-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-09-13 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 15 May 2026 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7907 | 2025-09-24 | 22-Dec-25 | 01-BAUT Approved by Tsel | 13-Wait AS Doc Complete | Done Upload | Invoiced 100%
1362 | 2508-REENG-4G#RO-TER199-0075 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP eNode B Modular Relocation Service | RRU+Module | TER199 | GipsiPuncak-DMT |  |  | TERNATE | 807413 | 127376266 | YPTT | August-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  | 5741754 | 2026-02-17 | Done | 2026-02-18 | 2026-02-20 | Done | 100% | 2026-02-18 | 2026-02-20 | 2026-02-20 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 07 May 2026 | 10 December 2025 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7907 | 2025-09-24 | 18-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1363 | 2508-UMIMO-4G#RO-BAU210-0474 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | BAU210 | E_BAU210M41_Waturombe-DMT |  |  | KENDARI | -5.379 | 122.3736 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Haerun | Done Productivity 100 % |  |  |  |  | 2025-09-21 | Done | Done | 2025-09-21 | Done | 100% | 2025-09-21 | 2025-09-21 | 2025-09-21 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-11-05 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2026-04-27 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 90%
1364 | 2508-UMIMO-4G#RO-KDI008-0480 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | KDI008 | Wanci |  |  | KENDARI | -5.3265 | 123.5418 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Ruslan | Done Productivity 100 % |  |  |  |  | 27-Aug-25 | Done | Done | 28-Aug-25 | Done | 100% | 27-Aug-25 | 28-Aug-25 | 28-Aug-25 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 20 May 2026 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 | 22-Dec-25 | 01-BAUT Approved by Tsel | 13-Wait AS Doc Complete | Done Upload | Invoiced 100%
1365 | 2508-UMIMO-4G#RO-KDI045-0483 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | KDI045 | DMT Napoosi |  |  | KENDARI | -4.0358 | 121.9908 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-05 | Done | Done | 2025-09-05 | Done | 100% | 2025-09-05 | 2025-09-05 | 2025-09-05 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-09-07 |  | Done Tagging |  | Done Tagging | No Need | [11 empty] | 20 May 2026 | 2025-09-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 100%
1366 | 2508-UMIMO-4G#RO-MBA034-0455 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | AAU+Module+Mounting Antenna | MBA034 | Lapangan Haltim |  |  | TERNATE | 0.68025 | 128.289 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Akbar | Done Productivity 100 % |  |  |  |  | 2025-09-13 | Done | Done | 2025-09-13 | Done | 100% | 2025-09-13 | 2025-09-13 | 2025-09-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-09-13 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 08 May 2026 | 2025-09-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7907 | 2025-09-24 | 31-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1367 | 2508-UMIMO-4G#RO-RHA008-0495 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | RHA008 | Kabawo |  |  | KENDARI | -5.0008 | 122.5008 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 17-Aug-25 | Done | Done | 24-Aug-25 | Done | 100% | 23-Aug-25 | 23-Aug-25 | 23-Aug-25 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start | 24-Aug-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 20 May 2026 | 27-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7906 | 2025-09-24 | 31-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1368 | 2508-UMIMO-4G#RO-SSU012-0498 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU012 | Permanenisasi SSU028 |  |  | TERNATE | 0.27947 | 128.7719 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [28 empty] | Done Req | 45999 | 45999 |  |  | YPTT | Junaedi | Done Productivity 100 % |  |  |  | 8342895 | 2026-02-08 | Done | 2026-02-08 | 2026-02-11 | Done | 100% | 2026-02-08 | 2026-02-11 | 2026-02-11 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 08 May 2026 | 19 January 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 | 2026-01-30 | 01-BAUT Approved by Tsel | 14-Wait Document Complete | Done Upload | Invoiced 100% | BOQ_Capex Ran 3 2025_Tech.xlsx
1369 | 2508-UMIMO-4G#RO-TER055-0469 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Swap Cabinet+Swap BBU+Swap Module+Mounting Antenna | TER055 | Suering |  |  | TERNATE | 0.78274 | 127.3877 | YPTT | August-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  | 11459309 | 2026-01-17 | Done | 2026-01-17 | 2026-01-19 | Done | 100% | 2026-01-17 | 2026-01-19 | 2026-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 13 February 2026 | 2025-11-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7907 | 2025-09-24 | 2025-11-29 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1370 | 2508-UMIMO-4G#RO-TER072-0501 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Module+Mounting Antenna | TER072 | TBG Santiong Ternate |  |  | TERNATE | 0.78949 | 127.3875 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Ahmad | Done Productivity 100 % |  |  |  |  | 2025-09-10 | Done | Done | 2025-09-12 | Done | 100% | 2025-09-11 | 2025-09-11 | 2025-09-12 | Connected | Connected |  | 03-NY SM | 03-NY SM | Passed | 2025-09-12 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 21 January 2026 | 20-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7907 | 2025-09-24 | 29-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1371 | 2508-UMIMO-4G#RO-TER128-0502 | CAPEX RAN 3 2025 Acceleration Support Part 2 for Capacity | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Module+Mounting Antenna | TER128 | MCR Ngade |  |  | TERNATE | 0.76413 | 127.3538 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Akbar | Done Productivity 100 % |  |  |  |  | 17-Aug-25 | Done | Done | 18-Aug-25 | Done | 100% | 17-Aug-25 | 18-Aug-25 | 18-Aug-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | 19-Aug-25 |  | Done Tagging |  | Done Tagging | Work Not Start | [11 empty] | 03 February 2026 | 2025-09-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-7907 | 2025-09-24 | 7-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1372 | 2508-UPGSW-4G#RO-SSU143-12880 | #N/A | EQP Upgrade SW UR24 | Upgrade SW UR24 | TER072 | Santiong Ternate_TBG |  |  | TERNATE | #N/A | #N/A | YPTT | 2026-09-25 |  | 2025 | 2025 | [34 empty] | CV. Puri Tepule Abadi | Akbar | [5 empty] | 2025-09-09 | Done | Done | 2025-09-09 | Done | 100% | 2025-09-09 | 2025-09-09 | 2025-09-09 | Connected | Connected |  | 03-NY SM | 03-NY SM | No Need | No Need |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 19 January 2026 | 0-Jan-00 | 17-Work NY Done | PO NY Release |  |  |  | #N/A |  | Work Not Start
1373 | 2509-4GDCS-4G#1034-DRB007-0110 | CAPEX RAN 3 PART 2 2025 | EQP New NE 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | DRB007 | GOTALAMO |  |  | TERNATE | 2.069 | 128.3039 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | New Infra | Waiitting Req | Release | NY Release |  |  | YPTT |  | Done Productivity 100 % |  |  |  | 11518218 | 2026-01-27 | Done | 2026-02-03 | 2026-02-05 | Done | 100% | 2026-02-03 | 2026-02-05 | 2026-02-05 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 20 May 2026 | 19 January 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 07-BAUT Preparation | 14-Wait Document Complete | Done Upload | Invoiced 100% | BOQ New Infra Batch 2_Sulawesi_20250807_1749_final_V3_Tech.xlsx
1374 | 2509-4GDCS-4G#1034-MBA036-0115 | CAPEX RAN 3 PART 2 2025 | EQP New NE 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | MBA036 | WAIJOI_DMT |  |  | TERNATE | 0.87625 | 127.9322 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | New Infra | Done Req | 46001 | NY Release |  |  | YPTT | Carlos | Done Productivity 90 % |  |  |  | 11518218 | 2026-02-10 | Done | 2026-02-10 | 2026-02-13 | Done | 100% | 2026-02-10 | 2026-02-13 | 2026-02-13 | Connected | Connected | TRM Ready for OA 14 Dec 2025 | 01-Passed | 01-Passed | No Need | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 08 May 2026 | 07 October 2025 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 70% | BOQ New Infra Batch 2_Sulawesi_20250807_1749_final_V3_Tech.xlsx
1375 | 2509-4GDCS-4G#RO-BOB002-0137 | CAPEX RAN 3 PART 4 2025 | EQP New NE 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | BOB002 | Pelabuhan Tikong |  |  | TERNATE | -1.6659 | 124.5278 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TBD | Done Req | Release |  |  |  | YPTT | Arman | Done Productivity 90 % | Approval Completed (PR NY) | 6500000 | additional cost special transportation from Ternate to Kilong | 11518218 | 2026-01-01 | Done | 2026-01-02 | 2026-01-05 | Done | 100% | 2026-01-02 | 2026-01-05 | 2026-01-05 | Connected | Connected | Site Ready OA (waitting TRM) | 01-Passed | 01-Passed | No Need | passed | May-26 | Done Tagging | 15-May-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 2025-11-04 | 2025-11-04 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload | NEW PO | BOQ_CP 3 PART 4 2025_V9a_Tech_.xlsx
1376 | 2509-4GDCS-4G#RO-BOB003-0138 | CAPEX RAN 3 PART 4 2025 | EQP New NE 4G LTE 1800 20 Mhz | Handover Only | DRB008 | SOPI_SURYA_TBG |  |  | TERNATE | -1.9686 | 124.6886 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TBD | Waiitting Req | Release | Release |  |  | YPTT |  | Done Productivity 100 % |  |  |  | 11518218 | 2026-01-20 | Done | 2026-02-01 | 2026-02-03 | Done | 100% | 2026-02-01 | 2026-02-03 | 2026-02-03 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 2026-04-28 | 21 January 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 90% | BOQ_CP 3 PART 4 2025_V9a_Tech_.xlsx
1377 | 2509-4GDCS-4G#RO-DRB006-0140 | CAPEX RAN 3 PART 4 2025 | EQP New NE 4G LTE 1800 20 Mhz | Handover Only | DRB006 | Tiley-DMT |  |  | TERNATE | 2.1986 | 128.2503 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TBD | Waiitting Req | Release | NY Release |  |  | YPTT |  | Done Productivity 100 % |  |  |  | 11518218 | 2026-01-22 | Done | 2026-01-25 | 2026-01-27 | Done | 100% | 2026-01-25 | 2026-01-27 | 2026-01-27 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 15 May 2026 | 2025-09-12 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 100% | BOQ_CP 3 PART 4 2025_V9a_Tech_.xlsx
1378 | 2509-4GGSM-4G#1034-BOB004-0065 | CAPEX RAN 3 PART 2 2025 | EQP New NE 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | BOB004 | KILONG_DMT |  |  | TERNATE | -1.9381 | 124.3797 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | New Infra | Done Req | Release |  |  |  | YPTT | Arman | Done Productivity 90 % | Done Invoice | 2500000 | additional cost special transportation from Ternate to Bobong | 11518218 | 2026-01-18 | Done | 2026-01-22 | 2026-01-24 | Done | 100% | 2026-01-22 | 2026-01-24 | 2026-01-24 | Connected | Connected | TRM Ready for OA 14 Dec 2025 | 01-Passed | 01-Passed | No Need | passed | May-26 | Done Tagging | 17-May-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 07 May 2026 | 27 January 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8470 | 2025-11-16 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | NEW PO | BOQ New Infra Batch 2_Sulawesi_20250807_1749_final_V3_Tech.xlsx
1379 | 2509-ADSTR-4G#RO-ADL028-0369 | CAPEX RAN 3 PART 1 2025 | EQP Add Sector LTE 900 2T2R | Add Antenna and RRU and Swap Module BBU | ADL028 | WOWALAHUMBUTI |  |  | KENDARI | -3.9674 | 122.2705 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-26 | Done | Done | 2025-09-26 | Done | 100% | 2025-09-26 | 2025-09-26 | 2025-09-26 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-09-28 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2026-04-27 | 1-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 | 12-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 90%
1380 | 2509-ADSTR-4G#RO-KKA167-0376 | CAPEX RAN 3 PART 1 2025 | EQP Add Sector LTE 900 2T2R | Add Antenna and RRU and Swap Module BBU | KKA167 | BMT PUURODA |  |  | KENDARI | -4.1356 | 121.6394 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 06-Oct-25 | Done | Done | 05-Oct-25 | Done | 100% | 06-Oct-25 | 06-Oct-25 | 06-Oct-25 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start | 08-Oct-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 20 May 2026 | 1-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8160 | 18-Oct-25 | 12-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1381 | 2509-NNE4G-4G#RO-ADL067-0191 | CAPEX RAN 3 PART 1 2025 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Swap Module BBU | ADL067 | DMT Poros Poleang |  |  | KENDARI | -4.7785 | 121.7903 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-19 | Done | Done | 2025-09-19 | Done | 100% | 2025-09-19 | 2025-09-19 | 2025-09-19 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-09-20 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 20 May 2026 | 2025-09-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 70%
1382 | 2509-NNE4G-4G#RO-LGI003-0200 | CAPEX RAN 3 PART 1 2025 | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | LGI003 | TANAILANDU |  |  | KENDARI | -5.2373 | 122.3247 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Haerun | Done Productivity 100 % |  |  |  |  | 2025-09-23 | Done | Done | 2025-09-23 | Done | 100% | 2025-09-23 | 2025-09-23 | 2025-09-23 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start | 20-Oct-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 08 May 2026 | 2025-11-18 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 90%
1383 | 2509-NNE4G-4G#RO-MAM023-0201 | CAPEX RAN 3 PART 1 2025 | QP New NE 4G LTE 2300 50 Mhz Macro_1 | Swap Antenna+Module BBU & Add RRU | MAM023 | Kabuloang |  |  | PARE PARE | -2.4988 | 119.0726 | YPTT | August-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Asdi | Done Productivity 100 % |  |  |  |  | 2025-09-09 | Done | Done | 2025-09-10 | Done | 100% | 2025-09-09 | 2025-09-10 | 2025-09-10 | Connected | Connected |  | 03-NY SM | 03-NY SM | Work Not Start |  |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 20 May 2026 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8469 | 2025-11-15 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 90%
1384 | 2509-NNE5G-5G#RO-MRW222-0171 | Upgrade | EQP Upgrade NR 2300 Massive MIMO 64T64R | Add RRU | UPD537 | TBG Alaudin DMT Jalan Bilawayah DMT SMA17 | N2300 |  | MAKASSAR |  |  | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Aditia | Done Productivity 70 % |  |  |  | 9708096 | 16-May-26 | Done | 16-May-26 | 18-May-26 | Done | 100% | 16-May-26 | 18-May-26 | 18-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [6 empty] | 08 May 2026 |  | 17-Work NY Done | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1385 | 2509-NNE5G-5G#RO-MRW222-0171 | Upgrade | EQP Upgrade NR 2300 Massive MIMO 64T64R | Add RRU | UPD500 UPD331 | DMT Jalan Bilawayah DMT SMA17 | N2300 |  | MAKASSAR |  |  | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Aditia | Done Productivity 70 % |  |  |  | 9708096 | 16-May-26 | Done | 16-May-26 | 21-May-26 | Done | 100% | 16-May-26 | 21-May-26 | 21-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Done Tagging | 2026-06-08 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [9 empty] | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1386 | 2509-UMIMO-4G#RO-ADL043-0689 | CAPEX RAN 3 PART 1 2025 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU | ADL043 | DMT Buke |  |  | KENDARI | -4.2875 | 122.2086 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-22 | Done | Done | 2025-09-22 | Done | 100% | 2025-09-22 | 2025-09-22 | 2025-09-22 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-09-23 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 13 February 2026 | 27-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 | 31-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1387 | 2509-UMIMO-4G#RO-ADL047-0637 | CAPEX RAN 3 PART 1 2025 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | ADL047 | Poleang Utara |  |  | KENDARI | -4.7099 | 121.768 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-18 | Done | Done | 2025-09-18 | Done | 100% | 2025-09-18 | 2025-09-18 | 2025-09-18 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-09-19 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 21 January 2026 | 3-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 | 2025-11-29 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1388 | 2509-UMIMO-4G#RO-ADL088-0690 | CAPEX RAN 3 PART 1 2025 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU | ADL088 | TBG Basala |  |  | KENDARI | -4.3016 | 122.0573 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-15 | Done | Done | 2025-09-15 | Done | 100% | 2025-09-15 | 2025-09-15 | 2025-09-15 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start | 2025-09-16 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 03 February 2026 | 2025-09-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 90%
1389 | 2509-UMIMO-4G#RO-KKA006-0700 | CAPEX RAN 3 PART 1 2025 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | KKA006 | Dawi-Dawi |  |  | KENDARI | -4.1709 | 121.6169 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | TELKOMSEL | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 2025-09-29 | Done | Done | 2025-09-29 | Done | 100% | 2025-09-29 | 2025-09-29 | 2025-09-29 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-09-30 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 19 January 2026 | 27-Oct-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 | 31-Oct-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1390 | 2509-UMIMO-4G#RO-RHA112-0719 | CAPEX RAN 3 PART 1 2025 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | RHA112 | DMT Tondasi |  |  | KENDARI | -4.7573 | 122.3721 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | DMT | [5 empty] | CV. Puri Tepule Abadi | Haerun | Done Productivity 100 % |  |  |  |  | 2025-09-24 | Done | Done | 2025-09-24 | Done | 100% | 2025-09-24 | 2025-09-24 | 2025-09-24 | Connected | Connected |  | 01-Passed | 01-Passed | Work Not Start | 14-Oct-25 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 20 May 2026 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8180 | 22-Oct-25 | 22-Dec-25 | 01-BAUT Approved by Tsel | 13-Wait AS Doc Complete | Done Upload | Invoiced 100%
1391 | 2509-UMIMO-4G#RO-RHA131-0720 | CAPEX RAN 3 PART 1 2025 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | RHA131 | TBG Wakorumba Utara |  |  | KENDARI | -443098 | 12295932 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | TBG | [5 empty] | CV. Puri Tepule Abadi | Haerun | Done Productivity 100 % |  |  |  |  | 05-Oct-25 | Done | Done | 06-Oct-25 | Done | 100% | 06-Oct-25 | 06-Oct-25 | 06-Oct-25 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | 2025-11-07 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 08 May 2026 | 17-Dec-25 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8160 | 18-Oct-25 | 22-Dec-25 | 01-BAUT Approved by Tsel | 13-Wait AS Doc Complete | Done Upload | Invoiced 100%
1392 | 2509-UMIMO-4G#RO-SNN004-0667 | CAPEX RAN 3 PART 1 2025 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SNN004 | Bobong |  |  | TERNATE | -1.9495 | 124.3918 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [28 empty] | Done Req | 45976 | NY Release |  |  | YPTT | Arman | Done Productivity 90 % |  |  |  | 8929450 | 2026-01-15 | Done | 2026-01-16 | 2026-01-18 | Done | 100% | 2026-01-16 | 2026-01-16 | 2026-01-16 | Connected | Connected | Done HI 19 Nov 2025, Conected 06 Dec 2025 because waitting team integrator onboard | 03-NY SM | 01-Passed | No Need | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 20 May 2026 | 25 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8470 | 2025-11-16 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | NEW PO | BOQ_PO 4100008293_Tech.xlsx
1393 | 2509-UMIMO-4G#RO-SNN004-0668 | CAPEX RAN 3 PART 1 2025 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU | SNN004 | Bobong |  |  | TERNATE | -1.9495 | 124.3918 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [28 empty] | Done Req | 45976 | NY Release |  |  | YPTT | Arman | Done Productivity 90 % |  |  |  | 1920499 | 2026-01-15 | Done | 2026-01-16 | 2026-01-18 | Done | 100% | 2026-01-16 | 2026-01-16 | 2026-01-16 | Connected | Connected | Done HI 19 Nov 2025, Conected 06 Dec 2025 because waitting team integrator onboard | 03-NY SM | 01-Passed | No Need | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 20 May 2026 | 12 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8470 | 2025-11-16 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | NEW PO | BOQ_PO 4100008293_Tech.xlsx
1394 | 2509-UMIMO-4G#RO-TOB051-0738 | CAPEX RAN 3 PART 1 2025 | EQP Upgrade BW LTE 2300 50 - 50Mhz Massive MIMO 32T32R | Add RRU | KKA098 | Protelindo Oko Oko |  |  | KENDARI | -4.2883 | 121.5591 | YPTT | 2026-09-25 |  | 2025 | 2025 | [28 empty] | PTI | [5 empty] | CV. Puri Tepule Abadi | Irfan | Done Productivity 100 % |  |  |  |  | 03-Oct-25 | Done | Done | 04-Oct-25 | Done | 100% | 03-Oct-25 | 04-Oct-25 | 04-Oct-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | 2025-11-15 |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2025-11-18 | 2026-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8512 | 2025-11-19 | 22-Dec-25 | 01-BAUT Approved by Tsel | 05-BAST Approved | Done Upload | Invoiced 100%
1395 | 2510-MODRN-4G#RO-TDE018-0063 | CAPEX RAN 3 PART 3 2025 | EQP Modular Upgrade |  | TDE018 | DMT Bale Oba |  |  | TERNATE | 0.39552 | 127.6965 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [28 empty] | Done Req |  |  |  |  | YPTT | Junaedi | Done Productivity 100 % |  |  |  | 6919667 | 2026-01-02 | Done | 2026-01-02 | 2026-01-04 | Done | 100% | 2026-01-02 | 2026-01-04 | 2026-01-04 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound | 30-Dec-25 | DRID07520251230002TSEL |  | Inbound |  |  | 11 May 2026 | 26 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 100%
1396 | 2510-UMIMO-4G#RO-LBA102-0868 | CAPEX RAN 3 PART 4 2025 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | LBA102 | Office HPAL - 909 |  |  | TERNATE | -1.5406 | 127.4146 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TELKOMSEL | Done Req | 46001 | 46001 |  |  | YPTT | Ahmad Jufri | Done Productivity 90 % | Done Invoice | 3500000 | additional cost special transportation from Ternate to Bacan island | 9520808 | 2026-02-01 | Done | 2026-02-06 | 2026-02-08 | Done | 100% | 2026-02-06 | 2026-02-08 | 2026-02-08 | Connected | Connected | Progress started on 15 Dec 2025, but did not start on the 10 Dec 2025 after the team arrived at PT Harita, because the team had to follow company rules. | 01-Passed | 01-Passed | Passed | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound |  | DRID07520260120005TSEL |  | Inbound |  |  | 2026-04-09 | 26 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 70% | BOQ_CP 3 PART 4 2025_V9a_Tech_.xlsx
1397 | 2510-UMIMO-4G#RO-LBA118-0870 | CAPEX RAN 3 PART 4 2025 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | LBA118 | Apartement 14-15 |  |  | TERNATE | -1.5319 | 127.4091 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TELKOMSEL | Waiitting Req |  |  |  |  | YPTT |  | Done Productivity 90 % |  |  |  | 9520808 | 2026-02-02 | Done | 2026-02-05 | 2026-02-07 | Done | 100% | 2026-02-05 | 2026-02-07 | 2026-02-07 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 20 January 2026 | 2026-04-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 90% | BOQ_CP 3 PART 4 2025_V9a_Tech_.xlsx
1398 | 2510-UMIMO-4G#RO-MBA040-0872 | CAPEX RAN 3 PART 4 2025 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU | MBA040 | IWIP Camp Km38 |  |  | TERNATE | 0.66636 | 127.9807 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 9520808 | 2026-03-21 | Done | 2026-03-23 | 2026-03-23 | Done | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | March-26 | Done Tagging | 2026-03-01 | Done Tagging | Progress |  | Done |  | NY Release | NY Release |  |  |  | Inbound |  |  | 2026-04-28 | 2026-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9551 | 2026-04-13 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload | Workoad 70%
1399 | 2511-4GDCS-4G#RO-MBA047-0186 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP New NE 4G LTE 1800 20 Mhz |  | MBA047 | IAAS Hauling Road IWIP KM 53 |  |  | TERNATE | 0.72777 | 128.0274 | YPTT | January-26 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Unqualified 90% |  |  |  | 5741754 | 2026-01-20 | Done | 2026-01-22 | 2026-01-23 | Done | 100% | 2026-02-26 | 2026-02-26 | 2026-02-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | 2026-04-26 | Done Tagging | 2026-04-30 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 15 May 2026 | 15 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9372 | 2026-03-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1400 | 2511-4GDCS-4G#RO-MBA049-0190 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP New NE 4G LTE 1800 20 Mhz |  | MBA049 | IAAS Hauling Road IWIP KM31 |  |  | TERNATE | 0.63995 | 127.9517 | YPTT | January-26 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 5741754 | 2026-01-17 | Done | 2026-01-19 | 2026-01-19 | Done | 100% | 2026-01-19 | 2026-01-19 | 2026-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 07 May 2026 | 07 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9372 | 2026-03-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1401 | 2511-4GDCS-4G#RO-SIN055-0177 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | SSU098 | IAAS Hauling Road IWIP BL South |  |  | TERNATE | 0.53591 | 127.9538 | YPTT | January-26 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 100 % |  |  |  | 5741754 | 2026-01-05 | Done | 2026-01-06 | 2026-01-08 | Done | 100% | 2026-01-06 | 2026-01-08 | 2026-01-08 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 2026-04-27 | 2026-04-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1402 | 2511-4GDCS-4G#RO-SSU017-0205 | IAAS SEPTEMBER 2025 | EQP New NE 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | SSU017 | IWIP KM15 Smelter |  |  | TERNATE | TBD | TBD | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | New Infra | Done Req | 45997 | 45997 |  |  | YPTT | Candra A Putra | Done Productivity 70 % |  |  |  | 13277883 | 2026-01-06 | Done | 2026-01-10 | 2026-01-11 | Done | 100% | 2026-01-10 | 2026-01-11 | 2026-01-11 | Connected | Connected | Waitting Power PLN & FO from PT Iwip | 01-Passed | 01-Passed | No Need | passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 20 May 2026 | 2026-04-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | NY Upload | NEW PO | BOQ_New Infra_IAAS_20251107_14 NE_Tech.xlsx
1403 | 2511-4GDCS-4G#RO-SSU158-0208 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | SSU158 | IWIP PROYEK BATERAI |  |  | TERNATE | 0.48378 | 127.9723 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Waiting approval 100% |  |  |  | 13277883 | 2026-04-02 | Done | 2026-04-04 | 2026-04-06 | Done | 100% | 2026-04-04 | 2026-04-06 | 2026-04-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | May-26 | Done Tagging | May-26 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 20 May 2026 | 20 May 2026 | 00-eATP Approved Tsel | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1404 | 2511-4GDCS-4G#RO-SSU159-0207 | IAAS OKTOBER 2025 | EQP New NE 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | SSU159 | IWIP WORKSHOP DT |  |  | TERNATE | TBD | TBD | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | New Infra | Waiitting Req | Release | Release |  |  | YPTT | Candra A Putra | Done Productivity 90 % |  |  |  | 13277883 | 2026-01-23 | Done | 2026-01-23 | 2026-01-24 | Done | 100% | 2026-01-23 | 2026-01-24 | 2026-01-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | May-26 | Done Tagging | 24-May-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 08 May 2026 | 20 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload | NEW PO | BOQ_New Infra_IAAS_20251107_14 NE_Tech.xlsx
1405 | 2511-ADSTR-4G#RO-LBA073-0452 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Add Sector LTE 2100 2T2R | Swap RRU | LBA073 | GPS Kawasi Lama |  |  | TERNATE | -1.5772 | 127.4423 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TELKOMSEL | Done Req | 46007 | 46007 |  |  | YPTT | Ahmad Jufri | Done Productivity 90 % |  |  |  | 6919667 | 2026-01-16 | Done | 2026-01-20 | 2026-01-23 | Done | 100% | 2026-01-20 | 2026-01-23 | 2026-01-23 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound |  |  |  | Inbound |  |  | 20 May 2026 | 08 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 70% | BOQ_CP1 2026_V9_Acceleration_Tech
1406 | 2511-ADSTR-4G#RO-SSU111-0456 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Add Sector LTE 2100 2T2R | Add Antenna and RRU | SSU111 | IWIP Akomodasi-Q |  |  | TERNATE | 0.49092 | 127.9769 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TELKOMSEL | Done Req | 46005 | 46005 |  |  | YPTT | Candra A Putra | Invoiced 100% |  |  |  | 9516109 | 2026-01-14 | Done | 2026-01-17 | 2026-01-18 | Done | 100% | 2026-01-17 | 2026-01-18 | 2026-01-18 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | July-26 | Done Tagging | July-26 | Done Tagging | waiting tiket |  | Done |  |  | Inbound | 2026-01-06 | DRID07520260108004TSEL |  | Inbound |  |  | 08 May 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | NY Upload | NEW PO | BOQ_CP1 2026_V9_Acceleration_Tech
1407 | 2511-ADSTR-4G#RO-TOB001-0448 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP Add Sector LTE 1800 2T2R |  | TOB001 | DMT Tobelo |  |  | TERNATE | 1.7245 | 127.9986 | YPTT | January-26 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 6919667 | 2026-01-18 | Done | 2026-01-19 | 2026-01-19 | Done | 100% | 2026-01-19 | 2026-01-19 | 2026-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound |  |  |  | Inbound |  |  | 13 February 2026 |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9372 | 2026-03-09 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 70%
1408 | 2511-ADSTR-4G#RO-TOB019-0472 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP Add Sector LTE 900 2T2R |  | TOB019 | Gosoma |  |  | TERNATE | 1.7197 | 128.0104 | YPTT | January-26 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT | Edy Kurniawan | Done Productivity 100 % |  |  |  | 5741754 | 2026-01-10 | Done | 2026-01-11 | 2026-01-11 | Done | 100% | 2026-01-11 | 2026-01-11 | 2026-01-11 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 21 January 2026 | 08 March 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9372 | 2026-03-09 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 90%
1409 | 2511-ADSTR-4G#RO-UPD238-0524 | CAPEX RAN 1 2026 Acceleration Support Part 5 For 5G Implementation | EQP Add Sector NR 2300 Massive MIMO 32T32R | EQP Add Sector NR 2300 Massive MIMO 32T32R | UPD238 | KantorTelkomselPettarani |  |  | MAKASSAR | -5.1718 | 119.4322 | YPTT | January-26 | January-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | Done Productivity 100 % | Done Invoice | 2060000 | Addcost Splicing Qcell_ | 14378479 | 2026-01-23 | Done | 2026-01-29 | 2026-01-29 | Done | 100% | 2026-01-29 | 2026-01-31 | 2026-01-31 | Connected | Connected |  | 01-Passed | 01-Passed | Progress | Passed | February-26 | Done Tagging | 2026-02-17 | Done Tagging | Work Not Start |  | Need | [9 empty] | 03 February 2026 | 14 March 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9516 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1410 | 2511-NNE4G-4G#RO-COI395-0247 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP New NE 4G LTE 2300 50 Mhz |  | COI395 | CombatARRSanana |  |  | TERNATE | 0.46816 | 127.9329 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 100 % |  |  |  | 6211954 | 2025-01-17 | Done | 2025-01-18 | 2025-01-19 | Done | 100% | 2025-01-18 | 2026-01-19 | 2026-01-19 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 19 January 2026 | 2026-04-29 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9052 | 2026-01-21 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 100%
1411 | 2511-NNE4G-4G#RO-DRB001-0252 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP New NE 4G LTE 2300 50 Mhz |  | DRB001 | TBG Ktr Bupati Morotai |  |  | TERNATE | 2.0604 | 128.316 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [29 empty] | Release | Release |  |  | YPTT | Carlos | Done Productivity 100 % |  |  |  | 6211954 | 29-Dec-25 | Done | Done | 2026-01-02 | Done | 100% | 2026-01-02 | 2026-01-02 | 2026-01-02 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 20 May 2026 | 26 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9052 | 2026-01-21 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 90%
1412 | 2511-REENG-4G#RO-COI063-0287 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP eNode B Modular Relocation Service New NE LTE 2100 |  | COI063 | CombatCRUUmaloya |  |  | TERNATE | 0.04852 | 127.8894 | YPTT | January-26 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 6919667 | 2026-01-25 | Done | 2026-01-27 | 2026-01-27 | Done | 100% | 2026-01-27 | 2026-01-27 | 2026-01-27 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Progress |  | Done |  |  | NY Release |  |  |  | Inbound |  |  | 08 May 2026 | 26 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9372 | 2026-03-09 |  | 08-BAUT NY Submit |  | Done Upload | NEW PO
1413 | 2511-REENG-4G#RO-COI935-0290 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP eNode B Modular Relocation Service New NE LTE 2300 |  | COI935 | NIB#3_00060 |  |  | TERNATE | 1.597 | 127.9966 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT | Carlos | Unqualified 90% |  |  |  | 14646757 | 2026-01-01 | Done | Done | 2026-01-03 | Done | 100% | 2026-01-03 | 2026-01-03 | 2026-01-03 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | January-26 | Done Tagging | 2026-01-01 | Progress | Done Tagging |  | Done |  |  | Inbound | 2025-01-06 | DRID07520260105001TSEL |  | Inbound |  |  | 2026-04-09 | 2026-04-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9052 | 2026-01-21 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 70%
1414 | 2511-REENG-4G#RO-SNN003-0320 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP eNode B Modular Relocation Service |  | SNN003 | SULAWESI_00410 |  |  | TERNATE | -2.132 | 125.9573 | YPTT | January-26 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 100 % |  |  |  | 6919667 | 2026-01-17 | Done | 2026-01-18 | 2026-01-18 | Done | 100% | 2026-01-18 | 2026-01-18 | 2026-01-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 2026-05-06 | 2026-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9372 | 2026-03-09 |  | 08-BAUT NY Submit |  | Done Upload | NEW PO
1415 | 2511-UMIMO-4G#RO-COI015-1072 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU | COI015 | IAAS Combat KPS Smelter 1 |  |  | TERNATE | -1.5683 | 127.4259 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TELKOMSEL | Waiitting Req | Release | Release |  |  | YPTT |  | Done Productivity 100 % |  |  |  | 9520808 | 2026-01-23 | Done | 2026-01-28 | 2025-01-30 | Done | 100% | 2026-01-28 | 2026-01-30 | 2026-01-30 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound |  | DRID07520260120004TSEL |  | Inbound |  |  | 2026-04-09 | 15 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 70% | BOQ_CP1 2026_V9_Acceleration_Tech
1416 | 2511-UMIMO-4G#RO-COI287-1167 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU | COI287 | Kantor Penyuluh Pertanian Sagea |  |  | TERNATE | 0.46204 | 128.0891 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TELKOMSEL | Done Req | 46004 | 46004 |  |  | YPTT | Junaedi | Done Productivity 100 % |  |  |  | 9520808 | 2026-02-15 | Done | 2026-02-15 | 2026-02-17 | Done | 100% | 2026-02-15 | 2026-02-17 | 2026-02-17 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound | 2026-01-14 | DRID07520260114001TSEL |  | Inbound |  |  | 2026-04-09 | 07 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 70% | BOQ_CP1 2026_V9_Acceleration_Tech
1417 | 2511-UMIMO-4G#RO-LBA033-1179 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE |  | LBA033 | Protelindo Bacan Kupal |  |  | TERNATE | -0.6666 | 127.4798 | YPTT | December-25 |  | 2025 | 2025 | [42 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 03-NY SM | Work Not Start | Work Not Start |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 06 May 2026 | 2026-04-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9052 | 2026-01-21 |  | 08-BAUT NY Submit |  | NY Upload | NEW PO
1418 | 2511-UMIMO-4G#RO-LBA073-1085 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | LBA073 | GPS Kawasi Lama |  |  | TERNATE | -1.5772 | 127.4423 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TELKOMSEL | Done Req | 46007 | 46007 |  |  | YPTT | Ahmad Jufri | Done Productivity 100 % |  |  |  | 10107363 | 2026-01-16 | Done | 2026-01-20 | 2026-01-23 | Done | 100% | 2026-01-20 | 2026-01-23 | 2026-01-23 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound |  |  |  | Inbound |  |  | 06 May 2026 | 2026-04-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 70% | BOQ_CP1 2026_V9_Acceleration_Tech
1419 | 2511-UMIMO-4G#RO-LBA073-1086 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU | LBA073 | GPS Kawasi Lama |  |  | TERNATE | -1.5772 | 127.4423 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TELKOMSEL | Done Req | 46007 | 46007 |  |  | YPTT | Ahmad Jufri | Done Productivity 90 % |  |  |  | 1920499 | 2026-01-16 | Done | 2026-01-20 | 2026-01-23 | Done | 100% | 2026-01-20 | 2026-01-23 | 2026-01-23 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound |  |  |  | Inbound |  |  | 20 May 2026 | 20 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 70% | BOQ_CP1 2026_V9_Acceleration_Tech
1420 | 2511-UMIMO-4G#RO-LBA102-1087 | Capacity Upgrade 4G | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | LBA102 | Office HPAL - 909 |  |  | TERNATE | -1.5406 | 127.4146 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 8342895 | 02-Dec-25 | Done | 2026-01-03 | 2026-01-03 | Done | 100% | 2026-01-03 | 2026-01-03 | 2026-01-03 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No need |  | No Need | [6 empty] | No Need |  |  | 08 May 2026 | 20 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9372 | 2026-03-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 90%
1421 | 2511-UMIMO-4G#RO-LBA108-0984 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Dismantle RRU | LBA108 | Desa Kawasi 1 |  |  | TERNATE | -1.5409 | 127.4087 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TELKOMSEL | Waiitting Req |  |  |  |  | YPTT |  | Done Productivity 100 % |  |  |  | 1177913 | 2026-01-27 | Done | 2026-01-30 | 2026-01-30 | Done | 100% | 2026-01-30 | 2026-01-30 | 2026-01-30 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound |  |  |  | Inbound |  |  | 13 February 2026 | 08 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8717 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 100% | BOQ_CP1 2026_V9_Acceleration_Tech
1422 | 2511-UMIMO-4G#RO-MBA040-0991 | CAPEX RAN 1 PART 1 2026 | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Dismantle RR | MBA040 | IWIP Camp Km38 |  |  | TERNATE | 0.66636 | 127.9807 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Ready for Productivity 70% |  |  |  | 4782294 | 2026-03-21 | Done | 2026-03-23 | 2026-03-23 | Done | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | No Need |  | No Need |  | No Need | Done Tagging |  | Done |  | NY Release | NY Release |  |  |  | Inbound |  |  | 21 January 2026 |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1423 | 2511-UMIMO-4G#RO-MBA041-1095 | Upgrade | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | MBA041 | IWIP KM70 | L2100 |  | TERNATE | 128.0264 | 0.8 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | In Progress for Productivity |  |  |  | 8342895 | 2026-06-26 | Done | 2026-06-27 | 2026-06-29 | Done | 100% | 2026-06-27 | 2026-06-29 | 2026-06-29 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | June-26 | Done Tagging | June-26 | Done Tagging | no need |  | no need | no need | no need | no need
1424 | 2511-UMIMO-4G#RO-MBA041-1096 | Upgrade | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU | MBA041 | IWIP KM70 | L2100 |  | TERNATE | 128.0264 | 0.8 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | In Progress for Productivity |  |  |  | 2507054 | 2026-06-26 | Done | 2026-06-27 | 2026-06-29 | Done | 100% | 2026-06-27 | 2026-06-29 | 2026-06-29 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | June-26 | Done Tagging | June-26 | Done Tagging | no need |  | no need | no need | no need | no need
1425 | 2511-UMIMO-4G#RO-SSU075-1132 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE |  | SSU075 | EOS Pole-1 |  |  | TERNATE | 0.52541 | 127.9349 | YPTT | January-26 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 9520808 | 2026-01-23 | Done | 2026-01-24 | 2026-01-25 | Done | 100% | 2026-01-24 | 2026-01-25 | 2026-01-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound |  |  |  | Inbound |  |  | 03 February 2026 |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9372 | 2026-03-09 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 70%
1426 | 2511-UMIMO-4G#RO-SSU146-1144 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU | SSU146 | IWIP Industri 4 |  |  | TERNATE | 0.48978 | 127.9731 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | TELKOMSEL | Done Req | 46002 | 46002 |  |  | YPTT | Candra A Putra | Done Productivity 90 % |  |  |  | 8342895 | 2026-01-11 | Done | 2026-01-12 | 2026-01-13 | Done | 100% | 2026-01-12 | 2026-01-13 | 2026-01-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 19 January 2026 | 13 February 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Invoiced 70% | BOQ_CP1 2026_V9_Acceleration_Tech
1427 | 2511-UMIMO-4G#RO-SSU149-1147 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU149 | IAAS IWIP Bengkel 5 |  |  | TERNATE | 49923861 | 1279729718 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | CORPORATE | Waiitting Req | 46006 | 46006 |  |  | YPTT | Candra A Putra | Done Productivity 90 % |  |  |  | 8929450 | 2026-01-15 | Done | 2026-01-20 | 21-Dec-25 | Done | 100% | 2026-01-20 | 2026-01-21 | 2026-01-21 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | May-26 | Done Tagging | 22-May-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 20 May 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | NY Upload | NEW PO | BOQ_CP1 2026_V9_Acceleration_Tech
1428 | 2511-UMIMO-4G#RO-SSU149-1148 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Add RRU | SSU149 | IAAS IWIP Bengkel 5 |  |  | TERNATE | 49923861 | 1279729718 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | CORPORATE | Waiitting Req | 46006 | 46006 |  |  | YPTT | Candra A Putra | Done Productivity 90 % |  |  |  | 1920499 | 2026-01-15 | Done | 2026-01-20 | 21-Dec-25 | Done | 100% | 2026-01-20 | 2026-01-21 | 2026-01-21 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | May-26 | Done Tagging | 22-May-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 08 May 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | NY Upload | NEW PO | BOQ_CP1 2026_V9_Acceleration_Tech
1429 | 2511-UMIMO-4G#RO-SSU151-1150 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU | SSU151 | IAAS IWIP Plant Hydro 2 |  |  | TERNATE | 127.9598 | 127.9598 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | CORPORATE | Waiitting Req | Release | Release |  |  | YPTT | Candra A Putra | Done Productivity 90 % |  |  |  | 10107363 | 2026-01-23 | Done | 2026-01-25 | 2026-01-28 | Done | 100% | 2026-01-25 | 2026-01-28 | 2026-01-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound | 2026-01-08 | DRID07520260108001TSEL |  | Inbound |  |  | 21 January 2026 | 21 January 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Reject Workload 70%, (quality self check ny finished) | BOQ_CP1 2026_V9_Acceleration_Tech
1430 | 2511-UMIMO-4G#RO-SSU151-1151 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU | SSU151 | IAAS IWIP Plant Hydro 2 |  |  | TERNATE | 127.9598 | 127.9598 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | CORPORATE | Waiitting Req | Release | Release |  |  | YPTT | Candra A Putra | Done Productivity 90 % |  |  |  | 1920499 | 2026-02-23 | Done | 2026-02-25 | 2026-02-28 | Done | 100% | 2026-02-25 | 2026-02-28 | 2026-02-28 | Connected | Connected |  | Progress | 01-Passed | Passed | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound | 2026-01-08 | DRID07520260108005TSEL |  | Inbound |  |  | 03 February 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Reject Workload 70%, (quality self check ny finished) | BOQ_CP1 2026_V9_Acceleration_Tech
1431 | 2511-UMIMO-4G#RO-SSU151-1205 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | SSU151 | IAAS IWIP Plant Hydro 2 |  |  | TERNATE | 127.9598 | 127.9598 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | CORPORATE | Waiitting Req | Release | Release |  |  | YPTT | Candra A Putra | Done Productivity 90 % |  |  |  | 10107363 | 2026-01-23 | Done | 2026-01-25 | 2026-01-28 | Done | 100% | 2026-01-25 | 2026-01-28 | 2026-01-28 | Connected | Connected |  | Progress | 01-Passed | Passed | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound | 2026-01-08 | DRID07520260108002TSEL |  | Inbound |  |  | 19 January 2026 | 03 February 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Reject Workload 70%, (quality self check ny finished) | BOQ_CP1 2026_V9_Acceleration_Tech
1432 | 2511-UMIMO-4G#RO-SSU151-1206 | CAPEX RAN 1 2026 Acceleration Support Part 3 for Capacity NARU | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | SSU151 | IAAS IWIP Plant Hydro 2 |  |  | TERNATE | 127.9598 | 127.9598 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [27 empty] | CORPORATE | Waiitting Req | Release | Release |  |  | YPTT | Candra A Putra | Done Productivity 90 % |  |  |  | 1920499 | 2026-01-23 | Done | 2026-01-25 | 2026-01-28 | Done | 100% | 2026-01-25 | 2026-01-28 | 2026-01-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound | 2026-01-08 | DRID07520260108003TSEL |  | Inbound |  |  | 20 May 2026 | 19 January 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-8716 | 9-Dec-25 |  | 08-BAUT NY Submit | 14-Wait Document Complete | Done Upload | Reject Workload 70%, (quality self check ny finished) | BOQ_CP1 2026_V9_Acceleration_Tech
1433 | 2511-UMIMO-4G#RO-TDE018-1210 | Capacity Upgrade 4G | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | TDE018 | DMT Bale Oba |  |  | TERNATE | 0.39552 | 127.6965 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 9520808 | 2026-01-01 | Done | 2026-01-02 | 2026-01-02 | Done | 100% | 2026-01-02 | 2026-01-02 | 2026-01-02 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No need |  | No Need | [6 empty] | No Need |  |  | 08 May 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9372 | 2026-03-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1428 | 2512-4GDCS-4G#RO-JLO009-0211 | New NE | EQP New NE 4G LTE 1800 20 Mhz | RRU | JLO009 | REP LALODA |  |  | TERNATE | 1.5535 | 127.5603 | YPTT | January-26 | January-26 | 2026 | 2026 | 2026 | [7 empty] | YPTT |  |  | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 03-NY SM | 03-NY SM | Work Not Start | Work Not Start |  | Work Not Start | [6 empty] | YPTT |  | Unqualified 90% | Done Email waitting approval | 3500000 | additional cost special transportation from jailolo to site (hard accses) | 5741754 | 2029-06-27 | Done | 2029-06-27 | 2029-06-29 | Done | 100% | 2029-06-27 | 2029-06-29 | 2029-06-29 | Connected | Connected | hard acses | 01-Passed | 01-Passed | No need | passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need |  |  |  | No Need |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9524 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1435 | 2512-4GGSM-4G#RO-JLO021-0111 | RO Jailolo VIP Event | EQP New NE 4G LTE 900 10 Mhz | Add RRU and Module BBU | JLO021 | GAMSIDA_DMT |  |  | TERNATE | 1.3618 | 127.4892 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [28 empty] | Done Req | 46004 | NY Release |  |  | YPTT | Carlos | Done Productivity 70 % |  |  |  | 5741754 | 2026-02-13 | Done | 2026-02-14 | 2026-02-16 | Done | 100% | 2026-02-14 | 2026-02-16 | 2026-02-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 15-Tagging New Asset NY, SM ATP NY | PO Confirmed | S1ID2023070102WBF1-9052 | 2026-01-21 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 70%
1436 | 2512-4GGSM-4G#RO-JLO023-0113 | RO Jailolo VIP Event | EQP New NE 4G LTE 900 10 Mhz | Add RRU and Module BBU | JLO023 | NANAS_DMT |  |  | TERNATE | 1.3862 | 127.4909 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [28 empty] | Done Req | 46007 | NY Release |  |  | YPTT | Carlos | Done Productivity 70 % |  |  |  | 5741754 | 2026-02-16 | Done | 2026-02-16 | 2026-02-18 | Done | 100% | 2026-02-16 | 2026-02-18 | 2026-02-18 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 14-Tagging New Asset NY, SM ATP Done | PO Confirmed | S1ID2023070102WBF1-9052 | 2026-01-21 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 70%
1437 | 2512-ADSTR-4G#RO-TOB027-0548 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP Add Sector LTE 2300 4T4R |  | TOB027 | Protelindo Gamarmalamo |  |  | TERNATE | 1.8175 | 127.7969 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT | Junaedi | Done Productivity 100 % |  |  |  | 2576565 | 2026-01-08 | Done | Done | 2026-01-13 | Done | 100% | 2026-01-13 | 2026-01-13 | 2026-01-13 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 13 March 2026 | 14 March 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9052 | 2026-01-21 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 90%
1438 | 2512-NNE4G-4G#RO-LBA026-0277 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP New NE 4G LTE 2300 50 Mhz |  | LBA026 | PAPALOANG=DMT |  |  | TERNATE | -0.64403 | 127.4996 | YPTT | December-25 |  | 2025 | 2025 | [42 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | 01-Passed | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | Work Not Start | [11 empty] | 2026-03-06 | 2026-03-08 |  | PO Confirmed | S1ID2023070102WBF1-9052 | 2026-01-21 |  | 08-BAUT NY Submit |  | NY Upload | NEW PO
1439 | 2512-REENG-4G#RO-TOB126-0370 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP eNode B Modular Relocation Service New NE LTE 2300 |  | TOB126 | TBG Kakara Pulau |  |  | TERNATE | 1.7479 | 128.0484 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % | Done Invoice | 1500000 | additional cost special transportation from Tobelo to Pulau Karaka | 5741754 | 2026-01-01 | Done | 2026-01-24 | 2026-01-24 | Done | 100% | 2026-01-24 | 2026-01-24 | 2026-01-24 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 12-Tagging New Asset Done, Wait BARA | PO Confirmed | S1ID2023070102WBF1-9052 | 2026-01-21 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 70%
1440 | 2512-UMIMO-4G#RO-SNN018-1481 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE |  | SNN018 | DMT Mangoli |  |  | TERNATE | -1.9298 | 125.9283 | YPTT | January-26 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 100 % |  |  |  | 8342895 | 2026-01-27 | Done | 2026-01-30 | 2026-01-30 | Done | 100% | 2026-01-30 | 2026-01-30 | 2026-01-30 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 06 March 2026 | 08 March 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9372 | 2026-03-09 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 90%
1441 | 2512-UMIMO-4G#RO-TOB003-1467 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE |  | TOB003 | Galela |  |  | TERNATE | 1.823 | 127.839 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT | Junaedi | Done Productivity 90 % |  |  |  | 8342895 | 2026-01-08 | Done | Done | 2026-01-14 | Done | 100% | 2026-01-12 | 2026-01-14 | 2026-01-14 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound |  |  |  | Inbound |  |  | 25 May 2026 | 26 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9052 | 2026-01-21 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 70%
1442 | 2512-UMIMO-4G#RO-TOB016-1470 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE |  | TOB016 | Desa MKCM, Kec. Tobelo |  |  | TERNATE | 1.7313 | 127.9909 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT | Junaedi | Done Productivity 100 % |  |  |  | 9520808 | 2026-01-01 | Done | Done | 2026-01-03 | Done | 100% | 2026-01-03 | 2026-01-03 | 2026-01-03 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound |  |  |  | Inbound |  |  | 2026-04-29 | 2026-04-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9052 | 2026-01-21 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 100%
1443 | 2512-UMIMO-4G#RO-TOB029-1471 | CAPEX RAN 1 2026 Acceleration Support Part 6 For 4G Implementation | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE |  | TOB029 | DMT Tolabit |  |  | TERNATE | 1.7245 | 128.0074 | YPTT | December-25 | January-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT | Junaedi | Done Productivity 100 % |  |  |  | 8342895 | 2026-01-01 | Done | Done | 2026-01-01 | Done | 100% | 2026-01-01 | 2026-01-01 | 2026-01-01 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | January-26 | Done Tagging | 2026-01-01 | Done Tagging | Done Tagging |  | Done |  |  | Inbound |  |  |  | Inbound |  |  | 2026-04-23 | 2026-04-28 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9052 | 2026-01-21 |  | 08-BAUT NY Submit |  | Done Upload | Invoiced 100%
1444 | 2601-4GGSM-4G#RO-DRB013-0024 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | DRB013 | MAKODIM_MOROTAI_DMT |  |  | TERNATE | 2.0545 | 128.3286 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 100 % |  |  |  | 11518218 | 2026-03-14 | Done | 2026-03-15 | 2026-03-16 | Done | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | 2026-04-26 | Done Tagging | 2026-04-30 | Done Tagging | No need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 04 June 2026 | 15 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1445 | 2601-4GGSM-4G#RO-DRB014-0026 |  | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | DRB014 | SAMBIKI_BARU_TBG |  |  | TERNATE | 2.0936 | 128.5421 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 100 % |  |  |  | 11518218 | 2026-04-11 | Done | 2026-04-11 | 2026-04-15 | Done | 100% | 2026-04-11 | 2026-04-15 | 2026-04-15 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | No need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 11 May 2026 | 07 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9654 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1446 | 2602-4GDCS-4G#RO-ARD003-0014 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | ARD003 | MATUNGKAS | L1800 |  | MANADO | 1480822 | 12495517 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | rahmanto hervis | Done Productivity 90 % |  |  |  | 9214574 | 01-May-26 | Done | 01-May-26 | 01-May-26 | Done | 100% | 01-May-26 | 01-May-26 | 16-May-26 | Connected | Connected | waiting PLN & TRM | 01-Passed | 01-Passed | No need | passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need |  |  |  | No Need |  |  | 06 May 2026 | 2026-04-30 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9745 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1447 | 2602-4GDCS-4G#RO-LBA040-0012 | Activity Non MPSL_R09 Sulawesi_2026_MKT New Infra IAAS Batch 2 |  |  | LBA040 | IAAS SPLIT MESS P2 |  |  | TERNATE | -1.5576 | 127.4272 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 12449374 | 2026-02-27 | Done | 2026-02-28 | 2026-03-02 | Done | 100% | 2026-02-28 | 2026-03-02 | 2026-03-02 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 2026-04-29 | 2026-04-27 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9551 | 2026-04-13 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload | NEW PO
1448 | 2602-4GDCS-4G#RO-LBA042-0013 | Activity Non MPSL_R09 Sulawesi_2026_MKT New Infra IAAS Batch 2 |  |  | LBA042 | IAAS HJF TUGU |  |  | TERNATE | -1.5584 | 127.4227 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 100 % |  |  |  | 12449374 | 2026-03-05 | Done | 2026-03-05 | 2026-03-07 | Done | 100% | 2026-03-05 | 2026-03-07 | 2026-03-05 | Connected | Connected |  | Progress | 01-Passed | No Need | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 2026-04-23 | 20 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9525 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1449 | 2602-4GDCS-4G#RO-LBA140-0009 | Activity Non MPSL_R09 Sulawesi_2026_MKT New Infra IAAS Batch 2 | EQP New Site 4G LTE 1800 20 Mhz | New Infra (Add Antenna and RRU and module BBU) | LBA140 | IAAS HPALNS |  |  | TERNATE | -1.5502 | 127.4242 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 11518218 | 2026-03-12 | Done | 2026-03-15 | 2026-03-15 | Done | 100% | 2026-03-15 | 2026-03-15 | 2026-03-15 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | March-26 | Done Tagging | 2026-03-01 | Done Tagging | No need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 04 June 2026 | 20 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9696 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1450 | 2602-4GDCS-4G#RO-LBA141-0010 | Activity Non MPSL_R09 Sulawesi_2026_MKT New Infra IAAS Batch 2 | EQP New Site 4G LTE 1800 20 Mhz | New Infra (Add Antenna and RRU and module BBU) | LBA141 | IAAS OSTPowerPlant |  |  | TERNATE | -1.5631 | 127.42 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 11518218 | 2026-03-12 | Done | 2026-03-13 | 2026-03-15 | Done | 100% | 2026-03-13 | 2026-03-15 | 2026-03-15 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | March-26 | Done Tagging | 2026-03-01 | Done Tagging | No need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 07 June 2026 | 08 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9696 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1451 | 2602-4GDCS-4G#RO-MBA046-0008 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | MBA046 | IAAS Hauling Road IWIP KM43 | L1800 |  | TERNATE | 127.9767 | 0.69152 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | In Progress for Productivity |  |  |  | 5741754 | 2026-06-27 | Done | 2026-06-27 | 2026-06-29 | Done | 100% | 2026-06-27 | 2026-06-29 | 2026-06-29 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | June-26 | Done Tagging | June-26 | Done Tagging | no need |  | no need | no need | no need | no need
1452 | 2602-4GDCS-4G#RO-UPD087-0022 | CAPEX RAN 1 PART 2 2026 | EQP New Site 4G LTE 1800 20 Mhz | Add RRU | UPD087 | WRAPUPUPD794 |  |  | MAKASSAR | -5.133 | 119.4944 | YPTT | June-26 | May-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [9 empty] | 2026-05-13 |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1453 | 2602-4GGSM-4G#1078-SSU147-0135 |  | EQP New NE 4G LTE 900 10 Mhz | RRU+Module | SSU147 | IAAS IWIP Mess KM15-2 | L1800 |  | TERNATE | 127.8886 | 127.8886 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  | 5741754 | 2026-06-27 | Done | 2026-06-27 | 2026-06-29 | Done | 100% | 2026-06-27 | 2026-06-29 | 2026-06-29 | Connected | Connected |  | 0 | 01-Passed | Passed | Passed | June-26 | Done Tagging | June-26 | Done Tagging | no need |  | no need | no need | no need | no need | [8 empty] | 00-eATP Approved Tsel
1454 | 2602-4GGSM-4G#RO-BIT010-0039 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | BIT010 | Permanenisasi COI969 Combat FUN Desa Doorbolang Lembeh | L900 |  | MANADO | 12519646 | 140362 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start |  | Work Not Start | Work Not Start | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need |  | No Need | No Need | [6 empty] | 2026-06-07
1455 | 2602-4GGSM-4G#RO-BIT014-0040 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | BIT014 | PINANGUNIAN | L900 |  | MANADO | 1496075 | 125184803 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 9214574 | 04-May-26 | Done | 06-May-26 | 08-May-26 | Done | 100% | 06-May-26 | 08-May-26 | 08-May-26 | Connected | Connected |  | Progress | 01-Passed | No Need | passed | May-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need |  |  |  | No Need | Ny Upload |  | 2026-05-17 |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9745 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload |  | BOQ_New Infra_Main Buffer_20260429_as IRR_75 sites_Tech
1456 | 2602-4GGSM-4G#RO-BOB005-0041 |  | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | BOB005 | SAHU | L900 |  | TERNATE | -1.6442 | 124553211 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Waitting MOS |  | 5000000 |  | 13572035 |  | NY |  |  | NY |  |  |  |  | NY | Work Not Start | Tower NY RFI | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | Work Not Start |  | Work Not Start | [6 empty] | No Need |  |  | 2026-05-06 |  | 17-Work NY Done | PO NY Release | S1ID2023070102WBF1-9743 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1457 | 2602-4GGSM-4G#RO-DRB009-0043 |  | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | DRB009 | HINO |  |  | TERNATE | 2198397 | 128606766 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | In Progress for Productivity |  |  |  | 11518218 | 2026-06-07 | Done | 2026-06-07 | 2026-06-11 | Done | 100% | 2026-06-07 | 2026-06-11 | 2026-06-11 | Connected | Connected | Tower NY RFI | 01-Passed | 01-Passed | No need | passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 2026-06-05 |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9745 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1458 | 2602-4GGSM-4G#RO-DRB010-0044 |  | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | DRB010 | GORUASELATAN |  |  | TERNATE | 2425922 | 128689623 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | In Progress for Productivity |  |  |  | 11518218 | 2026-06-05 | Done | 2026-06-05 | 2026-06-07 | Done | 100% | 2026-06-05 | 2026-06-07 | 2026-06-07 | Connected | Connected | Tower NY RFI | 01-Passed | 01-Passed | No need | passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 2026-06-05 |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1459 | 2602-4GGSM-4G#RO-DRB011-0045 |  | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | DRB011 | GORUGO_MOROTAIJAYA |  |  | TERNATE | 2568962293 | 1286093387 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 11518218 | 29-May-26 | Done | 29-May-26 | 31-May-26 | Done | 100% | 29-May-26 | 31-May-26 | 31-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 2026-06-05 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9822 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1460 | 2602-4GGSM-4G#RO-DRB012-0046 |  | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | DRB012 | CENDANA_MOROTAIJAYA |  |  | TERNATE | 2630640507 | 1285528813 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 11518218 | 2026-06-01 | Done | 2026-06-01 | 2026-06-05 | Done | 100% | 2026-06-01 | 2026-06-05 | 2026-06-05 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 2026-06-07 |  | 17-Work NY Done | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1461 | 2602-4GGSM-4G#RO-DRB015-0047 |  | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | DRB015 | MIRA_MOROTAITIMUR |  |  | TERNATE | 2157587953 | 1285843671 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | In Progress for Productivity |  |  |  | 11518218 | 2026-06-08 | Done | 2026-06-08 | 2026-06-11 | Done | 100% | 2026-06-08 | 2026-06-11 | 2026-06-11 | Connected | Connected |  | Progress | 01-Passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 2026-06-07 |  | 17-Work NY Done | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1462 | 2602-4GGSM-4G#RO-JNP066-0060 | CAPEX RAN 1 PART 2 2026 | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | JNP066 | Marayoka | L900 |  | MAKASSAR | -5.48862 | 119653839 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | Done Productivity 90 % |  |  |  | 8935345 | 10-May-26 | Done | 10-May-26 | 11-May-26 | Done | 100% | 10-May-26 | 11-May-26 | 24-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | May-26 | Done Tagging | May-26 | Done Tagging | No Need |  | No Need | [9 empty] | 2026-06-07 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9743 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1463 | 2602-4GGSM-4G#RO-LBA037-0064 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | LBA037 | AIRMANGGAINDAH | L900 |  | TERNATE | 127.7546 | -1.36 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Waitting MOS | Waitting Evidance For Email | 4800000 | additional cost special transportation | 9520808 | 11-Aug-26 | Done | 11-Aug-26 | 13-Aug-26 | Done | 100% | 11-Aug-26 | 13-Aug-26 | 13-Aug-26 | Connected | Connected |  | Progress | Progress | No need | Progress |  | Progress |  | Progress | No Need |  | No Need
1464 | 2602-4GGSM-4G#RO-MGN010-0071 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | MGN010 | BANTANE_TBG | L900 |  | MANADO | 12685733 | 424306 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Waiting approval 70% |  |  |  | 9214574 | 2026-07-01 | Done | 2026-07-01 | 2026-07-05 | 13-Aug-26 | 100% | 2026-07-01 | 2026-07-05 | 2026-07-05 | Connected | Connected |  | 01-Passed | passed | No Need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need |  | No Need | No Need | [8 empty] | 00-eATP Approved Tsel
1465 | 2602-4GGSM-4G#RO-MGN011-0072 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | MGN011 | Gemeh-TBG Perm COI575 | L900 |  | MANADO | 12678892 | 424703 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 90 % | Done Invoice | 5000000 | additional cost special transportation from Manado Talaud island | 9214574 | 2026-06-03 | Done | 2026-06-03 | 2026-06-05 | Done | 100% | 2026-06-03 | 2026-06-05 | 2026-07-03 | Connected | Connected | waitting TRM | 01-Passed | 01-Passed | No Need | passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need |  | No Need | No Need | [8 empty] | 00-eATP Approved Tsel | PO Confirmed
1466 | 2602-4GGSM-4G#RO-MGN021-0074 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | MGN021 | BOWOMBARU_TBG | L900 |  | MANADO | 12679199 | 402646 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | In Progress for Productivity |  |  |  | 9214574 | 2026-06-06 | Done | 2026-06-06 | 2026-06-08 | Done | 100% | 2026-06-06 | 2026-06-08 |  | NY | Work Not Start | waitting TRM | Progress | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need |  | No Need | No Need | [9 empty] | PO Confirmed
1467 | 2602-4GGSM-4G#RO-PSW004-0092 | New NE 4G | EQP New NE 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | KWA015 | IloTunggulo-TBG | L900 |  | MANADO | 0.99974 | 122.1389 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 90 % |  |  |  | 9214574 | 04-May-26 | Done | 05-May-26 | 07-May-26 | Done | 100% | 05-May-26 | 7-May-26 | 7-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | May-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need |  |  |  | No Need |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9745 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload |  | BOQ_New Infra_Main Buffer_20260429_as IRR_75 sites_Tech
1468 | 2602-4GGSM-4G#RO-RTN008-0094 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | RTN008 | PERMCOI725COMBATMOPMOREAH_TBG | L900 |  | MANADO |  |  | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 11518218 | 18-May-26 | Done | 18-May-26 | 20-May-26 | Done | 100% | 18-May-26 | 20-May-26 | 01-Aug-26 | Connected | Connected | waiting TRM | 01-Passed | 01-Passed | No need | passed | August-26 | Done Tagging | August-26 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [8 empty] | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1469 | 2602-4GGSM-4G#RO-SNN021-0030 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | RRU+Swap Cabinet+Swap BBU+Swap Module+Antenna Multi Port+Mounting Antenna | SNN021 | B2G_BUYA_MANGOLI | L900 |  | TERNATE | 125.5818 | -1.9275 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Herlianto Ali Sahfi | Done Productivity 70 % |  |  |  | 14209040 | 04-May-26 | Done | 04-May-26 | 07-May-26 | Done | 100% | 04-May-26 | 07-May-26 | 07-May-26 | Connected | Connected | waiting PLN & TRM | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | 2026-06-16 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [8 empty] | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1470 | 2602-4GGSM-4G#RO-SNN022-0103 |  | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | SNN022 | WAIMAN | L900 |  | TERNATE | -2.2144 | 125.9754 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Ready for Productivity 70% |  |  |  | 13572035 | 2026-06-26 | Done | 2026-06-26 | 2026-06-29 | Done | 100% | 2026-06-26 | 2026-06-29 | 2026-06-29 | Connected | Connected | Tower NY RFI | 01-Passed | passed | No need | passed | June-26 | Done Tagging | June-26 | Done Tagging | No need |  | No Need | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1471 | 2602-4GGSM-4G#RO-SNN023-0104 |  | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | SNN023 | WAIU | L900 |  | TERNATE | -191231 | 125.8807 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | In Progress for Productivity | Waitting Evidance For Email | 5500000 | additional cost special transportation | 13572035 | 2026-07-17 | Done | 2026-07-17 | 2026-07-21 | Done | 100% | 2026-07-17 | 2026-07-21 | 2026-07-21 | Connected | Connected |  | Progress | 01-Passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | Progress | [8 empty] | No Need |  |  |  |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1472 | 2602-4GGSM-4G#RO-SNN024-0105 |  | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | SNN024 | PASTINA_DMT |  |  | TERNATE | -2.1128 | 125.9588 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Unqualified 90% |  |  |  | 11518218 | 03-May-26 | Done | 03-May-26 | 08-May-26 | Done | 100% | 03-May-26 | 08-May-26 | 2026-06-14 | Connected | Connected | waitting TRM | 01-Passed | 01-Passed | No need | passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1473 | 2602-4GGSM-4G#RO-SNN025-0106 |  | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | SNN025 | KAWATA |  |  | TERNATE | -1.8824 | 126164252 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Waitting MOS |  |  |  | 11518218 |  | NY |  |  | NY |  |  |  |  | NY | Work Not Start | Tower NY RFI | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | Work Not Start |  | Work Not Start | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1474 | 2602-4GGSM-4G#RO-SNN026-0107 |  | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | SNN026 | MANGON_SANANA |  |  | TERNATE | -2.0532 | 125985481 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 11518218 | 2026-07-03 | Done | 2026-07-03 | 2026-07-06 | Done | 100% | 2026-07-03 | 2026-07-06 | 2026-07-06 | Connected | Connected | Tower NY RFI | 01-Passed | passed | No need | passed | July-26 | Done Tagging | July-26 | Done Tagging | Done Tagging |  | No Need | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1475 | 2602-4GGSM-4G#RO-SNS096-0108 | CAPEX RAN 1 PART 2 2026 | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | SNS096 | Sulawesi_05352 |  |  | MAKASSAR | -5.1606 | 119908149 | YPTT | March-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | Done Productivity 100 % |  |  |  | 10528609 | 27-May-26 | Done | 27-May-26 | 29-May-26 | Done | 100% | 27-May-26 | 29-May-26 | 29-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1476 | 2602-4GGSM-4G#RO-SNS106-0109 | CAPEX RAN 1 PART 2 2026 | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | SNS106 | Bontolempangang |  |  | MAKASSAR | -5.425018 | 119808323 | YPTT | March-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | In Progress for Productivity |  |  |  | 10528609 | 25-May-26 | Done | 25-May-26 | 27-May-26 | Done | 100% | 25-May-26 | 27-May-26 | 27-May-26 | Connected | Connected |  | Progress | 01-Passed | No Need | Progress |  | Progress |  | Progress | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1477 | 2602-4GGSM-4G#RO-SWW022-0113 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | SWW022 | TILANGOBULA_DMT | L900 |  | MANADO |  |  | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 90 % |  |  |  | 10622306.63 | 17-May-26 | Done | 17-May-26 | 18-May-26 | Done | 100% | 17-May-26 | 18-May-26 | 18-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | 22-May-26 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [6 empty] | 04 June 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9822 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1478 | 2602-4GGSM-4G#RO-SWW023-0114 | New NE 4G | EQP New NE 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | SWW023 | UABANGA | L900 |  | MANADO | 0.35386 | 123.2359 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 90 % |  |  |  | 9214574 | 2026-04-28 | Done | 2026-04-30 | 2026-04-30 | Done | 100% | 2026-04-28 | 2026-04-30 |  | Connected | Connected |  | Progress | 01-Passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need |  |  |  | No Need |  |  | 2026-06-07 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1479 | 2602-4GGSM-4G#RO-TOB031-0124 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | TOB031 | BERINGINAGUNG | L900 |  | TERNATE | 12778833 | 137949 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Syahril | Done Productivity 70 % |  |  |  | 11518218 | 03-May-26 | Done | 03-May-26 | 06-May-26 | Done | 100% | 03-May-26 | 06-May-26 | 06-May-26 | Connected | Connected | waiting PLN & TRM | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | 2026-06-12 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [6 empty] | 2026-05-13 |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1480 | 2602-4GGSM-4G#RO-TOB032-0125 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | TOB032 | DORUME | L900 |  | TERNATE | 12783765 | 208887 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Samud Noh | In Progress for Productivity | Waitting Evidance For Email | 3500000 | additional cost special transportation | 11518218 | 2026-06-07 | Done | 2026-06-07 | 2026-07-23 | Done | 100% | 2026-06-07 | 2026-07-23 | 03-Aug-26 | Connected | Connected |  | Progress | 01-Passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need |  | No Need | No Need | [6 empty] | 2026-06-07 |  |  | PO Confirmed | S1ID2023070102WBF1-9742
1481 | 2602-4GGSM-4G#RO-TOB040-0126 | New NE 4G | EQP New Site 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | TOB040 | GAMSUNGI_KAOTELUK | L900 |  | TERNATE | 12764737 | 104684 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Samud Noh | Done Productivity 90 % |  |  |  | 11518218 | 03-May-26 | Done | 03-May-26 | 06-May-26 | Done | 100% | 03-May-26 | 06-May-26 | 06-May-26 | Connected | Connected | waiting PLN & TRM | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | 2026-06-11 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [6 empty] | 2026-05-17 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1482 | 2602-4GGSM-4G#RO-UPD087-0127 | CAPEX RAN 1 PART 2 2026 | EQP New Site 4G LTE 900 10 Mhz | Add Antenna and RRU and module BBU | UPD087 | WRAPUPUPD794 |  |  | MAKASSAR | -5.133 | 119.4944 | YPTT | June-26 | May-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [9 empty] | 2026-05-06 |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1483 | 2602-ADSTR-4G#RO-EPS063-0052 | CAPEX RAN 1 PART 2 2026 | EQP Add Sector LTE 1800 4T4R | Add Antenna and RRU and Swap Module BBU | SNS005 | SNS005 |  |  | MAKASSAR | -5.2946 | 1194396 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | Done Productivity 90 % |  |  |  | 9390369 | 2026-02-23 | Done | 2026-02-23 | 2026-02-25 | Done | 100% | 2026-02-25 | 2026-02-25 | 2026-02-25 | Connected | Connected | SNS005 Swap BBBU Done 24 Feb | 01-Passed | 01-Passed | Passed | Passed | March-26 | Done Tagging | 2026-03-04 | Done Tagging | waiting tiket |  | Need | 2026-03-04 |  | 06-Inbound Done, Wait LDM Submit To WH | 2026-03-02 | DRID03320260227011TSELLTE | Pandu | Inbound |  |  | 2026-06-05 |  | 10-Tagging New Asset & SM ATP Done, Wait BAPA | PO Confirmed | S1ID2023070102WBF1-9516 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1484 | 2602-ADSTR-4G#RO-EPS063-0053 | CAPEX RAN 1 PART 2 2026 | EQP Add Sector LTE 1800 2T2R | Add RRU | SNS005 | SNS005 |  |  | MAKASSAR | -5.2946 | 1194396 | YPTT | March-26 | February-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [9 empty] | 2026-06-05 |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1485 | 2602-ADSTR-4G#RO-UPD207-0327 | Accel CP2 5G 2026 | EQP Add Sector LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU | UPD207 | SCA Tamangapa |  |  | MAKASSAR | -5.1865 | 119.4959 | YPTT | March-26 | February-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [9 empty] | 2026-06-05 |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1486 | 2602-ADSTR-4G#RO-UPD317-0357 | Accel CP2 5G 2026 | EQP Add Sector LTE 2100 2T2R | Swap RRU | UPD317 | TBG Perumahan NTI |  |  | MAKASSAR | -5.1211 | 119.5003 | YPTT | March-26 | February-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [9 empty] | 2026-06-07 |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1487 | 2602-ADSTR-4G#RO-UPD438-0337 | Accel CP2 5G 2026 | EQP Add Sector LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU | UPD438 | Protelindo Bira SMU 6 |  |  | MAKASSAR | -5.0854 | 119.4802 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | Done Productivity 90 % |  |  |  | 1489841 | 2026-03-01 | Done | 2026-03-01 | 2026-03-01 | Done | 100% | 2026-03-01 | 2026-03-01 | 2026-03-01 | Connected | Connected | Partial connected sec 2 & 3, Issue load recty | 01-Passed | 01-Passed | Passed | Passed | March-26 | Done Tagging | 2026-04-15 | Done Tagging | waiting tiket |  | Need | 2026-03-03 | [5 empty] | Ongoing |  |  | 07 June 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9516 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1488 | 2602-iMACR-4G#RO-EPS040-0001 | Activity Non MPSL_R09 Sulawesi_2026_MKT New Infra IAAS Batch 2 |  |  | EPS040 | IAAS Macro HPAL Jetty |  |  | TERNATE | -1.532 | 127.4056 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 7756340 | 2026-03-08 | Done | 2026-03-09 | 2026-03-09 | Done | 100% | 2026-03-09 | 2026-03-09 | 2026-03-10 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 07 June 2026 | 20 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9525 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1489 | 2602-NNE4G-4G#RO-LBA014-0007 | New NE | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | LBA014 | Pertambangan Obi Anggai |  |  | TERNATE |  |  | YPTT | March-26 | March-26 | 2026 | 2026 | [34 empty] | YPTT |  | already 90% ; waiting BAUT |  |  |  | 5741754 | 16-May-26 | Done | 16-May-26 | 18-May-26 | Done | 100% | 16-May-26 | 18-May-26 | 18-May-26 | Connected | Connected | Material Ready 25 Maret 2026 | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | 2026-06-09 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 20 May 2026 | 20 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1490 | 2602-NNE5G-5G#RO-MDO008-0256 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | MDO008 | Singkil |  |  | MANADO |  |  | YPTT | March-26 | March-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 10105936 | 2026-03-26 | Done | 2026-03-27 | 2026-03-29 | Done | 100% | 2026-03-27 | 2026-03-29 | 2026-04-01 | Connected | Connected | TMM done, 5G waiting app tsel | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-15 | Done Tagging | waiting tiket |  | Need | 2026-04-15 | Done Inbound | Release |  |  |  | Inbound |  |  | 08 May 2026 | 08 May 2026 |  | PO Confirmed | S1ID2023070102WBF1-9552 | 2026-04-13 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Workoad 70%
1491 | 2602-NNE5G-5G#RO-MDO023-0258 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | MDO023 | DMT Singkil 2 |  |  | MANADO |  |  | YPTT | March-26 | March-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 70 % |  |  |  | 10105936 | 2026-04-02 | Done | 2026-04-02 | 2026-04-02 | Done | 100% | 2026-04-02 | 2026-04-04 | 2026-04-04 | Connected | Connected | MDO023 Singkil 2 >> HI OG - Comcase | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-07 | Done Tagging | waiting tiket |  | Need | 2026-04-07 | Done Inbound | Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9552 | 2026-04-13 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Workoad 70%
1492 | 2602-NNE5G-5G#RO-MDO166-0261 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | MDO166 | TBG Ranotana |  |  | MANADO |  |  | YPTT | March-26 | March-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 8555135 | 2026-03-26 | Done | 2026-03-26 | 2026-03-27 | Done | 100% | 2026-03-27 | 2026-03-27 | 2026-04-04 | Connected | Connected | need add modul recti | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-07 | Done Tagging | waiting tiket |  | Need | 2026-04-07 | Waitting PU | Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9552 | 2026-04-13 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Workoad 70%
1493 | 2602-NNE5G-5G#RO-MDO258-0267 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | MDO258 | TBG Teling Bawah |  |  | MANADO |  |  | YPTT | March-26 | March-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 70 % |  |  |  | 10427011 | 2026-03-30 | Done | 2026-04-05 | 2026-04-05 | Done | 100% | 2026-04-05 | 2026-04-06 | 2026-04-06 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-10 | Done Tagging | waiting tiket |  | Need | 2026-04-10 | Waitting PU | Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9552 | 2026-04-13 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Workoad 70%
1494 | 2602-NNE5G-5G#RO-MDO263-0268 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | MDO263 | TBG Tuminting Galaxi |  |  | MANADO |  |  | YPTT | March-26 | March-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 10105936 | 2026-04-01 | Done | 2026-04-02 | 2026-04-02 | Done | 100% | 2026-04-02 | 2026-04-03 | 2026-04-04 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-06 | Done Tagging | waiting tiket |  | Need | 2026-04-05 | Done Inbound | Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9552 | 2026-04-13 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Workoad 70%
1495 | 2602-NNE5G-5G#RO-MDO294-0269 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | MDO294 | Protelindo Bogani |  |  | MANADO |  |  | YPTT | March-26 | March-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 70 % |  |  |  | 10427011 | 2026-03-30 | Done | 2026-03-30 | 2026-03-30 | Done | 100% | 2026-03-30 | 2026-03-30 | 2026-04-03 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-13 | Done Tagging | waiting tiket |  | Need | 2026-04-13 | Waitting PU | Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9552 | 2026-04-13 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Workoad 70%
1496 | 2602-NNE5G-5G#RO-MDO462-0274 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | MDO462 | TBG Jembatan Megawati |  |  | MANADO | 124.8453 | 1.4984 | YPTT | March-26 | March-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 8555135 | 2026-03-16 | Done | 2026-03-16 | 2026-03-16 | Done | 100% | 2026-03-16 | 2026-03-17 | 2026-04-02 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-14 | Done Tagging | waiting tiket |  | Need | 2026-04-14 | Waitting PU | Release |  |  |  | Ongoing |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9552 | 2026-04-13 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Workoad 70%
1497 | 2602-NNE5G-5G#RO-MDO524-0275 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | MDO524 | API MCP Malalayang Satu |  |  | MANADO |  |  | YPTT | March-26 | March-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 10105936 | 2026-03-26 | Done | 2026-04-01 | 2026-04-01 | Done | 100% | 2026-04-01 | 2026-04-01 | 2026-04-04 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-07 | Done Tagging | waiting tiket |  | Need | 2026-04-07 | Done Inbound | Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9552 | 2026-04-13 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Workoad 70%
1498 | 2602-NNE5G-5G#RO-SNS002-0005 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | SNS002 | Kab. Gowa |  |  | MAKASSAR | -5.2208 | 119.4466 | YPTT | March-26 | February-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1499 | 2602-NNE5G-5G#RO-SNS009-0007 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | SNS009 | Barombong |  |  | MAKASSAR | -5.2169 | 119.3891 | YPTT | March-26 | February-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1500 | 2602-NNE5G-5G#RO-SNS109-0194 | Accel CP2 5G 2026 | EQP New NE 4G LTE 2300 20 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | SNS109 | ACO Pangka Binanga |  |  | MAKASSAR | -5.2193 | 119.4532 | YPTT | March-26 | February-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1501 | 2602-NNE5G-5G#RO-SNS110-0027 | Accel CP2 5G 2026 | EQP New NE 4G LTE 2300 20 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | SNS110 | ACO Pabangiang |  |  | MAKASSAR | -5.1939 | 119.461 | YPTT | March-26 | February-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1502 | 2602-NNE5G-5G#RO-SNS127-0028 | Accel CP2 5G 2026 | EQP New NE 4G LTE 2300 20 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | SNS127 | ACO Nusa Tamarunang |  |  | MAKASSAR | -5.2198 | 119.4635 | YPTT | March-26 | February-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1503 | 2602-NNE5G-5G#RO-SNS161-0195 | Accel CP2 5G 2026 | EQP New NE 4G LTE 2300 20 Mhz Massive MIMO 32T32R | Add RRU and Swap Module BBU | SNS161 | ACO Bonto Majannang |  |  | MAKASSAR | -5.2054 | 119.4297 | YPTT | March-26 | February-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1504 | 2602-NNE5G-5G#RO-SNS215-0029 | Accel CP2 5G 2026 | EQP New NE 4G LTE 2300 20 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | SNS215 | MC Citra Garden |  |  | MAKASSAR | -5.2014 | 119.4688 | YPTT | March-26 | February-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1505 | 2602-NNE5G-5G#RO-SNS289-0030 | Accel CP2 5G 2026 | EQP New NE 4G LTE 2300 20 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | SNS289 | ACO MM BTN Aura Permai |  |  | MAKASSAR | -5.2037 | 119.4409 | YPTT | March-26 | February-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1506 | 2602-NNE5G-5G#RO-SNS294-0031 | Accel CP2 5G 2026 | EQP New NE 4G LTE 2300 20 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | SNS294 | ACO MM Pao Pao |  |  | MAKASSAR | -5.1895 | 119.4648 | YPTT | August-26 | August-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 15-Tagging New Asset NY, SM ATP NY | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1507 | 2602-NNE5G-5G#RO-TER008-0238 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU | TER008 | DMT Gerai Halo |  |  | TERNATE | 0.79779 | 127.3809 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 10693918 | 2026-03-30 | Done | 2026-03-30 | 2026-04-02 | Done | 100% | 2026-03-30 | 2026-04-02 | 2026-04-02 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1508 | 2602-NNE5G-5G#RO-TER013-0277 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | TER013 | Protelindo Akehuda |  |  | TERNATE | 0.82477 | 127.381 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 13805530 | 2026-03-30 | Done | 2026-03-30 | 2026-04-02 | Done | 100% | 2026-03-30 | 2026-04-02 | 2026-04-02 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1509 | 2602-NNE5G-5G#RO-TER029-0239 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | TER029 | DMT Toboko |  |  | TERNATE | 0.77763 | 127.3805 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 10693918 | 2026-04-02 | Done | 2026-04-02 | 2026-04-04 | Done | 100% | 2026-04-02 | 2026-04-04 | 2026-04-04 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9584 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1510 | 2602-NNE5G-5G#RO-TER031-0278 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | TER031 | Protelindo Ternate Utara |  |  | TERNATE | 0.79398 | 127.3855 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 12632419 | 2026-04-01 | Done | 2026-04-01 | 2026-04-03 | Done | 100% | 2026-04-01 | 2026-04-03 | 2026-04-03 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1511 | 2602-NNE5G-5G#RO-TER059-0240 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | TER059 | TBG Kayu Merah |  |  | TERNATE | 0.76787 | 127.3678 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 12632419 | 2026-04-02 | Done | 2026-04-02 | 2026-04-04 | Done | 100% | 2026-04-02 | 2026-04-04 | 2026-04-04 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1512 | 2602-NNE5G-5G#RO-TER070-0243 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | TER070 | TBG Hotel Majang Ternate |  |  | TERNATE | 0.78252 | 127.3845 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 10693918 | 2026-04-03 | Done | 2026-04-03 | 2026-04-05 | Done | 100% | 2026-04-03 | 2026-04-05 | 2026-04-05 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | 2026-04-26 | Done Tagging | 2026-06-07 | Done Tagging | Done Tagging |  | Ongoing |  |  | NY Release |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1513 | 2602-NNE5G-5G#RO-TER073-0245 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Add RRU and Swap Module BBU | TER073 | TBG Tabona |  |  | TERNATE | 0.77288 | 127.366 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 10867951 | 2026-04-01 | Done | 2026-04-01 | 2026-04-03 | Done | 100% | 2026-04-01 | 2026-04-03 | 2026-04-03 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | 2026-04-26 | Done Tagging | 2026-04-30 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1514 | 2602-NNE5G-5G#RO-TER074-0282 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | TER074 | TBG Fatcey |  |  | TERNATE | 0.80798 | 127.3852 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 12632419 | 2026-04-02 | Done | 2026-04-02 | 2026-04-04 | Done | 100% | 2026-04-02 | 2026-04-04 | 2026-04-04 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | 2026-04-26 | Done Tagging | 2026-04-30 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1515 | 2602-NNE5G-5G#RO-TER075-0246 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU | TER075 | TBG Tanah Tinggi |  |  | TERNATE | 0.78132 | 127.3788 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 13620319 | 2026-04-04 | Done | 2026-04-04 | 2026-04-07 | Done | 100% | 2026-04-04 | 2026-04-07 | 2026-04-07 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1516 | 2602-NNE5G-5G#RO-TER076-0247 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | TER076 | TBG Salahuddin |  |  | TERNATE | 0.7936 | 127.3757 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 12632419 | 2026-03-30 | Done | 2026-03-30 | 2026-04-02 | Done | 100% | 2026-03-30 | 2026-04-02 | 2026-04-02 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1517 | 2602-NNE5G-5G#RO-TER079-0248 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | TER079 | TBG Marikurubu |  |  | TERNATE | 0.78768 | 127.3746 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 12632419 | 2026-03-30 | Done | 2026-03-30 | 2026-04-02 | Done | 100% | 2026-03-30 | 2026-04-02 | 2026-04-02 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1518 | 2602-NNE5G-5G#RO-TER085-0249 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | TER085 | Protelindo Sikko Ternate |  |  | TERNATE | 0.81146 | 127.3812 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 12045864 | 2026-04-01 | Done | 2026-04-01 | 2026-04-03 | Done | 100% | 2026-04-01 | 2026-04-03 | 2026-04-03 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1519 | 2602-NNE5G-5G#RO-TER124-0251 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | TER124 | DMT Pantai Falajawa |  |  | TERNATE | 0.78478 | 127.388 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 12632419 | 2026-04-06 | Done | 1936-04-06 | 2026-04-08 | Done | 100% | 1936-04-06 | 2026-04-08 | 2026-04-08 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1520 | 2602-NNE5G-5G#RO-TER161-0283 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Add RRU | TER161 | DMT Mesjid Raya Al Munawar |  |  | TERNATE | 0.7887 | 127.3907 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 8929450 | 2026-03-13 | Done | 2026-03-13 | 2026-03-13 | Done | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | March-26 | Done Tagging | 2026-03-01 | Done Tagging | No need |  | No Need |  |  | No Need |  |  |  | No Need |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1521 | 2602-NNE5G-5G#RO-TER199-0254 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | TER199 | GipsiPuncak-DMT |  |  | TERNATE | 0.80741 | 127.3763 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 10693918 | 2026-04-01 | Done | 2026-04-01 | 2026-04-03 | Done | 100% | 2026-04-01 | 2026-04-03 | 2026-04-03 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1522 | 2602-NNE5G-5G#RO-UPD025-0206 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz | Add Qcell and Module BBU (5G Qcell 10 pcs) | UPD025 | Mall Ratu Indah |  |  | MAKASSAR | -5.1533 | 119.4167 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | Done Productivity 100 % | Done Invoice | 25441000 | Addcost Installation Qcell | 18028160 | 2026-03-14 | Done | 2026-03-14 | 2026-03-17 | Done | 100% | 2026-03-14 | 2026-03-16 | 2026-03-17 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | passed | 2026-04-26 | Done Tagging | 2026-06-02 | Done Tagging | Done Tagging |  | Need | 2026-04-26 | [10 empty] | 15-Tagging New Asset NY, SM ATP NY | PO Confirmed | S1ID2023070102WBF1-9695 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1523 | 2602-NNE5G-5G#RO-UPD092-0207 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz | Add Qcell and Module BBU (5G Qcell 10 pcs) | UPD092 | Mall Panakukkang |  |  | MAKASSAR | 119.4464 | 119.4464 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Narfin | Done Productivity 100 % | Done Invoice | 9512000 | Addcost Installation Qcell | 33723008 | 2026-03-11 | Done | 2026-03-11 | 2026-03-16 | Done | 100% | 2026-03-11 | 2026-03-16 | 2026-03-17 | Connected | Connected |  | 01-Passed | 01-Passed | passed | passed | 2026-04-26 | Done Tagging | 2026-04-20 | Done Tagging | Work Not Start |  | Need | 2026-04-20 |  | 06-Inbound Done, Wait LDM Submit To WH | 2026-04-22 | DRID03320260414001TSEL5G |  | Inbound |  |  |  |  | 15-Tagging New Asset NY, SM ATP NY | PO Confirmed | S1ID2023070102WBF1-9695 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1524 | 2602-NNE5G-5G#RO-UPD207-0058 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | UPD207 | SCA Tamangapa |  |  | MAKASSAR | -5.1865 | 119.4959 | YPTT | August-26 | August-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1525 | 2602-NNE5G-5G#RO-UPD280-0082 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD280 | Protelindo Batua Raya |  |  | MAKASSAR | -5.1549 | 119.4587 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Kurniadi | Done Productivity 70 % |  |  |  | 10254720 | 2026-03-04 | Done | 2026-03-04 | 2026-03-06 | Done | 100% | 2026-03-06 | 2026-03-06 | 2026-03-11 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | 2026-04-26 | Done Tagging | 2026-04-04 | Done Tagging | Work Not Start |  | Need | [6 empty] | Inbound |  |  |  |  | 10-Tagging New Asset & SM ATP Done, Wait BAPA | PO Confirmed | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1526 | 2602-NNE5G-5G#RO-UPD283-0190 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Add RRU and Swap Module BBU | UPD283 | Protelindo Bandang |  |  | MAKASSAR | -5.1268 | 119.4194 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Kurniadi | Done Productivity 70 % |  |  |  | 9799695 | 2026-03-02 | Done | 2026-03-02 | 2026-03-02 | Done | 100% | 2026-03-02 | 2026-03-02 | 2026-03-02 | Connected | Connected | Ruko tutup minggu | 01-Passed | 01-Passed | Passed | passed | March-26 | Done Tagging | 2026-04-07 | Done Tagging | Work Not Start |  | Done | 2026-03-14 |  |  | 2026-03-30 | DRID03320260313008TSELLTE | DHL | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9516 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1527 | 2602-NNE5G-5G#RO-UPD289-0183 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD289 | Protelindo Perumnas Tamalate |  |  | MAKASSAR | -5.172 | 119.4474 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Kurniadi | Ongoing approval 70% |  |  |  | 9799695 | 2026-03-04 | Done | 2026-03-04 | 2026-03-05 | Done | 100% | 2026-03-04 | 2026-03-05 | 2026-03-14 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | March-26 | Done Tagging | 2026-04-04 | Done Tagging | Work Not Start |  | Done | 2026-03-12 |  | 06-Inbound Done, Wait LDM Submit To WH | 2026-03-27 | DRID03320260313009TSELLTE | Schenker | Inbound |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1528 | 2602-NNE5G-5G#RO-UPD301-0197 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD301 | Protelindo Permata Sudiang |  |  | MAKASSAR | -5.0735 | 119.5303 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | Quintel | Rifqi | Done Productivity 70 % |  |  |  | 9799695 | 2026-03-08 | Done | 2026-03-08 | 2026-03-09 | Done | 100% | 2026-03-10 | 2026-03-10 | 2026-03-14 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | 2026-04-26 | Done Tagging | 2026-04-08 | Done Tagging | Work Not Start |  | Done | 2026-03-27 |  | 06-Inbound Done, Wait LDM Submit To WH | 2026-03-31 | DRID03320260318002TSELLTE | Sinotrans | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1529 | 2602-NNE5G-5G#RO-UPD311-0083 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD311 | TBG BTN Makkiobaji |  |  | MAKASSAR | -5.17 | 119.479 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | Done Productivity 70 % |  |  |  | 9799695 | 2026-03-04 | Done | 2026-03-04 | 2026-03-05 | Done | 100% | 2026-03-05 | 2026-03-05 | 2026-03-05 | Connected | Connected | LOM Power 60m | 01-Passed | 01-Passed | Passed | passed | March-26 | Done Tagging | 2026-04-02 | Done Tagging | Work Not Start |  | Need | [6 empty] | Ongoing |  |  |  |  | 11-Tagging New Asset Done, SM ATP NY & Wait BAPA | PO Confirmed | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1530 | 2602-NNE5G-5G#RO-UPD314-0084 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD314 | Protelindo Pepabri |  |  | MAKASSAR | -5.0916 | 119.5347 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Kurniadi | Done Productivity 70 % |  |  |  | 9799695 | 2026-03-07 | Done | 2026-03-07 | 2026-03-08 | Done | 100% | 2026-03-08 | 2026-03-08 | 2026-03-14 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-06 | Done Tagging | Work Not Start |  | Need | 2026-04-11 |  | 06-Inbound Done, Wait LDM Submit To WH | 2026-04-11 | DRID03320260407001TSEL5G | Uniair | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1531 | 2602-NNE5G-5G#RO-UPD317-0086 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD317 | TBG Perumahan NTI |  |  | MAKASSAR | -5.1211 | 119.5003 | YPTT | August-26 | August-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1532 | 2602-NNE5G-5G#RO-UPD324-0090 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | UPD324 | Protelindo Tol Barukang |  |  | MAKASSAR | -5.1168 | 119.4217 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Kurniadi | Done Productivity 70 % |  |  |  | 8295888 | 2026-03-30 | Done | 2026-03-30 | 2026-03-31 | Done | 100% | 2026-03-31 | 2026-03-31 | 2026-04-01 | Connected | Connected | Comecase 1 mar 2026, clear | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Work Not Start |  | Need | [6 empty] | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1533 | 2602-NNE5G-5G#RO-UPD330-0091 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD330 | DMT Kaluku Bodoa |  |  | MAKASSAR | -5.1177 | 119.4379 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Kurniadi | Done Productivity 70 % |  |  |  | 9799695 | 2026-02-28 | Done | 2026-02-28 | 2026-03-01 | Done | 100% | 2026-03-01 | 2026-03-01 | 2026-03-01 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | March-26 | Done Tagging | 2026-04-20 | Done Tagging | Work Not Start |  | Need | 2026-03-28 |  | 06-Inbound Done, Wait LDM Submit To WH | 2026-04-02 | DRID03220260330003TSEL5G | Schenker | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9516 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1534 | 2602-NNE5G-5G#RO-UPD331-0092 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD331 | DMT SMA17 |  |  | MAKASSAR | -5.1202 | 119.4305 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Narfin | Done Productivity 70 % |  |  |  | 9799695 | 2026-02-28 | Done | 2026-02-28 | 2026-03-01 | Done | 100% | 2026-03-01 | 2026-03-01 | 2026-03-02 | Connected | Connected | Return mounting 3 pcs | 01-Passed | 01-Passed | Passed | passed | March-26 | Done Tagging | 2026-04-29 | Done Tagging | Work Not Start |  | Need | 2026-03-10 |  | 06-Inbound Done, Wait LDM Submit To WH | 2026-03-11 | DRID03320260308001TSELLTE | Temans | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9516 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1535 | 2602-NNE5G-5G#RO-UPD333-0093 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Add RRU and Swap Module BBU | UPD333 | DMT Jl Tajuddin Daya |  |  | MAKASSAR | -5.1102 | 119.517 | YPTT | August-26 | August-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1536 | 2602-NNE5G-5G#RO-UPD341-0094 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Add RRU and Module BBU | UPD341 | DMT Antang 2 |  |  | MAKASSAR | -5.1685 | 119.5054 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | Quintel | Rifqi | Done Productivity 90 % |  |  |  | 8295888 | 2026-03-01 | Done | 2026-03-01 | 2026-03-02 | Done | 100% | 2026-03-02 | 2026-03-02 | 2026-03-03 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | 2026-04-26 | Done Tagging | 2026-04-12 | Done Tagging | No need |  | No Need | [9 empty] | 07 June 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9516 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1537 | 2602-NNE5G-5G#RO-UPD346-0095 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD346 | TBG Bumi Tamalanrea |  |  | MAKASSAR | -5.1366 | 119.5064 | YPTT | August-26 | August-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [9 empty] | 2026-05-17 |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1538 | 2602-NNE5G-5G#RO-UPD352-0097 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD352 | Protelindo Bringkanaya |  |  | MAKASSAR | -5.098 | 119.5166 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | Ongoing approval 70% |  |  |  | 9799695 | 2026-03-08 | Done | 2026-03-09 | 2026-03-09 | Done | 100% | 2026-03-09 | 2026-03-09 | 2026-03-09 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | March-26 | Done Tagging | 2026-04-04 | Done Tagging | Work Not Start |  | Done | 2026-03-14 |  | 06-Inbound Done, Wait LDM Submit To WH | 2026-03-27 | DRID03320260313006TSELLTE | DHL | Inbound |  |  | 2026-05-06 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1539 | 2602-NNE5G-5G#RO-UPD364-0098 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD364 | TBG Kopertis |  |  | MAKASSAR | -5.1458 | 119.4894 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | Quintel | Rifqi | Done Productivity 70 % |  |  |  | 9799695 | 2026-03-12 | Done | 2026-03-12 | 2026-03-13 | Done | 100% | 2026-03-13 | 2026-03-13 | 2026-03-14 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-08 | Done Tagging | Work Not Start |  | Done | [6 empty] | Ongoing |  |  | 2026-06-05 |  | 11-Tagging New Asset Done, SM ATP NY & Wait BAPA | PO Confirmed | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1540 | 2602-NNE5G-5G#RO-UPD369-0099 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Add RRU and Swap Module BBU | UPD369 | Protelindo Galangan kapal |  |  | MAKASSAR | -5.1116 | 119.4313 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | Quintel | Rifqi | Ongoing approval 70% |  |  |  | 8885920 | 2026-03-04 | Done | 2026-03-05 | 2026-03-05 | Done | 100% | 2026-03-05 | 2026-03-05 | 2026-03-14 | Connected | Connected | Issue access smartkey, clear | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-19 | Done Tagging | Done Tagging |  | Done | 2026-04-29 | [5 empty] | Inbound |  |  | 2026-06-05 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1541 | 2602-NNE5G-5G#RO-UPD433-0101 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD433 | Protelindo Mangga Tiga |  |  | MAKASSAR | -5.1265 | 119.5291 | YPTT | August-26 | August-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [9 empty] | 2026-06-05 |  | 17-Work NY Done | PO NY Release | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1542 | 2602-NNE5G-5G#RO-UPD434-0102 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD434 | Protelindo Sudiang 2 |  |  | MAKASSAR | -5.0848 | 119.5162 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Narfin | Done Productivity 70 % |  |  |  | 9799695 | 2026-03-04 | Done | 2026-03-04 | 2026-03-05 | Done | 100% | 2026-03-05 | 2026-03-09 | 2026-03-13 | Connected | Connected | Return mounting 3 pcs,LOM Cable power 50m | 01-Passed | 01-Passed | Passed | Passed | May-26 | Done Tagging | May-26 | Done Tagging | waiting tiket |  | Done |  |  | 06-Inbound Done, Wait LDM Submit To WH | 2026-03-10 | DRID03320260308002TSELLTE | Uniair | Inbound |  |  | 2026-06-07 |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1543 | 2602-NNE5G-5G#RO-UPD435-0103 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD435 | Protelindo 3G Kima Kawasan |  |  | MAKASSAR | -5.1049 | 119.4933 | YPTT | August-26 | August-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [9 empty] | 2026-06-07 |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1544 | 2602-NNE5G-5G#RO-UPD438-0104 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD438 | Protelindo Bira SMU 6 |  |  | MAKASSAR | -5.0854 | 119.4802 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | Done Productivity 70 % |  |  |  | 9799695 | 2026-03-01 | Done | 2026-03-01 | 2026-03-01 | Done | 100% | 2026-03-01 | 2026-03-01 | 2026-03-14 | Connected | Connected | Partial connected sec 2 & 3, Issue load recty | 01-Passed | 01-Passed | Passed | Passed | March-26 | Done Tagging | 2026-04-01 | Done Tagging | Work Not Start |  | Need | 2026-03-14 |  | 06-Inbound Done, Wait LDM Submit To WH | 2026-03-10 | DRID03320260308003TSELLTE | Uniair | Inbound |  |  | 2026-06-07 |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9516 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1545 | 2602-NNE5G-5G#RO-UPD440-0105 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD065 | RS.KustaDaya-DMT |  |  | MAKASSAR | -5.1067 | 119.5219 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Kurniadi | Done Productivity 70 % |  |  |  | 9799695 | 2026-03-16 | Done | 2026-03-16 | 2026-03-17 | Done | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-18 | Done Tagging | Done Tagging |  | Need | [6 empty] | Inbound |  |  |  |  | 15-Tagging New Asset NY, SM ATP NY | PO Confirmed | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1546 | 2602-NNE5G-5G#RO-UPD446-0107 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Add RRU and Swap Module BBU | UPD446 | DMT XL Pacerakkang |  |  | MAKASSAR | -5.1366 | 119.5222 | YPTT | August-26 | August-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1547 | 2602-NNE5G-5G#RO-UPD462-0111 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD462 | DMT BTN Anugrah |  |  | MAKASSAR | -5.1221 | 119.521 | YPTT | August-26 | August-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release | S1ID2023070102WBF1-9743 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1548 | 2602-NNE5G-5G#RO-UPD597-0137 | Accel CP2 5G 2026 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | UPD223 | UKIP_PTI |  |  | MAKASSAR | -5.1167 | 119.5006 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | Quintel | Rifqi | Done Productivity 70 % |  |  |  | 8295888 | 2026-03-16 | Done | 2026-03-16 | 2026-03-17 | Done | 100% | 2026-03-16 | 2026-03-17 | 2026-03-17 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-20 | Done Tagging | Work Not Start |  | Need | [6 empty] | Inbound |  |  |  |  | 15-Tagging New Asset NY, SM ATP NY | PO Confirmed | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1549 | 2602-NNE5G-5G#RO-UPD873-0166 | New NE 5G | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | UPD018 | TBG Ciputra Tallasa City | L1800 |  | MAKASSAR | -5.1081 | 119.4884 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | Done Productivity 70 % |  |  |  | 9799695 | 2026-04-29 | Done | 2026-04-29 | 2026-04-29 | Done | 100% | 2026-04-29 | 2026-04-29 | 2026-04-29 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | May-26 | Done Tagging | 03-May-26 | Done Tagging | waiting tiket |  | Need | 2026-04-30 | [5 empty] | No Need |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9743 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1550 | 2602-REENG-4G#RO-COI013-0004 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP eNode B Modular Relocation Service New NE LTE 900 | Add RRU and Module BBU | COI013 | IAAS Combat KIJA/CCECC/CRCC/MAA |  |  | TERNATE | -1.516 | 127.4462 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Ongoing approval 70% |  |  |  | 5741754 | 2026-03-11 | Done | 2026-03-12 | 2026-03-12 | Done | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1551 | 2602-REENG-4G#RO-SSU102-0022 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP eNode B Modular Relocation Service | Add RRU | SSU102 | IWIP Hauling Road 4 |  |  | TERNATE | 0.61481 | 127.9213 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Ready for Productivity 70% |  |  |  | 2576565 | 2026-03-11 | Done | 07-May-26 | 07-May-26 | Done | 100% | 07-May-26 | 07-May-26 | 07-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | June-26 | Done Tagging | June-26 | Done Tagging | No need |  | No Need |  |  | No Need |  |  |  | No Need |  |  |  |  | Ny Upload | PO Confirmed | S1ID2023070102WBF1-9525 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1552 | 2602-REENG-4G#RO-TOB001-0024 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP eNode B Modular Relocation Service | Add RRU | TOB001 | DMT Tobelo |  |  | TERNATE | 1.7245 | 127.9986 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 5741754 | 2026-02-11 | Done | 2026-02-12 | 2026-02-12 | Done | 100% | 2026-02-12 | 2026-02-12 | 2026-02-12 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | No need |  | No Need |  |  | No Need |  |  |  | No Need |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1553 | 2602-REENG-4G#RO-TOB091-0025 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP eNode B Modular Relocation Service | Swap RRU | TOB091 | DMT Non3T Jere |  |  | TERNATE | 2.165 | 128.0561 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 6919667 | 2026-02-11 | Done | 2026-02-17 | 2026-02-17 | Done | 100% | 2026-02-17 | 2026-02-17 | 2026-02-17 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  | NY Release | Inbound |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1554 | 2602-UMIMO-4G#RO-LBA006-0056 | Upgrade | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU and Swap Module BBU | LBA006 | Laiwui |  |  | TERNATE |  |  | YPTT | March-26 | March-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % | Done Invoice | 3005000 | additional cost special transportation from Ternate to Lawui (Obi) & Lawui (Obi) to Ternate | 10281396 | 15-May-26 | Done | 15-May-26 | 17-May-26 | Done | 100% | 15-May-26 | 17-May-26 | 17-May-26 | Connected | Connected | Material Ready 25 Maret 2026 | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | 2026-06-09 | Done Tagging | No Need |  | No Need | [6 empty] | Inbound |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1555 | 2602-UMIMO-4G#RO-LBA006-0057 | Upgrade | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Mounting Antenna | LBA006 | Laiwui | L2300 |  | TERNATE | 127633842 | -1337707 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Sandy Hayoto | Done Productivity 70 % |  |  |  | 2507054 | 09-May-26 | Done | 09-May-26 | 10-May-26 | Done | 100% | 09-May-26 | 10-May-26 | 10-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | Progress | passed | May-26 | Done Tagging | 2026-06-09 | Done Tagging | waiting tiket |  | Progress | [6 empty] | Inbound |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1556 | 2602-UMIMO-4G#RO-LBA101-0059 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | LBA101 | LQ HPAL Activity Center |  |  | TERNATE | -1.5346 | 127.4073 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 9520808 | 2026-02-05 | Done | 2026-02-06 | 2026-02-06 | Done | 100% | 2026-02-06 | 2026-02-06 | 2026-02-06 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  | NY Release | Inbound | 2026-02-24 | DRID07520260217007TSEL |  | Inbound |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1557 | 2602-UMIMO-4G#RO-MDO258-0776 | Accel CP2 5G 2026 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | MDO258 | TBG Teling Bawah |  |  | MANADO |  |  | YPTT | March-26 | March-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 70 % |  |  |  | 1536399 | 2026-03-30 | Done | 2026-04-05 | 2026-04-05 | Done | 100% | 2026-04-05 | 2026-04-06 | 2026-04-06 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-10 | Done Tagging | Work Not Start |  | Need | 2026-04-10 | Waitting PU | Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9552 | 2026-04-13 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Workoad 70%
1558 | 2602-UMIMO-4G#RO-MDO294-0827 | 2026-CP#2 Part 5G | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | MDO294 | Protelindo Bogani |  |  | MANADO |  |  | YPTT | March-26 | March-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 70 % |  |  |  | 1536399 | 2026-03-30 | Done | 2026-03-30 | 2026-03-30 | Done | 100% | 2026-03-30 | 2026-03-30 | 2026-04-03 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-13 | Done Tagging | Work Not Start |  | Need | 2026-04-13 | Waitting PU | Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9552 | 2026-04-13 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Workoad 70%
1559 | 2602-UMIMO-4G#RO-SNN005-0106 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Dismantle RRU and Activate FMM L18 | SNN005 | TBG Waihama |  |  | TERNATE | -2.0745 | 125.9744 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 4782294 | 2026-02-04 | Done | 2026-02-05 | 2026-02-05 | Done | 100% | 2026-02-05 | 2026-02-05 | 2026-02-05 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | No Need |  | No Need |  | No Need | Progress |  | Done |  | NY Release | NY Release |  |  |  | Inbound |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1560 | 2602-UMIMO-4G#RO-SNN019-0107 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | SNN019 | TBG Sanana |  |  | TERNATE | -2.065 | 125.9804 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 9520808 | 2026-02-17 | Done | 2026-02-21 | 2026-02-21 | Done | 100% | 2026-02-21 | 2026-02-21 | 2026-02-21 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  | NY Release | NY Release |  |  |  | Ongoing |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1561 | 2602-UMIMO-4G#RO-SNS215-0535 | Accel CP2 5G 2026 | EQP Add Sector LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | SNS215 | MC Citra Garden |  |  | MAKASSAR | -5.2014 | 119.4688 | YPTT | August-26 | August-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [5 empty] | NY |  |  | NY |  |  |  |  | NY | Work Not Start | pending | 03-NY SM | 03-NY SM | No Need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1562 | 2602-UMIMO-4G#RO-SSU066-0109 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU | SSU066 | IWIPPelabuhan5 |  |  | TERNATE | -2.5746 | 121.2753 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 9520808 | 2026-03-11 | Done | 2026-03-14 | 2026-03-15 | Done | 100% | 2026-03-15 | 2026-03-15 | 2026-03-15 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  | NY Release | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9525 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Workoad 70%
1563 | 2602-UMIMO-4G#RO-SSU069-0110 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | SSU069 | New Office 3 IWIP |  |  | TERNATE | 0.4761 | 128.0093 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 9520808 | 2026-03-07 | Done | 2026-03-08 | 2026-03-09 | Done | 100% | 2026-03-08 | 2026-03-09 | 2026-03-09 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  | NY Release | NY Release |  |  |  | Inbound |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9525 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1564 | 2602-UMIMO-4G#RO-SSU093-0112 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Dismantle RRU and Activate FMM L18 | SSU093 | IWIP Hauling Road 1 |  |  | TERNATE | 0.48229 | 127.9239 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 4782294 | 2026-02-04 | Done | 2026-02-05 | 2026-02-05 | Done | 100% | 2026-02-05 | 2026-02-05 | 2026-02-05 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | No Need |  | No Need |  | No Need | Passed |  | Done |  | NY Release | NY Release |  |  |  | Inbound |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1565 | 2602-UMIMO-4G#RO-SSU106-0023 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Dismantle RRU and Activate FMM L18 | SSU106 | Akomodasi H |  |  | TERNATE | 0.4915 | 127.9883 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 4782294 | 2026-02-04 | Done | 2026-02-05 | 2026-02-05 | Done | 100% | 2026-02-05 | 2026-02-05 | 2026-02-05 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | No Need |  | No Need |  | No Need | waiting tiket |  | Done |  | NY Release | NY Release |  |  |  | Inbound |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1566 | 2602-UMIMO-4G#RO-SSU111-0113 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Dismantle RRU and Activate FMM L18 | SSU111 | IWIP Akomodasi-Q |  |  | TERNATE | 0.49092 | 127.9769 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | In Progress for Productivity |  |  |  | 4782294 | 2026-02-06 | Done | 2026-02-07 | 2026-02-07 | Done | 100% | 2026-02-07 | 2026-02-07 | 2026-02-07 | Connected | Connected |  | Progress | 01-Passed | Progress | No Need |  | No Need |  | No Need | waiting tiket |  | Ongoing |  | NY Release | NY Release |  |  |  | Ongoing |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1567 | 2602-UMIMO-4G#RO-SSU124-0114 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Dismantle RRU and Activate FMM L18 | SSU124 | IWIP Camp Biri-Biri |  |  | TERNATE | 0.52541 | 127.9349 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 4782294 | 2026-02-06 | Done | 2026-02-07 | 2026-02-07 | Done | 100% | 2026-02-07 | 2026-02-07 | 2026-02-07 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | No Need |  | No Need |  | No Need | waiting tiket |  | Done |  | NY Release | NY Release |  |  |  | Inbound |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1568 | 2602-UMIMO-4G#RO-SSU129-0115 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Dismantle RRU and Activate FMM L18 | SSU129 | IWIP KM17 |  |  | TERNATE | 0.53302 | 127.9041 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 4782294 | 2026-02-08 | Done | 2026-02-08 | 2026-02-08 | Done | 100% | 2026-02-08 | 2026-02-08 | 2026-02-08 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | No Need |  | No Need |  | No Need | waiting tiket |  | Done |  | NY Release | NY Release |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1569 | 2602-UMIMO-4G#RO-SSU147-0118 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | SSU147 | IAAS IWIP Mess KM15-2 |  |  | TERNATE | 127.8886 | 127.8886 | YPTT | February-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 8934253 | 12-May-26 | Done | 13-May-26 | 14-May-26 | Done | 100% | 13-May-26 | 14-May-26 | 14-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | June-26 | Done Tagging | June-26 | Done Tagging | waiting tiket |  | Done |  | NY Release |  |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1570 | 2602-UMIMO-4G#RO-SSU160-0121 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | SSU160 | IWIP Apartemen Tj Eju-1 |  |  | TERNATE | TBD | TBD | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 9520808 | 2026-03-11 | Done | 2026-03-16 | 2026-03-16 | Done | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-30 | Done Tagging | Done Tagging |  | Done |  | NY Release | NY Release |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9525 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1571 | 2602-UMIMO-4G#RO-SSU160-0122 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU | SSU160 | IWIP Apartemen Tj Eju-1 |  |  | TERNATE | TBD | TBD | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 1920499 | 2026-03-11 | Done | 2026-03-16 | 2026-03-16 | Done | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-30 | Done Tagging | Done Tagging |  | Done |  | NY Release | NY Release |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9525 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1572 | 2602-UMIMO-4G#RO-TER008-0717 | Upgrade | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | TER008 | DMT Gerai Halo |  |  | TERNATE | 0.79779 | 127.3809 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 1920499 | 2026-03-30 | Done | 2026-03-30 | 2026-04-02 | Done | 100% | 2026-03-30 | 2026-04-02 | 2026-04-02 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1573 | 2602-UMIMO-4G#RO-TER008-0838 | Upgrade | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU | TER008 | DMT Gerai Halo |  |  | TERNATE | 0.79779 | 127.3809 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 1920499 | 2026-03-30 | Done | 2026-03-30 | 2026-04-02 | Done | 100% | 2026-03-30 | 2026-04-02 | 2026-04-02 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1574 | 2602-UMIMO-4G#RO-TER013-0796 | Upgrade | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | TER013 | Protelindo Akehuda |  |  | TERNATE | 0.82477 | 127.381 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 1920499 | 2026-03-30 | Done | 2026-03-30 | 2026-04-02 | Done | 100% | 2026-03-30 | 2026-04-02 | 2026-04-02 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1575 | 2602-UMIMO-4G#RO-TER013-0797 | Upgrade | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU | TER013 | Protelindo Akehuda |  |  | TERNATE | 0.82477 | 127.381 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 1920499 | 2026-03-30 | Done | 2026-03-30 | 2026-04-02 | Done | 100% | 2026-03-30 | 2026-04-02 | 2026-04-02 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1576 | 2602-UMIMO-4G#RO-TER075-0816 | Upgrade | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | TER075 | TBG Tanah Tinggi |  |  | TERNATE | 0.78132 | 127.3788 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 1920499 | 2026-04-04 | Done | 2026-04-04 | 2026-04-07 | Done | 100% | 2026-04-04 | 2026-04-07 | 2026-04-07 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1577 | 2602-UMIMO-4G#RO-TER075-0817 | Upgrade | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU | TER075 | TBG Tanah Tinggi |  |  | TERNATE | 0.78132 | 127.3788 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 1920499 | 2026-04-04 | Done | 2026-04-04 | 2026-04-07 | Done | 100% | 2026-04-04 | 2026-04-07 | 2026-04-07 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1578 | 2602-UMIMO-4G#RO-TER075-0818 | Upgrade | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU | TER075 | TBG Tanah Tinggi |  |  | TERNATE | 0.78132 | 127.3788 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 1920499 | 2026-04-04 | Done | 2026-04-04 | 2026-04-07 | Done | 100% | 2026-04-04 | 2026-04-07 | 2026-04-07 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 2026-04-01 | Done Tagging | Done Tagging |  | Done |  |  | NY Release |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1579 | 2602-UMIMO-4G#RO-TOB001-0146 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Dismantle Antenna | TOB001 | DMT Tobelo |  |  | TERNATE | 1.7245 | 127.9986 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 10545080 | 2026-02-13 | Done | 2026-02-15 | 2026-02-15 | Done | 100% | 2026-02-15 | 2026-02-15 | 2026-02-15 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  | NY Release | Inbound |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1580 | 2602-UMIMO-4G#RO-TOB017-0148 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | TOB017 | Gorua Selatan |  |  | TERNATE | 1.7595 | 127.9895 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 9520808 | 2026-02-15 | Done | 2026-02-16 | 2026-02-16 | Done | 100% | 2026-02-16 | 2026-02-16 | 2026-02-16 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  | NY Release | Inbound |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1581 | 2602-UMIMO-4G#RO-TOB019-0028 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Dismantle RRU and Activate FMM L18 | TOB019 | Gosoma |  |  | TERNATE | 1.7197 | 128.0104 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 100 % |  |  |  | 4782294 | 2026-02-10 | Done | 2026-02-10 | 2026-02-10 | Done | 100% | 2026-02-10 | 2026-02-10 | 2026-02-10 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | No Need |  | No Need |  | No Need | Passed |  | Done |  | NY Release | Release |  |  |  | Inbound |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1582 | 2602-UMIMO-4G#RO-TOB051-0029 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU | TOB051 | TBG Dakulamo Galela |  |  | TERNATE | 1.8277 | 127.793 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 9520808 | 2026-03-17 | Done | 2026-03-18 | 2026-03-20 | Done | 100% | 2026-03-18 | 2026-03-20 | 2026-03-20 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | March-26 | Done Tagging | 2026-03-01 | Done Tagging | Done Tagging |  | Done |  | NY Release | Inbound |  |  |  | Inbound |  |  |  |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1583 | 2602-UMIMO-4G#RO-TOB061-0154 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU and Dismantle Antenna | TOB061 | DMT Darame |  |  | TERNATE | 2.0556 | 128.3063 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % | Done Invoice | 3000000 | additional cost special transportation from Ternate to Morotai (Daruba) | 10545080 | 2026-02-13 | Done | 2026-02-14 | 2026-02-14 | Done | 100% | 2026-02-14 | 2026-02-14 | 2026-02-14 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  | NY Release | Inbound | 2026-02-26 | DRID07520260217010TSEL |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9525 | 2026-04-09 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1584 | 2602-UMIMO-4G#RO-TOB074-0156 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU | TOB074 | DMT Gosoma Tobelo |  |  | TERNATE | 1.7177 | 128.002 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 9520808 | 2026-02-13 | Done | 2026-02-14 | 2026-02-14 | Done | 100% | 2026-02-14 | 2026-02-14 | 2026-02-14 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | February-26 | Done Tagging | 2026-02-01 | Done Tagging | Done Tagging |  | Done |  | NY Release | Inbound |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | Invoiced 70%
1585 | 2602-UMIMO-4G#RO-TOB122-0158 | CAPEX RAN 1 2026 Acceleration Support Part 3 For Capacity 4G | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Dismantle RRU and Activate FMM L18 | TOB122 | DMT Wosia |  |  | TERNATE | 1.7116 | 128.0105 | YPTT | February-26 | February-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 4782294 | 2026-02-10 | Done | 2026-02-10 | 2026-02-10 | Done | 100% | 2026-02-10 | 2026-02-10 | 2026-02-10 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | No Need |  | No Need |  | No Need | Passed |  | Done |  | NY Release | Release |  |  |  | Inbound |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9354 | 2026-03-06 |  | 08-BAUT NY Submit | 03-Work NY Done | Done Upload | NEW PO
1586 | 2602-UMIMO-4G#RO-UPD280-0586 | Accel CP2 5G 2026 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | UPD280 | Protelindo Batua Raya |  |  | MAKASSAR | -5.1549 | 119.4587 | YPTT | March-26 | February-26 | 2026 | 2026 | [34 empty] | YPTT | Narfin | Done Productivity 70 % |  |  |  | 1489841 | 2026-03-09 | Done | 2026-03-09 | 2026-03-09 | Done | 100% | 2026-03-09 | 2026-03-09 | 2026-03-09 | Connected | Connected |  | 01-Passed | 01-Passed | passed | passed | March-26 | Done Tagging | 19-May-26 | Done Tagging | waiting tiket |  | Need | 2026-03-27 |  | 06-Inbound Done, Wait LDM Submit To WH | 2026-03-30 | DRID03320260313007TSELLTE | Schenker | Inbound |  |  |  |  | 15-Tagging New Asset Done, SM ATP Done | PO Confirmed | S1ID2023070102WBF1-9650 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1587 | 2603-NNE4G-4G#1087-LBA043-0026 |  | EQP New NE 4G LTE 1800 20 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | LBA043 | IAAS_TBP Tondano 2 |  |  | TERNATE | -1.5561 | 127.4397 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Waitting MOS |  |  |  | 11518218 |  | NY |  |  | NY |  |  |  |  | NY | Work Not Start | Tower NY RFI | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | Work Not Start |  | Work Not Start | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1588 | 2603-NNE4G-4G#1087-LBA044-0027 |  | EQP New NE 4G LTE 1800 20 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port | LBA044 | IAAS Eco Village |  |  | TERNATE | -1.5907 | 127.4084 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Waitting MOS |  |  |  | 11518218 |  | NY |  |  | NY |  |  |  |  | NY | Work Not Start | Tower NY RFI | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | Work Not Start |  | Work Not Start | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1589 | 2603-NNE4G-4G#1087-SSU026-0028 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | SSU026 | IAAS IWIP JW-2 |  |  | TERNATE | 0.49965 | 127.9773 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 100 % |  |  |  | 13277883 | 2026-03-30 | Done | 2026-04-02 | 2026-04-06 | Done | 100% | 2026-04-02 | 2026-04-06 | 2026-04-06 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | May-26 | Done Tagging | 16-May-26 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 17 May 2026 | 20 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9582 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1590 | 2603-NNE4G-4G#1087-SSU031-0029 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | SSU031 | IAAS IWIP JW-3 |  |  | TERNATE | 0.49475 | 127.9756 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 13277883 | 2026-03-30 | Done | 2026-04-02 | 2026-04-04 | Done | 100% | 2026-04-02 | 2026-04-04 | 2026-04-04 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | May-26 | Done Tagging | 16-May-26 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  | 06 May 2026 | 08 May 2026 | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9584 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1591 | 2603-TRIAL-4G#RO-TDO156-0003 | FNI | FNI RRU 92642M1821N | FNI RRU 92642M1821N | TDO156 | SoekarnoMatungkas |  |  | MANADO |  |  |  | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 5535733 | 2026-04-02 | Done | 2026-04-02 | 2026-04-02 | Done | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | 2026-04-26 | No Need |  | No Need | No Need |  | No Need | No Need | No Need | No Need | [6 empty] | 2026-06-05 |  | 09-eATP NY Uploaded | PO Confirmed | S1ID2023070102WBF1-9683 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1592 | 2603-UMIMO-4G#1087-SSU112-0866 |  | Dismantle RRU and Activate FMM L18 | Dismantle RRU and Activate FMM L18 | SSU112VL1 | IWIP MESS KM15 |  |  | TERNATE | 0.51198 | 127.9023 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 4782294 | 2026-03-13 | Done | 2026-03-14 | 2026-03-15 | Done | 100% | 2026-03-14 | 2026-03-15 | 2026-03-15 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | No Need |  | No Need |  | No Need | Done Tagging |  | Ongoing |  |  | NY Release |  |  |  | Inbound |  |  | 2026-06-05 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9584 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1593 | 2603-UMIMO-4G#1087-SSU120-0861 |  | Dismantle RRU and Activate FMM L18 | Dismantle RRU and Activate FMM L18 | SSU120VL1 | IWIP AKOMODASI P2 |  |  | TERNATE | 0.47858 | 128.0172 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | On going approval 100% |  |  |  | 4782294 | 2026-03-13 | Done | 2026-03-14 | 2026-03-15 | Done | 100% | 2026-03-14 | 2026-03-15 | 2026-03-15 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | No Need |  | No Need |  | No Need | Done Tagging |  | Ongoing |  |  | NY Release |  |  |  | Inbound |  |  | 2026-06-05 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9584 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1594 | 2603-UMIMO-4G#1087-SSU152-0867 |  | Dismantle RRU and Activate FMM L18 | Dismantle RRU and Activate FMM L18 | SSU152VL1 | IAAS IWIP HF 4 |  |  | TERNATE | 0.47528 | 127.9399 | YPTT | March-26 | March-26 | 2026 | 2026 | 2026 | [33 empty] | YPTT |  | In Progress for Productivity |  |  |  | 4782294 | 2026-03-13 | Done | 2026-03-14 | 2026-03-15 | Done | 100% | 2026-03-14 | 2026-03-15 | 2026-03-15 | Connected | Connected |  | 01-Passed | 01-Passed | Progress | No Need |  | No Need |  | No Need | Progress |  | Ongoing |  |  | NY Release |  |  |  | Ongoing |  |  | 2026-06-07 |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9584 | 2026-04-21 |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1595 | 2604-4GDCS-4G#RO-BIT014-0090 | New NE 4G | BIT014L1800EQP New Site 4G LTE 1800 20 MhzMacro-1_2_3 | Add Antenna and RRU and module BBU | BIT014 | Pinangunian | L1800 |  | MANADO | 125184803 | 1496075 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 4593402.81 | 07-May-26 | Done | 07-May-26 | 08-May-26 | Done | 100% | 07-May-26 | 08-May-26 | 08-May-26 | Connected | Connected |  | Progress | Progress | No need | passed | May-26 | Done Tagging | 2026-06-11 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [6 empty] | 2026-06-07 |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9822 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1596 | 2604-4GDCS-4G#RO-BOB005-0091 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add RRU | BOB005 | SAHU | L1800 |  | TERNATE | -1.6442 | 124553211 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Waitting MOS |  |  |  | 1920499 | [12 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1597 | 2604-4GDCS-4G#RO-COI684-0047 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | RRU+Module | COI684 | Combat MV Malifut CMI | L1800 |  | TERNATE |  |  | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Samud Noh | Done Productivity 90 % |  |  |  | 5741754 | 17-May-26 | Done | 17-May-26 | 17-May-26 | Done | 100% | 17-May-26 | 17-May-26 | 17-May-26 | Connected | Connected |  | Progress | 01-Passed | No need | passed | May-26 | Done Tagging | 2026-06-09 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [8 empty] | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1598 | 2604-4GDCS-4G#RO-DRB009-0094 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | DRB009 | HINO | L1800 |  | TERNATE | 128.6062 | 2.198 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT | Syahril | Ready for Productivity 70% |  |  |  | 5741754 | 2026-06-09 | Done | 2026-06-09 | 2026-06-13 | Done | 100% | 2026-06-09 | 2026-06-13 | 2026-06-13 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need | [18 empty] | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1599 | 2604-4GDCS-4G#RO-DRB010-0241 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add RRU | DRB010 | GORUASELATAN | L1800 |  | TERNATE | 2425922 | 128689623 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT |  | Waitting MOS |  |  |  | 5741754 | [12 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1600 | 2604-4GDCS-4G#RO-DRB011-0313 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add RRU | DRB011 | GORUGO_MOROTAIJAYA | L1800 |  | TERNATE | 2568962293 | 1286093387 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT |  | Waitting MOS |  |  |  | 5741754 | [12 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1601 | 2604-4GDCS-4G#RO-DRB012-0124 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add RRU | DRB012 | CENDANA_MOROTAIJAYA | L1800 |  | TERNATE | 2630640507 | 1285528813 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT |  | Waitting MOS |  |  |  | 5741754 | [12 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1602 | 2604-4GDCS-4G#RO-DRB014-0095 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add RRU | DRB014 | SAMBIKI_BARU | L1800 |  | TERNATE | 12854308 | 209673 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Done Productivity 100 % |  |  |  | 5741754 | 2026-06-18 | Done | 2026-06-18 | 2026-06-21 | Done | 100% | 2026-06-18 | 2026-06-21 | 2026-06-21 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need
1603 | 2604-4GDCS-4G#RO-ISM070-0102 | New NE 4G | ISM070L1800EQP New Site 4G LTE 1800 20 MhzMacro-1_2 | Add RRU | ISM070 | Potanga Boliyohuto | L1800 |  | MANADO | 1226092864 | 0.6995 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 90 % |  |  |  | 4593402.81 | 12-May-26 | Done | 12-May-26 | 13-May-26 | Done | 100% | 12-May-26 | 13-May-26 | 13-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | 2026-06-11 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [8 empty] | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9822 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1604 | 2604-4GDCS-4G#RO-JNP066-0105 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | JPN066 | Marayoka | L1800 |  | MAKASSAR | -5.4886 | 119.6538 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | Done Productivity 70 % |  |  |  | 4454209 | 10-May-26 | Done | 10-May-26 | 11-May-26 | Done | 100% | 10-May-26 | 11-May-26 | 24-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | May-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload |  | BOQ_New Infra_Main Buffer_20260429_as IRR_75 sites_Tech
1605 | 2604-4GDCS-4G#RO-KTG054-0051 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | KTG054 | DMT Dumoga 2 | L1800 |  | MANADO | 0.60381 | 124.0512 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 90 % |  |  |  | 4593403 | 2026-04-25 | Done | 2026-04-25 | 2026-04-25 | Done | 100% | 2026-04-25 | 2026-04-25 | 2026-04-25 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | 2026-04-26 | Done Tagging | 2026-04-27 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [6 empty] | 05 June 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1606 | 2604-4GDCS-4G#RO-KWA015-0129 | New NE 4G | KWA015L1800EQP New Site 4G LTE 1800 20 MhzMacro-1_3 | Add Antenna and RRU and module BBU | KWA015 | Mulangato | L1800 |  | MANADO | 122.138 | 0.99978 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Waiting approval 70% |  |  |  | 4593402.81 | 06-May-26 | Done | 07-May-26 | 07-May-26 | Done | 100% | 07-May-26 | 07-May-26 | 07-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | 2026-06-16 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [6 empty] | 2026-06-05 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9822 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1607 | 2604-4GDCS-4G#RO-LBA037-0111 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add RRU | LBA037 | Air Mangga Indah | L1800 |  | TERNATE | 127.7546 | -1.36 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | In Progress for Productivity |  |  |  | 5741754 | 11-Aug-26 | Done | 11-Aug-26 | 13-Aug-26 | Done | 100% | 11-Aug-26 | 13-Aug-26 | 13-Aug-26 | Connected | Connected |  | Progress | Progress | No need | Progress |  | Progress |  | Progress | No Need |  | No Need
1608 | 2604-4GDCS-4G#RO-NTI447-0059 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | NTI447 | Laba Kecil | L1800 |  | TERNATE | 127.5965 | 1.7017 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  | 5741754 |  |  |  |  | 13-Aug-26 | [7 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need | [11 empty] | Done Upload eATP Waitting Review
1609 | 2604-4GDCS-4G#RO-SNN022-0138 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add RRU | SNN022 | WAIMAN | L1800 |  | TERNATE | -2.2144 | 125.9754 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | In Progress for Productivity |  |  |  | 1920499 | 2026-06-27 | Done | 2026-06-27 | 2026-06-29 | Done | 100% | 2026-06-27 | 2026-06-29 | 2026-06-29 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Done Tagging | June-26 | Done Tagging | no need |  | no need | no need | no need | no need
1610 | 2604-4GDCS-4G#RO-SNN023-0139 | Upgrade | EQP New Site 4G LTE 1800 20 MhZ | Add RRU | SNN023 | WAIU | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | In Progress for Productivity |  |  |  | 1920499 | 2026-07-25 | Done | 2026-07-25 | 2026-07-27 | Done | 100% | 2026-07-25 | 2026-07-27 | 2026-07-27 | Connected | Connected |  | 01-Passed | passed | No need | Passed | August-26 | Done Tagging | August-26 | Done Tagging | No Need |  | No Need
1611 | 2604-4GDCS-4G#RO-SNS096-0140 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | SNS096 | Sulawesi_05352 | L1800 |  | MAKASSAR | -5.1606 | 119.9081 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | Ready for Productivity 70% |  |  |  | 1489841 | 27-May-26 | Done | 27-May-26 | 29-May-26 | Done | 100% | 27-May-26 | 29-May-26 | 29-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 2026-06-05 |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9822 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload |  | BOQ_New Infra_Main Buffer_20260429_as IRR_75 sites_Tech
1612 | 2604-4GDCS-4G#RO-SNS106-0141 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | SNS106 | Bontolempangang | L1800 |  | MAKASSAR | -5.425 | 119.8083 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | In Progress for Productivity |  |  |  | 1489841 | 25-May-26 | Done | 25-May-26 | 27-May-26 | Done | 100% | 25-May-26 | 27-May-26 | 27-May-26 | Connected | Connected |  | Progress | 01-Passed | No need | Progress |  | Progress |  | Progress | No Need |  | No Need | [6 empty] | No Need |  |  | 2026-06-07 |  | 17-Work NY Done | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload |  | BOQ_New Infra_Main Buffer_20260429_as IRR_75 sites_Tech
1613 | 2604-4GDCS-4G#RO-SSU033-0077 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | SSU033 | IAAS_IWIPMESSKM154 | L1800 |  | TERNATE | 127.8895 | 0.5129 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Candra A Putra | Ready for Productivity 70% |  |  |  | 13277883 | 2026-06-02 | Done | 2026-06-02 | 2026-06-06 | Done | 100% | 2026-06-02 | 2026-06-06 | 2026-06-06 | Connected | Connected |  | 01-Passed | passed | No need | Passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | [12 empty] | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1614 | 2604-4GDCS-4G#RO-SSU034-0082 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | SSU034 | IAAS_IWIPHYDROWTP | L1800 |  | TERNATE | 127.9626 | 0.50321 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT | Candra A Putra | Done Productivity 70 % |  |  |  | 13277883 | 2026-06-07 | Done | 2026-06-11 | 2026-06-14 | Done | 100% | 2026-06-11 | 2026-06-14 | 2026-06-14 | Connected | Connected |  | 01-Passed | passed | No need | Passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | [16 empty] | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1615 | 2604-4GDCS-4G#RO-SSU039-0078 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add Antenna and RRU and module BBU | SSU039 | IAAS_IWIPEOSJETTY | L1800 |  | TERNATE | 127.9667 | 0.47723 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Candra A Putra | Done Productivity 70 % |  |  |  | 13277883 | 30-May-26 | Done | 30-May-26 | 03-May-26 | Done | 100% | 30-May-26 | 03-May-26 | 03-May-26 | Connected | Connected |  | 01-Passed | passed | No need | Passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | [12 empty] | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1616 | 2604-4GDCS-4G#RO-TOB031-0152 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add RRU | TOB031 | Beringin Agung | L1800 |  | TERNATE | 127.788 | 1.3778 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT | Sandy Hayoto | Done Productivity 70 % |  |  |  | 13277883 | 2026-06-14 | Done | 2026-06-14 | 2026-06-16 | Done | 100% | 2026-06-14 | 2026-06-16 | 2026-06-16 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Done Tagging | July-26 | Done Tagging | No Need | [18 empty] | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1617 | 2604-4GDCS-4G#RO-TOB040-0153 | New NE 4G | EQP New Site 4G LTE 1800 20 Mhz | Add RRU | TOB040 | GAMSUNGI _Kao Teluk | L1800 |  | TERNATE | 127.6477 | 1.0461 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Sandy Hayoto | Done Productivity 70 % |  |  |  | 5741754 | 2026-06-08 | Done | 2026-06-08 | 2026-06-10 | Done | 100% | 2026-06-08 | 2026-06-10 | 2026-06-10 | Connected | Connected |  | 01-Passed | passed | No Need | Passed | June-26 | Done Tagging | 2026-06-13 | Done Tagging | No Need |  | No Need |  | No Need | No Need | [9 empty] | PO Confirmed
1618 | 2604-4GDCS-4G#RO-TOB040-0126 | New NE 4G | EQP New Site 4G LTE 900 20 Mhz | Add RRU | TOB040 | GAMSUNGI _Kao Teluk | L1800 |  | TERNATE | 127.6474 | 1.0468 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT | Sandy Hayoto | Done Productivity 70 % |  |  |  | 5741754 | 2026-06-11 | Done | 2026-06-11 | 2026-06-13 | Done | 100% | 2026-06-11 | 2026-06-13 | 2026-06-13 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Progress |  | Progress | No Need | [18 empty] | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1619 | 2604-ADSTR-4G#RO-AMR031-0433 | Upgrade | MDO110_Capacity Upgrade 4G_L900_Macro_2_EQP Add Sector LTE 900 2T2R_2026 | Add RRU | MDO110 | DMT Eklesia | L900 |  | MANADO | 124.7929 | 1.4421 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 4593402.81 | 13-May-26 | Done | 13-May-26 | 13-May-26 | Done | 100% | 13-May-26 | 13-May-26 | 13-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | May-26 | Done Tagging | May-26 | Done Tagging | waiting tiket |  | Done |  | Release | Inbound |  |  |  | No Need | Ny Upload |  | 2026-06-07 |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9822 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1620 | 2604-ADSTR-4G#RO-GTO014-0531 | Capacity Upgrade 4G | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Antenna and Module BBU | GTO014 | DMT Limboto 3 | L2300 |  | MANADO | 0.61918 | 123.0044 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 70 % |  |  |  | 7409259 | 2026-04-26 | Done | 2026-04-26 | 2026-04-26 | Done | 100% | 2026-04-26 | 2026-04-26 | 2026-04-26 | Connected | Connected |  | 01-Passed | 01-Passed | SM Passed | passed | 2026-04-26 | Done Tagging | 11-May-26 | Done Tagging | waiting tiket |  | Done | 2026-04-28 | Waitting PU | Release |  |  |  | Inbound |  |  | 2026-06-07 |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1621 | 2604-ADSTR-4G#RO-SSU111-0487 |  | EQP Add Sector LTE 900 2T2R | RRU+Antenna Multi Port | SSU111 | IWIP Akomodasi-Q |  |  | TERNATE | 0.49092 | 127.9769 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 8929554 | 2026-06-24 | Done | 2026-06-24 | 2026-06-26 | Done | 100% | 2026-06-24 | 2026-06-26 | 2026-06-26 | Connected | Connected |  | 01-Passed | passed | No need | Passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1622 | 2604-ADSTR-4G#RO-TOB001-0495 |  | EQP eNode B Modular Relocation Service | RRU+Antenna Multi Port | TOB001 | DMT Tobelo |  |  | TERNATE | 1.7245 | 127.9986 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 5741754 | 2026-04-21 | Done | 2026-04-21 | 2026-04-23 | Done | 100% | 2026-04-21 | 2026-04-23 | 2026-04-23 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | 2026-04-26 | Done Tagging | 2026-04-25 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1623 | 2604-ADSTR-4G#RO-TOB017-0533 | Upgrade | EQP Add Sector LTE 2300 4T4R | RRU | TOB017 | Gorua Selatan |  |  | TERNATE | 1.7595 | 127.9895 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Syahril | Done Productivity 90 % |  |  |  | 5741754 | 11-May-26 | Done | 11-May-26 | 11-May-26 | Done | 100% | 11-May-26 | 11-May-26 | 11-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | 2026-06-09 | Done Tagging | No need |  | No need | [6 empty] | No Need |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1624 | 2604-NNE4G-4G#RO-BAR034-0104 | New NE 4G | EQP New NE 4G LTE 2300 20 Mhz | Add RRU and Swap Antenna and Module BBU | BAR034 | DMT Tuwung Barru | N2300 |  | MAKASSAR | -4.4074 | 119.6227 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Kurniadi | Ongoing approval 70% |  |  |  | 10452283 | 2026-04-28 | Done | 2026-04-28 | 2026-04-28 | Done | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | 2026-04-26 | Done Tagging | 2026-06-17 | Done Tagging | waiting tiket |  | No Need | 2026-04-29 | [5 empty] | Inbound |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9743 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1625 | 2604-NNE4G-4G#RO-BOA079-0050 | Capacity Upgrade 4G | EQP eNode B Modular Relocation Service New NE LTE 2300 | Add RRU and Module BBU | BOA079 | DMT Molombulahe Paguyaman | L2300 |  | MANADO | 0.62927 | 122.5746 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 70 % |  |  |  | 4593403 | 2026-04-22 | Done | 2026-04-22 | 2026-04-22 | Done | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | 2026-04-26 | Done Tagging | 2026-04-24 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [8 empty] | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9681 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1626 | 2604-NNE4G-4G#RO-DRB007-0065 |  | EQP New NE 4G LTE 2300 50 Mhz | RRU+Module | DRB007 | GOTALAMO |  |  | TERNATE | 2.0685 | 128.3039 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 5741754 | 2026-04-20 | Done | 2026-04-20 | 2026-04-22 | Done | 100% | 2026-04-20 | 2026-04-22 | 2026-04-22 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | 2026-04-26 | Done Tagging | 2026-04-30 | Done Tagging | No need |  | No Need | [6 empty] | No Need |  |  | 05 June 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1627 | 2604-NNE4G-4G#RO-ISM066-0106 |  | EQP New NE 4G LTE 2300 50 Mhz | Add RRU and Module BBU | ISM066 | SULAWESI_02801 | L2300 |  | MANADO | 0.60341 | 122.9099 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 90 % |  |  |  | 4593403 | 2026-04-30 | Done | 01-May-26 | 01-May-26 | Done | 100% | 01-May-26 | 01-May-26 | 01-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | May-26 | Done Tagging | 01-May-26 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [6 empty] | 2026-06-05 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9745 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1628 | 2604-NNE4G-4G#RO-SNN009-0108 | New NE | EQP New NE 4G LTE 2300 50 Mhz | RRU+Module+Swap Antenna Multi Port+GPS | SNN009 | WAITINA_DMT |  |  | TERNATE | -1.9162 | 125.9795 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Herlianto Ali Sahfi | already 90% ; waiting BAUT | Done Invoice | 2005000 | additional cost special transportation from Sanana to Buya & Buya To Sanana | 5741754 | 11-May-26 | Done | 11-May-26 | 11-May-26 | Done | 100% | 11-May-26 | 11-May-26 | 11-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | 11-May-26 | Done Tagging | No need |  | No need | [6 empty] | No Need |  |  | 2026-06-07 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1629 | 2604-NNE4G-4G#RO-SSU017-0093 |  | EQP New NE 4G LTE 2300 50 Mhz | RRU | SSU017 | IWIP KM15 Smelter |  |  | TERNATE | 0.51101 | 127.8957 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 1920499 | 2026-06-21 | Done | 2026-06-21 | 2026-06-23 | Done | 100% | 2026-06-21 | 2026-06-23 | 2026-06-23 | Connected | Connected |  | 01-Passed | passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 2026-06-07 |  | 00-eATP Approved Tsel | PO NY Release | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1630 | 2604-NNE4G-4G#RO-TOB026-0098 |  | EQP New NE 4G LTE 2300 50 Mhz | RRU+Module | TOB026 | Cand_CP#1-24__02120 |  |  | TERNATE | 1.7076 | 127.9946 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 5741754 | 2026-04-20 | Done | 2026-04-20 | 2026-04-23 | Done | 100% | 2026-04-20 | 2026-04-23 | 2026-04-23 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | 2026-04-26 | Done Tagging | 2026-06-13 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  | 07 June 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9743 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1631 | 2604-REENG-4G#RO-BLK012-0062 | New NE 4G | EQP eNode B Modular Relocation Service | Swap RRU and Module BBU | BLK012 | DMT Tanuntung | L2100 |  | MAKASSAR | -5.3979 | 120.3753 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Romy | Done Productivity 70 % |  |  |  | 8098511 | 11-May-26 | Done | 11-May-26 | 12-May-26 | Done | 100% | 11-May-26 | 12-May-26 | 12-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | May-26 | Done Tagging | May-26 | Done Tagging | waiting tiket |  | Done |  | Waitting PU |  |  |  |  | No Need |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9745 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1632 | 2604-REENG-4G#RO-BRK016-0034 | Capacity Upgrade 4G | EQP eNode B Modular Relocation Service New NE LTE 1800 | Add RRU | BRK016 | TBG Boroko Kaidipang | L1800 |  | MANADO | 0.90695 | 123.2565 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 4593403 | 02-May-26 | Done | 02-May-26 | 02-May-26 | Done | 100% | 02-May-26 | 03-May-26 | 03-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | May-26 | Done Tagging | 04-May-26 | Work Not Start | No Need |  | No Need | No Need | No Need | No Need | [8 empty] | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9745 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1633 | 2604-REENG-4G#RO-COI519-0063 |  | EQP eNode B Modular Relocation Service New NE LTE 2100 | Swap RRU and Module BBU | COI519 | Combat CRU KM 3DA | L2100 |  | MANADO | 0.87341 | 124.6969 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Unqualified 90% |  |  |  | 8351590 | 2026-04-29 | Done | 2026-04-30 | 2026-04-30 | Done | 100% | 2026-04-30 | 2026-04-30 | 2026-04-30 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | 2026-06-07 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [8 empty] | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9822 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1634 | 2604-REENG-4G#RO-KTG145-0040 | Capacity Upgrade 4G | TDO304_Re-engineering 4G_L2100_Macro_1_EQP eNode B Modular Relocation Service_2026 | Add RRU | TDO304 | TGM Paniki Atas | L2100 |  | MANADO | 124.9211 | 1.4935 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 5535733 | 12-May-26 | Done | 12-May-26 | 13-May-26 | Done | 100% | 12-May-26 | 13-May-26 | 13-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | May-26 | Done Tagging | 16-May-26 | Done Tagging | waiting tiket |  | Done | [6 empty] | Inbound |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1635 | 2604-REENG-4G#RO-MBA048-0041 |  | EQP eNode B Modular Relocation Service New NE LTE 1800 | RRU+Module | MBA048 | IWIP Hauling Road 3-2 |  |  | TERNATE | 0.77521 | 128.0371 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Ready for Productivity 70% |  |  |  | 5741754 | 2026-06-22 | Done | 2026-06-22 | 2026-06-24 | Done | 100% | 2026-06-22 | 2026-06-24 | 2026-06-24 | Connected | Connected |  | 01-Passed | passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO NY Release | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1636 | 2604-REENG-4G#RO-SSU017-0049 |  | EQP eNode B Modular Relocation Service | RRU+Module | SSU017 | IWIP KM15 Smelter |  |  | TERNATE | 0.51101 | 127.8957 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 5741754 | 2026-06-21 | Done | 2026-06-21 | 2026-06-23 | Done | 100% | 2026-06-21 | 2026-06-23 | 2026-06-23 | Connected | Connected |  | 01-Passed | passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1637 | 2604-REENG-4G#RO-SSU018-0050 |  | EQP New NE 4G LTE 900 10 Mhz | RRU+Module | SSU018 | IWIP KM13 Limestone |  |  | TERNATE | 0.48982 | 127.9017 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 5403495 | 29-May-26 | Done | 29-May-26 | 31-May-26 | Done | 100% | 29-May-26 | 31-May-26 | 31-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1638 | 2604-REENG-4G#RO-SSU018-0051 |  | EQP eNode B Modular Relocation Service New NE LTE 2300 | RRU+Module | SSU018 | IWIP KM13 Limestone |  |  | TERNATE | 0.48982 | 127.9017 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 6892736 | 29-May-26 | Done | 29-May-26 | 31-May-26 | Done | 100% | 29-May-26 | 31-May-26 | 31-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | [6 empty] | No Need |  |  |  |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1639 | 2604-REENG-4G#RO-SSU159-0052 |  | EQP New NE 4G LTE 900 10 Mhz | RRU+Module | SSU159 | IWIP WORKSHOP DT |  |  | TERNATE | 0.48836 | 128.0072 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 5741754 | 29-May-26 | Done | 29-May-26 | 31-May-26 | Done | 100% | 29-May-26 | 31-May-26 | 31-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Done Tagging | 2026-06-25 | Done Tagging | No Need |  | No Need |  |  | No Need |  |  |  | No Need |  |  |  |  | 17-Work NY Done | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1640 | 2604-UMIMO-4G#RO-COI016-0934 |  | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Module+Mounting Antenna | COI016 | IAAS Combat Mess & Lab Tondano |  |  | TERNATE | -1.5555 | 127.4443 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | already 90% ; waiting BAUT |  |  |  | 9520808 | 21-May-26 | Done | 21-May-26 | 23-May-26 | Done | 100% | 21-May-26 | 23-May-26 | 23-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | May-26 | Done Tagging | 25-May-26 | Done Tagging | waiting tiket |  | Progress |  | NY Release |  |  |  |  | Inbound |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1641 | 2604-UMIMO-4G#RO-COI896-0938 |  | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | RRU to AAU+Module+Mounting Antenna | COI896 | Combat FUN Event IWIP (SupportKunKerPresiden) |  |  | TERNATE | 0.47999 | 127.9775 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 8342895 | 27-May-26 | Done | 27-May-26 | 29-May-26 | Done | 100% | 27-May-26 | 29-May-26 | 29-May-26 | Connected | Connected |  | passed | passed | No need | Passed | May-26 | Done Tagging | May-26 | Done Tagging | No need |  | No Need | [6 empty] | Work Not Start |  |  |  |  | 17-Work NY Done | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1642 | 2604-UMIMO-4G#RO-DRB003-0941 |  | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | RRU to AAU+Module+Mounting Antenna | DRB003 | Permanenisasi COI620 - Combat FUN Gotalamo Morotai |  |  | TERNATE | 2.0546 | 128.2952 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 8342895 | 2026-04-18 | Done | 2026-04-18 | 2026-04-20 | Done | 100% | 2026-04-18 | 2026-04-20 | 2026-04-20 | Connected | Connected |  | Work Not Start | 01-Passed | No need | Passed | 2026-04-26 | Done Tagging | 2026-04-30 | Done Tagging | No need |  | No Need | [6 empty] | Work Not Start |  |  | 07 June 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1643 | 2604-UMIMO-4G#RO-ISM118-1054 |  | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU | ISM118 | DMT Hutuo Limboto | L2300 |  | MANADO | 0.62562 | 122.9998 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 70 % |  |  |  | 9167447 | 2026-04-25 | Done | 2026-04-25 | 2026-04-25 | Done | 100% | 2026-04-25 | 2026-04-25 | 2026-04-25 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | 2026-04-26 | Done Tagging | 10-May-26 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need |  |  |  | Inbound |  |  | 2026-06-07 |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1644 | 2604-UMIMO-4G#RO-ISM143-0943 | Capacity Upgrade 4G | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU | ISM143 | DMT Makmur Abadi | L1800 |  | MANADO | 0.69865 | 122.5628 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Burhan Pasigi | Done Productivity 70 % |  |  |  | 9167447 | 2026-04-18 | Done | 2026-04-18 | 2026-04-18 | Done | 100% | 2026-04-18 | 2026-04-18 | 2026-04-18 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | May-26 | Done Tagging | 2026-06-11 | Done Tagging | waiting tiket |  | Need | [6 empty] | Inbound |  |  | 2026-06-07 |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1645 | 2604-UMIMO-4G#RO-KTG272-1055 |  | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | KTG272 | DMT TADOY | L1800 |  | MANADO | 0.93242 | 124.1526 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 6674316 | 2026-04-28 | Done | 2026-04-28 | 2026-04-28 | Done | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | 2026-06-13 | Done Tagging | No Need |  | No Need | No Need | No Need | No Need | [8 empty] | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1646 | 2604-UMIMO-4G#RO-LBA021-0953 |  | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | RRU to AAU+Module+Mounting Antenna | LBA021 | Jikotamo |  |  | TERNATE | -1.345 | 127.6566 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Sandy Hayoto | Done Productivity 90 % |  |  |  | 8342895 | 12-May-26 | Done | 12-May-26 | 12-May-26 | Done | 100% | 12-May-26 | 12-May-26 | 12-May-26 | Connected | Connected |  | Progress | 01-Passed | No need | Passed | May-26 | Done Tagging | 15-May-26 | Done Tagging | No need |  | No Need | [6 empty] | Work Not Start |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1647 | 2604-UMIMO-4G#RO-LBA073-0956 |  | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Mounting Antenna | LBA073 | GPS Kawasi Lama |  |  | TERNATE | -1.5772 | 127.4423 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 9520808 | 2026-04-20 | Done | 2026-04-28 | 2026-04-30 | Done | 100% | 2026-04-28 | 2026-04-30 | 2026-04-30 | Connected | Connected |  | Progress | 01-Passed | Passed | Passed | May-26 | Done Tagging | 04-May-26 | Done Tagging | waiting tiket |  | Need | [6 empty] | Inbound |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1648 | 2604-UMIMO-4G#RO-LBA103-1056 | Upgrade | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Mounting Antenna | LBA103 | Mess HJF - P2 |  |  | TERNATE | -1.5576 | 127.4296 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 9520808 | 2026-04-23 | Done | 2026-04-25 | 2026-04-27 | Done | 100% | 2026-04-25 | 2026-04-27 | 2026-04-27 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | 2026-04-26 | Done Tagging | 2026-06-09 | Done Tagging | waiting tiket |  | Progress | [6 empty] | Inbound |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1649 | 2604-UMIMO-4G#RO-LBA112-0958 |  | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Module+Mounting Antenna | LBA112 | Desa EcoVillage |  |  | TERNATE | -1.5909 | 127.4174 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | already 90% ; waiting BAUT |  |  |  | 9520808 | 2026-04-20 | Done | 2026-04-26 | 2026-04-28 | Done | 100% | 2026-04-26 | 2026-04-28 | 2026-04-28 | Connected | Connected |  | Progress | 01-Passed | Passed | passed | May-26 | Done Tagging | 04-May-26 | Done Tagging | waiting tiket |  | Work Not Start | [6 empty] | Inbound |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1650 | 2604-UMIMO-4G#RO-SNN004-1014 |  | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | RRU to AAU+Mounting Antenna | SNN004 | Bobong |  |  | TERNATE | -1.9495 | 124.3918 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Herlianto Ali Sahfi | Done Productivity 90 % |  |  |  | 9520808 | 15-May-26 | Done | 15-May-26 | 16-May-26 | Done | 100% | 15-May-26 | 16-May-26 | 16-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | May-26 | Done Tagging | 18-May-26 | Done Tagging | waiting tiket |  | Done |  | Waitting PU |  |  |  |  | Inbound |  |  | 07 June 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1651 | 2604-UMIMO-4G#RO-SNN068-1068 | Upgrade | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | RRU to AAU+Swap Cabinet+Swap BBU+Swap Module+Mounting Antenna | SNN068 | DMT MM Waiipa Sanana |  |  | TERNATE | -2.0882 | 125.9709 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Herlianto Ali Sahfi | Done Productivity 70 % |  |  |  | 11459309 | 2026-04-28 | Done | 11-May-26 | 16-May-26 | Done | 100% | 11-May-26 | 16-May-26 | 16-May-26 | Connected | Connected | waitting bracket | 01-Passed | 01-Passed | Passed | Passed | June-26 | Done Tagging | June-26 | Done Tagging | waiting tiket |  | Done | [6 empty] | Inbound |  |  | 2026-06-07 |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1652 | 2604-UMIMO-4G#RO-SSU143-1069 | Upgrade | Dismantle RRU and Activate FMM L18 | Dismantle RRU and Activate FMM L18 | SSU143 | IWIP Industri 1 |  |  | TERNATE | 0.48329 | 127.9958 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | In Progress for Productivity |  |  |  | 4782294 | 28-May-26 | Done | 28-May-26 | 30-May-26 | Done | 100% | 28-May-26 | 30-May-26 | 05-Aug-26 | Connected | Connected |  | Progress | Progress | Progress | No Need |  | No Need |  | No Need | waiting tiket |  | Progress | [6 empty] | Work Not Start |  |  |  |  | 17-Work NY Done | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1653 | 2604-UMIMO-4G#RO-SSU151-1024 |  | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Mounting Antenna | SSU151 | IAAS IWIP Plant Hydro 2 |  |  | TERNATE | 127.9598 | 127.9598 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT |  | Unqualified 90% |  |  |  | 9520808 | 23-May-26 | Done | 24-May-26 | 25-May-26 | Done | 100% | 24-May-26 | 25-May-26 | 25-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | May-26 | Done Tagging | May-26 | Done Tagging | waiting tiket |  | Done |  | NY Release |  |  |  |  | Inbound |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1654 | 2604-UMIMO-4G#RO-SSU157-1026 |  | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Module+Mounting Antenna | SSU157 | Split Tambang Baru IWIP |  |  | TERNATE | 0.47713 | 127.9523 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 9520808 | 28-May-26 | Done | 28-May-26 | 30-May-26 | Done | 100% | 28-May-26 | 30-May-26 | 30-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | June-26 | Done Tagging | 2026-06-05 | Done Tagging | waiting tiket |  | Done |  | waitting PU |  |  |  |  | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1655 | 2604-UMIMO-4G#RO-SSU160-1028 |  | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Module+Mounting Antenna | SSU160 | IWIP Apartemen Tj Eju-1 |  |  | TERNATE | 0.48296 | 127.9813 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 9520808 | 2026-06-24 | Done | 2026-06-24 | 2026-06-26 | Done | 100% | 2026-06-24 | 2026-06-26 | 2026-06-26 | Connected | Connected |  | 01-Passed | passed | No need | Passed | June-26 | Done Tagging | June-26 | Done Tagging | No Need |  | No Need | [6 empty] | Inbound |  |  |  |  | 17-Work NY Done | PO NY Release |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1656 | 2604-UMIMO-4G#RO-TDO266-1035 | Capacity Upgrade 4G | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU | TDO266 | TBG Tatelu Sukur | L1800 |  | MANADO | 1.5244 | 124.9887 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Done Productivity 70 % |  |  |  | 9167447 | 2026-04-19 | Done | 2026-04-19 | 2026-04-19 | Done | 100% | 2026-04-19 | 2026-04-19 | 2026-04-19 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 2026-04-26 | Done Tagging | 04-May-26 | Done Tagging | waiting tiket |  | Need | [6 empty] | Inbound |  |  |  |  | Done Upload eATP Waitting Review | PO Confirmed | S1ID2023070102WBF1 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1657 | 2604-UMIMO-4G#RO-TMH019-1071 |  | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | TMH019 | STP Terminal Tomohon | L1800 |  | MANADO | 1.3274 | 124.8435 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | Quintel | Rahmanto hervis | Unqualified 90% |  |  |  | 7616646 | 09-May-26 | Done | 09-May-26 | 11-May-26 | Done | 100% | 09-May-26 | 11-May-26 | 11-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | May-26 | Done Tagging | 16-May-26 | Done Tagging | waiting tiket |  | Done | 15-May-26 | [5 empty] | Inbound |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9745 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1658 | 2604-UMIMO-4G#RO-TOB019-1043 |  | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Mounting Antenna | TOB019 | Gosoma |  |  | TERNATE | 1.7197 | 128.0104 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 9520808 | 2026-04-23 | Done | 2026-04-23 | 2026-04-25 | Done | 100% | 2026-04-23 | 2026-04-25 | 2026-04-25 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | 2026-04-26 | Done Tagging | 2026-06-09 | Done Tagging | waiting tiket |  | Need | [6 empty] | Inbound |  |  |  |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1659 | 2604-UMIMO-4G#RO-TOB020-1044 |  | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Swap Cabinet+Swap BBU+Swap Module+Mounting Antenna | TOB020 | DMT Pitu |  |  | TERNATE | 1.6832 | 128.008 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  | 11459309 | 2026-04-26 | Done | 2026-04-26 | 2026-04-28 | Done | 100% | 2026-04-26 | 2026-04-28 | 2026-04-28 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | 2026-04-26 | Done Tagging | 2026-06-10 | Done Tagging | waiting tiket |  | Need | [6 empty] | Inbound |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1660 | 2604-UMIMO-4G#RO-TOB023-1045 |  | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | RRU to AAU+Module+Mounting Antenna | TOB023 | DMT Tobelo Timur |  |  | TERNATE | 1.5715 | 128.0333 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 90 % |  |  |  | 8342895 | 2026-04-23 | Done | 2026-04-23 | 2026-04-25 | Done | 100% | 2026-04-23 | 2026-04-25 | 2026-04-25 | Connected | Connected |  | 01-Passed | 01-Passed | No Need | passed | 2026-04-26 | Done Tagging | 2026-06-08 | Done Tagging | No Need |  | No Need | [6 empty] | Work Not Start |  |  | 07 June 2026 |  | 00-eATP Approved Tsel | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1661 | 2604-UMIMO-4G#RO-TOB054-1047 |  | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Dismantle RRU and Activate FMM L18 | TOB054 | DMT Wari Tobelo |  |  | TERNATE | 1.7473 | 127.9952 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Syahril | Done Productivity 70 % |  |  |  | 4782294 | 2026-04-24 | Done | 2026-04-24 | 2026-04-24 | Done | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | No Need |  | No Need |  | No Need | waiting tiket |  | Done |  |  | Release |  |  |  | Inbound |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1662 | 2604-UMIMO-4G#RO-TOB075-1072 | Upgrade | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU to AAU+Mounting Antenna | TOB075 | TBG Leleoto |  |  | TERNATE | 1.595 | 127.9992 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Samud Noh | Done Productivity 70 % |  |  |  | 8342895 | 11-May-26 | Done | 11-May-26 | 11-May-26 | Done | 100% | 11-May-26 | 11-May-26 | 11-May-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | passed | May-26 | Done Tagging | 2026-06-11 | Done Tagging | No need |  | No need | [6 empty] | Inbound |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1663 | 2604-UMIMO-4G#RO-TOB123-1073 | Upgrade | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | RRU to AAU+Mounting Antenna | TOB123 | Desa Gomhaku |  |  | TERNATE | 1.6641 | 127.9885 | YPTT | 2026-04-26 | 2026-04-26 | 2026 | 2026 | [34 empty] | YPTT | Samud Noh | Done Productivity 70 % |  |  |  | 9520808 | 12-May-26 | Done | 12-May-26 | 12-May-26 | Done | 100% | 12-May-26 | 12-May-26 | 12-May-26 | Connected | Connected |  | Progress | 01-Passed | Progress | passed | May-26 | Done Tagging | 2026-06-11 | Done Tagging | Progress |  | Progress | [6 empty] | Inbound |  |  |  |  | 17-Work NY Done | PO Confirmed | S1ID2023070102WBF1-9742 |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1664 | 2605-QCELL-4G#RO-UPD092-0001 | Qcell MP | EQP New Qcell |  | UPD092 | Qcell MP |  |  | MAKASSAR |  |  | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Kurniadi | In Progress for Productivity | Waitting Evidance For Email | 40875000 | Addcost Installation Qcell | 20217472 | 08-May-26 | Done | 08-May-26 |  | NY | 50% | 08-May-26 |  |  | NY | Prorgress |  | Progress | Progress | No Need | Progress |  | Progress |  | Progress | Progress |  | No Need |  | No Need | No Need | [9 empty] | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1665 | 2605-QCELL-5G#RO-UPD088-0005 | Qcell Bandara | EQP New Qcell | Qcell_Area Terminal | UPD088 | Bandara Sultan Hasanuddin | L1800+L2100+L2300+NR2300 |  | MAKASSAR | 12783765 | 208887 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Kurniadi | In Progress for Productivity | PR Release | 22050000 | Addcost Installation Qcell | 15654016 | 23-May-26 | Done | 23-May-26 | 27-May-26 | Done | 100% | 23-May-26 | 27-May-26 | 27-May-26 | Connected | Connected |  | Progress | Progress | No Need | Progress |  | Progress |  | Progress | Progress |  | No Need |  | No Need | No Need | [9 empty] | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1666 | 2605-QCELL-5G#RO-UPD088-0005 | Qcell Bandara | EQP New Qcell | Qcell_Area Terminal | UPD088 | Bandara Sultan Hasanuddin | L1800+L2100+L2300+NR2300 |  | MAKASSAR | 12783765 | 208887 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Kurniadi | In Progress for Productivity |  |  |  | 15654016 | 23-May-26 | Done | 23-May-26 | 27-May-26 | Done | 100% | 23-May-26 | 27-May-26 | 27-May-26 | Connected | Connected |  | Progress | Progress | No Need | Progress |  | Progress |  | Progress | Progress |  | No Need |  | No Need | No Need | [13 empty] | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1667 | 2605-REENG-4G#RO-UPD239-0069 | Relocation | EQP eNode B Modular Relocation Service | Add RRU and Swap Antenna | UPD239 | TBG Parangloe | L1800 |  | MAKASSAR | 11946941 | -509471 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Kurniadi | Done Productivity 70 % |  |  |  | 7721756 | 2026-06-08 | Done | 2026-06-08 | 2026-06-10 | Done | 100% | 2026-06-08 | 2026-06-10 | 2026-06-10 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Done Tagging | 2026-06-13 | Done Tagging | No Need |  | Progress | [6 empty] | Inbound | [5 empty] | PO Confirmed |  |  |  | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1668 | 2605-UPBWL-4G#RO-TKA034-3055 | Upgrade | EQP Upgrade BW LTE 1800 20 - 20Mhz 4T4R | Swap RRU and Module BBU | TKA034 | DMT Tanakeke | L1800 |  | MAKASSAR | 11928464 | -551333 | YPTT | May-26 | May-26 | 2026 | 2026 | [34 empty] | YPTT | Kurniadi | Done Productivity 70 % |  |  |  | 8098511 | 2026-06-04 | Done | 2026-06-04 | 2026-06-07 | Done | 100% | 2026-06-04 | 2026-06-07 | 2026-06-07 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | passed | June-26 | Done Tagging | 2026-06-09 | Done Tagging | waiting tiket |  | Need | [6 empty] | Inbound | [5 empty] | PO Confirmed
1669 | 2606-4GDCS-4G#RO-EPS075-0161 | New-Imacro IWIP | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | EPS075 | IAAS_IWIP_ControlRoomPLTU1 | L1800 |  | TERNATE | 127.9987 | 0.47659 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT | Candra A Putra | Ready for Productivity 70% |  |  |  | 7756340 | 2026-06-10 | Done | 2026-06-12 | 2026-06-15 | Done | 100% | 2026-06-12 | 2026-06-15 | 2026-06-15 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Progress |  | Progress | No Need | [18 empty] | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1670 | 2606-4GDCS-4G#RO-EPS076-0162 | New-Imacro IWIP | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | EPS076 | IAAS_IWIP_ControlRoomPLTU2-1 | L1800 |  | TERNATE | 127.9962 | 0.47658 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT | Candra A Putra | Ready for Productivity 70% |  |  |  | 7756340 | 2026-06-10 | Done | 2026-06-15 | 2026-06-17 | Done | 100% | 2026-06-15 | 2026-06-17 | 2026-06-17 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Progress |  | Progress | No Need | [18 empty] | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1671 | 2606-4GDCS-4G#RO-EPS077-0166 | New-Imacro IWIP | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | EPS077 | IAAS_IWIP_ControlRoomPLTU2-2 | L1800 |  | TERNATE | 127.9946 | 0.47663 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT | Candra A Putra | Ready for Productivity 70% |  |  |  | 7756340 | 2026-06-10 | Done | 2026-06-15 | 2026-06-17 | Done | 100% | 2026-06-15 | 2026-06-17 | 2026-06-17 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Progress |  | Progress | No Need | [18 empty] | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1672 | 2606-4GDCS-4G#RO-EPS078-0164 | New-Imacro IWIP | EQP New NE 4G LTE 1800 20 Mhz | Add RRU and Module BBU | EPS078 | IAAS_IWIP_ControlRoomPLTU3 | L1800 |  | TERNATE | 128.0072 | 0.47684 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT | Candra A Putra | Ready for Productivity 70% |  |  |  | 7756340 | 2026-06-10 | Done | 2026-06-14 | 2026-06-16 | Done | 100% | 2026-06-14 | 2026-06-16 | 2026-06-16 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Progress |  | Progress | No Need | [18 empty] | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1673 | 2606-4GDCS-4G#RO-EPS079-0165 | New-Imacro IWIP | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | EPS079 | IWIP_ControlRoomPLTU4 | L1800 |  | TERNATE | 128.012 | 0.47698 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT | Candra A Putra | In Progress for Productivity |  |  |  | 7756340 | 2026-06-10 | Done | 2026-06-14 | 2026-06-16 | Done | 100% | 2026-06-14 | 2026-06-16 | 2026-06-16 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Progress |  | Progress | No Need | [18 empty] | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1674 | 2606-4GDCS-4G#RO-LBA045-0174 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port+Mounting Antenna | LBA045 | IAAS_HARITAMESSCENTRAL1 | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [34 empty] | YPTT |  | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need
1675 | 2606-4GDCS-4G#RO-LBA050-0172 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port+Mounting Antenna | LBA050 | IAAS_HARITAMESSCENTRAL2 | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [34 empty] | YPTT |  | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need
1676 | 2606-4GDCS-4G#RO-LBA053-0176 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port+Mounting Antenna | LBA053 | IAAS_HARITAMESSCENTRAL3 | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [34 empty] | YPTT |  | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need
1677 | 2606-4GDCS-4G#RO-LBA054-0175 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port+Mounting Antenna | LBA054 | IAAS_HARITAMESSCENTRAL4 | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [34 empty] | YPTT |  | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need
1678 | 2606-4GDCS-4G#RO-LBA055-0173 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port+Mounting Antenna | LBA055 | IAAS_HARITA_MESSCENTRAL5 | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [34 empty] | YPTT |  | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need
1679 | 2606-4GDCS-4G#RO-SSU101-0168 | New NE 4G | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | SSU101 | IAAS_IWIP_HaulingRoadBLNorth | L1800 |  | TERNATE | 127.976 | 0.54336 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT | Candra A Putra | Done Productivity 70 % |  |  |  | 5741754 | 2026-07-01 | Done | 2026-07-01 | 2026-07-03 | Done | 100% | 2026-07-01 | 2026-07-03 | 2026-07-03 | Connected | Connected |  | 01-Passed | passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need | [16 empty] | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1680 | 2606-4GGSM-4G#RO-LBA040-0144 | New NE | EQP New NE 4G LTE 900 10 Mhz | RRU | LBA040 | IAAS SPLIT MESS P2 | L900 |  | TERNATE | 127.4272 | -1.5576 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Done Productivity 70 % |  |  |  | 5741754 | 2026-06-24 | Done | 2026-06-24 | 2026-06-26 | Done | 100% | 2026-06-24 | 2026-06-26 | 2026-06-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | June-26 | Done Tagging | June-26 | Done Tagging | no need |  | no need | no need | no need | no need
1681 | 2606-4GGSM-4G#RO-LBA042-0145 | New NE | EQP New NE 4G LTE 900 10 Mhz | RRU | LBA042 | IAAS HJF TUGU | L900 |  | TERNATE | 127.4227 | -1.5584 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Done Productivity 70 % |  |  |  | 5741754 | 2026-06-24 | Done | 2026-06-27 | 2026-06-29 | Done | 100% | 2026-06-27 | 2026-06-29 | 2026-06-29 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | June-26 | Done Tagging | June-26 | Done Tagging | no need |  | no need | no need | no need | no need
1682 | 2606-4GGSM-4G#RO-SSU148-0147 | New NE | EQP New NE 4G LTE 900 10 Mhz | RRU | SSU148 | IAAS IWIP Mess KM15-3 | L900 |  | TERNATE | 127.8907 | 127.8907 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | already 90% ; waiting BAUT |  |  |  | 5741754 | 2026-07-18 | Done | 2026-07-18 | 2026-07-20 | Done | 100% | 2026-07-18 | 2026-07-20 | 2026-07-20 | Connected | Connected |  | 01-Passed | passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need | [11 empty] | 00-eATP Approved Tsel
1683 | 2606-ADSTR-5G#RO-LBA073-0534 | New NE | EQP Add Sector LTE 2300 4T4R | Swap Antenna Multi Port + RRU | LBA073 | GPS Kawasi Lama | L2300 |  | TERNATE | 127.4423 | -1.5772 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Unqualified 90% |  |  |  | 9953826 | 2026-07-11 | Done | 2026-07-11 | 2026-07-13 | Done | 100% | 2026-07-11 | 2026-07-13 | 2026-07-13 | Connected | Connected |  | 01-Passed | passed | Passed | passed | July-26 | Done Tagging | July-26 | Done Tagging | waiting tiket |  | Done | [6 empty] | Inbound |  |  |  |  | 00-eATP Approved Tsel
1684 | 2606-ADSTR-5G#RO-SSU026-0542 | Upgrade | EQP Add Sector LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU (Sec-3 in CP3 P3) | SSU026 | IAAS-IWIP_JW2 | L2300 Mimo |  | TERNATE | 127.9773 | 0.49965 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  | 9520808 | 2026-07-08 | Done | 2026-07-08 | 2026-07-10 | Done | 100% | 2026-07-08 | 2026-07-10 | 2026-07-10 | Connected | Connected |  | 01-Passed | passed | No need | passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need
1685 | 2606-ADSTR-5G#RO-SSU026-0543 | Upgrade | EQP Add Sector LTE 2300 Massive MIMO 32T32R impact New NE | Add RRU (Sec-3 in CP3 P3) | SSU026 | IAAS-IWIP_JW2 | L2300 Mimo |  | TERNATE | 127.9773 | 0.49965 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  | 9520808 | 2026-07-08 | Done | 2026-07-08 | 2026-07-10 | Done | 100% | 2026-07-08 | 2026-07-10 | 2026-07-10 | Connected | Connected |  | 01-Passed | passed | No need | passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need
1686 | 2606-ADSTR-5G#RO-SSU095-0538 | New NE | EQP Add Sector LTE 2300 4T4R | RRU | SSU095 | IWIP Hauling Road 1-3 | L2300 |  | TERNATE | 127.9333 | 0.49828 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Done Productivity 90 % |  |  |  | 5741754 | 2026-07-04 | Done | 2026-07-04 | 2026-07-06 | Done | 100% | 2026-07-04 | 2026-07-06 | 2026-07-06 | Connected | Connected |  | 01-Passed | passed | No need | passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need | [11 empty] | 00-eATP Approved Tsel
1687 | 2606-NNE4G-4G#RO-SSU026-0126 | Upgrade | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 32T32R | RRU + Module | SSU026 | IAAS IWIP JW-2 | L2300 |  | TERNATE | 127.9773 | 0.49965 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  | 5741754 | 2026-07-08 | Done | 2026-07-08 | 2026-07-10 | Done | 100% | 2026-07-08 | 2026-07-10 | 2026-07-10 | Connected | Connected |  | 01-Passed | passed | No need | passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need
1688 | 2606-NNE4G-4G#RO-SSU158-0131 | New NE 4G | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 32T32R | Add RRU and Module BBU | SSU158 | IWIP PROYEK BATERAI | L2300 Mimo |  | TERNATE | 127.9723 | 0.48378 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  | 8342895 | 2026-07-01 | Done | 2026-07-01 | 2026-07-03 | Done | 100% | 2026-07-01 | 2026-07-03 | 2026-07-03 | Connected | Connected |  | 01-Passed | passed | No need | passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need |  | No Need
1689 | 2606-QCELL-4G#1100-MDO044-0006 | Qcel | EQP Add Sector LTE 1800 2T2R | Qcelll_Area Terminal | MDO044 | Airport Sam Ratulangi | L1800 |  | MANADO | 154338 | 12492242 | YPTT | July-26 | July-26 | 2026 | 2026 | [34 empty] | Quintel |  | Ready for Productivity 70% | Waitting Evidance For Email | 51900000 | Addcost Installation Qcell | 15685229 | 2026-07-20 | Done | 2026-07-20 | 2026-07-27 | Done | 100% | 2026-07-20 | 2026-07-27 | 03-Aug-26 | Connected | Connected |  | 01-Passed | passed | Passed | Passed | August-26 | Done Tagging | August-26 | Done Tagging | Waitting Ticket |  | Done |  | Inbound |  |  |  |  | Inbound
1690 | 2606-QCELL-4G#1100-MDO044-0010 | Qcel | EQP Add Sector LTE 2300 Massive MIMO 32T32R impact New NE | Qcelll_Area Terminal | MDO044 | Airport Sam Ratulangi | L2300 |  | MANADO | 154338 | 12492242 | YPTT | July-26 | July-26 | 2026 | 2026 | [34 empty] | Quintel |  | Ready for Productivity 70% |  |  |  |  | 2026-07-20 | Done | 2026-07-20 | 2026-07-27 | Done | 100% | 2026-07-20 | 2026-07-27 | 03-Aug-26 | Connected | Connected |  | 01-Passed | passed | No need | Passed | August-26 | Done Tagging | August-26 | Done Tagging | No Need | [13 empty] | Done Upload eATP Waitting Review
1691 | 2606-QCELL-4G#1100-SSU156-0013 | New-Indoor QCELL IWIP | EQP Add Sector LTE 1800 2T2R | Qcell AAU | SSU156 | New Office IWIP | L1800 |  | TERNATE | 127.9775 | 0.47974 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Waitting MOS |  |  |  | 7756340 | [12 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1692 | 2606-TRIALSA-4G#RO-UPD943-0020 | Trial | EQP New NE 5G NR 2600 80 Mhz | Modernize to 3x A9652D M2326 | UPD943 | Hotel Rinra Makassar | NR 2600 |  | MAKASSAR |  |  |  | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  |  | 2026-07-30 | Done | 2026-07-30 | 01-Aug-26 | Done | 100% | 2026-07-30 | 01-Aug-26 | 01-Aug-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | August-26 | Done Tagging | August-26 | Done Tagging | Waitting Ticket | [8 empty] | Inbound
1693 | 2606-TRIALSA-4G#RO-UPX175-0024 | Trial | EQP New NE 5G NR 2600 80 Mhz | Insert Baseband Module | UPX175 | IBS Mesjid Kubah 99 | NR 2600 |  | MAKASSAR |  |  |  | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  |  | 2026-07-30 | Done | 2026-07-30 | 01-Aug-26 | Done | 100% | 2026-07-30 | 01-Aug-26 | 01-Aug-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | August-26 | Done Tagging | August-26 | Done Tagging | Waitting Ticket
1694 | 2606-UMIMO-4G#RO-KTG049-1077 | Upgrade | KTG049L2300EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NEMacro-3 | Swap RRU and Add Module BBU | KTG049 |  |  |  | TERNATE |  |  | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  | 6203715 | 2026-07-01 | Done | 2026-07-01 | 2026-07-03 | Done | 100% | 2026-07-01 | 2026-07-03 | 2026-07-03 | Connected | Connected |  | 01-Passed | passed | Passed | passed | July-26 | Done Tagging | July-26 | Done Tagging | waiting tiket |  | Done | [6 empty] | Inbound
1695 | 2606-UMIMO-4G#RO-KTG247-1078 | Upgrade | KTG247L2300EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NEMacro-3 | Add RRU and Swap Module BBU | KTG247 |  |  |  | TERNATE |  |  | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  | 9162247 | 2026-07-04 | Done | 2026-07-04 | 2026-07-06 | Done | 100% | 2026-07-04 | 2026-07-06 | 2026-07-03 | Connected | Connected |  | 01-Passed | passed | Passed | passed | July-26 | Done Tagging | July-26 | Done Tagging | waiting tiket |  | Done | [6 empty] | Inbound
1696 | 2606-UMIMO-4G#RO-SSU023-1091 | Upgrade | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | SWAP RRU to AAU+Module+Mounting Antenna | SSU023 | IWIP STOCKPILE HYDRO | L2300 |  | TERNATE | 127.9627 | 0.48678 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | In Progress for Productivity |  |  |  | 9520808 | 2026-07-19 | Done | 2026-07-19 | 2026-07-21 | Done | 100% | 2026-07-19 | 2026-07-21 | 2026-07-21 | Connected | Connected |  | 01-Passed | passed | Progress | Passed | 2026-07-27 | Done Tagging | 2026-07-27 | Done Tagging | Waitting Ticket |  | Progress | Progress | [10 empty] | Done Upload eATP Waitting Review
1697 | 2606-UMIMO-4G#RO-SSU066-1094 | Upgrade | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | RRU + Module | SSU066 | IWIPPelabuhan5 | L1800 |  | TERNATE | 121.2753 | -2.5746 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  | 5741754 | 2026-07-18 | Done | 2026-07-18 | 2026-07-20 | Done | 100% | 2026-07-18 | 2026-07-20 | 2026-07-20 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | August-26 | Done Tagging | August-26 | Done Tagging | no need |  | No Need | [11 empty] | 00-eATP Approved Tsel
1698 | 2606-UMIMO-4G#RO-SSU119-1096 | Upgrade | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | SWAP RRU to AAU+Module+Mounting Antenna | SSU119 | IWIP Storage Yard | L1800 |  | TERNATE | 128.0092 | 0.4745 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | In Progress for Productivity |  |  |  | 9520808 | 04-Aug-26 | Done | 04-Aug-26 | 06-Aug-26 | Done | 100% | 04-Aug-26 | 06-Aug-26 | 06-Aug-26 | Connected | Connected |  | 01-Passed | passed | Progress | Passed | 08-Aug-26 | Done Tagging | 08-Aug-26 | Done Tagging | Waitting Ticket |  | Progress | Progress
1699 | 2606-UMIMO-4G#RO-SSU119-1097 | Upgrade | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | SWAP RRU to AAU+Module+Mounting Antenna | SSU119 | IWIP Storage Yard | L1800 |  | TERNATE | 128.0092 | 0.4745 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | In Progress for Productivity |  |  |  | 2507054 | 04-Aug-26 | Done | 04-Aug-26 | 06-Aug-26 | Done | 100% | 04-Aug-26 | 06-Aug-26 | 06-Aug-26 | Connected | Connected |  | 01-Passed | passed | Progress | Passed | 08-Aug-26 | Done Tagging | 08-Aug-26 | Done Tagging | Waitting Ticket |  | Progress | Progress
1700 | 2606-UMIMO-4G#RO-SSU144-1103 | Upgrade | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | SWAP RRU to AAU+Mounting Antenna | SSU144 | IWIP Industri 2 | L1800 |  | TERNATE | 127.9878 | 0.48565 | YPTT | June-26 | June-26 | 2026 | 2026 | [36 empty] | Done Productivity 70 % |  |  |  | 9520808 | 04-Aug-26 | Done | 04-Aug-26 | 06-Aug-26 | Done | 100% | 04-Aug-26 | 06-Aug-26 | 06-Aug-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | 08-Aug-26 | Done Tagging | 08-Aug-26 | Done Tagging | Waitting Ticket |  | Done |  |  | Release | 04-Aug-26 |  |  | Inbound
1701 | 2606-UMIMO-4G#RO-UPD009-1076 | Upgrade | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | UPD009 | HotelSinggasana-DMT | L1800 |  | MAKASSAR | 119.41 | -5.1371 | YPTT | June-26 | June-26 | 2026 | 2026 | [34 empty] | YPTT | Rahmanto | Done Productivity 70 % |  |  |  | 6472064 | 2026-06-13 | Done | 2026-06-13 | 2026-06-15 | Done | 100% | 2026-06-13 | 2026-06-15 | 2026-06-15 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | June-26 | Done Tagging | July-26 | Done Taging | No Need | [18 empty] | 08-BAUT NY Submit | 03-Work NY Done | NY Upload
1702 | 2607-4GDCS-4G#RO-MBA044-0181 | New NE | EQP New NE 4G LTE 1800 20 Mhz | Add RRU+Mining Area | MBA044 | Indonesia Weda Bay Industrial Park | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1703 | 2607-4GDCS-4G#RO-MBA050-0189 | New NE | EQP New NE 4G LTE 1800 20 Mhz | Add RRU+Mining Area | MBA050 | Indonesia Weda Bay Industrial Park | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1704 | 2607-4GDCS-4G#RO-MBA051-0188 | New NE | EQP New NE 4G LTE 1800 20 Mhz | Add RRU+Mining Area | MBA051 | Indonesia Weda Bay Industrial Park | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1705 | 2607-4GDCS-4G#RO-MBA052-0182 | New NE | EQP New NE 4G LTE 1800 20 Mhz | Add RRU+Mining Area | MBA052 | Indonesia Weda Bay Industrial Park | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1706 | 2607-4GDCS-4G#RO-SSU058-0183 | New NE | EQP New NE 4G LTE 1800 20 Mhz | Add RRU+Mining Area | SSU058 | Indonesia Weda Bay Industrial Park | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1707 | 2607-4GDCS-4G#RO-SSU059-0184 | New NE | EQP New NE 4G LTE 1800 20 Mhz | Add RRU+Mining Area | SSU059 | Indonesia Weda Bay Industrial Park | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1708 | 2607-4GDCS-4G#RO-SSU060-0185 | New NE | EQP New NE 4G LTE 1800 20 Mhz | Add RRU+Mining Area | SSU060 | Indonesia Weda Bay Industrial Park | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1709 | 2607-4GDCS-4G#RO-SSU061-0186 | New NE | EQP New NE 4G LTE 1800 20 Mhz | Add RRU+Mining Area | SSU061 | Indonesia Weda Bay Industrial Park | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1710 | 2607-4GGSM-4G#RO-MBA044-0151 | Newsite | EQP New NE 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port+Mounting Antenna+Site Audit+Mining Area | MBA044 | Indonesia Weda Bay Industrial Park | L900 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1711 | 2607-4GGSM-4G#RO-MBA050-0158 | Newsite | EQP New NE 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port+Mounting Antenna+Site Audit+Mining Area | MBA050 | Indonesia Weda Bay Industrial Park | L900 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1712 | 2607-4GGSM-4G#RO-MBA051-0157 | Newsite | EQP New NE 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port+Mounting Antenna+Site Audit+Mining Area | MBA051 | Indonesia Weda Bay Industrial Park | L900 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1713 | 2607-4GGSM-4G#RO-MBA052-0152 | Newsite | EQP New NE 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port+Mounting Antenna+Site Audit+Mining Area | MBA052 | Indonesia Weda Bay Industrial Park | L900 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1714 | 2607-4GGSM-4G#RO-SSU058-0153 | Newsite | EQP New NE 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port+Mounting Antenna+Site Audit+Mining Area | SSU058 | Indonesia Weda Bay Industrial Park | L900 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1715 | 2607-4GGSM-4G#RO-SSU059-0154 | Newsite | EQP New NE 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port+Mounting Antenna+Site Audit+Mining Area | SSU059 | Indonesia Weda Bay Industrial Park | L900 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1716 | 2607-4GGSM-4G#RO-SSU060-0155 | Newsite | EQP New NE 4G LTE 900 10 Mhz | RRU+Cabinet+BBU+Module+Antenna Multi Port+Mounting Antenna+Site Audit+Mining Area | SSU060 | Indonesia Weda Bay Industrial Park | L900 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1717 | 2607-QCELL-4G#RO-UPD238-0027 | Qcel | EQP New Qcell | Swap Qcell + New Qcell Lt 1 | UPD238 | Baruga Telkomsel | (N2300+L1800) |  | MAKASSAR |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% | Waitting Evidance For Email | 8380000 | Addcost Installation Qcell |  | 2026-07-17 | Done | 2026-07-17 | 2026-07-22 | Done | 100% | 2026-07-17 | 2026-07-22 | 2026-07-22 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need
1718 | 2607-QCELL-4G#RO-UPD238-0028 | Qcel | EQP New Qcell | Swap Qcell + New Qcell Lt 2 | UPD238 | Baruga Telkomsel | (N2300+L1800) |  | MAKASSAR |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  |  | 2026-07-17 | Done | 2026-07-17 | 2026-07-22 | Done | 100% | 2026-07-17 | 2026-07-22 | 2026-07-22 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need
1719 | 2607-QCELL-4G#RO-UPD238-0029 | Qcel | EQP New Qcell | Swap Qcell + New Qcell Lt 3 | UPD238 | Baruga Telkomsel | (N2300+L1800) |  | MAKASSAR |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  |  | 2026-07-17 | Done | 2026-07-17 | 2026-07-22 | Done | 100% | 2026-07-17 | 2026-07-22 | 2026-07-22 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need
1720 | 2607-QCELL-4G#RO-UPD238-0030 | Qcel | EQP New Qcell | Swap Qcell + New Qcell Lt 4 | UPD238 | Baruga Telkomsel | (N2300+L1800) |  | MAKASSAR |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  |  | 2026-07-17 | Done | 2026-07-17 | 2026-07-22 | Done | 100% | 2026-07-17 | 2026-07-22 | 2026-07-22 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | July-26 | Done Tagging | July-26 | Done Tagging | Waitting Ticket | [8 empty] | Inbound
1721 | 2607-QCELL-4G#RO-UPD238-0031 | Qcel | EQP New Qcell | Swap Qcell + New Qcell Lt 5 | UPD238 | Baruga Telkomsel | (N2300+L1800) |  | MAKASSAR |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  |  | 2026-07-17 | Done | 2026-07-17 | 2026-07-22 | Done | 100% | 2026-07-17 | 2026-07-22 | 2026-07-22 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | July-26 | Done Tagging | July-26 | Done Tagging | No Need
1722 | 2607-UPMod-4G#1110-LBA082-0006 | Modular Modernization | EQP Modular Modernization | Swap RRU | LBA082 | PT.HPALObiHaritaKonstruksi | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [34 empty] | YPTT |  | Done Productivity 70 % |  |  |  |  | 2026-07-19 | Done | 2026-07-19 | 2026-07-21 | Done | 100% | 2026-07-19 | 2026-07-21 | 2026-07-21 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | July-26 | Done Tagging | July-26 | Done Tagging | Waitting Ticket |  | Done | [6 empty] | Inbound
1723 | 2608-4GDCS-4G#RO-SSU101-0191 | New NE | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | SSU101 | IWIP Hauling Road 3-3 |  |  | TERNATE | 127.976 | 0.54336 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1724 | 2608-4GGSM-4G#RO-SSU158-0160 | New NE | EQP New NE 4G LTE 900 10 Mhz | Add RRU | SSU158 | IWIP PROYEK BATERAI |  |  | TERNATE | 127.9723 | 0.48378 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  |  | 08-Aug-26 | Done | 10-Aug-26 | 14-Aug-26 | Done | 100% | 10-Aug-26 | 14-Aug-26 | 14-Aug-26 | Connected | Connected |  | 01-Passed | passed | No need | passed | August-26 | Done Tagging | August-26 | Done Tagging | No Need |  | No Need
1725 | 2608-NNE4G-4G#RO-MBA045-0139 | New NE | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 32T32R | Add RRU and Module BBU | MBA045 | IWIP Camp KM36 |  |  | TERNATE | 127.9748 | 0.65462 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1726 | 2608-NNE4G-4G#RO-SSU017-0141 | New NE | EQP New NE 4G LTE 2300 20 Mhz Massive MIMO 32T32R | Add RRU and Module BBU | SSU017 | IWIP KM15 Smelter |  |  | TERNATE | 127.8957 | 0.51101 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  |  | 02-Aug-26 | Done | 03-Aug-26 | 06-Aug-26 | Done | 100% | 03-Aug-26 | 06-Aug-26 | 06-Aug-26 | Connected | Connected |  | 01-Passed | 01-Passed | No need | Passed | August-26 | Done Tagging | August-26 | Done Tagging | No Need |  | No Need
1727 | 2608-NNE4G-4G#RO-SSU096-0140 | New NE | EQP New NE 4G LTE 2300 50 Mhz Massive MIMO 32T32R | Add RRU and Module BBU | SSU096 | IWIP Hauling Road 2 |  |  | TERNATE | 127.911 | 0.48675 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  |  | 05-Aug-26 | Done | 05-Aug-26 | 07-Aug-26 | Done | 100% | 05-Aug-26 | 07-Aug-26 | 07-Aug-26 | Connected | Connected |  | 01-Passed | Passed | No Need | Passed | August-26 | Done Tagging | August-26 | Done Tagging | No Need
1728 | 2608-UMIMO-4G#RO-SSU021-1139 | Upgrade | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | SSU021 | PT. WEDA BAY NIKEL 1 |  |  | TERNATE | 127.985 | 0.49211 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  |  | 16-Aug-26 | Done | 16-Aug-26 | 18-Aug-26 | Done | 100% | 16-Aug-26 | 18-Aug-26 | 18-Aug-26 | Connected | Connected |  | 01-Passed | passed | Passed | passed | August-26 | Done Tagging | August-26 | Done Tagging | Waitting Ticket |  | Done | 18-Aug-26
1729 | 2608-UMIMO-4G#RO-SSU021-1140 | Upgrade | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Activate by Software | SSU021 | PT. WEDA BAY NIKEL 1 |  |  | TERNATE | 127.985 | 0.49211 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1730 | 2608-UMIMO-4G#RO-SSU066-1147 | Upgrade | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU (Bundling) | SSU066 | IWIPPelabuhan5 |  |  | TERNATE | 121.2753 | -2.5746 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  |  | 03-Aug-26 | Done | 04-Aug-26 | 06-Aug-26 | Done | 100% | 04-Aug-26 | 06-Aug-26 | 06-Aug-26 | Connected | Connected |  | 01-Passed | 01-Passed | Passed | Passed | August-26 | Done Tagging | August-26 | Done Tagging | Waitting Ticket |  | Done |  |  | Release | 04-Aug-26 |  |  | Inbound
1731 | 2608-UMIMO-4G#RO-SSU068-1148 | Upgrade | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU068 | New Office 2 IWIP |  |  | TERNATE | 128.0005 | 0.47781 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1732 | 2608-UMIMO-4G#RO-SSU126-1149 | Upgrade | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU126 | IWIP Jetty 2 |  |  | TERNATE | 128.0041 | 0.4745 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1733 | 2608-UMIMO-4G#RO-SSU142-1137 | Upgrade | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU142 | IWIP Pelabuhan 2 |  |  | TERNATE | 127.9958 | 0.47448 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  |  | 12-Aug-26 | Done | 12-Aug-26 | 14-Aug-26 | Done | 100% | 12-Aug-26 | 14-Aug-26 | 14-Aug-26 | Connected | Connected |  | 01-Passed | passed | Progress | Passed | 2026-07-29 | Done Tagging | 2026-07-29 | Done Tagging | Waitting Ticket |  | No Need
1734 | 2608-UMIMO-4G#RO-SSU142-1138 | Upgrade | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Activate by software | SSU142 | IWIP Pelabuhan 2 |  |  | TERNATE | 127.9958 | 0.47448 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS |  |  |  |  | 12-Aug-26 | Done | 12-Aug-26 | 14-Aug-26 | Done | 100% | 12-Aug-26 | 14-Aug-26 | 14-Aug-26 | Connected | Connected |  | 01-Passed | passed | Progress | Passed | 2026-07-29 | Done Tagging | 2026-07-29 | Done Tagging | No Need |  | No Need
1735 | 2608-UMIMO-4G#RO-SSU147-1142 | Upgrade | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | SSU147 | IAAS IWIP Mess KM15-2 |  |  | TERNATE | 127.8886 | 127.8886 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1736 | 2608-UMIMO-4G#RO-SSU147-1143 | Upgrade | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Activate by Software | SSU147 | IAAS IWIP Mess KM15-2 |  |  | TERNATE | 127.8886 | 127.8886 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS | [16 empty] | Work Not Start | Work Not Start | No need | Work Not Start |  | Work Not Start |  | Work Not Start | No Need |  | No Need
1737 | 2608-UMIMO-4G#RO-SSU149-1144 | Upgrade | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Dismantle RRU and Activate FMM L18 | SSU149 | IAAS IWIP Bengkel 5 |  |  | TERNATE | 127.973 | 0.49924 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | In Progress for Productivity |  |  |  |  | 13-Aug-26 | Done | 13-Aug-26 | 14-Aug-26 | Done | 100% | 13-Aug-26 | 14-Aug-26 | 13-Aug-26 | Connected | Connected |  | 01-Passed | No Need | Progress | No need |  | No Need |  | No Need | Waitting Ticket |  | Progress
1738 | 2608-UMIMO-4G#RO-SSU150-1145 | Upgrade | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Add RRU and Module BBU | SSU150 | IAAS IWIP Workshop A |  |  | TERNATE | 127.9943 | 127.9943 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS |  |  |  |  | 05-Aug-26 | Done | 06-Aug-26 | 08-Aug-26 | Done | 100% | 06-Aug-26 | 08-Aug-26 | 08-Aug-26 | Connected | Connected |  | 01-Passed | passed | No need | Passed | August-26 | Done Tagging | August-26 | Done Tagging | No Need |  | No Need
1739 | 2608-UMIMO-4G#RO-SSU150-1146 | Upgrade | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Activate by software | SSU150 | IAAS IWIP Workshop A |  |  | TERNATE | 127.9943 | 127.9943 | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Waitting MOS |  |  |  |  | 05-Aug-26 | Done | 06-Aug-26 | 08-Aug-26 | Done | 100% | 06-Aug-26 | 08-Aug-26 | 08-Aug-26 | Connected | Connected |  | 01-Passed | passed | No need | Passed | August-26 | Done Tagging | August-26 | Done Tagging | No Need |  | No Need
1740 | 2310-4GDCS-4G#RO-JLO001-0245 | New Ne | EQP New Site 4G LTE L1800 20 MHz | New Infra | JLO001 | GamlamoSatim-TBG | L1800 |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | Ready for Productivity 70% |  |  |  |  | 05-Aug-26 | Done | 05-Aug-26 | 07-Aug-26 | Done | 100% | 05-Aug-26 | 07-Aug-26 | 07-Aug-26 | Connected | Connected |  | 01-Passed | Passed | No Need | Passed | August-26 | Done Tagging | August-26 | Done Tagging | No Need
1741 | 2506-iMACR-4G#RO-SSU164-0019 | Upgrade | EQP Add Sector LTE 1800+L2100 (iMacro) | Add RRU Imacro | SSU164 | AKOMODASI H-2 IWIP |  |  | TERNATE |  |  | YPTT | July-26 | July-26 | 2026 | 2026 | [36 empty] | In Progress for Productivity |  |  |  |  | 11-Aug-26 | Done | 11-Aug-26 | 13-Aug-26 | Done | 100% | 11-Aug-26 | 13-Aug-26 | 13-Aug-26 | Connected | Connected |  | 01-Passed | Passed | No Need | Passed | August-26 | Done Tagging | August-26 | Done Tagging | No Need

## Site_Upgrade PLN
WID | SOW Planning | Site ID Impl | Site Name Impl | Work Type | Actual registred (for WCC) | PLN ID | Registration code | Registration date | Survey date | Survey result | remarks Upgrade | remarks | Upgrade Time | ATP | Total PO Amt (IDR) No Tax | Site PLN Productivity Status
2602-UPPLN-4G#RO-UPD466-0016 | CME Upgrade PLN | UPD466 | Alauddin II | Upgrade PLN from 7,7Kva into 13,2Kva | PLN upgrade 7.7KVA to 13.2/13.9KVA | 321203177004 | 3212113038796 | 27-Feb-26 | 28-Feb-26 | No change KWH panel | - | Done | 1-May-26 | Passed | 16,520,900 | Done Invoice
2602-UPPLN-4G#RO-UPD663-0017 | CME Upgrade PLN | UPD663 | Protelindo Teuku Umar | Upgrade PLN from 7,7Kva into 13,2Kva | PLN upgrade 7.7KVA to 13.2/13.9KVA | 321103373354 | 3201013030402 | 27-Feb-26 | 28-Feb-26 | No change KWH panel | - | Done | 1-Apr-26 | Passed | 16,520,900 | Done Invoice
2602-UPPLN-4G#RO-UPD667-0018 | CME Upgrade PLN | UPD667 | MC Swadaya Mas | Upgrade PLN from 7,7Kva into 13,2Kva | PLN upgrade 7.7KVA to 13.2/13.9KVA | 321203192594 | 3211113051708 | 27-Feb-26 | 28-Feb-26 | Change KWH &ACPDB panel | Panel KWH dan Panle ACPDB, Power cable NYY 4x16mm (18m), Metal conduit (16m), Scuun (10), tape (4), cable tie (2) | Panel KWH dan ACPDB Ready, Waiting Permit Ready Panel (Done Upgrade) | 22-May-26 | Passed | 43,479,700 | Done Invoice
2602-UPPLN-4G#RO-UPD809-0020 | CME Upgrade PLN | UPD809 | DMT Kima Persero | Upgrade PLN from 7,7Kva into 13,2Kva | PLN upgrade 7.7KVA to 13.2/13.9KVA | 321301752339 | 3202013054597 | 27-Feb-26 | 2-Mar-26 | Change KWH Panel | Panel only | DONE Upgrade 22/04/2026 Done Ganti Panel Foto Ulang | 22-Apr-26 | Passed | 28,070,900 | Done Invoice
2602-UPPLN-4G#RO-UPD817-0021 | CME Upgrade PLN | UPD817 | Anugerah Daeng Sirua | Upgrade PLN from 7,7Kva into 13,2Kva | PLN upgrade 7.7KVA to 13.2/13.9KVA | 321203220304 | 3211113051710 | 27-Feb-26 | 28-Feb-26 | No change KWH panel | - | Done Upgrade 17 may 26 | 16-May-26 | Passed | 16,520,900 | Done Invoice
2602-UPPLN-4G#RO-UPD837-0022 | CME Upgrade PLN | UPD837 | KDI BTN Antara | Upgrade PLN from 7,7Kva into 13,2Kva | PLN upgrade 7.7KVA to 13.2/13.9KVA | 321301758884 | 3202013054602 | 27-Feb-26 | 2-Mar-26 | Change KWH & ACPDB panel | Panel KWH dan Panle ACPDB, Power cable NYY 4x16mm (7m), Metal conduit (7m), Scuun (10), tape (4), cable tie (2) | Material PLN Ready / Done replace KWH dan ACPDB | 13-May-26 | Passed | 39,154,500 | Done Invoice
2602-UPPLN-4G#RO-UPD854-0023 | CME Upgrade PLN | UPD854 | MC Jipang Permai | Upgrade PLN from 5,5Kva into 10,6Kva | PLN upgrade 5.5KVA to 10.6KVA | 321110010876 | 3211113051712 | 27-Feb-26 | 28-Feb-26 | Change KWH & ACPDB panel | Panel KWH dan Panle ACPDB,Power cable NYY 4x16mm (47m), Metal conduit (44m), Scuun (8), tape (4), cable tie (2) | DONE UPGRADE 01/04/2026 Done Ganti Panel | 1-Apr-26 | Passed | 54,012,090 | Done Invoice
2602-UPPLN-4G#RO-UPD868-0025 | CME Upgrade PLN | UPD868 | MC Kampung Rama | Upgrade PLN from 5,5Kva into 10,6Kva | PLN upgrade 5.5KVA to 10.6KVA | 321110026178 | 3211113051713 | 27-Feb-26 | 28-Feb-26 | Change KWH & ACPDB panel | Panel KWH dan Panle ACPDB, Power cable NYY 4x16mm (17m), Metal conduit (15m), Scuun (10), tape (4), cable tie (2) | DONE UPGRADE 02/04/2026 Done GANTI PANEL | 2-Apr-26 | Passed | 42,187,090 | Done Invoice
2602-UPPLN-4G#RO-UPD873-0028 | CME Upgrade PLN | MRW160 | MCR Penginapan Rahma | Upgrade PLN 10,6 Kva to 13,2 Kva | PLN upgrade 11KVA to 13.2KVA | 312110210309 | [5 empty] | process registrasi, pindah dari pelanggan pribadi ke bisnis | 19-May-26 |  | 49,045,590 | Ready for Invoice
2602-UPPLN-4G#RO-UPD110-0029 | CME Upgrade PLN | UPD110 | Baruga 2 | Upgrade PLN from 7,7Kva into 13,2Kva | PLN upgrade 7.7KVA to 13.2/13.9KVA | 321209184939 | 3211113051714 | 27-Feb-26 | 2-Mar-26 | No change KWH panel | - | Done Upgrade 19 may 26 | 19-May-26 | Passed | 16,520,900 | Done Invoice
2602-UPPLN-4G#RO-UPD118-0030 | CME Upgrade PLN | UPD118 | Dg. Ngepe | Upgrade PLN from 7,7Kva into 13,2Kva | PLN upgrade 7.7KVA to 13.2/13.9KVA | 321209184927 | 3212113038802 | 27-Feb-26 | 2-Mar-26 | No change KWH panel | - | Waiting kwh dan mcb dari ULP | 1-Jun-26 | Passed | 16,520,900 | Ready for Invoice
2602-UPPLN-4G#RO-UPD145-0031 | CME Upgrade PLN | UPD145 | Talasalapang | Upgrade PLN from 7,7Kva into 13,2Kva | PLN upgrade 7.7KVA to 13.2/13.9KVA | 321209184902 | 3211113051715 | 27-Feb-26 | 28-Feb-26 | No change KWH panel | - | Done Upgrade | 20-May-26 | Passed | 16,520,900 | Done Invoice
2604-UPPLN-4G#RO-THN075-0083 | CME Upgrade PLN | MRW013 | PTI Pasar Bahadopi Marse | Upgrade PLN 7,7Kva to 13,2Kva | PLN upgrade 10.6KVA to 13.2KVA | 312110683334 | 3121113021434 |  |  |  |  | waiting BPUJL payment |  |  | 16,520,900 | Ready for Invoice
371,596,170

## Pvt Dash Sul
PO Year | Kategori | Bulan | Zona | Jumlah
| PO Year | 2026 |  |  |  | PO Year | (All) | [8 empty] | PO Year | 2026 | [5 empty] | PO Year | 2026
| Count of WID | Column Labels |  |  |  | Count of WID | Column Labels |  |  |  | Count of WID | Column Labels |  |  |  | Count of WID | Column Labels | [5 empty] | Count of WID | ZTE ZONE
| Assignment | MAKASSAR | MANADO | TERNATE | Grand Total | SM ATP | MAKASSAR | MANADO | TERNATE | Grand Total | FI INEOM | MAKASSAR | MANADO | TERNATE | Grand Total | SM ATP | MAKASSAR | MANADO | TERNATE | Grand Total |  |  | Connected Date | TERNATE | MANADO | MAKASSAR | Grand Total
| Jan | 1 |  | 67 | 68 | Jan |  |  | 37 | 37 | Jan |  |  | 37 | 37 | No Need |  |  | 15 | 15 |  |  | Jan | 50 |  | 1 | 51
| Feb | 33 |  | 37 | 70 | Feb | 1 |  | 30 | 31 | Feb | 1 |  | 30 | 31 | passed | 42 | 37 | 209 | 288 |  |  | Feb | 37 |  | 1 | 38
| Mar |  | 10 | 31 | 41 | Mar | 10 |  | 10 | 20 | Mar | 1 |  | 10 | 11 | Progress | 5 | 2 | 26 | 33 |  |  | Mar | 18 |  | 20 | 38
| Apr | 3 | 15 | 45 | 63 | Apr | 12 | 16 | 36 | 64 | Apr | 18 | 12 | 30 | 60 | Work Not Start | 23 | 1 | 38 | 62 |  |  | Apr | 36 | 19 | 3 | 58
| May | 15 | 13 | 26 | 54 | May | 5 | 14 | 28 | 47 | May | 6 | 9 | 18 | 33 | Grand Total | 70 | 40 | 288 | 398 |  |  | May | 26 | 12 | 11 | 49
| Jun | 1 |  | 41 | 42 | Jun | 7 | 1 | 37 | 45 | Jun | 8 | 9 | 46 | 63 | [7 empty] | Jun | 38 |  | 3 | 41
| Jul | 7 | 2 | 41 | 50 | Jul | 6 | 3 | 35 | 44 | Jul | 7 | 3 | 36 | 46 | [7 empty] | Jul | 22 | 2 | 5 | 29
| Aug | 10 |  |  | 10 | Aug | 2 | 3 | 15 | 20 | Aug | 2 | 3 | 14 | 19 | [7 empty] | Aug | 19 | 3 | 2 | 24
| Grand Total | 70 | 40 | 288 | 398 | Grand Total | 43 | 37 | 228 | 308 | Grand Total | 43 | 36 | 221 | 300 | [7 empty] | Grand Total | 246 | 36 | 46 | 328
[16 empty] | ZTE ZONE | MAKASSAR |  | ZTE ZONE | MANADO | ZTE ZONE | TERNATE
| PO Year | 2026 | [13 empty] | PO Year | 2026 |  | PO Year | 2026 | PO Year | 2026
|  | Column Labels | [13 empty] | SM ATP | Count of WID |  | SM ATP | Count of WID | SM ATP | Count of WID
| Values | MAKASSAR | MANADO | TERNATE | Grand Total | [10 empty] | passed | 42 |  | passed | 37 | No Need | 15
| Count of MOS | 47 | 39 | 250 | 336 | [10 empty] | Progress | 5 |  | Progress | 2 | passed | 209
| Count of HI Done | 46 | 39 | 246 | 331 | [10 empty] | Work Not Start | 23 |  | Work Not Start | 1 | Progress | 26
| Count of Connected Date | 46 | 36 | 246 | 328 | [10 empty] | Grand Total | 70 |  | Grand Total | 40 | Work Not Start | 38
| PO Year | 2026 | [18 empty] | Grand Total | 288
| Count of WID | Column Labels
| SM Kitting, PTW & EHS | MAKASSAR | MANADO | TERNATE | Grand Total
| 01-Passed | 44 | 34 | 201 | 279
| 03-NY SM | 23 |  |  | 23
| Work Not Start |  | 1 | 38 | 39
| Progress | 3 | 2 | 13 | 18
| passed |  | 3 | 35 | 38
| No Need |  |  | 1 | 1
| Grand Total | 70 | 40 | 288 | 398
| PO Year | 2026
| Count of WID | Column Labels
| SM ATP | MAKASSAR | MANADO | TERNATE | Grand Total
| No Need |  |  | 15 | 15
| passed | 42 | 37 | 209 | 288
| Progress | 5 | 2 | 26 | 33
| Work Not Start | 23 | 1 | 38 | 62
| Grand Total | 70 | 40 | 288 | 398
| PO Year | 2026
| Count of WID | Column Labels
| SM Dismantle | MAKASSAR | MANADO | TERNATE | Grand Total
| No Need | 42 | 23 | 184 | 249
| Passed | 26 | 16 | 93 | 135
| Progress | 1 |  | 11 | 12
| SM Passed | 1 | 1 |  | 2
| Grand Total | 70 | 40 | 288 | 398
| PO Year | 2026
| Count of WID | Column Labels
| Inbound | MAKASSAR | MANADO | TERNATE | Grand Total
| Inbound | 22 | 16 | 90 | 128
| Ongoing | 3 | 1 | 3 | 7
| No Need | 7 | 5 | 89 | 101
| Grand Total | 32 | 22 | 182 | 236
| PO Year | 2026
| Count of WID | Column Labels
| FI Ineom | MAKASSAR | MANADO | TERNATE | Grand Total
| Done Tagging | 42 | 36 | 203 | 281
| No Need |  | 1 | 15 | 16
| Progress | 5 | 2 | 32 | 39
| Work Not Start | 23 | 1 | 38 | 62
| Grand Total | 70 | 40 | 288 | 398
| PO Year | 2026
| Count of WID | Column Labels
| eATP Done | MAKASSAR | MANADO | TERNATE | Grand Total
| 00-eATP Approved Tsel | 9 | 12 | 103 | 124
| 09-eATP NY Uploaded |  | 10 | 28 | 38
| 10-Tagging New Asset & SM ATP Done, Wait BAPA | 2 |  |  | 2
| 11-Tagging New Asset Done, SM ATP NY & Wait BAPA | 2 |  |  | 2
| 12-Tagging New Asset Done, Wait BARA |  |  | 1 | 1
| 14-Tagging New Asset NY, SM ATP Done |  |  | 1 | 1
| 15-Tagging New Asset NY, SM ATP NY | 5 |  | 2 | 7
| 17-Work NY Done | 29 | 10 | 40 | 79
| (blank) | 14 | 5 | 95 | 114
| Ny Upload |  |  | 1 | 1
| 15-Tagging New Asset Done, SM ATP Done | 1 |  |  | 1
| Done Upload eATP Waitting Review | 8 | 3 | 17 | 28
| Grand Total | 70 | 40 | 288 | 398
| Count of WID | Column Labels
| Assignment | MAKASSAR | MANADO | TERNATE | Grand Total
| Connected | 149 | 199 | 616 | 964
| 2023 | 20 | 30 | 49 | 99
| 2024 | 71 | 127 | 234 | 432
| 2025 | 12 | 5 | 87 | 104
| 2026 | 46 | 37 | 246 | 329
| Work Not Start | 23 | 11 | 11 | 45
| 2023 |  | 9 | 5 | 14
| 2025 |  |  | 2 | 2
| 2026 | 23 | 2 | 4 | 29
| Progress |  |  | 4 | 4
| 2026 |  |  | 4 | 4
| Prorgress | 1 |  |  | 1
| 2026 | 1 |  |  | 1
| (blank) |  | 1 | 34 | 35
| 2026 |  | 1 | 34 | 35
| Grand Total | 173 | 211 | 665 | 1049

## Pvt Productivity TI
PRODUCTIVITY TI JAN,FEB,MARET,APRIL MEY, JUNI, JULI AGUSTUS 2026
Years Assigned | 2026
Site Productivity Status | Count of WID | Sum of Total PO Amt (IDR) No Tax | Sum of Add Cost Amount | ADDCOST JAN,FEB,MARET,APRIL MEY, JUNI, JULI, AGUSTUS 2026
Done Productivity 100 % | 41 | 364628847 | 43513000 | Years Assigned | 2026
Done Productivity 70 % | 117 | 1056880413 | 6005000
Done Productivity 90 % | 65 | 519843914 | 19000000 | Count of WID | Addcost Productivity Status
In Progress for Productivity | 50 | 433417131 | 88325000 | Add Cost Amount | Approval Completed (PR NY) | PR Release | Waitting Evidance For Email | Done Invoice | Done Email waitting approval | Grand Total
Waitting MOS | 65 | 92305934 | 9800000 | 1500000 |  |  |  | 1 |  | 1
Ready for Productivity 70% | 36 | 159610200 | 60280000 | 2005000 |  |  |  | 1 |  | 1
Grand Total | 374 | 2626686438 | 226923000 | 3000000 |  |  |  | 1 |  | 1
|  |  |  | 3005000 |  |  |  | 1 |  | 1
|  |  |  | 3500000 |  |  | 1 | 1 | 1 | 3
PRODUCTIVITY UPGRADE PLN JAN, FEB, MARET, APRIL, MEY, JUNI, JULI, AGUSTUS 2026 |  |  |  | 6500000 | 1 |  |  | 1 |  | 2
Row Labels | Count of WID | Sum of Total PO Amt (IDR) No Tax |  | 22050000 |  | 1 |  |  |  | 1
In Progress for Productivity | 2 | 65566490 |  | 2500000 |  |  |  | 1 |  | 1
Ready for Productivity | 11 | 306029680 |  | 5000000 |  |  |  | 1 |  | 1
Grand Total | 13 | 371596170 |  | 2060000 |  |  |  | 1 |  | 1
|  |  |  | 25441000 |  |  |  | 1 |  | 1
TOTAL COST TI & UPGRADE PLN JAN,FEB,MARET,APR, MEY 2026 |  |  |  | 9512000 |  |  |  | 1 |  | 1
Cost Jan,Feb,Maret,April |  |  |  | 5500000 |  |  | 1 |  |  | 1
1588351830 |  |  |  | 4800000 |  |  | 1 |  |  | 1
|  |  |  | 8380000 |  |  | 1 |  |  | 1
TOTAL PRODUCTIVITY TI, UPGRADE PLN & ADDCOST DI KURANGI COST |  |  |  | 40875000 |  |  | 1 |  |  | 1
|  |  |  | 51900000 |  |  | 1 |  |  | 1
1636853778 |  |  |  | 16400000 | 1 |  |  |  |  | 1
|  |  |  | Grand Total | 2 | 1 | 6 | 11 | 1 | 21

## Pivot Kal
PO Year | Kategori | Bulan | Jumlah
| MOS |  |  | HI |  | Connected
| Row Labels | Count of WID |  | Row Labels | Count of WID | Row Labels | Count of WID | Row Labels | Count of WID | # MOS |  |  |  | # HI Done |  |  |  | # Connected
| <5/6/2025 | 8 |  | 2025 | 130 | <5/6/2025 | 11 | Connected | 171 | Count of WID | Column Labels |  |  | Count of WID | Column Labels |  |  | Count of WID | Column Labels
| 2025 | 130 |  | May | 3 | 2025 | 128 | ROLLBACK | 1 | Row Labels | 2025 | 2026 | Grand Total | Row Labels | 2025 | 2026 | Grand Total | Row Labels | 2025 | 2026 | Grand Total
| May | 3 |  | Jun | 11 | May | 3 | Work Not Start | 10 | Jan |  | 4 | 4 | Jan |  | 4 | 4 | Jan |  | 4 | 4
| Jun | 12 |  | Jul | 4 | Jun | 10 | Grand Total | 182 | Feb |  | 19 | 19 | Feb |  | 18 | 18 | Feb |  | 15 | 15
| Jul | 5 |  | Aug | 29 | Jul | 4 |  |  | Mar |  | 4 | 4 | Mar |  | 5 | 5 | Mar |  | 5 | 5
| Aug | 29 |  | Sep | 27 | Aug | 27 |  |  | Apr |  | 15 | 15 | Apr |  | 15 | 15 | Apr |  | 17 | 17
| Sep | 26 |  | Oct | 17 | Sep | 27 |  |  | May | 3 | 2 | 5 | May | 3 | 2 | 5 | May | 3 | 2 | 5
| Oct | 22 |  | Nov | 20 | Oct | 16 |  |  | Jun | 12 |  | 12 | Jun | 11 |  | 11 | Jun | 10 |  | 10
| Nov | 17 |  | Dec | 19 | Nov | 21 |  |  | Jul | 5 |  | 5 | Jul | 4 |  | 4 | Jul | 4 |  | 4
| Dec | 16 |  | <5/6/2025 | 8 | Dec | 20 |  |  | Aug | 29 |  | 29 | Aug | 29 |  | 29 | Aug | 27 |  | 27
| 2026 | 44 |  | 2026 | 44 | 2026 | 43 |  |  | Sep | 26 |  | 26 | Sep | 27 |  | 27 | Sep | 27 |  | 27
| Jan | 4 |  | Jan | 4 | Jan | 4 |  |  | Oct | 22 |  | 22 | Oct | 17 |  | 17 | Oct | 16 |  | 16
| Feb | 19 |  | Feb | 18 | Feb | 15 |  |  | Nov | 17 |  | 17 | Nov | 20 |  | 20 | Nov | 21 |  | 21
| Mar | 4 |  | Mar | 5 | Mar | 5 |  |  | Dec | 16 |  | 16 | Dec | 19 |  | 19 | Dec | 20 |  | 20
| Apr | 15 |  | Apr | 15 | Apr | 17 |  |  | Grand Total | 130 | 44 | 174 | Grand Total | 130 | 44 | 174 | Grand Total | 128 | 43 | 171
| May | 2 |  | May | 2 | May | 2
| Grand Total | 182 |  | Grand Total | 182 | Grand Total | 182

## Pivot Sul
[50 empty] | # MOS |  |  |  | # HI Done |  |  |  | # Connected | [18 empty] | Assignment Month
[50 empty] | ZTE ZONE | TERNATE | [10 empty] | Years (MOS) | 2026 |  |  |  | Years (HI Done) | 2026 |  |  |  | Years (Connected Date) | 2026 | [10 empty] | ZTE ZONE | MAKASSAR |  |  | ZTE ZONE | MAKASSAR
| MOS | [6 empty] | HI Done | [5 empty] | Connected | [6 empty] | Years (Connected Date) | (ALL) | [16 empty] | MOS | [37 empty] | Count of WID | Column Labels | [5 empty] | Years (Monthly Target) | (Multiple Items) |  |  | Years (Monthly Target) | 2026
| Row Labels | Count of WID | [5 empty] | Row Labels | Count of WID |  |  |  |  | Row Labels | Count of WID | [5 empty] | MOS VS OA | [10 empty] | HI VS OA | [6 empty] | PO Year | 2026 |  |  |  | # Connected |  |  |  | NY Connected |  | Count of WID | Column Labels |  |  | Count of WID | Column Labels |  |  | Count of WID | Column Labels |  |  | Count of WID | Column Labels |  |  |  | Count of WID | Column Labels |  |  |  | Count of WID | Column Labels |  |  |  |  | Jan | Feb | Mar | Apr | May | Grand Total
| <12/27/2022 | 87 | [5 empty] | <3/26/2023 | 334 |  |  |  |  | <1/24/2023 | 92 | [5 empty] | Count of WID | Column Labels | [9 empty] | Count of WID | Column Labels | [5 empty] | Monthly Assignment | (ALL) | [7 empty] | Monthly Target | (Multiple Items) |  | 2025 | 2026 | Grand Total | Row Labels | 2025 | 2026 | Grand Total | Row Labels | 2025 | 2026 | Grand Total | Row Labels | MAKASSAR | MANADO | TERNATE | Grand Total | Row Labels | MAKASSAR | MANADO | TERNATE | Grand Total | Row Labels | MAKASSAR | MANADO | TERNATE | Grand Total | [7 empty] | Count of WID | Column Labels |  |  | Count of WID | Column Labels
| 2022 | 1 | [5 empty] | 2023 | 4 |  |  |  |  | 2023 | 135 | [5 empty] | Row Labels | <12/27/2022 | 2022 | 2023 | 2024 | 2025 | 2026 | Grand Total |  |  |  | Row Labels | <3/26/2023 | 2023 | 2024 | 2025 | 2026 | Grand Total | [11 empty] | Row Labels |  |  |  | Jan | 115 | 49 | 164 | Jan | 116 | 51 | 167 | Jan | 1 |  | 51 | 52 | Jan | 1 |  | 48 | 49 | Jan | 1 |  | 50 | 51 | Row Labels | [7 empty] | Jan | Mar | Grand Total | Row Labels | Connected | Work Not Start | Grand Total
| 2023 | 139 | [5 empty] | 2024 | 745 |  |  |  |  | 2024 | 849 | [5 empty] | KENDARI |  | 1 | 60 | 201 | 133 |  | 395 |  |  |  | KENDARI | 95 | 1 | 166 | 133 |  | 395 | Count of WID | Column Labels |  |  |  | Count of WID | Column Labels |  |  | Row Labels | Count of WID | Jan | 41 | 51 | 92 | Feb | 33 | 37 | 70 | Feb | 38 | 38 | 76 | Feb | 3 |  | 35 | 38 | Feb | 1 |  | 36 | 37 | Feb | 1 |  | 37 | 38 | MAKASSAR | 1 | 48 |  | 3 | 6 | 58 | Row Labels |  |  |  | Jan | 1 |  | 1
| 2024 | 857 | [5 empty] | 2025 | 337 |  |  |  |  | 2025 | 343 | [5 empty] | MAKASSAR | 29 |  | 13 | 73 | 17 | 29 | 161 |  |  |  | MAKASSAR | 49 | 1 | 66 | 17 | 28 | 161 | Row Labels | Done | NY | Grand Total |  | Row Labels | 2025 | 2026 | Grand Total | Work Not Start | 48 | Feb | 14 | 35 | 49 | Mar | 36 | 44 | 80 | Mar | 37 | 38 | 75 | Mar | 19 | 8 | 28 | 55 | Mar | 21 | 5 | 18 | 44 | Mar | 20 |  | 18 | 38 | MANADO |  |  | 10 | 15 | 14 | 39 | Kurniadi |  | 7 | 7 | Mar | 22 | 26 | 48
| 2025 | 333 | [5 empty] | Jan | 115 |  |  |  |  | Jan | 116 | [5 empty] | MANADO | 15 |  | 23 | 124 | 15 | 33 | 210 |  |  |  | MANADO | 46 |  | 116 | 15 | 33 | 210 | MAKASSAR | 29 | 29 | 58 |  | Connected | 343 | 215 | 558 | Grand Total | 48 | Mar | 15 | 28 | 43 | Apr | 23 | 53 | 76 | Apr | 24 | 58 | 82 | Apr | 2 | 13 | 27 | 42 | Apr | 2 | 15 | 36 | 53 | Apr | 3 | 19 | 36 | 58 | TERNATE | 67 | 37 | 31 | 45 | 23 | 203 | Connected |  | 7 | 7 | Grand Total | 23 | 26 | 49
| Jan | 111 | [5 empty] | Feb | 33 |  |  |  |  | Feb | 38 | [5 empty] | PALU |  |  | 32 | 106 |  |  | 138 |  |  |  | PALU | 40 |  | 98 |  |  | 138 | MANADO | 33 | 6 | 39 |  | Grand Total | 343 | 215 | 558 |  |  | Apr | 12 | 27 | 39 | May | 22 | 33 | 55 | May | 21 | 30 | 51 | May | 4 | 12 | 33 | 49 | May | 3 | 13 | 17 | 33 | May | 2 | 11 | 17 | 30 | Grand Total | 68 | 85 | 41 | 63 | 43 | 300 | Narfin |  | 4 | 4
| Feb | 33 | [5 empty] | Mar | 36 |  |  |  |  | Mar | 37 | [5 empty] | PARE PARE |  |  | 3 | 131 | 25 |  | 159 |  |  |  | PARE PARE | 13 | 1 | 120 | 25 |  | 159 | TERNATE | 177 | 26 | 203 | [7 empty] | May | 18 | 33 | 51 | Jun | 32 |  | 32 | Jun | 33 |  | 33 | Grand Total | 29 | 33 | 174 | 236 | Grand Total | 28 | 33 | 155 | 216 | Grand Total | 27 | 30 | 158 | 215 | [7 empty] | Connected |  | 4 | 4
| Mar | 37 | [5 empty] | Apr | 23 |  |  |  |  | Apr | 24 | [5 empty] | TERNATE | 33 |  | 8 | 222 | 143 | 174 | 580 |  |  |  | TERNATE | 98 | 1 | 179 | 147 | 155 | 580 | Grand Total | 239 | 61 | 300 | [7 empty] | Jun | 13 |  | 13 | Jul | 15 |  | 15 | Jul | 12 |  | 12 | [22 empty] | Rifqi |  | 5 | 5
| Apr | 24 | [5 empty] | May | 22 |  |  |  |  | May | 21 | [5 empty] | Grand Total | 77 | 1 | 139 | 857 | 333 | 236 | 1643 |  |  |  | Grand Total | 341 | 4 | 745 | 337 | 216 | 1643 | [11 empty] | Jul | 7 |  | 7 | Aug | 15 |  | 15 | Aug | 17 |  | 17 | [22 empty] | Connected |  | 5 | 5
| May | 21 | [5 empty] | Jun | 32 |  |  |  |  | Jun | 33 | [34 empty] | Aug | 6 |  | 6 | Sep | 41 |  | 41 | Sep | 37 |  | 37 | [22 empty] | Romy | 1 | 6 | 7
| Jun | 31 | [5 empty] | Jul | 15 |  |  |  |  | Jul | 12 | [23 empty] | HI | [10 empty] | Sep | 15 |  | 15 | Oct | 3 |  | 3 | Oct | 7 |  | 7 | [22 empty] | Connected | 1 | 6 | 7
| Jul | 14 | [5 empty] | Aug | 15 |  |  |  |  | Aug | 17 | [23 empty] | PO Year | 2026 | [9 empty] | Dec | 2 |  | 2 | Dec | 2 |  | 2 | Nov | 1 |  | 1 | [22 empty] | NY |  | 26 | 26
| Aug | 16 | [5 empty] | Sep | 41 |  |  |  |  | Sep | 37 | [23 empty] | Monthly Assignment | (ALL) | [9 empty] | Grand Total | 143 | 174 | 317 | Grand Total | 337 | 216 | 553 | Grand Total | 343 | 215 | 558 | [22 empty] | Work Not Start |  | 26 | 26
| Sep | 41 | [5 empty] | Oct | 3 |  |  |  |  | Oct | 7 | [68 empty] | Grand Total | 1 | 48 | 49
| Oct | 3 | [5 empty] | Dec | 2 |  |  |  |  | Nov | 1 | [23 empty] | Count of WID | Column Labels
| Dec | 2 | [5 empty] | 2026 | 185 |  |  |  |  | 2026 | 186 | [23 empty] | Row Labels | Done | NY | Progres | Grand Total
| 2026 | 188 | [5 empty] | Jan | 49 |  |  |  |  | Jan | 51 | [23 empty] | MAKASSAR | 28 | 30 |  | 58
| Jan | 52 | [5 empty] | Feb | 37 |  |  |  |  | Feb | 38 | [23 empty] | MANADO | 33 | 6 |  | 39
| Feb | 38 | [5 empty] | Mar | 44 |  |  |  |  | Mar | 38 | [23 empty] | TERNATE | 159 | 28 | 16 | 203
| Mar | 55 | [5 empty] | Apr | 52 |  |  |  |  | Apr | 57 | [23 empty] | Grand Total | 220 | 64 | 16 | 300
| Apr | 40 | [5 empty] | May | 3 |  |  |  |  | May | 2
| May | 3
Connected
[39 empty] | PO Year | 2026
[39 empty] | Monthly Assignment | (ALL)
[39 empty] | Count of WID | Column Labels
[39 empty] | Row Labels | Connected | NY | Grand Total
[39 empty] | MAKASSAR | 27 | 31 | 58
[39 empty] | MANADO | 32 | 7 | 39
[39 empty] | TERNATE | 159 | 44 | 203
[39 empty] | Grand Total | 218 | 82 | 300
Row Labels | 2025 | 2026 | Grand Total |  | Work Not Start | 48 |  | Feb | 14 | 35 | 49 |  | Mar | 36 | 44 | 80 |  | Mar | 37 | 38 | 75 |  | Mar | 19 | 8 | 28 | 55 |  | Mar | 21 | 5 | 18 | 44
Connected | 343 | 215 | 558 |  | Grand Total | 48 |  | Mar | 15 | 28 | 43 |  | Apr | 23 | 53 | 76 |  | Apr | 24 | 58 | 82 |  | Apr | 2 | 13 | 27 | 42 |  | Apr | 2 | 15 | 36 | 53
Grand Total | 343 | 215 | 558 |  |  |  |  | Apr | 12 | 27 | 39 |  | May | 22 | 33 | 55 |  | May | 21 | 30 | 51 |  | May | 4 | 12 | 33 | 49 |  | May | 3 | 13 | 17 | 33
[8 empty] | May | 18 | 33 | 51 |  | Jun | 32 |  | 32 |  | Jun | 33 |  | 33 |  | Grand Total | 29 | 33 | 174 | 236 |  | Grand Total | 28 | 33 | 155 | 216
[8 empty] | Jun | 13 |  | 13 |  | Jul | 15 |  | 15 |  | Jul | 12 |  | 12
[8 empty] | Jul | 7 |  | 7 |  | Aug | 15 |  | 15 |  | Aug | 17 |  | 17
[8 empty] | Aug | 6 |  | 6 |  | Sep | 41 |  | 41 |  | Sep | 37 |  | 37
[8 empty] | Sep | 15 |  | 15 |  | Oct | 3 |  | 3 |  | Oct | 7 |  | 7
[8 empty] | Dec | 2 |  | 2 |  | Dec | 2 |  | 2 |  | Nov | 1 |  | 1
[8 empty] | Grand Total | 143 | 174 | 317 |  | Grand Total | 337 | 216 | 553 |  | Grand Total | 343 | 215 | 558
Assignment Month
Years (Connected Date) | 2026 | [12 empty] | ZTE ZONE | MAKASSAR |  |  |  | ZTE ZONE | MAKASSAR
[6 empty] | Count of WID | Column Labels | [6 empty] | Years (Monthly Target) | (Multiple Items) |  |  |  | Years (Monthly Target) | 2026
Count of WID | Column Labels | [5 empty] | Jan | Feb | Mar | Apr | May | Grand Total
Row Labels | MAKASSAR | MANADO | TERNATE | Grand Total | [9 empty] | Count of WID | Column Labels |  |  |  | Count of WID | Column Labels
Jan | 1 |  | 50 | 51 |  | Row Labels | [8 empty] | Jan | Mar | Grand Total |  | Row Labels | Connected | Work Not Start | Grand Total
Feb | 1 |  | 37 | 38 |  | MAKASSAR | 1 | 48 |  | 3 | 6 | 58 |  | Row Labels |  |  |  |  | Jan | 1 |  | 1
Mar | 20 |  | 18 | 38 |  | MANADO |  |  | 10 | 15 | 14 | 39 |  | Kurniadi |  | 7 | 7 |  | Mar | 22 | 26 | 48
Apr | 3 | 19 | 36 | 58 |  | TERNATE | 67 | 37 | 31 | 45 | 23 | 203 |  | Connected |  | 7 | 7 |  | Grand Total | 23 | 26 | 49
May | 2 | 11 | 17 | 30 |  | Grand Total | 68 | 85 | 41 | 63 | 43 | 300 |  | Narfin |  | 4 | 4
Grand Total | 27 | 30 | 158 | 215 | [9 empty] | Connected |  | 4 | 4
[14 empty] | Rifqi |  | 5 | 5
[14 empty] | Connected |  | 5 | 5
[14 empty] | Romy | 1 | 6 | 7
[14 empty] | Connected | 1 | 6 | 7
[14 empty] | NY |  | 26 | 26
[14 empty] | Work Not Start |  | 26 | 26
[14 empty] | Grand Total | 1 | 48 | 49

## Inbound
No. | Region | WID | Freq | SOW | Work Type | Site Name | Site ID | Region | Name Team | Muver By | Status DR | No DR | Date Realise | Date Pickup | Date Inbound | Status LDM | Status Tagging | Detail Material | Remark
1 | South Sulawesi | 2602-ADSTR-4G#RO-EPS063-0052 | L1800 | EQP Add Sector LTE 1800 4T4R | Add Antenna and RRU and Swap Module BBU | PTIONELEGKALEBAJENG | EPS063 | South | Romy & Rahmat | Pandu | DR Realese | DRID03320260227011TSELLTE | 2026-03-02 | 2026-03-02 | 2026-03-02 | 06-Inbound Done, Wait LDM Submit To WH | Done Tagging | Cabinet ZXSDR BS8900A(1Pcs),B.FAN.5 (1),LPU (1),BBU (1),FA0 (1),PM5 (2),SA (1),CCE1B (1),CC16B (1),CR0 (1),BPN2 (4),PM CABLE 1M (2),Cable SA (1),DCDP7 (2)
2 | South Sulawesi | 2602-NNE5G-5G#RO-UPD331-0092 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | DMT SMA17 | UPD331 | South | Narfin & Sahril | Temans | DR Realese | DRID03320260308001TSELLTE | 2026-03-11 | 2026-03-11 | 2026-03-11 | 06-Inbound Done, Wait LDM Submit To WH | NY Tagging | Mounting3m (3),Bracket Mounting (6),Cabinet ZXSDR BS8900A(1Pcs),B.FAN.5 (1),LPU (1),DCPD7 (2),DCPD10B (1),BBU (1),BPN2 (3),CR0 (1),CCE1B (1),CCF0 (1),PM5 (1),PM3 (1),PM Cable 1m (1),SA (1),Cable SA (1),FA0 (1),GPS (1),RRU R8978 S2300 (2),Cable Power 2x6 38m,Connector Plastick (2),Bracket RRU (2),Jumper (12),SFP 10G (4)
3 | South Sulawesi | 2602-NNE5G-5G#RO-UPD330-0091 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | DMT Kaluku Bodoa | UPD330 | South | Kurniadi & Edar | Schenker | DR Realese | DRID03220260330003TSEL5G | 2026-03-31 | 2026-04-01 | 2026-04-02 | 06-Inbound Done, Wait LDM Submit To WH | NY Tagging | Rack BC 8910 (1),BPN2 (4),CR0 (1),FS5 (1),CCE1B (1),CCF0 (1),PM5 (1),PM3 (1),DCPD7 (2),LPU (1),FA0 (1),PM CABLE 1M (1),Cable SA (1), B.FAN 5 (1),GPS (1),SFP 10G (4),Jumper NM (12),Cable Power 2x6 18M/Tarikan,CONNECTOR PLASTICK (2),Bracket RRU (2),RRU R8978 S2300 (2)
4 | South Sulawesi | 2602-NNE5G-5G#RO-UPD438-0104 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | Protelindo Bira SMU 6 | UPD438 | South | Romy & Rahmat | Uniair | DR Realese | DRID03320260308003TSELLTE | 2026-03-10 | 2026-03-10 | 2026-03-10 | 06-Inbound Done, Wait LDM Submit To WH | NY Tagging | BBU (1),BPN2 (3),CR0 (2),CCF0 (1),BPQ2 (1),FA0 (1),PM5 (2),SA (1),PM Cable 1M (2),Cable SA (1),Cabinet ZXSDR BS8900A(1Pcs),B.FAN.5 (1),LPU (1),DCPD7 (1),RRU R8978 S2300 (1),Cable Power 2x6 20m,Connector Plastick (1),Bracket RRU (1),SFP 10G (2),Jumper NM (4)
5 | South Sulawesi | 2602-NNE5G-5G#RO-UPD283-0190 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Add RRU and Swap Module BBU | Protelindo Bandang | UPD283 | South | Kurniadi & Edar | DHL | DR Realese | DRID03320260313008TSELLTE | 2026-03-16 | 2026-03-30 | 2026-03-30 | 06-Inbound Done, Wait LDM Submit To WH | NY Tagging | Rack BS8900 GU360 (1),BFAN 5 (1),DCPD7 (1),LPU (1),BBU (1),BPN2 (2),CCF0 (1),FS5 (1),PM3 (2),SA (1),PM CABLE 1M (2),Cable SA (1),FA0 (1)
6 | South Sulawesi | 2602-NNE5G-5G#RO-UPD434-0102 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | Protelindo Sudiang 2 | UPD434 | South | Narfin & Sahril | Uniair | DR Realese | DRID03320260308002TSELLTE | 2026-03-10 | 2026-03-10 | 2026-03-10 | 06-Inbound Done, Wait LDM Submit To WH | NY Tagging | Rack BS8900A (1),Bfan 5 (1),DCPD7 (1),LPU (1),BBU (1),FA0 (1),BPN2 (4),FS5 (1),CR0 (1),CCE1B (1),CCF0 (1),PM5 (2),SA (1),Cable SA (1),PM CABLE 1M (1),RRU R8978 S2300 (1),ZTE Bracket RRU (1),Connector Plastick (1),Jumper NM (4),SFP 10G (2),Cable Power 2x6 30M,GPS (1),Mounting 3 (Return),Bracket Mounting 6 (Return)
7 | South Sulawesi | 2602-UMIMO-4G#RO-UPD280-0586 | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R impact New NE | Swap RRU and Add Module BBU | Protelindo Batua Raya | UPD280 | South | Narfin & Sahril | Schenker | DR Realese | DRID03320260313007TSELLTE | 2026-03-16 | 2026-03-25 | 2026-03-30 | 06-Inbound Done, Wait LDM Submit To WH | NY Tagging | RRU R8872 S1800 (1),Cable Power 2x6 3M (1),SFP 1,25G (2),CONNECTOR PLASTICK (1),ZTE Bracket RRU (1)
8 | South Sulawesi | 2602-NNE5G-5G#RO-UPD280-0082 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | Protelindo Batua Raya | UPD280 | South | Kurniadi & Edar | Schenker | DR Realese | DRID03320260414002TSEL5G | 2026-04-15 | 2026-04-20 | 2026-04-22 | 06-Inbound Done, Wait LDM Submit To WH | NY Tagging | Rack BC8900A GU360 (1),B FAN.5 (1),DCPD7 (2),LPU (1),BBU (1),PM5 (1),PM3 (1),SA (1),FS5 (1),CR0 (1),CCE1B (1),CC16B (1),BPN2 (4),RRU R8978 S2300 (2),SFP 10G (4),Cable Power 2x4 5M/Tarikan (2tarikan),Bracket RRU (2),CONNECTOR PLASTICK (2),Jumper NM (12),FA0 (1),PM CABLE 1M (2)
9 | South Sulawesi | 2602-NNE5G-5G#RO-UPD289-0183 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Add RRU and Swap Module BBU | Perumnas Tamalate | UPD289 | South | Kurniadi & Edar | Schenker | DR Realese | DRID03320260313009TSELLTE | 2026-03-16 | 2026-03-25 | 2026-03-27 | 06-Inbound Done, Wait LDM Submit To WH | NY Tagging | Rack BS8900A GU360 (1),BFAN 5 (1),DCPD7 (2),LPU (1),BBU (1),BPN2 (4),CR0 (2),CCE1B (1),CCF0 (1),PM5 (1),PM3 (1),SA (1),Cable SA (1),PM CABLE 1M (2),FA0 (1),RRU R8978 S2300 (1),SFP 10G (2),CONNECTOR PLASTICK (1),ZTE Bracket RRU (1),Jumper NM (4),Cable Power 2x6 10M/Tarikan (1)
10 | South Sulawesi | 2602-NNE5G-5G#RO-UPD352-0097 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | Protelindo Biringkanaya | UPD352 | South | Romy & Rahmat | DHL | DR Realese | DRID03320260313006TSELLTE | 2026-03-16 | 2026-03-27 | 2026-03-27 | 06-Inbound Done, Wait LDM Submit To WH | NY Tagging | Rack BS8900A GU360 (1),BFAN 5 (1),DCPD7 (1),LPU (1),BBU (1),BPN2 (4),CR0 (2),CCE1B (1),CC16B (1),PM5 (2),SA (1),Cable SA (1),PM CABLE 1M (2),FA0 (1),RRU R8978 S2300 (1),SFP 10G (2),CONNECTOR PLASTICK (1),ZTE Bracket RRU (1),Jumper NM (4),Cable Power 2x6 14M/Tarikan (1)
11 | South Sulawesi | 2602-NNE5G-5G#RO-UPD301-0197 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | Protelindo Permata Sudiang | UPD301 | South | Rifqi & Aidil | Sinotrans | DR Realese | DRID03320260318002TSELLTE | 2026-03-25 | 2026-03-28 | 2026-03-31 | 06-Inbound Done, Wait LDM Submit To WH | NY Tagging | BBU (1),BPN2 (3),CC16B (1),CR0 (2),CCE1B (1),PM5 (2),SA (1),FA0 (1),LPU (1),DCPDB6 (1),DCPD7 (1),Rack BS8900A GU360 (1),B FAN.5 (1),RRU R8978 S2300 (1),Jumper NM (8),CONNECTOR PLASTICK (1),ZTE Bracket RRU (1), SFP 10G (2),GPS (1),Cable Power 2x6 25M/Tarikan (1)
12 | South Sulawesi | 2511-ADSTR-4G#RO-UPD238-0524 | L2300 | EQP Add Sector NR 2300 Massive MIMO 32T32R | Swap Qcell & Add Module BBU | Kantor Telkomsel Pettarani | UPD238 | South | Narfin & Sahril |  | 17-No Need Dismantle | 17-No Need Dismantle |  |  |  | 17-No Need Dismantle |  | 17-No Need Dismantle
13 | South Sulawesi | 2602-NNE5G-5G#RO-UPD311-0083 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | TBG BTN Makkiobaji | UPD311 | South | Romy & Rahmat | [8 empty] | (All Module BBU Stolen)
14 | South Sulawesi | 2602-NNE5G-5G#RO-UPD364-0098 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | TBG Kopertis | UPD364 | South | Rifqi & Aidil | [8 empty] | (BBU,DCPD,LPU Stolen)
15 | South Sulawesi | 2602-NNE5G-5G#RO-UPD324-0090 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | Protelindo Tol Barukang | UPD324 | South | Kurniadi & Edar |  | DR Realese | DRID03320260427001TSEL5G | 2026-04-27
16 | North Sulawesi | 2602-NNE5G-5G#RO-UPD314-0084 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | Protelindo Pepabri | UPD314 | South | Kurniadi & Edar | Uniair | DR Realese | DRID03320260407001TSEL5G | 2026-04-10 | 2026-04-11 | 2026-04-11 | 06-Inbound Done, Wait LDM Submit To WH | NY Tagging | Rack BC 8910 (1),B FAN 5(1),DCPD7 (1),BBU (1),BPN2 (3),BPQ (1),FS5 (1),CR0 (1),CCE1B (1),CC16B (1),PM5 (2),SA3 (1),PM CABLE 1M (1),Cable SA (1),FA0 (1),LPU (1),RRU R8978 S2300 (2), SFP 10G (4),Jumper NM (12),ZTE Bracket RRU (2),Cable Power 2x6 13M/Tarikan (2)
17 | North Sulawesi | 2602-NNE5G-5G#RO-UPD092-0207 | L2300 | EQP New NE 5G NR 2300 30 Mhz | Add Qcell and Module BBU (5G Qcell 10 pcs) | Mall Panakukkang | UPD092 | South | Narfin & Sahril | Schenker | DR Realese | DRID03320260414001TSEL5G | 2026-04-15 | 2026-04-20 | 2026-04-22 | 06-Inbound Done, Wait LDM Submit To WH | NY Tagging | Plco RRU ZXSDR R8119 M182126 (6),ZTE Bracket Antenna (5)
18 | North Sulawesi | 2602-NNE5G-5G#RO-UPD440-0105 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | RS.KustaDaya-DMT | UPD440 | South | Kurniadi & Edar | Schenker | DR Realese | DRID03320260421001TSEL5G | 2026-04-25 | 2026-04-25 | 2026-04-25 | 06-Inbound Done, Wait LDM Submit To WH | NY Tagging | RRU R8978 S2300 (2),Rack BC 8910 (1),B FAN.5 (1),BBU (2),FA0 (2),BPN2 (5),CR0 (3),CCE1B (2),CC16B (1),PM5 (3),SA (2),DCPD7 (1),SFP 10G (4),Cable Power 2x6 18M/Tarikan (2),Jumper NM (8),ZTE Bracket RRU (2)
19 | North Sulawesi | 2602-NNE5G-5G#RO-UPD369-0099 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Add RRU and Swap Module BBU | Protelindo Galangan kapal | UPD369 | South | Rifqi & Aidil | Schenker | DR Realese | DRID03320260427002TSEL5G | 2026-04-27
20 | North Sulawesi | 2604-NNE4G-4G#RO-BAR034-0104 | L2300 | EQP New NE 4G LTE 2300 20 Mhz | Add RRU and Swap Antenna and Module BBU | DMT Tuwung Baru | BAR034 | South | Kurniadi & Edar |  | Waiting DR Realese
21 | North Sulawesi | 2602-NNE5G-5G#RO-MDO294-0269 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | Protelindo Bogani | MDO294 | North | Burhan Pasigi |  | Waiting DR Realese
22 | North Sulawesi | 2602-UMIMO-4G#RO-MDO294-0827 | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R | Swap RRU and Add Module BBU | Protelindo Bogani | MDO294 | North | Burhan Pasigi |  | Waiting DR Realese
23 | North Sulawesi | 2602-UMIMO-4G#RO-MDO294-0827 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | API MCP Malalayang Satu | MDO524 | North | Sulaiman Bastian |  | Waiting DR Realese
24 | North Sulawesi | 2602-NNE5G-5G#RO-MDO258-0267 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | TBG Telling Bawah | MDO258 | North | Burhan Pasigi |  | Waiting DR Realese
25 | North Sulawesi | 2602-UMIMO-4G#RO-MDO258-0776 | L2100 | EQP Upgrade LTE 2100 Massive MIMO 32T32R | Swap RRU and Module BBU | TBG Telling Bawah | MDO258 | North | Burhan Pasigi |  | Waiting DR Realese
26 | North Sulawesi | 2602-NNE5G-5G#RO-MDO023-0258 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU And BTS | Singkil 2 | MDO023 | North | Burhan Pasigi |  | Waiting DR Realese
27 | North Sulawesi | 2602-NNE5G-5G#RO-MDO166-0261 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | TBG Ranotana | MDO166 | North | Sulaiman Bastian |  | Waiting DR Realese
28 | North Sulawesi | 2602-NNE5G-5G#RO-MDO263-0268 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU And BTS | TBG Tuminting Galaxy | MDO263 | North | Sulaiman Bastian |  | Waiting DR Realese
29 | North Sulawesi | 2602-NNE5G-5G#RO-MDO008-0256 | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU,BTS | Singkil | MDO008 | North | Sulaiman Bastian |  | Waiting DR Realese
30 | North Sulawesi | 2602-NNE5G-5G#RO-MDO462-0274 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Add Module BBU | Jembatan Megawti | MDO462 | North | Sulaiman Bastian |  | Waiting DR Realese
31 | North Sulawesi | 2604-UMIMO-4G#RO-TDO266-1035 | L2300 | EQP Upgrade LTE 1800 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU,BTS | TBG Tatelu Sukur | TDO266 | North | Sulaiman Bastian |  | Waiting DR Realese
32 | North Sulawesi | 2604-ADSTR-4G#RO-AMR031-0433 | L9000 | EQP eNode B Modular Relocation Service | Add RRU | DMT Ratatotok | AMR031 | North | Sulaiman Bastian |  | Waiting Info Muver
33 | North Sulawesi | 2604-4GDCS-4G#RO-KTG054-0051 | L1800 | EQP New NE 4G LTE 1800 20 Mhz | Add RRU | DMT Dumoga 2 | KTG054 | North | Sulaiman Bastian |  | 17-No Need Dismantle |  |  |  |  | 17-No Need Dismantle
34 | North Sulawesi | 2604-UMIMO-4G#RO-ISM118-1054 | L2300 | EQP Upgrade LTE 2300 Massive MIMO 32T32R impact New NE | Swap RRU and Module BBU,BTS | DMT Hutuo Limboto | ISM118 | North | Burhan Pasigi |  | Waiting DR Realese
35 | North Sulawesi | 2604-ADSTR-4G#RO-GTO014-0531 | L2300 | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Antenna and Module BBU,BTS | DMT Limboto 3 | GTO014 | North | Burhan Pasigi |  | Waiting DR Realese

## Inbound Return
WID | Freq | SOW | Work Type | Site Name | Site ID | Name Team | Region | Muver By | No DRID | Date Realese | Date Pickup | Date Inbound | Status Inbound | Detail Material
2602-NNE5G-5G#RO-UPD301-0197 | L2300 | EQP New NE 5G NR 2300 30 Mhz Massive MIMO 32T32R | Swap RRU and Module BBU | Protelindo Permata Sudiang | UPD301 | Rifqi & Aidil | South | Sinotrans | DR03820260318001TSELLTE | 2026-03-25 | 2026-03-28 | 2026-03-31 | Done Inbound | Mounting 3m (1),Bracket Mounting (2)
2604-NNE4G-4G#RO-BAR034-0104 | L2300 | EQP New NE 4G LTE 2300 20 Mhz | Add RRU and Swap Antenna and Module BBU | DMT Tuwung Baru | BAR034 | Kurniadi | South
2604-ADSTR-4G#RO-AMR031-0433 | L2300 | EQP eNode B Modular Relocation Service | Add RRU | DMT Ratatotok | AMR031 | Sulaiman Bastian | North
2604-ADSTR-4G#RO-GTO014-0531 | L2300 | EQP Add Sector LTE 2300 4T4R | Add RRU and Swap Antenna and Module BBU | DMT Limboto 3 | GTO014 | Burhan Pasigi | North
2604-REENG-4G#RO-KTG145-0040 | L2300 | EQP eNode B Modular Relocation Service | Add RRU | Protelindo Ratatotok | KTG145 | Sulaiman Bastian | North

## Team List
No. | Name | Position | Kontak | Email | Region / City | Akun Iepms | Info Team | No. | Name | Position | ID Card No. | Kontak | Email | Region / City | epms/iCenter | Ineom | Info Team | WAH | remarks
1 | Rizal Ismail | Site Engineer | 82246016030 | codernate3@gmail.com | TERNATE |  | Team 1 | 1 | Romy Rawung | Site engineer | 7371130309910000 | 81245238938 | romyvirgino91@gmail.com | Makassar | 6000017447 |  | Tsel Internal | 5/914/AS.02.03/X/2020 | WAH (expired)
2 | Sahril Kasim Karim | Team Leader | 82191862043 | syahrilrilex123@gmail.com | TERNATE |  |  |  | RAHMAT | Leader | 7371071806040000 | 82252412875 | rahmathidayat196768@gmail.com | Makassar |  |  | Tsel Internal | 5/4585060224/AS.01.04/II/2024 | WAH/BE/FA
3 | Arwan | Installer | 82189345984 | coolarwan9@gmail.com | TERNATE |  |  |  | Fakhrul Afandi Djalil | Installer | 7471051611830000 | 82189327788 | gayustambunang74@gmail.com | Makassar |  |  | Tsel Internal
4 | MARTHEN KUDUBUN | Installer | 85254371933 | marthenkudubun@gmail.com | TERNATE |  |  | 2 | Narfin | Engineer | 7371091706960000 | 85774849807 | vinkgbd@gmail.com | Makassar |  |  | xlsmart |  | WAH
5 | Yakup balubun | Site Engineer | 82199039621 | Yakupbalubun@gmail.com | TERNATE |  | Team 2 |  | SAHRIL | Engineer | 7304111410960000 | 895611974122 | sahril1408@gmail.com | Makassar | 6000060217 |  | xlsmart |  | WAH (expired)
6 | Ahmad Jufri | Team Leader | 82274781621 | jufri9442@gmail.com | TERNATE | Muhammad/Amien/Syarif/6000051095 |  |  | Refi Alfajri Anwar | Leader | 7317021205020000 | 82331222909 | alfajrianwar30@gmail.com | Makassar |  |  | xlsmart |  | WAH
7 | Jerry Warley Jasso | Installer | 82131419512 | jw1209293@gmail.com | TERNATE |  |  |  | Muhammad amien syarif | Installer | 7371062201020000 | 87898810446 | aminira589@gmail.com | Makassar |  |  | xlsmart
8 | Michael Daniel De Fretes | Installer | 81248527518 | michael17defretes@gmail.com | TERNATE |  |  | 3 | Kurniadi | Site engineer | 7306050506880000 | 82191396273 | sdimakkatutu77@gmail.com | Makassar | 6000051098 |  | xlsmart |  | WAH (expired)
9 | Sandi hayoto | Site Engineer | 82397998919 | gamessandy07@gmail.com | TERNATE |  | Team 3 |  | Andi Mapi Edar | Leader | 7210020208950000 | 81256550516 | andimapiedar010@gmail.com | Makassar |  |  | xlsmart
10 | Gusti yahellisa | Team Leader | 82397998919 | gustiyahelissa@icloud.com | TERNATE |  |  |  | Muh. Ilham Gymnastiar | Installer | 7371102710030009 | 81527834861 | ilhamgyimnastiar@gmail.com | Makassar |  |  | xlsmart |  | WAH
11 | Fikri sanahuyo | Installer | 81248167223 | fikrisanahuyo16@gmail.com | TERNATE |  |  |  | Sumarir | Installer | 7403041602930000 | 85342184409 | teavoltajhon@gmail.com | Makassar |  |  | xlsmart |  | WAH (expired)
12 | Aswat yahellisa | Installer | 82274769651 | aswatlissa06@gamil.com | TERNATE |  |  | 4 | Muh Ilham Rifqi | Engineer | 731-00513030500001 | 88246516838 | rifqiilham378@gmail.com | Makassar | 6000051103 |  | Quintel | 5/0658040923/AS.01.04/IX/2023 | WAH
13 | Junaedi Kurniawan Renuat | Site Engineer | 82297424116 | junedirenuat@gmail.com | TERNATE | Alam//Alam/6000051090 | Team 4 |  | Aidil | Leader |  | 85333932846 | idilaidil486@gmail.com | Makassar |  |  | Quintel
14 | Oktopianus Patty | Team Leader | 82143286805 | oktoalexmarthen@gmail.com | TERNATE |  |  |  | Muh Ariadi | Member |  | 82120865845 | ariadimuh497@gmail.com | Makassar |  |  | Quintel
15 | Yulens Melki Dangeubun | Installer | 82248598125 | Yulensmelkidangeubun@gmail.com | TERNATE |  |  |  | Muh Arya Putra | Member |  | 85756041048 | muhammadaryaputra2728@gmail.com | Makassar |  |  | Quintel
16 | Usman Pesilette | Installer | 82195935797 | usmanpesilette@gmail.com | TERNATE
17 | Gusti | Team Leader | 82187573759 | stempeq28@gmail.com | TERNATE |  | Team 5
18 | Candra Ardiansa Putra | Site Engineer | 82152398885 | candrajrcandrajrcandrajr@gmail.com | TERNATE | Fakhrul/Afandi/Djalil/6000051107 |  | No. | Name | Position | ID Card No. | Kontak | Email | Region / City | epms | Ineom | Info Team | WAH
19 | David Dadiara | Installer | 82274741245 | fillaumalydadiara@gmail.com | TERNATE |  |  | 1 | Rahmanto hervis | Engineer | 7207040407970001 | 82226543658 | panjisremped04@gmail.com | Manado
20 | Svendrobersen Liliefna | Installer | 81248552837 | svendrobersenliliefna@gmail.com | TERNATE |  |  |  | Andres isa | Leader | 7171010701010001 | 82189162182 | Andreisa0916@gmail.com | Manado
21 | AGUS PRIANTO MALIKASA |  | 85178208551 | agusmalikasa3@gmail.com | TERNATE |  | Team 6 |  | Sulaiman | Member | 7171031905980005 | 081344290985 | renaldidats@gmail.com | Manado |  |  |  | FA:2160/PJK3-EXA/IIX/2024 & BE:2131/PJK3-EXA/K3LISTRIK/IX/2024
22 | Armand Jafar |  | 81342141481 | armandjafar79@gmail.com | TERNATE | 600057626 |  |  | ANGGA MAULIDAN LAHIYA | Member | 7171020105040002 | 082189089866 | anggalahiya@gmail.com | Manado |  |  |  | License K3 WAH:177/07/TKPK-1/XII/2025
23 | Arfa Jafar |  | 85396896015 | arfahjafar20@gmail.com | TERNATE |  |  | 2 | BURHAN PASIGI | Engineer | 7571093112880001 | 0811-4333-935 | burhan31pasigi@gmail.com | Manado |  |  |  | WAH : Nomor 5/4694240624/AS.01.04/VI/2024
[9 empty] | SANDI LAMUDA | Leader | 7501022401920003 | 0878-5654-3701 | sandilamuda24@gmail.com | Manado |  |  |  | WAH : Nomor 5/4694240624/AS.01.04/VI/2024
[9 empty] | MUHAR | Member | 7324070107900080 | 0812-29151774 | muharmur051@gmail.com | Manado
[9 empty] | ALPINO MUSAFIR | Member | 7324072207010001 | 0821-92993104 | Alpinomusafir27@gmail.com | Manado
[9 empty] | Syafri Mokoginta | Engineer | 7101192806930001 | 85823331026 | Syafrimokoginta1@gmail.com | Manado
[9 empty] | RIFALDO DAMIMA | Leader | 7171022910040004 | 81244106460 | rivaldodamima72@gmail.com | Manado |  |  |  | K3 WAH:176/07/TKPK-1/XII/2025
[9 empty] | Indra Pramana Harun | Member | 7171022709000003 | 087886628111 | indraharun833@gmail.com | Manado
[9 empty] | DIDI DARMADI | Member | 1275040601870002 | 087883179519 | dididarmadi29@gmail.com | Manado |  |  |  | K3 WAH:0811051124/N-TKPK1/31/XI/2024
[9 empty] | Arifin Karim | Engineer | 7108023006940001 | 085954510760 | Arifinkarim6@gmail.com | Manado |  |  |  | K3 WAH:0718090822/N-TPK1/31/VIII/2022
[9 empty] | AGUSTINUS ANTHONI | Leader | 7171082508920041 | 082118594150 | agusantoni.221@gmail.com | Manado
[9 empty] | Meiky Christian Mamusung | Member | 7171080705900001 | 085395598073 | meikymamusung93@gmail.com | Manado
[9 empty] | Halilintar Burahima | Engineer | 7201053007970001 | 82296650695 | lintarburahima123@gmail.com | Manado |  |  |  | WAH : 0590261124/N-TPK1/72/XI/2024. K3 : 0590261124/N-TPK1/72/XI/2024
[9 empty] | A.GALANK SAPUTRA | Leader | 7315080709010001 |  |  | Manado |  |  |  | WAH : 789/SKL-TKPK/EXCT/08/25. K3 : 789/SKL-TKPK/EXCT/08/25
[9 empty] | ALIF GESANG | Member | 7201060306060001 | 82396671581 | alifgesang020@gmail.com | Manado
[9 empty] | NOPAL H BURAHIMA | Member | 7201064406050001 | 85126713145 | nopalburahima1@gmail.com | Manado